## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | January 2017 - December 2017
| Project Title: | Reduction of vulnerability to coastal flooding through ecosystem-based adaptation in the south of Artemisa and Mayabeque provinces.
| Project Summary: | The proposed project seeks to reduce the vulnerability of communities in coastal areas of Artemisa and Mayabeque provinces in southern Cuba from climate change (CC) related phenomena including coastal erosion, flooding and saltwater intrusion. This will be achieved through Ecosystem Based Adaptation (EBA), taking advantage of the proven potential of mangrove forests and associated coastal wetlands to limit the effects of wave erosion and coastal flooding, which are among the most damaging results of climate-change related SLR and storms. The project’s objective will be achieved through investments in three complementary components. Component 1 will focus on concrete investments in ecosystem recovery, leading to improved coastline resilience to the impacts of wave action, and improvements to coastal morphology which will reduce seawater incursion. Component 2 will focus on integrated and participatory management of coastal ecosystems, through mainstreaming EBA into integrated coastal zone planning and productive sector activities, promoting buy-in, participation and governance in local communities and developing knowledge management systems at community level. Component 3 will focus on establishing a favourable enabling environment at regional level for the effectiveness and sustainability of adaptation investments, through the provision of consolidated information on costs and benefits of EBA to decision makers and planners and the strengthening of institutions supporting EBA actions, within the framework of updated and actively implemented action plans.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | 84007 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Cuba | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Coastal areas of Artemisa and Mayabeque provinces in southern Cuba | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-05-19
IE-AFB Agreement Signature Date: |  | 2014-06-19 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | September 2014 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | October 2017
| Terminal Evaluation Date: | September 2019
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | - Inception workshow report, Quarterly Reports from UNPD. - 1st issue of Living Mangrove Forest bulletin. 2nd issue of Living Mangrove Forest bulletin. - http://www.cu.undp.org/content/cuba/es/home/presscenter/articles/2015/04/14/crece-el-proyecto-manglar-vivo.html. - http://www.radiohc.cu/noticias/ciencias/138840-avanza-en-cuba-proyecto-internacional-manglar-vivo. - http://www.radiomayabeque.icrt.cu/es/167-valor-agregado-en-espanol/5768-proyecto-manglar-vivo. - http://www.guerrillero.cu/pinar-del-rio/2802-inauguran-expo-manglar-vivo.html | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.ama.cu/manglar/manglar.html | Democratic Republic of the Congo
|  | https://www.facebook.com/manglarvivo/?ref=ts&fref=ts | Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Luis David Almeida Famada | Dominican Republic
| Email: | almeidafamada@ama.cu; almeidafamada@gmail.com | Ecuador
| Date: | February 28th, 2018 | Egypt
| Government DA |  | El Salvador
| Name: |  | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Gricel Acosta Acosta | Fiji
| Email: | gricel.acosta@undp.org | Finland
| Date: | February 28th, 2018 | France
| Executing Agency |  | Gambia
| Name: |  | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31 December 2017
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31 December 2017 | 2711887
Add any comments on AF Grant Funds. (word limit=200) | By the end of December 2017, Project cumulative disbursment rate is 69%, related to the total cash availability ($3,925,280). As explained in previous Project Performance Reports, the vast majority of acquisitions for international cooperation projects in Cuba need to be internationally procured, due to the low availability of products and services nationally. This is a long and complex process that has to comply with a wide range of national regulations, and has caused delays in the procurement of some goods. However, period Jan-Dec 2017 is the greatest annual disbursment since the begining of the Project ($1,258,436), as a result of the close coordination between Project and EMIDICT (import enterprise), which continues improving. In consequence, by the end of December 2017, more than $ 1,000,000 (for goods internationally procured) is committed in contracts signed in 2017 or ready to be signed in the first quarter of 2018. Additionally, $569,000 are ready to be internationally tendered in the first/second quarter of 2018. (See details below, in "Planned Expenditure Schedule" section). Period Jan-Dec 2018 is critical in order to accelerate the finantial execution.
INVESTMENT INCOME | Not applicable
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period (1 January 2017 - 31 December 2017) | ITEM / ACTIVITY / ACTION/OUTCOME | OUTPUT | AMOUNT
| 1. Reduction of the impacts of coastal flooding through the recovery of coastal ecosystems | 1.1. Re-establishment of coastal belt of red mangrove (Rhizophora mangle) between Surgidero de Batabanó and Punta Mora | 235147.59
|  | 1.2. Restoration of mangrove ecosystems between Majana and Surgidero de Batabanó | 321043.65
|  | 1.3. Restoration and enrichment of woodlands along the landward limit of the coastal wetland belt, between Majana and Punta Mora | 186330.16
|  | 1.4. Elimination and/or control of invasive alien species in coastal wetlands between Majana and Punta Mora in order to improve ecosystem resilience | 134841.37
| Subtotal Outome 1 |  | 877362.77
| 2. Increase the adaptive capacity of coastal communities to climate change | 2.1. EBA mainstreamed into integrated coastal zone planning and productive sector activities | 63024.72
|  | 2.2. Buy-in, participation and governance in local communities | 45081.93
|  | 2.3. Knowledge management systems at community level | 30522.86
| Subtotal Outome 2 |  | 138629.51
| 3. Ensure the effectiveness and sustainability of adaptation investments through the establishment of a favourable enabling environment at regional level | 3.1. Consolidated information on costs and benefits of EBA available to decision makers and planners | 145751.13
|  | 3.2. Strengthened institutions (provincial and municipal Governments, Forest Guard Corps, Frontier Guards and Fisheries Department) supporting EBA actions, within the framework of updated and actively implemented action plans | 29371.16
| Subtotal Outome 3 |  | 175122.29
| Project Management |  | 67321.29
| TOTAL EXPENDITURE |  | 1258435.86
PLANNED EXPENDITURE SCHEDULE | ITEM / ACTIVITY / ACTION/ OUTCOME | OUTPUT | PROJECTED COST | Est. Completion Date
List outputs planned and corresponding projected cost for the upcoming reporting period (Jan 2018 - Dec 2018) | 1. Reduction of the impacts of coastal flooding through the recovery of coastal ecosystems | 1.1. Re-establishment of coastal belt of red mangrove (Rhizophora mangle) between Surgidero de Batabanó and Punta Mora | 158685.93 | 2018-12-31
|  | 1.2. Restoration of mangrove ecosystems between Majana and Surgidero de Batabanó | 505500 | 2018-12-31
|  | 1.3. Elimination and/or control of invasive alien species in coastal wetlands between Majana and Punta Mora in order to improve ecosystem resilience | 353000 | 2018-12-31
|  | 1.4. Restoration and enrichment of woodlands along the landward limit of the coastal wetland belt, between Majana and Punta Mora | 812208.52 | 2018-12-31
| Subtotal Outome 1 |  | 1829394.45 | 2018-12-31
| 2. Increase the adaptive capacity of coastal communities to climate change | 2.1. EBA mainstreamed into integrated coastal zone planning and productive sector activities | 52000 | 2018-12-31
|  | 2.2. Buy-in, participation and governance in local communities | 99290 | 2018-12-31
|  | 2.3. Knowledge management systems at community level | 59000 | 2018-12-31
| Subtotal Outome 2 |  | 210290 | 2018-12-31
| 3. Ensure the effectiveness and sustainability of adaptation investments through the establishment of a favourable enabling environment at regional level | 3.1. Consolidated information on costs and benefits of EBA available to decision makers and planners | 66800 | 2018-12-31
|  | 3.2. Strengthened institutions (provincial and municipal Governments, Forest Guard Corps, Frontier Guards and Fisheries Department) supporting EBA actions, within the framework of updated and actively implemented action plans | 47268.26 | 2018-12-31
| Subtotal Outome 3 |  | 114068.26 | 2018-12-31
| Project Management |  | 48600 | 2018-12-31
| TOTAL |  | 2202352.71 | 2018-12-31
Details:
| Remaining balance of previous contracts |  | 450195
| Contracts ready to be signed in the first quarter of 2018 |  | 594500
| Goods and services to be internationally tendered in the first/second quarter of 2018 |  | 568700
| Goods and services to be nationally procured in 2018 |  | 588957.71
| AVAILABLE CASH |  | 1213392.71
| NEW TRANCH |  | 988960
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | At the end of 2017, the national co-financing committed in ProDoc, 5,052,000 CUP (Cuban Pesos), has been over fulfilled: 6,903,769 CUP - 136.6%.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 6903769
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | A specific procedure was established by the Project Management Unit for the monitoring of the national co-financing in CUP. The National Forestry Development Fund (FONADEF) (through the State Forestry Service (SEF)) is the main source this co-financing. A digital record is regularly updated with all the certifications that SEF issues for the rehabilitation actions in the Project areas. According to this record, by October 2017, FONADEF has issued certifications in an amount of 6,543,682 CUP: Artemisa Province 1,920,482 CUP and Mayabeque Province 4,623,200 CUP. The rest of the national co-financing comes mainly from the salaries paid to the personnel involved in the Project management by Cuban institutions: Institute of Ecology and Systematics (IES) 350,700 CUP; Institute of Agroforestry Research (INAF) 93,872 CUP and Environmental Agency (AMA) 196,314 CUP.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
| Identified Risk | Type | Impact / Probability 1: Low 5: High | Current Status | Steps Taken to Mitigate Risk
1 | Extreme climatic events (storms, droughts) and fires, affecting plant survival rates. | Environmental | Impact: Low (2) Probability: High (4) | Medium | In this period the national territory was affected by the Hurricane Irma, it caused great damage to the economy and natural heritage. This event hit the northern coast of Mayabeque, but did not directly affect the coastal forests in the project's intervention area. As part of the actions developed to deal with extreme weather events, the provincial and municipal disaster reduction plans were updated. An analysis of the behavior of forest fires was made, highlighting a reduction of fires in the project areas. This is the result of the effectiveness of the surveillance and early warning system, the relevance of the means acquired by the project to fight fires, training and working with communities.
2 | Climate change related changes in tree phenology affecting seed collection and nursery activities. | Environmental | Impact: Low (1) Probability: Medium (3) | Low | Although no phenological affectations were detected that compromised the development and establishment of the forests, as part of the plan of adaptation measures to reduce the risk of the CC in the coastal wetland areas, the following actions were taken: - Publication and implementation of a manual for the management of native species in nurseries; and, - Monitoring restoration / rehabilitation actions to periodically evaluate the success of establishing red mangrove forests.
3 | Variations in commitment to EBA among policy makers. | Institutional | Impact: Low (2) Probability: Medium (3) | Low | The development plan and the confrontation to the climate change of the provinces Artemisa and Mayabeque have incorporated adaptation actions based on ecosystems. In 2017, the council of ministers approved the State Plan for the Confrontation of Climate Change, known as "Tarea Vida". This plan includes among the prioritized areas the southern coast of the provinces Artemisa and Mayabeque. The successful experience of the project in the implementation of actions with the ABE approach is beginning to be replicated in other provinces.
4 | Slow equipment procurement processes in local Governments. | Institutional | Impact: High (4) Probability: High (4) | Medium | Although there is a delay in the execution of the budget, there is evidence of an important advance in this regard with respect to the previous period. The procurement procedure continues to improve to make it faster and more effective. Also, the following measures were applied: - A strategic replanning exercise was carried out to order the execution of the project until its completion. - The capacities that have been created by the government and other projects in the intervention are used. - The process of requesting and bidding on media to be imported is done early, to reduce the time of acquisition and delivery at the final destination.
5 | Limited availability of inputs and equipment on national market. | Institutional | Impact: Medium (3) Probability: Medium (3) | Medium | To continue reducing this risk, the following actions are carried out: - The offers of national products and services are evaluated periodically with the purpose of substituting imports. Example: prints of books and other materials. - New suppliers of products and services are identified in the country to facilitate their rapid contracting and acquisition.
6 | Short term economic and livelihood considerations outweigh medium term benefits of EBA actions in priorities of community members. | Institutional | Impact: Low (2) Probability: Low (1) | Low | The benefits of actions with ABE approach can not be observed in the short term. Therefore, the impacts of the implemented actions are monitored and evaluated, with the purpose of quickly disseminating the results. In addition, these are complemented by alternative economic options for local communities. For example: the use of IAS for the manufacture of charcoal has increased the income of the forest workers of the EAF Costa Sur and Mayabeque. Taking into account the potential of each province, two new projects have been proposed to diversify the sources of income of local communities: production of honey in the mangrove and the use of mineral-medicinal sludge.
7 | Short term political considerations outweigh medium term benefits of EBA actions in priorities of members of local institutions | Institutional | Impact: Low (1) Probability: Low (1) | Low | In order to ensure the sustainability of the benefits of the EBA the following actions were developed: - The project is evaluating possible sources of national and sectoral financing for the creation of economic incentives and their inclusion in local development strategies. Also, economic alternatives are identified so that the new productive forms promoted by the country do not affect the goods and services provided by the coastal forests. - Working groups for economic evaluation are trained and propose economic development alternatives for each province - The project continues to support the preparation of decision-makers at the provincial and municipal levels, so that they increase their empowerment of the benefits of actions with an ABE approach in coastal wetlands.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
| Identified Risk | Type | Impact / Probability 1: Low 5: High | Current Status | Steps Taken to Mitigate Risk
| Delays in the import process of equipment, materials and goods has delayed the financial execution of the project. | Operational | Impact: Medium (3) Probability: High (4) | High | The following measures has been implemented: 1. The project team and the Environment Agency support and maintain a permanent exchange with the new importing company (EMIDICT). 2. UNDP CO in coordination with CITMA (Economics and Planning Department, International Relations Office, Environment Agency, Project Unit), MINCEX and the importing company has carried out 4 financial analysis meetings of this project. These meetings were focused on the analysis and monitoring of all national import and purchasing processes. In those meetings measures have been adopted to ensure the implementation of the project.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The project team considers that this set of measures have prevented the Project to have a negative impact on its implementation. New measures are carrying out to accelerate the financial execution, which continues being a critical risk.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Key Milestones I. Recovery of mangrove areas along a stretch of 84 kilometers for the protection of the coast. |  | Increased the: a. Restored mangrove ecosystem area (Artemisa: Majana - Surgidero de Batabano). b. Red mangrove area along the coast (Mayabeque Batabano - Punta Mora). |  | IES and INAF conducted 2 trips to diagnose mangrove areas to intervene in the provinces of Mayabeque and Artemisa. A detailed report was delivered to the forestry companies with the type of management to be applied in each of the areas. | S
2 field expeditions were carried out to evaluate the success in the growth/survival of propagules and other indicators, such as soil and salinity, by means of permanent lots in Melena, including the participation of forestry workers, technicians and specialists from SEF, IES and INAF. The results in the growth were very positive, which indicates that the planting of red mangrove by triads method reinforced with thinning actions is efficient. A marked difference was evidenced between the parcels with actions of water restoration and those that only plantation was made due to the distance of the source of fresh water.
Four expeditions were carried out to update the health map of the mangrove ecosystem, combining field measurements and remote sensing techniques. Almost 200 monitoring points for the health of the mangrove and the swamp forests
10 technical projects to carry out restoration activities during the third year were approved by the State Forestry Service, 3 in Artemisa province (1 in Artemisa with efective 4.6 ha, and 2 in Guira de Melena with efective 53.1 ha) and 7 in Mayabeque province (2 in Batabano with efective 48.4 ha; 3 in Melena with efective 39.8 ha; and 2 in Güines with efective 11.6 ha).
499 new total hectares of mangrove forests have been benefited with rehabilitation actions for restore of the red mangrove belt, combining works for promoting natural regeneration with direct planting, along the coast of Güines, Melena and Batabano municipalities in Mayabeque province.
Maintenance was carried out in 311.7 ha (total) worked during the second year and 85 ha (total) started in the first year
2.4 km of antierosion barrier were built along the coastline of Batabanó and Guines.
2.1 km of gutters and channels were recovered by means of manual dredging in Melena to facilitate freshwater and seawater exchange.
Maintenance at 6.8 km of ditches and canals worked during the second year in Batabano and Güines
Reposition of 10% of the propagules that had been affected or lost were carried out in second year
577.3 new total hectares of mangrove forests have been benefited with rehabilitation actions for restore of the red mangrove belt, combining works for promoting natural regeneration with direct planting, along the coast of Güira de Melena and Artemisa municipalities in Artemisa province.
Maintenance was carried out in 426.5 ha (total) worked during the second year and 148 ha (total) started in the first year
88.0 km of ditches and canals were cleaned as a specialized measure for the protection against fires and to facilitate the hydrological flow in the area.
Maintenance at 68.96 km of ditches and canals worked during the second year in Artemisa and Güira de Melena
Reposition of 10% of the propagules that had been affected or lost were carried out in second year
Ten training activities were carried out to: members of the forestry sector of the territory, forestry brigades, specialists of the companies and of the State Forestry Service. Courses were held on: seeds, mycorrhizae, and rapid identification of plants. They were taught by the Institute of Ecology and Systematics and the National Botanical Garden.
Three exchanges of experiences with forestry companies or similar projects were carried out. The exchange with the forestry company of Caimanera (Guantanamo) was highlighted, in which forestry company workers and forestry service specialists from the three provinces participated. It was focused on showing the actors of the territory other experiences in the rehabilitation of mangroves and their use. Another exchange was made in Panama where relations with the "Panamanglar" network were established.
A consultancy was carried out by Dr. Luz Esther Sánchez Arias. She trained the project team in a new monitoring methodology to assess the health status of the mangroves; She also advised the technical rehabilitation and restoration actions carried out by the forestry companies.
An advisory was made for the monitoring and rehabilitation of the mangroves of the Havana Bay.
2 knowledge interchange in the mangrove restoration between Caimarera municipality, in Guantanamo Bay, and specialists from the restoration technical group and the forestry brigades in the proyect territory.
Using MODIS images, the monitoring of the behavior of the photosynthetic activity in the different forests of the area was continued. This monitoring was carried out in the areas where rehabilitation actions are carried out and also in other areas with similar ecological conditions but with better health; the latter are used as a reference.
The geographic information system continues to provide essential information to plan and guide rehabilitation actions.
| II. Restoration and enrichment of woodlands along the landward limit of the coastal wetland belt, between Majana and Punta Mora. |  | Increased the: c. Enriched border forest area. d. Control and eradication of IAS. |  | IES and INAF conducted 2 trips to diagnose swap forest areas to intervene in the provinces of Mayabeque and Artemisa. A detailed report was delivered to the forestry companies with the type of management to be applied in each of the areas. | S
14 technical projects starts execution to carry out the restoration activities of the third year were approved by the State forestry service, 6 in Mayabeque (3 in Batabano with efective 68.5 ha; 2 in Melena with efective 40.8 ha; 1 in Güines with efective 24 ha) and 8 in Artemisa (1 in Artemisa with efective 32.2 ha; 7 in Güira with efective 54 ha)
666.5 new total hectares of swamp forests have been benefited with enrichment actions of native tree species, combining works for promoting natural regeneration with direct planting in Mayabeque province.
863.0 new total hectares of swamp forests have been benefited with enrichment actions of native tree species, combining works for promoting natural regeneration with direct planting in Artemisa province.
Maintenance works were carried out in 1097.5 ha from the second year between Majana and Punta Mora.
During the the project implementation 56 km of barriers against forest fires have been maintained as a measure to protect the forests in both provinces
38 939 postures of 18 different species were produced and planted by the nursery of Cajio, province of Artemisa
41 502 postures of 14 different species were produced and planted by the nursery of Mayabeque
There are in Mayabeque province 50 ha under natural regeneration management in swamp forests, 25 ha during the second year and 25 ha during the third year of project execution in Mayabeque province
A enriched substrate with mycorrhizae is used in nurseries to promote the growth and survival of native species.
A management plan for 20 invasive alien species has been developed with information on the main characteristics and proposals for control and management for each one.
In Mayabeque province, 20 ha are reported under management of invasive alien species, among which the Indian carob and leucaena (10 ha during the second year and 10 during the third year).
In the province of Artemisa, 17.3 ha are reported under the management of invasive exotic species, including Almendro de la India, Casuarina and Majaguilla (4 ha during the second year and 13.3 during the third year).
It makes use of the invasive alien species eliminated Example: the Indian Almond is used in the production of charcoal, carpentry works, rustic buildings, and small amounts of its foliage is collected for the extraction of essential oils in laboratories of the INAF.
149.4m³ of Almendro wood and 2.6 m³ of Majagüilla wood have been extracted from Artemisa. The Almendro has been destined to the production of charcoal (obtaining 299 net bags) and the Majaguilla was used for the carpentry and rustic constructions.
| III. Incorporation of EBA as a main activity in coastal zone planning and activities of the productive sector. |  | Increased the number of: a. Provincial and municipal development plans that effectively incorporate the EBA. b. Provincial and municipal governments with knowledge management systems incorporating EBA implemented. |  | The two provinces are using the information system of the project to make decisions related to the climate change plan; also in the planning and execution of supervisions to the coastal zone, and in the incorporation of ABE actions in the local development strategies and the forestry sector economy plans. | S
The Geographical Information System continues to be used to obtain reliable information on the sites where the restoration works are carried out, and the dangers and vulnerabilities of the coastal zone and the prospects for climate change up to 2100.
There were updated the follow issues: the project database with the latest results of the mangrove health map, the technical projects, the project information on the Environmental Agency website, the Facebook profile and the National Institute profile Agroforestry, and on the local websites of Artemisa and Mayabeque.e.
It is located all the information generated and collected by the project, since September 2014, in the main node in the National Implementation Office, making it easier to use.
The draft of a publication containing the foundations of the EBA has been finalized. It is aimed at perfecting the way in which this theme is included in the local development strategies of the 6 municipalities.
The EBA approach is included in the Local Development Strategy of the 6 municipalities of both provinces. This is the result of the participation of stable form in the meetings of the local development groups and taking advantage of the process of improvement that takes place at the moment.
Included in the economic plans of governments and companies actions for adaptation to the impacts of climate change. The actions of the project are included within the provincial environmental strategy of Artemisa and Mayabeque for the period 2016-2020 and in the strategic plan of the agricultural and forestry sector of the republic of Cuba until 2030.
The achievements and challenges of the project were presented in a meeting convened by the CITMA Minister with the presence of the presidents of the assemblies and the heads of the administrations of the project's intervention areas. One of the positive aspects of the meeting was the recognition of the importance of the knowledge disseminated by the project about the role played by the mangrove ecosystem in the protection of the coastal areas of the country.
24 training actions were carried out to members of the provincial government. The topics addressed were: the achievements and challenges of the project, economic valuation, the life task, among others.
20 training actions were carried out to members of the municipal government, and decision-makers of the key productive sectors (fishing, energy, agriculture, physical planning, water, health and education).
The Economy and Environment Workshop was held in the municipality of San Nicolás de Bari, coordinated by the provincial governments. It was about the activities of the Living Mangrove project and its economic significance. This activity was an exchange of experiences.
| IV. Local communities increase the knowledge and develop skills to participate in EBA activities. |  | Increased the number of: c. Community members (men and women) belonging to local volunteer groups addressing environmental and adaptation issues. d. Local schools with curricula incorporating adaptation to climate change. e. Awareness materials on climate change adaptation issues produced by local media. |  | Created 2 new groups of volunteers, one at Playa Mayabeque with 25 members (3 women) and another at Playa Majana with 5 members and 5 boats. These groups support: the inspections and controls carried out on the project, the forestry brigades, and help in the dissemination of the results of the project. | S
14 training actions were carried out by the groups of volunteer activists, using the training room (10) and talks in homes (4) in Mayabeque.
The forest guards carry out 58 conversations and talks with 76 citizens of the coastal communities. The topics addressed were: the importance of the role of the community in the protection of the ecosystem and the importance of the forest fire prevention campaign in Artemisa (28), Guira de Melena (18) and Alquizar (12).
4 awareness-raising activities were carried out in the communities. These activities were organized by the governments on significant dates, such as the "Mangrove Festival" for the world day of the mangrove in Batabano and the activities for the day of the wetlands in Cajío beach.
In Surgidero de Batabanó the "Festival del Monte" took place; which was dedicated to the Mangrove. This festival was organized by the governments in coordination with the initiative "Planta" of the Cuban Society of Botanica. More than 100 people participated in this activity, achieving a positive impact beyond what was expected.
Two exhibitions were held in Old Havana and the city of Pinar del Rio, which includes 40 billboards with photographs of the company "Mundo Latino" and the project "Costa Salvaje" of Mexico.
34 schools in the two provinces were include CC and EBA issues in the syllabus for 2016-2017 course, of which: 5 are mixed centers, 18 primary schools, 4 secondary schools, 1 pre-university school of basic science, and 6 municipal university centers.
62 professors were trained in the third edition of the postgraduate course "Perfection of Environmental Education" for sustainable development in the national education system.
Created 5 circles of interest in 4 schools with 60 children, who carry out environmental education activities, on issues related to the importance and care of coastal ecosystems. The educommunicative Workshop with children of the Manuela Sanguily school was very relevant.
The award ceremony for the second edition of the "Manglar Vivo" competition was held with the presentation of 149 works in the different modalities, in both provinces.
Educational activities were carried out with the schools and the circles of interest; for example: the workshop "The Mangrove that unites us", which consisted of an exchange of drawings between several children of Surgidero de Batabano and Havana; and the scientific event for children "Por los Caminos de la Ciencia": with the participation of selected students in the 3 municipalities of the project and CITMA specialists as jury.
The project signed an agreement with the Agrarian University of Havana (UNAH), which supports the joint work on knowledge management, the incorporation of the ecosystem-based adaptation approach in the study plans and the execution of cost-benefit studies of the application of the ABE.
4 students from the University of Havana trained in monitoring the health of the mangrove ecosystem
Three training actions were carried out for journalists and communicators from the local media. The most relevant activity was the "Provincial Workshop on Climate Change, Life Task and Live Mangrove" with the participation of 30 representatives of radio, television, correspondents and the written press.
49 materials and reports were produced. Made and disseminated by national television (8), local television (16), international television (2), local radio (11), national radio (6), local written press (2), national written press (2) and web sites (2)
3 audiovisuals produced by Mundo Latino: - the homage to "Leda", outstanding scientist in the study of the mangroves and technical coordinator of the project that died at the beginning of 2017; - the "Life Task"; and - documentary about the mangroves as a whole with "Costa Salvaje". All audiovisuals have been presented by national television on several occasions.
8 reports produced and broadcast by national news programs about the project, its interventions, progress and perspectives.
16 reports produced and broadcast by local television stations with a wide range of approaches and audiences from children to adults. Pro example: "USB 3.0" dedicated to the mangrove forest and adaptation to CC, "Double Click" with children from the Bac Ly Primary School of Surgidero de Batabanó and "El Laboratorio" with young people working in the forestry brigades.
Two foreign television stations made reports of the project. The American TV channel PBS and its educational program "NewHour", and another that shows the exchange of experiences between the forestry sector of the project area and the "Panamanglar" network carried out in Panama.
17 interviews and reports were made on the local radio (11) and the national radio (6) about the actions of the project, the importance of the mangrove and the role of the actors of the territory.
4 articles about the project were published in the national press. One of the most relevant articles was "Between the sea and the land" published in the Bohemia magazine, No. 21, Year 109, of October 13, 2017 (http://www.bohemia.cu)
as part of the communication campaign a lot of materials have been designed and produced: posters, stickers, radio spots, circulars, information spots, educational kits, calendars, adhesive labels for dissemination and raising awareness in the local population.
6 knowledge systematization products were completed, 4 of them were printed and disseminated and 2 are in the design process
3 scientific articles were published by the research institutes associated with the project. Highlights topics such as seed management, honey production from mangrove species and new reports of species of flora in the area.
The results of the project were presented at national (5), provincial (1) and international (1) scientific events. In the Environment Convention the participation of several beneficiaries of the intervention areas (children, workers and governments) was achieved.
| V. Strengthened institutions (provincial and municipal governments, forest service corps, Coastguard and Fishery Departments) supporting EBA actions, within the framework of action plans actively updated and implemented. |  | Increased the: a. Training activities and technical support in coastal communities (to incorporate EBA approaches) undertaken by provincial and municipal governments; b. Inspection activities to coastal areas by provincial and municipal governments to incorporate EBA. |  | Two training courses were held in the 2 provinces for the preparation of comprehensive inspections with the ABE approach. | S
The Artemisa forestry company built 3 observation towers to detect forest fires and 8 houses for surveillance and protection.
8 training events were held for: the Professional Brigades (10 men) of the forest ranger, and specialized brigades of the UEB silviculture of Cajío (16 men) and the UEB Silviculture of Mayabeque (10 men).
In 2017, 28 contraventions were applied, evidencing a reduction of 75% with respect to the contraventions applied at the beginning of the project.
The forest brigades and forest ranger were mobilized during 12 fires that occurred in the intervention area of the project, which affected 6.3 ha of forests and 650 ha of swamp grassland.
8 inspections were carried out from Majana to Batabanó by the new regulation group for the South Dike, in the Artemisa province.
There were 59 naval tours. The protection circuit is redesigned and the effectiveness of the protection of the coast is improved. 375 patrols were carried out in terrestrial areas.
Five comprehensive inspections were carried out in the intervention areas of the project: 2 in the province of Mayabeque and 3 in the province of Artemisa. The participation of all the regulatory institutions of each municipality was achieved.
In the National Workshop 52 members of the State Forestry Service of the country were trained in ecological restoration and adaptation based on ecosystem.
| VI. Consolidated information on the costs and benefits of EBA available for decision makers and planners. |  | Increased the: c. Studies and methodologies carried out to estimate the cost - benefit ratio of the ABE approach, available to planners and decision makers, is increased. |  | Four training actions were carried out to specialists from different institutions in the economic valuation of goods and services of the ecosystems. | MS
The demographic data on direct and indirect beneficiaries in the project area, which covers the two provinces and 6 municipalities, were updated. It was determined that 35 038 inhabitants receive direct benefits from the project's actions, (evaluated from the coast to the maximum flood level due to category 5 hurricanes in scenario 2100). While, 230 736 inhabitants receive indirect benefits in the 6 municipalities involved in the project.
A draft of the methodology for the economic valuation of the ecosystem goods and services of the coastal wetlands south of Artemisa and Mayabque has been completed.
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Luis David Almeida Famada
| Email: | almeidafamada@ama.cu; almeidafamada@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
In its third year, the project shows a significant progress in all the expected results, achieving over-compliance in some indicators such as: - training actions for communities, - dissemination of activities carried out in different media platforms, and - schools that include topics of ABE. This positive result has been possible, thanks to the high degree of commitment and ownership of the project by the governments and local institutions, also to the impact of the awareness-raising work carried out, aligned with the "Life Task". There is a positive trend in the restoration work of the coastal ecosystems. It have been rehabilitated 4774.9 ha (2047.9 ha in mangrove and 2727 ha in bordering forests), which has been certified by forestry companies. This has been possible thanks to the combination of the support provided by the project to the forestry sector in the intervention area, and also to the national co-financing contributed by the Forest Development Fund (with a contribution of more than 6 million pesos , surpassing what was committed at the beginning of the project). Component 1. Progress in increasing the resilience of ecosystems, through rehabilitation and restoration, has had a positive trend, finding us 64% with respect to the final goal. The improvement has not only been in the number of areas benefited, but also in the quality of IAS management work, and in the increase of native species in the nurseries. Even so, it is important to continue incorporating complementary actions in the intervention area; for example: placement of honeycombs of native bees to enhance pollination activity and natural regeneration. There are several areas in which actions of control, management and exploitation of invasive alien species are carried out in success way. There is a management plan for the 20 most harmful species of these coastal wetlands. Component 2. Work with governments has begun to show important results; for example: the inclusion of the ecosystem-based adaptation approach in several of the territorial management instruments, such as local development strategies, the environmental strategy and the climate change adaptation plan. Although territorial governments use the information and knowledge generated by the project to make decisions, there is no available automated system that allows them to access to this information in a fast and organized manner. The reduction of social and sectoral vulnerability is progressing, concentrating above all on capacity building and the commitment of decision makers in the territories, based on the execution of the communication strategy. The work with the schools located in the project area has generated influences in schools not included in this area, sample of this are the different circles of interest related to mangroves and climate change that have been generated outside the direct intervention of the project. Finally, there are several indicators that are almost fulfilled with respect to the life of the project. Component 3. The actions to guarantee the sustainability of the project have been consolidated, evidenced by the passage of Hurricane Irma and the rapid recovery shown by the provinces strengthened by the project. Training and awareness-raising actions aimed at the population have been unprecedented, because of the 9 training and technical support activities committed, 209 have already been carried out. In addition, in the different interviews and during the midterm evaluation, the high degree of awareness of the inhabitants of several of the project's objective settlements was evidenced. It is reported a gradual decrease in the contraventions detected by the Ranger Corps; In addition, in the interviews conducted during the control and inspection work, there is a real awareness of the population about the importance of the mangrove ecosystem to reduce the effects of coastal floods, erosion and salinization, and even see it as an alternative to avoid the relocation of their communities. On the other hand, there is a real delay in the realization of the cost - benefit studies. In this respect, the efforts have been concentrated in the creation of capacities so that these analyzes are carried out by members of the key institutions of the territory involved (CITMA, forestry sector). So, that once the project had concluded they can able to continue updating these studies. In addition, progress was made in the publication of the methodology and the compilation of all the information necessary to begin the analyzes. In the fourth year of the project implementation, it is a priority to complete the studies in at least 3 municipalities.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Key Milestones I. Recovery of mangrove areas along a stretch of 84 kilometers for the protection of the coast. II. Restoration and enrichment of woodlands along the landward limit of the coastal wetland belt, between Majana and Punta Mora. Component 1. Reduction of the impacts of coastal flooding through the recovery of coastal ecosystems. |  | Increased the: a. Restored mangrove ecosystem area (Artemisa: Majana - Surgidero de Batabano). b. Red mangrove area along the coast (Mayabeque Batabano - Punta Mora). c. Enriched border forest area. d. Control and eradication of IAS. |  | The progress in those key milestones contribute to compliance with Component 1 of the project. Key Milestone No. I had a satisfactory compliance, because the expected progress in indicators a and b were achieved. The main progress are: a. Artemisa, 1151 ha of the mangrove ecosystem have been benefited with rehabilitation actions (67.3% of the final goal). b. Mayabeque, 895.7 ha of the red mangrove have been increased (69.4% of the final goal). In both cases, the level of compliance is very close to the final goal of the project. Key Milestone No. II had an adequate compliance, because the expected progress in indicator c was overfull and the indicator d was so close to compliance. The main results are: c. Although there were significant advances (nurseries, planting of native species, control of exotic species, etc.), there is a slight delay in meeting the goal of rehabilitated areas in swamp forests. d. Management plans for 20 invasive alien species are prepared and approved. It is reported the control and eradication of 4 IAS in 65 ha. Despite of the slight delay reported in the compliance with indicator c, the MTR considers that it is recoverable in the life time remaining for the project. | MS
| Key Milestones III. Incorporation of EBA as a main activity in coastal zone planning and activities of the productive sector. IV. Local communities increase the knowledge and develop skills to participate in EBA activities. Component 2. Integrated and participatory management of coastal ecosystems to increase resilience to climate change. |  | Increased the number of: a. Provincial and municipal development plans that effectively incorporate the EBA. b. Provincial and municipal governments with knowledge management systems incorporating EBA implemented. c. Community members (men and women) belonging to local volunteer groups addressing environmental and adaptation issues. d. Local schools with curricula incorporating adaptation to climate change. e. Awareness materials on climate change adaptation issues produced by local media. |  | The progress in those key milestones contribute to compliance with Component 2 of the project. Key Milestone No. III had an adequate compliance, because the expected progress in indicator a and c were achieved, while the indicator b had slide delayed. The main progress are: a. The two provinces and the 6 municipalities involved in the project have already incorporated the ABE approach in its development plans and strategies. In addition, as part of the implementation of the “Life Task”, the project had been advising the incorporation of the ABE approach into the economy plans in both provinces. b. Although significant progress is reported in the preparation of the knowledge management system incorporating the EBA, it is not yet fully available to the provincial and municipal governments. c. There are 3 volunteers groups that promoting activities related to environmental and adaptation issues: Surgidero de Batabanó (with 16 members, 9 women); Cajio (with 10 members, 2 women) and Playa Majana (Fishing Federation, with 6 boats). Key Milestone No. IV had a satisfactory compliance, because the expected progress in indicator d and e were achieved. The main progress are: d. In 34 schools methodological guidance is given to teachers on how to include the topics of Climate Change and ABE in the curricula. Groups of students from 11 elementary schools are trained systematically in adaptation to climate change and ABE issues through the “Circulos de Interes”. e. A large amount of awareness materials on climate change and the adaptation measurements were produced and disseminated by local and national media. The MTR highlighted the high level of ownership found in all institutions and in the communities involved in the implementation of the project. | MS
| Key Milestones V. Strengthened institutions (provincial and municipal governments, forest service corps, Coastguard and Fishery Departments) supporting EBA actions, within the framework of action plans actively updated and implemented. VI. Consolidated information on the costs and benefits of EBA available for decision makers and planners. |  | Increased the: a. Training activities and technical support in coastal communities (to incorporate EBA approaches) undertaken by provincial and municipal governments; b. Inspection activities to coastal areas by provincial and municipal governments to incorporate EBA. c. Studies and methodologies carried out to estimate the cost - benefit ratio of the ABE approach, available to planners and decision makers, is increased. |  | The progress in those key milestones contribute to compliance with Component 3 of the project. Key Milestone No. V had a satisfactory compliance, because the expected progress in indicators a and b was achieved. The main progress are: a. All training activities planned in support of EBA were carried out. Also, all the prevention actions related with forest fires and for the protection of natural resources were carried out. b. There were carried out comprehensive inspections in the intervention areas of the project coordinated by the government. In both cases, the level of compliance is very close to the final tasks of the project. The MTR evidenced a high level of knowledge and empowerment by local actors as a result of the activities developed by the project | MS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Gricel Acosta Acosta
| Email: | gricel.acosta@undp.org
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. In this period (third year of implementation) the project shows a positive progress in meeting the main milestones. This trend brings it closer to meeting the project's targets and final goal. However, the project shows a delay in complying with some indicators and shows low financial execution. This is a worries situation because this project must close in 2019. Taking in to account this considerations the overall evaluation proposed is MS. The main aspects that support this evaluation are: • There is a delay in compliance with the rehabilitation actions in the swamp forests (only had been benefited 2,727 ha - 63.1 % of the final target). • The knowledge management system that incorporates EBA is not yet fully available for provincial and municipal governments. • The execution of the cost-benefit estimation studies of the ABE approach have a significant delay. • The project has a low financial execution (69%). The arguments that support our evaluation by components are: Component 1. There is evidence of progress in the recovery of coastal ecosystems because the expected results in this period were reached. For this reason, we considered that this component has a satisfactory performance. Nevertheless, in the next period the project unit must focused in to accelerate the rehabilitation actions of the swamp forests in the sector Artemisa-Mayabeque, in order to recovery the accumulated delay in this target. This delay is due to the fact that it is the most complex ecosystem to rehabilitate, it requires equipment that has not been acquired or were acquired recently, it requires the creation of nurseries, and it is where the project team has least experience. Component 2. The results achieved in this period contribute to enhance the integrated and participatory management of coastal ecosystems. We considered that this component has a satisfactory performance. Although progress is reported in the design of the integrated knowledge management system that incorporates the EBA in each territory, this tool is still not available to governments, which represents a delay in complying with this indicator. Component 3. It is considered an evaluation of MS because, the studies and methodologies to estimate the cost-benefit of the EBA approach have not yet been made available to planners and decision-makers, reflecting delay in the reached of this indicator. It is recommended special attention be paid to the progress of this aspect in the planning of the last year of implementation. 2. Detail critical risks that have affected progress. We consider that the accumulated delay in financial execution constitutes a critical risk. By the end of December 2017, Project cumulative disbursment rate is 69%, related to the total cash availability ($3,925,280). This means that in the two years that remains to complete, the Project must run about 2,88 MMUSD, which is a huge challenge. The report of the MTR concludes that this delay is the result of the combination of several events that occurred during the project implementation, these are: - The start of the project outside the fiscal year created difficulties for the initial implementation; - The agreements with the institutions responsible for the implementation of the project in the intervention areas took more time than expected; - The adjustments for the revision of the technical worksheets in the mangrove, nonexistent before the project, took time to be formulated and formalized; and - Change in the importing agency, which required an initial period of training, learning and adjustment between the agency and the project, which generated delays. In addition, the agency that initially handled international acquisitions, had so much workload that also generated delays in the execution of this and other projects. For this reason, the procurement plan in 2014 and 2015 were affected. Following a recommendation from the MTR, a strategic re-planning is carried out for the two years remaining for the project. The project identified and presented all pending requests to the importing company. In addition, MINCEX, CITMA and UNDP continue to hold systematic meetings to support and accelerate the procurement process. 3. Outline response to MTR undertaken this reporting period. The Project Management Unit is implementing 19 measures to meet the MTR recommendations, which was approved by the National Steering Committee. This plan is focused on improving: design, budget performance, compliance with project goals, performance and verification, impact and verification, and project sustainability and impacts (the plan of measures is attached)
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: To increase the resilience of populations living in the coastal zone ofthe provinces to Mayabeque Artemisa and the effects of climate change. | I. Areas with high rates of health and the conditions of the mangroves (soil and salinity of the water, the density of the canopy, the existence of local regimes of protection). | Coastal ecosystems that cover 7 318 ha are degraded, have excessive levels of salinity due to seawater intrusion and the obstruction of channels and have a limited protection regime. | Rehabilitation actions have been developed in 4774.9 ha (in mangrove forests - 2047.9 ha and cienaga forests - 2727 ha), which represents 65.25% with respect to the goal at the end of the project. The monitoring system of the health status of mangrove forests and swamp forests has been maintained by combining field work with remote sensing techniques. | 7 318 Ha (total area where will be carried out reforestation of mangrove, the restoration of the mangrove ecosystems, and the enrichment of the forested areas inland) Note: the rates of coastal mangroves and wetlands must be nominated in the methodological documents to be developed at the start of the project.
| II. Numbers of people (men and women) with reduced vulnerability due to proximity of functioning mangrove forest and wetland ecosystems. | 17 524 People in 47 communities are directly affected by coastal flooding. | Awareness raising activities about about the importance of coastals ecosistems have been conducted with the local government and inhabitants of local communities. These included coastal flooding, mitigation measures, mangrove forest restoration, and opportunities that the Project can bring to the communities to implement national policies on climate change adaptation. | 21 502 People (of which at least 45% are women) directly affected by the reduction of coastal flooding.
|  | 270,705 People are indirectly affected by the impacts of the phenomena associated with the CC on economic activities. | Awareness raising activities (about flooding impacts, mitigation measures, the importance of the mangrove restoration, etc) have been conducted in all communities located in the interventions areas of the project. This activities has involved the governments, decision makers of selected productive sectors, and regulatory authorities. Theses actions has contributed to increase the level of risk perception of the people. | 270,705 People (at least 45% are women) benefit indirectly by the reduction of the impact of the phenomena associated with the CC on economic activitie.
| 1.1 Area (ha) of red mangrove is established along shore between Batabanó and Punta Mora. | 533ha | Rehabilitation actions have been developed in 895.7 ha of red mangrove forest (includes restoration of ditches and canals, management of natural regeneration and sowing of propagules). It represents the 69.4% of final tarjet of the project. | 1290,6 ha of which 85% survived* (1097 ha) *Survival can only be measured 3 years after planting
| 1.2 Cumulative area of mangrove ecosystem restored between Majana and Surgidero de Batabanó. | 144ha | Rehabilitation actions have been developed in 1152.2 ha of the mangrove ecosystem (includes restoration of ditches and channels, management of natural regeneration and sowing of propagules). It represents the 67.31% of final tarjet of the project. | 1711,9 ha of which 85% survived* (1455,1 ha) *Survival can only be measured 3 years after planting
| 1.3 Cumulative area of landward edge woodlands restored and enriched. | 939 ha | 2727 ha of landward edge woodlands were enriched by planting native species and encouraging natural regeneration. It represented the 63.19% of of final tarjet of the project. | 4315,5 ha of which 85% survived* (3668,2 ha) *Survival can only be measured 3 years after planting
| 1.4 Numbers of IAS management plans developed. | 0 | In the formulation process a Management Plan for 20 invasive alien species; It contains information on the main characteristics of these species and proposals for control and management measurements for each one. 4 Invasive Alien Species have been eliminating in 37.3 ha of the intervention area. | 1, covering 7,318ha
Outcome Indicator | 2.1 Numbers of provincial and municipal development plans that make specific provision for EBA. | 2 provincial and 6 municipal governments are preparing development plans that do not include EBA. | The ABE approach has been included in 3 management instruments. This approach has been included in the local development strategies in 6 municipalities, in the environmental strategy of the 2 provinces, and in the plan to combat the climate change in the 2 provinces and the 6 municipalities. | 2 provincial plans and 6 municipal plans
Outcome Indicator | 2.2 Numbers of provincial and municipal governments with EBA-related knowledge management systems in place. | 0 | The two provinces use the information system of the project to: make decisions related to the plan to combat the climate change, the execution of inspections to the coastal areas, and the incorporation of ABE actions in the local and sectorial development strategies. | 2 provincial and 6 municipal governments
Outcome Indicator | 2.3 Numbers of community members (men and women) belonging to local voluntary groups addressing environmental and adaptation issues. | 0 | 4 working volunteer groups: one in Surgidero de Batabano (with 16 members, including 9 women), one in Cajio (with 10 members, including 2 women), one in Playa Mayabeque (with 25 members, of them 3 women), and another at Majana beach (with 5 members and 5 boats). These groups support: the inspections and controls carried out on the project, the transfer of the trunks to make the palisades, the dissemination of the work of the project in the area. | 1 group with at least 15 members (of which at least 45% are women) in four municipalities
Outcome Indicator | 2.4 Numbers of local schools with study programmes incorporating adaptation issues. | 0 | 34 schools in the two provinces include CC and EBA issues in the syllabus for 2016-2017 course, of which: 5 are mixed centers, 18 primary schools, 4 secondary schools, 1 pre-university school of basic science, and 6 municipal university centers. Incorporando actividades como trabajos practicos y capacitaciones teorico practicas en los diferentes circulos de interes ambientalistas. | 16 primary schools 15 secondary schools 3 municipal universities 1 teacher training institute
Outcome Indicator | 2.5 Numbers of dissemination and awareness raising materials on adaptation issues, produced by local media | 0 | 8 audiovisuals were produced and broadcasted on several occasions by national and local television stations, related to the objectives and advances of the project, the mangroves and the importance of their protection. It highlights the documentary made in tribute to Leda Menendez, highlights researcher and project member. | 17 audiovisual 3 local television . 5 local radio 2 articles
34 reports were broadcasted by local (20), national (12) and international (2) television stations about the project, its actions, progress and perspectives as well as the importance of mangroves and other coastal wetlands.
30 reports and interviews were disseminated on national (6) and local (24) radio.
9 articles were published in national (3), local (9) and web (2) media. Many with accceso via internet.
Outcome Indicator | 3.1 Frequency of training and technical support visits carried out by provincial and municipal governments to coastal communities in support of EBA | 0 | 209 training and technical support actions were carried out with the coastal communities. These activities were conducted by the government, the forest ranger and research institutes. | 3 training and technical assistant activities undertaken per year by technical authorities to coastal areas.
Outcome Indicator | 3.2 Frequency of inspection visits to coastal areas by provincial and municipal governments in support of EBA | 0 | Lead by the goverment, 14 comprehensive inspections were carried out in the intervention areas of the project; 6 in the first year, 3 in the second year and 5 in the third year. In these inspections were participating representatives of all the regulatory institutions of each municipality: the CAP and CAM, SEF, CGB, TGF, PNR, and the fishing inspection department of MINAL. | 3 inspection activities undertakern per year by provincial municipal goverment and other regulatorities authorities
143 maritime journeys along the coast (1 during the first year, 83 during the second and 59 during the third year) and 555 on land (180 during the second years and 375 this third year) were carried out for the monitoring and protection of natural resources within the Project intervention area for the Forest ranger.
Outcome Indicator | 3.3 Number of studies and methodologies carried out to estimate the cost - benefit from the implementation of the approach ABE, available for planners and policy makers. | 0 | 8 training actions were conducted for specialists from different agencies, 2 in provincial governments governments, with participatory approaches in economic valuation of ecosystem goods and services. | 3
The draft of the book "Methodology for the economic valuation of the ecosystem goods and services of the coastal wetlands south of Artemisa and Mayabque" was completed.
Information was gathered on the value of fixed asset, forest heritage, flora and fauna, volume of agricultural, fishery and livestock raising production, for the assessment of the current state the coastal zone in the 6 municipalities.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | During the mid-term review were identified positive results in the project implementation, these are: - The wide production of audiovisual materials showing the work done in the coastal communities and the role of the local leaders (example: - the documentary "Creciendo", with testimonies before and after the intervention of the project; - and - documentary "Bosque Lost"). The tribute made to Dr. Leda Menéndez with the documentary "A Leda"Great had a great impact. This documentary shows the life and work developed by this renowned Cuban scientist, who has become a national inspiration about the importance of these ecosystems. - The dissemination and coverage of territory activities by radio stations of Artemisa (ARTV) and Mayabeque (Tele Mayabeque) has also been very positive. The transmission of programs dedicated to the results of the project by Cubavisión Internacional and Canal Caribe has had a great impact. Press coverage with national issues such as the Granma newspaper and the Bohemia magazine. - The integration of the scientists with the forestry specialists and technicians of the involved companies, allowed: - to identify the best and worst practices to be applied in the restoration of the mangrove ecosystem and coastal forests, and - the preparation of methodological materials to execute the actions of restoration and care of nurseries of native species. - The project has signed agreements with the entities of the MES involved in project tasks (the School of Communication, University of Havana and the Agrarian University of Havana, Mayabeque). - The project family has been expanded and strengthened (scientific institutions, forestry companies, CAP, CAM, AP, CGB, etc.), and also with the communities that benefit from the project.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There is a significant delay in the financial execution of the project in this period. However, the contribution from the co-financing of the national counterpart was over fulfilled (142.3%). The execution delay was mainly due to difficulties of the importing agency. A plan of measures to recover this delay was prepared and implemented. This delay did not cause non-compliance in the fulfillment of the project's goals.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | In this period, no changes have been made in the project design nor in the outputs in the logical framework.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | In this third year of the project, progress has been reported in gender issues, mainly with women and young people directly and indirectly benefiting from the results of project implementation. The brigades of the Costa Sur Agroforestry Company increased their workforce with the incorporation of 10 women and young people from the coastal communities. These people are directly involved in restoration tasks with an ABE approach and in nursery care with tube technology. The average monthly salary of the workers of this company has been increased from 333.00 cup to 1200 cup. Meanwhile, in the brigades of the Mayabeque Company, the workforce has incorporated 6 women and young people from the coastal area. The increase of the salary and the delivery of means, tools and equipment promoted by the project have favored the incorporation of new workers. In addition, there are 4 groups of volunteers (32 members), 14 are women.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | We have learned that, in the design of future adaptation projects to climate change for the coastal zone, the hydrographic basin approach must be taken into account. In other words, it is necessary to consider the management effects upstream and downstream of the intervention area. In addition, indicators of impact and tasks must be included to ensure the sustainability of the project in the long term.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The measures implemented by the project have a great potential for replication inside and outside the intervention area, because the mangrove has shown a great adaptive capacity and responded positively to the restoration interventions carried out. We recommended to review and update (from the technical and economic point of view) before to execute the rehabilitation actions that will be carried out by the forestry company, because it is a key factor to raise the interest of this productive group. In addition, must be considered that the social resilience is not limited to increasing the protection function that ecosystems offer to face the impacts of climate change, it also incorporates attention in the aspects related to the adaptation and improvement of the livelihoods of local inhabitants.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | The lessons learned are: - The correct application of the principles of ecological restoration in the mangrove ecosystem, taking into account a diagnosis and the preparation of the ecosystem health map. - Constitution of a multidisciplinary team to plan and develop the adaptation actions required by the coastal zone. - Incorporation of adaptation actions in the local development plans.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The project has developed and validated a methodology for the restoration of coastal wetlands, this methodology is available to be applied in other areas of the country. Groups of experts in coastal ecosystems have been set up in the research centers directly linked to the project. The forestry brigades are able to carry out the rehabilitation actions with the required quality. So, the technical conditions to scale the results of the project are created.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The active participation of leaders and coastal communities in activities is a key link to achieve the goals of the project. The training of community leaders on topics such as: climate change, life task, local development and ecosystem services guarantee the sustainability of the project's results. In addition, the involvement of the schools guarantees the environmental education of the young generations in transcendental aspects such as the EBA, and the services provided by the coastal wetlands.
What measures are/have been put in place to ensure sustainability of the project/program results? | Incorporation of adaptation actions in the development plans at the municipal and provincial levels; this ensures the sustainability of the achievements. Incorporation of restoration / rehabilitation actions in technical projects and improvement of control indicators.
What measures are being/could have been put in place to improve project/program results? | It is considered that it would be very useful to implement a pilot project with local families to promote beekeeping (with native bee); for obtaining honey and wax (non-wood forest products). In addition, this action could enhance pollination in the biological cycles of mangrove species and swamp forests, contributing to the ecological restoration of coastal wetlands.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The project has made an adequate use of the available information and knowledge. Among the documents and information used are: Annual reports of the Mayabeque and South Coast Companies, the Red List of the Flora of Cuba (2016), the protocols for the control protocols of EEI, the annual reports of the Forest Ranger, the inspections reports, and census data (ONEI).
If learning objectives have been established, have they been met? Please describe. | The learnings generated by the project have been included in the development plans of the coastal municipalities, this allows their technical and financial planning. The results of the project are shown in government meetings, this allows decision making as adaptive management.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | All the information that the project needs has been available.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The accumulated experience by the project team has motivated to carry out the redesign of the Communication Strategy; also to establish a mechanisms to measure the impact of the communication strategy and ownership sense of the involved people. Aditionaly, it is proposed to start a designing process of the Knowledge Management System generated by the project.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 84007
Implementing Entity | United Nations Development Program
Type of implementing entity | MIE
Country | Cuba
Region | Latin America and Caribbean
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 288224 | 17519 | 270705 | Total | 281505 | 10800 | 270705 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 49% | 48% | 50% | % of female beneficiaries | 41% | 38% | 50% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 15% | 15% | 14% | % of Youth beneficiaries | 15% | 13% | 14% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  | Coastal flooding | 2: Partially effective | Total |  | Coastal flooding | 4: Effective | Total |  | Coastal flooding | 3: Moderately effective | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Multi-sector | National | 2: Undertaking or updating of assessments in progress | 1 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated | 1 | Multi-sector | Regional | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 3: Dissemination and communication | Geographical coverage | Regional | 1 | 4: Response capability | Geographical coverage | Local | 1 | 4: Response capability | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 6 |  |  | Number of municipalities | 6 |  |  | Number of municipalities | 6 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Coastal management | 2: Low capacity | Total | 88 | Coastal management | 4: High capacity | Total | 132 | Coastal management | 4: High capacity | Total
|  | % of female targeted | 0 |  |  | % of female targeted | 25% |  |  | % of female targeted | 40% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Coastal management | land | 4: Effective |  | Coastal management | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 677 | ha rehabilitated | 1: Ineffective | Mangroves | 3002 | ha rehabilitated | 4: Effective | Mangroves | 2047 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 939 | ha rehabilitated | 1: Ineffective | Forests | 4315 | ha rehabilitated | 4: Effective | Forests | 2727 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 |  |  |  | 84 | Natural capital | Coastal management | Mangrove reforestation | 60 | Natural capital | Coastal management | Mangrove reforestation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 5: All (Fully integrated) |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 |  |  |  | 8 | 4: Enforced (Most elements implemented) |  | 4: Effective | 8 | 4: Enforced (Most elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on H113: Tomas Escobar: 84 km de costa rehabilitados
Note on L113: Tomas Escobar: 60 km de costa rehabilitados
Note on H129: Tomas Escobar: 6 municipales y 2 provinciales

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness. 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions. 2.2. Number (men and women and other vulnerable groups). 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses. 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None. 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements). 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved. 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement. 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention. 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.