## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | January 2018 - December 2018
| Project Title: | Reduction of vulnerability to coastal flooding through ecosystem-based adaptation in the south of Artemisa and Mayabeque provinces.
| Project Summary: | The proposed project seeks to reduce the vulnerability of communities in coastal areas of Artemisa and Mayabeque provinces in southern Cuba from climate change (CC) related phenomena including coastal erosion, flooding and saltwater intrusion. This will be achieved through Ecosystem Based Adaptation (EBA), taking advantage of the proven potential of mangrove forests and associated coastal wetlands to limit the effects of wave erosion and coastal flooding, which are among the most damaging results of climate-change related SLR and storms. The project’s objective will be achieved through investments in three complementary components. Component 1 will focus on concrete investments in ecosystem recovery, leading to improved coastline resilience to the impacts of wave action, and improvements to coastal morphology which will reduce seawater incursion. Component 2 will focus on integrated and participatory management of coastal ecosystems, through mainstreaming EBA into integrated coastal zone planning and productive sector activities, promoting buy-in, participation and governance in local communities and developing knowledge management systems at community level. Component 3 will focus on establishing a favourable enabling environment at regional level for the effectiveness and sustainability of adaptation investments, through the provision of consolidated information on costs and benefits of EBA to decision makers and planners and the strengthening of institutions supporting EBA actions, within the framework of updated and actively implemented action plans.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | 84007 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Cuba | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Coastal areas of Artemisa and Mayabeque provinces in southern Cuba | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-05-19
IE-AFB Agreement Signature Date: |  | 2014-06-19 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | September 2014 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | October 2017
| Terminal Evaluation Date: | September 2019
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | - Inception workshow report, Quarterly Reports from UNPD. - 1st issue of Living Mangrove Forest bulletin. 2nd issue of Living Mangrove Forest bulletin. - http://www.cu.undp.org/content/cuba/es/home/presscenter/articles/2015/04/14/crece-el-proyecto-manglar-vivo.html. - http://www.radiohc.cu/noticias/ciencias/138840-avanza-en-cuba-proyecto-internacional-manglar-vivo. - http://www.radiomayabeque.icrt.cu/es/167-valor-agregado-en-espanol/5768-proyecto-manglar-vivo. - http://www.guerrillero.cu/pinar-del-rio/2802-inauguran-expo-manglar-vivo.html | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.ama.cu/manglar/manglar.html | Democratic Republic of the Congo
|  | https://www.facebook.com/manglarvivo/?ref=ts&fref=ts | Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Luis David Almeida Famada | Dominican Republic
| Email: | almeidafamada@ama.cu; almeidafamada@gmail.com | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: |  | Equatoral Guinea
| Email: |  | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Gricel Acosta Acosta | Fiji
| Email: | gricel.acosta@undp.org | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: |  | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 31 December 2018
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31 December 2018 | 3972734
Add any comments on AF Grant Funds. (word limit=200) | By December 31st 2018, the Project's delivery rate was 71% of the total budget. Total expenditure for the year 2018 was $1,260,847. All the balances of previous contracts (signed before 2018) were paid. The next reporting period will be for January 2019 to December 2019. A 1-year extension is being requested to the AF Secretariat from September 2019 to September 2020. An amount of $578,772 corresponds to remaining balances of contracts signed in 2018. In addition, by the first quarter of 2019, new contracts for $409,200 (corresponding to goods internationally procured) are being signed and $187,100 are being tendered by EMIDICT (national import enterprise). Also, an amount of $444,194 has been budgeted for national contracts (see details in "Planned Expenditure Schedule" section).
INVESTMENT INCOME | Not applicable
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period (1 january 2018 - 31 December 2018) | ITEM / ACTIVITY / ACTION/OUTCOME | OUTPUT | AMOUNT
| 1. Reduction of the impacts of coastal flooding through the recovery of coastal ecosystems | 1.1. Re-establishment of coastal belt of red mangrove (Rhizophora mangle) between Surgidero de Batabanó and Punta Mora | 86494.74
|  | 1.2. Restoration of mangrove ecosystems between Majana and Surgidero de Batabanó | 158113.75
|  | 1.3. Restoration and enrichment of woodlands along the landward limit of the coastal wetland belt, between Majana and Punta Mora | 155075.35
|  | 1.4. Elimination and/or control of invasive alien species in coastal wetlands between Majana and Punta Mora in order to improve ecosystem resilience | 538451.85
| Subtotal Outome 1 |  | 938135.69
| 2. Increase the adaptive capacity of coastal communities to climate change | 2.1. EBA mainstreamed into integrated coastal zone planning and productive sector activities | 33120.19
|  | 2.2. Buy-in, participation and governance in local communities | 86430.73
|  | 2.3. Knowledge management systems at community level | 48941
| Subtotal Outome 2 |  | 168491.92
| 3. Ensure the effectiveness and sustainability of adaptation investments through the establishment of a favourable enabling environment at regional level | 3.1. Consolidated information on costs and benefits of EBA available to decision makers and planners | 88871.16
|  | 3.2. Strengthened institutions (provincial and municipal Governments, Forest Guard Corps, Frontier Guards and Fisheries Department) supporting EBA actions, within the framework of updated and actively implemented action plans | 23394.53
| Subtotal Outome 3 |  | 112265.69
| Project Management |  | 41953.22
| TOTAL EXPENDITURE |  | 1260846.52
PLANNED EXPENDITURE SCHEDULE | ITEM / ACTIVITY / ACTION/ OUTCOME | OUTPUT | PROJECTED COST | Est. Completion Date
List outputs planned and corresponding projected cost for the period of January 2019 until September 2020 * considering that a 1-year extension is being requested to the AF Secretariat | 1. Reduction of the impacts of coastal flooding through the recovery of coastal ecosystems | 1.1. Re-establishment of coastal belt of red mangrove (Rhizophora mangle) between Surgidero de Batabanó and Punta Mora | 590506 | 09/31/2020
|  | 1.2. Restoration of mangrove ecosystems between Majana and Surgidero de Batabanó | 415000 | 09/31/2020
|  | 1.3. Elimination and/or control of invasive alien species in coastal wetlands between Majana and Punta Mora in order to improve ecosystem resilience | 86500 | 09/31/2020
|  | 1.4. Restoration and enrichment of woodlands along the landward limit of the coastal wetland belt, between Majana and Punta Mora | 228765.61 | 09/31/2020
| Subtotal Outome 1 |  | 1320771.61 | 09/31/2020
| 2. Increase the adaptive capacity of coastal communities to climate change | 2.1. EBA mainstreamed into integrated coastal zone planning and productive sector activities | 64094 | 09/31/2020
|  | 2.2. Buy-in, participation and governance in local communities | 25800 | 09/31/2020
|  | 2.3. Knowledge management systems at community level | 70600 | 09/31/2020
| Subtotal Outome 2 |  | 160494 | 09/31/2020
| 3. Ensure the effectiveness and sustainability of adaptation investments through the establishment of a favourable enabling environment at regional level | 3.1. Consolidated information on costs and benefits of EBA available to decision makers and planners | 4000 | 09/31/2020
|  | 3.2. Strengthened institutions (provincial and municipal Governments, Forest Guard Corps, Frontier Guards and Fisheries Department) supporting EBA actions, within the framework of updated and actively implemented action plans | 10000 | 09/31/2020
| Subtotal Outome 3 |  | 14000 | 09/31/2020
| Project Management |  | 124000 | 09/31/2020
| TOTAL |  | 1619265.61 | 09/31/2020
Total Breakdown:
| Remaining balance of previous contracts |  | 578772
| Contracts ready to be signed in the first quarter of 2019 |  | 409200
| Goods and services to be internationally tendered in the first/second quarter of 2019 |  | 187100
| Goods and services to be nationally procured in 2019 and 2020 |  | 444194
| AVAILABLE CASH |  | 941505.61
| FINAL TRANCHE REQUESTED |  | 677760
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | At the end of 2018, the national co-financing committed in ProDoc, 5,052,000 CUP (Cuban Pesos), has been over fulfilled: 10,700,069 CUP - 200 %.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 10700069
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | A specific procedure was established by the Project Management Unit for the monitoring of the national co-financing in CUP. The National Forestry Development Fund (FONADEF), through the State Forestry Service (SEF), is the main source of co-financing. A digital record is regularly updated with all the certifications that SEF issues for the rehabilitation actions in the Project areas. By the end of 2018, this record shows that FONADEF has issued certifications in an amount of 10,700,069 CUP: Artemisa Province 2,082,000 CUP and Mayabeque Province 1,714,300 CUP. The rest of the national co-financing comes mainly from the salaries to technical and administrative personnel involved in the Project implementation, paid by Cuban government .

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
| Identified Risk | Type | Impact / Probability 1: Low 5: High | Current Status | Steps Taken to Mitigate Risk
1 | Extreme climatic events (storms, droughts) and fires, affecting plant survival rates. | Environmental | Impact: Low (2) Probability: High (4) | Low | During this period there were no extreme weather events or forest fires that affected the survival rate of the plantations.
2 | Climate change related changes in tree phenology affecting seed collection and nursery activities. | Environmental | Impact: Low (1) Probability: Medium (3) | Low | During the period, no phenological affectations were detected that compromised the development and establishment of the forests. As a result of the knowledge management of the project, the book "Ecotechnologies for ecological restoration: The treatments of seeds and mycorrhizae" was published. This book gathers the experience obtained in the nurseries (to potentiate the germination of the seeds and to assure the rapid development of the plants).
3 | Variations in commitment to EBA among policy makers. | Institutional | Impact: Low (2) Probability: Medium (3) | Low | The institutions and actors involved in the implementation of the project show a high degree of commitment to its results. The governments and sector authorities in both provinces have incorporated the results of the project into their development plans. Also the local communities recognize the great impact that the project has had in the improvement of the environmental conditions.
4 | Slow equipment procurement processes in local Governments. | Institutional | Impact: High (4) Probability: High (4) | Medium | In this period, procurement ocurred according to plan and faster than last year, as a result of improved coordination and monitoring measures. However, there is an overall delay in the project due to technical activities accumulating delays in its execution.
5 | Limited availability of inputs and equipment on national market. | Institutional | Impact: Medium (3) Probability: Medium (3) | Medium | To reduce the impact of this risk, thas has been reported in previous yeats, the project team has actively searched within the national market. To date, all the required equipment has been procured.
6 | Short term economic and livelihood considerations outweigh medium term benefits of EBA actions in priorities of community members. | Institutional | Impact: Low (2) Probability: Low (1) | Low | To minimize this risk, the project has developed an intense campaign to publicize and raise awareness of the benefits of EBA. Forest workers have obtained a significant improvement in their income. In a general sense, the population begins to verify the benefit of the rehabilitation actions of the coastal wetlands. In fact, they begin to see other socio-economic opportunities such as the development of beekeeping. The conclusion of the cost/benefit studies of the ecosystems rehabilitation with ABE approach will contribute to consolidated the project results.
7 | Short term political considerations outweigh medium term benefits of EBA actions in priorities of members of local institutions | Institutional | Impact: Low (1) Probability: Low (1) | Low | This has ceased to be a risk, to become an opportunity for the project. The approved of The State Plan for Facing the Climate Change in abril 2017, had a great impact in the project implementation. Because, this political document defined the priorities areas in the coastal zone of Cuba, in which is neccesary to carry up ecosystems rehabilitation actions as strategy to increase the resiliense of the coastal communities. The Manglar project has been providing the knowledge and methologies to implement this State Plan.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
| Identified Risk | Type | Impact / Probability 1: Low 5: High | Current Status | Steps Taken to Mitigate Risk
| Delays in the Project implementations. | Operational | Impact: Medium (3) Probability: High (4) | High | The following are some of the risk mitigation measures already adopted by the PMU and UNDP Cuba, to counterbalance experienced delays: 1) the PMU and the importing enterprise (EMIDICT) have weekly meetings to follow up on importing processes. 2) the PMU has drafted the procurement plan for the remainder of 2019 and for 2020 (pending extension request approval). EMIDICT is already aware of any future procurement needs and required timeframes. 3) UNDP Cuba has scheduled monthly exchanges with the following partners, to monitor delivery and address bottlenecks: Ministry of Foreign Trade, Ministry of Science, Technology and Environment, and the Agency of Environment (implementing partner), and EMIDICT. 4) the PMU has scheduled site visits every 2 weeks, to monitor rehabilitation activities and ensure the effectiveness of the new rehabilitation methodology. This is done jointly with the forestry enterprises.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Despite the measures applied, the project shows a delay in the fulfillment of some indicators at the end of its fourth year of implementation. The main causes are: - Delay in the rehabilitation of the swamp forests, due to: a) difficulty in accessing the sites; b) the need to establish nurseries and specialized equipment. - Need to incorporate new techniques of rehabilitation or restoration (ej. the islands methods and building "estaquillados"), to accelerate the process of increasing resilience. This in turn delayed the impact evaluation and cost-benefit analysis of the rehabilitation interventions (both recommendations of the MTR), since these interventions need 2 to 3 years to showcase any results and therefore distill and disseminate lessons. -Low budget execution as a consequence of the aspects indicated above. The technical analysis carried out to recover this delay indicates that it will be necessary to extend the implementation phase by one year. This will allow to fully fulfill the final goals committed.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Key Milestones I. Recovery of mangrove areas along a stretch of 84 kilometers for the protection of the coast. |  | Increased the: a. Restored mangrove ecosystem area (Artemisa: Majana - Surgidero de Batabano). b. Red mangrove area along the coast (Mayabeque Batabano - Punta Mora). |  | IES and INAF conducted 4 trips to diagnose mangrove areas to intervene in the provinces of Mayabeque and Artemisa. A detailed report was delivered to the forestry companies with the type of management to be applied in each of the areas. | S
1 field expeditions were carried out to evaluate the success in the growth/survival of propagules and other indicators, such as soil and salinity, by means of permanent lots in Melena, including the participation of forestry workers, technicians and specialists from SEF, IES and INAF. There is evidence of a radical increase in the growth rate favored by the work with the canals and the increase in rainfall during 2018.
2 expeditions were carried out to update the health map of the mangrove ecosystem, combining field measurements and remote sensing techniques. Almost 48 monitoring points for the health of the mangrove and the swamp forests.
15 technical projects for on-the-ground intervention were approved this year by the State Forestry Service to carry out restoration activities: 7 in Artemisa province (4 in Artemisa with 25.3 ha of efective area, 2 in Alquizar with 5 ha of efective área1 and 1 Guira de Melena 0.9 ha of efective area) and 8 in Mayabeque province (3 in Batabano with efective area of 30.2 ha; 4 in Melena with efective area of 30.73 ha; and 1 in Güines with efective area of 7.3 ha).
311.7 new total hectares of mangrove forests have been benefited with rehabilitation actions for restore of the red mangrove belt, combining works for promoting natural regeneration with direct planting, along the coast of Güines, Melena and Batabano municipalities in Mayabeque province.
Maintenance was carried out in 499 ha (total) worked during the third year and 311.7 ha (total) started in the second year. More than 18 000 red mangrove propagules were maintained and more than 11,200 in Artemisa.
291.6 new total hectares of mangrove forests have been benefited with rehabilitation actions for restore of the red mangrove belt, combining works for promoting natural regeneration with direct planting, along the coast Artemisa province.
In the "Gulf of Batabanó wildlife refuge" there are 361.2 ha of mangrove forests under conservation actions. In this area of conservation, different interventions are carried out; for example: monitoring, maintenance, improvement of ecosystem services and elimination of anthropogenic pressures.
To increase sediment retention and mitigate the erosive action of the waves 5.5 km of antierosion barrier were built along the coastline of Güines (1.3 km); Melea del Sur (1.9 km) and Batabanó (2.3 km). This will allow to create the appropriate substrate to seed mangrove propagules.
The new rehabilitation method called "Plantation Niche" was perfected, which allowed the restoration of coastal areas with sandy substrate. 45 plantation niches were built (30 Batabanó and 15 in Melena del Sur).
14.3 km in Mayabeque Province and of ditches and canals were cleaned as a specialized measure for the protection against fires and to facilitate the hydrological flow in the area.
21 440 m³ ditches and canals from the province of Artemisa were cleaned to facilitate the hydrological flow in the area favoring the natural regeneration of red mangroves; and 10.6 km of firebreaks were cleaned, as a specialized measure for fire protection.
Five training activities were carried out, in which participated: members of the forestry sector of the territory, forestry brigades, specialists of the companies, State Forestry Service and other specialists from sister provinces. Courses were held that addressed the issues: ecology and monitoring of the mangrove ecosystem, control of forest fires, study of soil in the mangrove ecosystem, management of invasive alien species, management of seeds in the mangrove ecosystem and use and management of water . They were taught by specialists from the Institute of Ecology and Systematics, the National Botanical Garden, the Institute of Agroforestry Research and the Faculty of Geography, University of Havana.
Three exchanges of experiences with forestry companies or similar projects were carried out. The exchange with the forestry company of Caimanera (Guantanamo) was highlighted, in which forestry company workers and forestry service specialists from the three provinces participated. It was focused on showing the actors of the territory other experiences in the rehabilitation of mangroves and their use. Another exchange was made in Panama with the Panamanglar network. Participated in the 1st regional cooperation workshop "Mangrove Science: Use of ICT to Assess the Mangrove Restoration Potential of Panama"
Dr. Luz Esther Sánchez Arias conducted an advisory mission that contributed to the theoretical and practical preparation of the technical team of the project and set the guidelines for work aimed at monitoring and evaluating the results of the restoration. The results of this consultancy were taken into account in the preparation of the 2019 Annual Operational Plan (POA).
Seven Knowledge Exchanges in Mangrove Restoration were developed with representatives from the provinces of Santiago de Cuba, Guantánamo (Caimanera), Holguín (Banes), Camagüey, Cienfuegos, Matanzas and La Habana. Synergies are maintained with more than six national and international projects that are executed in the country or are in the preparation phase.
Through the use of MODIS images, the team continued with the monitoring of the behavior of the photosynthetic activity in the different forests of the area. This monitoring is applied in the areas where rehabilitation actions are carried out and also in other areas with similar ecological conditions, but with better health (as a reference).
The geographic information system is perfected and the database is updated, which allows monitoring and mid- and long-term evaluations of the results in rehabilitation and restoration.
| II. Restoration and enrichment of woodlands along the landward limit of the coastal wetland belt, between Majana and Punta Mora. |  | Increased the: c. Enriched border forest area. d. Control and eradication of IAS. |  | The IES and the INAF made the diagnosis of the area that allowed to determine the existence or not of native species and identify the associated vegetation, which allowed to strengthen the method to be used for the rehabilitation. | S
10 technical projects start execution to carry out the restoration activities of the third year, as approved by the State forestry service, 8 in Mayabeque (3 in Batabano with efective 42.8 ha; 4 in Melena with efective 25.6 ha; 1 in Güines with efective 15 ha) and 2 in Artemisa (1 in Güira with efective 2.1 ha; 1 in Artemisa with efective 3.2 ha)
416.6 new total hectares of swamp forests have been benefited with enrichment actions of native tree species, combining works for promoting natural regeneration with direct planting in Mayabeque province.
21.2 new total hectares of swamp forests have been benefited with enrichment actions of native tree species, combining works for promoting natural regeneration with direct planting in Artemisa province.
In the protected area of Batabano Gulf there are 393.2 ha of marsh forests under conservation actions. In this area, projects of monitoring, maintenance, improvement of ecosystem services and elimination of anthropogenic pressures are developed.
Maintenance works were carried out in 1529.5 ha of swap forest from the third year between Majana and Punta Mora.
More than 10 native species were planted, including: palo campeche, majagua, occuje, arabo and white oak. There was a planting experience with 250 seedlings of black júcaro (speckled) that was collected in areas of the municipality of Nueva Paz.
A enriched substrate with mycorrhizae is used in nurseries to promote the growth and survival of native species.
EAF Mayabeque extracted 295.0 m3 of wood from almond trees, algarrobo from India and majagua from florida. For charcoal, more than 5,980 kg were obtained among the entities participating in the project.
It is working on 10 effective hectares, with invasive alien species, of which 4.5 ha in mangrove forests and 5.5 ha in swamp forests.
The INAF obtained a bioactive extract from the leaves of the almond tree
| III. Incorporation of EBA as a main activity in coastal zone planning and activities of the productive sector. |  | Increased the number of: a. Provincial and municipal development plans that effectively incorporate the EBA. b. Provincial and municipal governments with knowledge management systems incorporating EBA implemented. |  | Information of the project continues to be used to make decisions related to the climate change plan; also in the planning and execution of supervisions to the coastal zone, and in the incorporation of ABE actions in the local development strategies and the forestry sector economy plans. | S
The information needed to make decisions regarding the adaptation to climate change is in the process of organization, using the structure of the Environmental Information System (SIAM) implemented by the BASAL project in other provinces of the country.
The Geographical Information System continues to be used to obtain reliable information on the sites where the restoration works are carried out, and the dangers and vulnerabilities of the coastal zone and the prospects for climate change up to 2100.
Realized the map of environmental units and incorporated into the information system of two municipalities (Batabano and Melena del Sur). This is a very useful tool for planning the territory.
The Knowledge Management System Workshop was held for the groups coordinating the project at the different levels of each province.
The implementation of adaptation actions based on Ecosystems included in the local development plans is controlled by the government through biannual meetings.
The planned investments with an EBA approach are met, included in the economic plans of governments in both province.
The recent approval of the State Plan for facing to climate change in the Republic of Cuba known as "Tarea Vida" represented an opportunity for the project, due to the close link with the objectives, strategic actions and tasks where specifically the mangroves are mentioned as a means of adaptation and coastal protection. Hence, in the process of updating the local development plans of the 6 municipalities and 2 provinces, each territory established an action plan based on a state budget that will be allocated for the corresponding execution of specific activities based on the of Adaptation based on Ecosystems (EbA) in the planning of the coastal zone.
6 training actions were carried out to members of the provincial government. The topics addressed were: good practices in water managment, economic valuation, mangrove ecosystem and Reducción de Riesgos de Desastres.
5 training actions were carried out to members of the municipal government, and decision-makers of the key productive sectors (fishing, energy, agriculture, physical planning, water, health and education).
| IV. Local communities increase the knowledge and develop skills to participate in EBA activities. |  | Increased the number of: c. Community members (men and women) belonging to local volunteer groups addressing environmental and adaptation issues. d. Local schools with curricula incorporating adaptation to climate change. e. Awareness materials on climate change adaptation issues produced by local media. |  | A group of volunteers was formed in Alquízar (Guanímar), with a total of 18 members, of whom 10 are women and 8 are men. This group carries out maintenance actions to the areas under rehabilitation actions. | S
[5 empty] | The forest guards conduct over 1000 sensitization encounters with over 2500 coastal community members. The topics addressed were: the importance of the role of the community in the protection of the ecosystem and the importance of the forest fire prevention campaign in Artemisa (679) and Mayabeque (372) |  | .
28 activities with the 8 circles of interest that the CGB attends in the areas of intervention of the project.
An exhibition fair was held in Batabanó together with 5 research centers of the Environmental Agency (Institute of Ecology and Systematics, Institute of Marine Sciences, Institute of Meteorology, National Aquarium of Cuba, Institute of Geophysics and Astronomy to socialize experiences
Celebration of the 1st National Day "The Mangroves of Cuba" under the motto (For Life) Tours of mangrove areas, schools, protected areas, CITMA delegations, environmental study centers, communities, forestry companies and fishing bases in ( Santiago de Cuba, Holguín, Camagüey, Cienfuegos, Matanzas, Havana, Artemisa and Mayabeque.) The objective was to pay homage to Leda Menéndez and that this period of celebration serves for the socialization of results and exchange of experiences at the country level contributing to knowledge management
The webseries documentary "Hijos del Monte" was broadcasted on ntional TV, Facebook sites "Secret Nature" and "Living Mangrove", communities of Artemisa and Mayabeque.
Presentación de la Expo Gigantografía de Manglares en Artemisa “Candelaria y Artemisa” y Mayabeque (Güines y Batabanó)
6 tours to explain the importance of the conservation of the built natural and cultural heritage, as well as the function of the swamp forests.
9 Conferences and / or workshops addressed to the communities were taught in the Artemisa Training Classroom.
4 workshops were held in 4 schools in the project areas. We worked with a total of 38 children (15 males and 23 females). These contributed to the systematization of knowledge related to the environment and climate change from a community perspective. The final output of the workshops is the return of products made by children as an alternative to communication and socialization of the actions carried out.
As part of the process of methodological preparation and improvement of the Education System at the national level, 21 teachers were trained (17 Women and 4 Men) corresponding to the schools of the project areas.
Materials in digital format were distributed in the schools on the Living Mangrove project and complementary general bibliography as part of the management of project knowledge and the development of environmental education for students and teachers.
A nivel nacional en libros de 5to y 10mo grado cuentan información sobre el proyecto y conceptos sobre AbE y CC.
The award ceremony for the third edition of the "Manglar Vivo" competition, in Batabano, was held with the presentation of 183 works in the different modalities, in both provinces.
27 materials and reports were produced. Made and disseminated by national television (5), local television (6), international television (2), local radio (8), national radio (1), national written press (1) international written press (1) and web sites (2). Among the most outstanding is the program, with national and international coverage, of the "Round Table" dedicated entirely to the project; and the article of the Life Stories of the project published on the official website of the adaptation fund.
Produced 4 videos in webseries format, entitled "Hijos del Monte" produced by Mundo Latino. The documentary series deals with the impact of the project in the southern coastal area of the Artemisa and Mayabeque provinces, taking as a central axis the life stories of people related to the project in their respective territories.
6 knowledge systematization products were completed, 2 of them were printed and disseminated and 4 are in the design process. The Mangrove Restoration Protocol is noteworthy, which summarizes the methods of rehabilitation and restoration employed in the project area.
1 scientific articles were published by the research institutes associated with the project.
In the period, the results of the project have been presented in 18 events (16 national and 2 international) where members of the project team participated. The most relevant were: The Ramsar Convention (Dubai), the workshop of the "Mangrove Science" (Panama) and the 2nd National Workshop on Ecological Flows of UNESCO (Havana).
| V. Strengthened institutions (provincial and municipal governments, forest service corps, Coastguard and Fishery Departments) supporting EBA actions, within the framework of action plans actively updated and implemented. |  | Increased the: a. Training activities and technical support in coastal communities (to incorporate EBA approaches) undertaken by provincial and municipal governments; b. Inspection activities to coastal areas by provincial and municipal governments to incorporate EBA. |  | One training course was held for the preparation of comprehensive inspections with the ABE approach with 15 participants . | S
In 2018, 124 fines were applied, thereby demonstrating an increase of 23% with respect to the fines applied during 2017.
The forest brigades and forest ranger were mobilized during 11 fires that occurred in the intervention area of the project, which affected 4.0 ha of planted forests and 401,5 ha of swamp grassland. A new brigade of forester worker was built during this year.
38 inspections were carried out from Majana to Batabanó by the new regulation group for the South Dike, in the Artemisa province.
There were 170 naval tours. The protection circuit is redesigned and the effectiveness of the protection of the coast is improved. 548 patrols were carried out in terrestrial areas.
156 comprehensive inspections were carried out in the intervention areas of the project: 78 in the province of Mayabeque and 78 in the province of Artemisa. The participation of all the regulatory institutions of each municipality was achieved.
In the National Workshop 67 members of the State Forestry Service of the country were trained in ecological restoration and adaptation based on ecosystem. 30 people attended a Workshop on the Classification of Mangrove types of Soils.
[5 empty] | Two trainings were carried out to specialists from different institutions in the economic valuation of goods and services of the ecosystems. Mayabeque (30 people) and Artemisa (18 people). | S
The validation of the Methodology designed for the economic evaluation was started, the information for the baseline was developed in four municipalities of the two provinces and the economic evaluation of different environmental assets of the mangrove and swamp forest ecosystems was achieved, which allowed to validate the first two steps of the proposed methodology.
8 Diploma Graduate University thesis were choosen that they will be discussed in 2019. Provincial working groups were updated for the economic evaluation of ecosystem goods and services. Training was developed for Provincial and Municipal Groups in the economic evaluation of ecosystem goods and services.
The methodology was presented in the Forum of Science and Technology where it was granted an award under the province- level category.
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Luis David Almeida Famada
| Email: | almeidafamada@ama.cu; almeidafamada@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
In the fourth year, the project shows a significant progress in all the expected results. This positive result has been possible, thanks to the work done by the forestry companies and the international and national financing that allows to raise to a great extent the working conditions and workers' earnings. In general, there is a positive trend in the restoration work of the coastal ecosystems, are under rehabilitation and restoration actions 6570.4 ha (in mangrove forests - 3012.4 ha and swamp forests - 3558 ha). This has been possible thanks to the combination of the support provided by the project to the forestry sector in the intervention area, and also to the national co-financing contributed by the Forest Development Fund (with a contribution of more than 6 million pesos, surpassing what was committed at the beginning of the project). Component 1. Progress in increasing the resilience of ecosystems, through rehabilitation and restoration, has had a positive trend, standing at 89.7% with respect to the final goal. In addition, the commitment has been fulfilled in two indicators of this component within the logical framework (1.2: 1.4) and has even been fulfilled in one of them (1.2). The improvement has not only been in the number of areas benefited, but also in the quality of management work, and in the increase of native species in the nurseries. Areas were identified where the rehabilitation actions have had an indirect beneficial impact, reporting, in some places, higher success indicators than in areas where interventions have been carried out directly. Even so, it is important to continue incorporating complementary actions in the intervention area; for example: placement of honeycombs of native bees to enhance pollination activity and natural regeneration. There are several areas in which actions of control, management and exploitation of invasive alien species are carried out in success way. We must also point out that there are areas where certification cannot be given until two or three years after the project is finished, which is why it is important to ensure the quality of these certifications. Component 2.In this component, most targets are close to being met. Work with governments showed important results; for example: the inclusion of the ecosystem-based approach in several of the territorial management instruments, such as the local development strategies, the environmental strategy and the climate change adaptation plan. The indicator apparently lagging behind in its fulfillment had significant advances this year, the mechanisms were defined for the implementation of the project knowledge management system in conjunction with the international BASAL project. In addition, established synergies of work with other institutions in the country, with the aim of developing a network of collaboration and extension activities as an instrument for the implementation of the Life Task and alternative sustainability and impact of the results of the project. Component 3. Progress in this component this year has been significant. Training and awareness-raising actions for the population have significantly increased: 1260 training and technical support actions were carried out with the coastal communities. Thanks to this, we continue reporting a gradual decrease in the contraventions detected by the Forest Ranger. In addition, during the fire campaign, for the first time in many years, no fire occurred in the coastal wetland areas of the project. In the indicator that lagged behind (3.3), considerable progress has been made during this year. Eight jobs of economic valuation of goods and services in the coastal wetland were discussed as a project and were successfully approved. Furhter, a cost-benefit analysis of Mangrove restoration vs construction and maintenance of the south dam was initated. The Government is requesting a 1-year extension to complete the studies in at least 3 municipalities.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Key Milestones I. Recovery of mangrove areas along a stretch of 84 kilometers for the protection of the coast. II. Restoration and enrichment of woodlands along the landward limit of the coastal wetland belt, between Majana and Punta Mora. |  | Increased the: a. Restored mangrove ecosystem area (Artemisa: Majana - Surgidero de Batabano). b. Red mangrove area along the coast (Mayabeque Batabano - Punta Mora). c. Enriched border forest area. d. Control and eradication of IAS. |  | The progress in those key milestones contribute to compliance with Component 1 of the project. Key Milestone No. I. Indicators a and b - There is progress in the rehabilitation of the mangrove ecosystem in both provinces. In fact, the number of committed hectares have been exceeded. Furthermore, to ensure the sustainability of the interventions carried out, maintenance actions on established plantations were developed, coastal anti-erosion barriers were built, canal cleaning and ditches were carried out to restore water flow. Also, the responsible institutions made visits to diagnose and certify the quality of the work performed. Key Milestone No. II. Indicator c - Although there are advances in the rehabilitation of the swamp forests, there is a delay in compliance of the committed hectares. For that reason, 760 hectares should be rehabilitated in 2019, which is considered a great challenge. The rehabilitation process has included the elimination of exotic species combined with natural regeneration. In the reforestation, 10 native species are being used. The use of mycorrhizae in the nurseries is consolidated. Indicator d - The IAS Control and eradication Plan is running as planned. It is accumulated the control and eradication of 4 IAS in 75 ha. | MS
| Key Milestones III. Incorporation of EBA as a main activity in coastal zone planning and activities of the productive sector. IV. Local communities increase the knowledge and develop skills to participate in EBA activities. |  | Increased the number of: a. Provincial and municipal development plans that effectively incorporate the EBA. b. Provincial and municipal governments with knowledge management systems incorporating EBA implemented. c. Community members (men and women) belonging to local volunteer groups addressing environmental and adaptation issues. d. Local schools with curricula incorporating adaptation to climate change. e. Awareness materials on climate change adaptation issues produced by local media. |  | The progress in those key milestones contribute to compliance with Component 2 of the project. Key Milestone No. III. It had an adequate compliance, because the expected progress in indicators a and c were achieved, while the indicator b had slide delayed. The main progresses are: Indicator a -The two provinces and the 6 municipalities involved in the project have already incorporated the ABE approach in its development plans and strategies. In addition, as part of the implementation of the National State Plan for facing Climate Change “Tarea Vida”, the project had been advising the incorporation of the ABE approach into the economy plans in both provinces. The state budget has been approved to develop actions in the coastal zone with an ABE approach in both provinces. Indicator b - Although a progress is reported in the preparation of the knowledge management automatized system incorporating the EBA, it is not yet fully available to the provincial and municipal governments. In order to get the quickly implementation of this system, the platform of the Municipal Environmental Information System developed by the BASAL Project is being used. It was developed a comprehensive training plan for governments on these issues. Indicator c - Up to date, there are 4 volunteers groups that promoting activities related to environmental and adaptation issues: Surgidero de Batabanó (with 16 members, 9 women); Cajio (with 10 members, 2 women) and Playa Majana (Fishing Federation, with 6 boats). This year was created the last one in Guanimar (with 18 members, 10 women). Key Milestone No. IV. It had a satisfactory compliance, because the expected progress in indicator d and e were achieved. The main progresses are: Indicator d - Textbooks of the 5th and 10th grade of the National Education System includes information about the Manglar Project and Ecosystem Based Adaptation and Climate Change concepts. Indicator e - A large amount of awareness materials on climate change and the adaptation measurements were produced and disseminated by local and national media. The project has achieved wide recognition at the national level. | MS
| Key Milestones V. Strengthened institutions (provincial and municipal governments, forest service corps, Coastguard and Fishery Departments) supporting EBA actions, within the framework of action plans actively updated and implemented. VI. Consolidated information on the costs and benefits of EBA available for decision makers and planners. |  | Increased the: a. Training activities and technical support in coastal communities (to incorporate EBA approaches) undertaken by provincial and municipal governments; b. Inspection activities to coastal areas by provincial and municipal governments to incorporate EBA. c. Studies and methodologies carried out to estimate the cost - benefit ratio of the ABE approach, available to planners and decision makers, is increased. |  | The progress in those key milestones contribute to compliance with Component 3 of the project. Key Milestone No. V. The indicators a and b had a satisfactory compliance, because the expected progress was achieved. The main progresses are: Indicator a - All training activities planned in support of EBA were carried out. Also, all the prevention actions related with forest fires and for the protection of natural resources were carried out. Indicator b - There were carried out comprehensive inspections in the intervention areas of the project coordinated by the government. The information and methodologies elaborated by the project are being used during the execution of this supervisión actions. Key Milestone No. VI. There is delay in completion of indicator c. Indicator c - The cost-benefit estimation studies (3) of the EBA approach have not been finished; therefore, there are not available for planners and policy makers. The methodology was elaborated and its validation started. It is expected that these studies will be completed in 2019, which is considered a great challenge. | MS
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Gricel Acosta Acosta
| Email: | gricel.acosta@undp.org
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. The Project implementation shows a positive progress in meeting the main milestones at the end of the Year 4. This trend brings it closer to meeting the project's targets and final goal. However, some activities are delayed, which in turn is delaying the analyses and studies required to assess the project results appropriately. This delay is the reason of the low financial execution (71%). Taking this into account, the overall evaluation proposed is MS. The summarized aspects that support this evaluation are: • There is a delay in compliance the number of hectares of the coastal ecosystem rehabilitated, especially in the swamp forests. • The knowledge management automatized system that incorporates EBA, is not yet fully available for provincial and municipal governments. • The cost-benefit estimation studies of the ABE approach have not been finished. • The Project has a low financial execution (71%) at the end of its fourth year. That means that an amount of $1,619,266.00 should be disbursed in 2019. The detailed arguments that support this evaluation, by Component, are as follows: Component 1. The final goal of the Project is to rehabilitate 7,318 ha of coastal ecosystem (mangroves: 3,012.4 ha and swamp forest: 4,315.5 ha). Up to December 2018, the rehabilitation actions developed by the Project have benefited 6,570.4 ha, which represents 89.7% of the final goal. A detailed analysis of this indicator shows that the number of committed hectares of mangrove has been met (and exceeded). Nevertheless, about 760 ha should be rehabilitated (18% of the total of swamp forest), which is a significant challenge due to the complexity of the rehabilitation works in this type of ecosystem. As explained in the previous PPR, the project execution has accumulated a delay because of the equipment and supplies required to carry on this work, were not available in the expected time. Component 2. One of the most important results achieved by the project is the inclusion of the ecosystem-based adaptation approach in relevant territorial management tools, such as the local development strategies, the environmental strategies and the climate change adaptation plans. Although a progress in the design of the integrated knowledge management system that incorporates the EBA at territorial level, has been reported, this tool is not yet available to governments, which represents a delay in meeting this indicator. Component 3. The studies and methodologies to assess the cost-benefit of the EBA approach have not been made available to planners and decision-makers yet, which has caused a delay in meeting this indicator. 2. Detail critical risks that have affected progress. The low Project’s financial implementation rate can be considered as a critical risk. According to the ProDoc, by the end of 2018 the Project delivery rate should had been 85%. However, the cumulative financial execution showed 71% of delivery. This means that the Project must deliver $1,619,266 in 2019 (last year of the Project), which will be an important challenge therefore an extension for 1 year is being requested. 3. Outline response to MTR undertaken this reporting period. The Project Management Unit has been implementing the 19 measures Plan to meet the MTR recommendations. By the end of 2018 more than 50% of the measures are completed and the rest are in progress. There are evidences that the UNDP Country Office has followed and reported the advances reached. Also, this Plan is followed-up by the National Steering Committee. In summary, considering the proximity of the closure date (6 months), it can be considered that the Project is at risk of not meeting the final targets. For this reason, the Environmental Agency requesting a project extension to the AF Secretariat.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: To increase the resilience of populations living in the coastal zone ofthe provinces to Mayabeque Artemisa and the effects of climate change. | I. Areas with high rates of health and the conditions of the mangroves (soil and salinity of the water, the density of the canopy, the existence of local regimes of protection). | Coastal ecosystems that cover 7 318 ha are degraded, have excessive levels of salinity due to seawater intrusion and the obstruction of channels and have a limited protection regime. | Rehabilitation actions have taken place in 6570.4 ha (in mangrove forests - 3012.4 ha and cienaga forests - 3558 ha), which represents 89.7% with respect to the goal at the end of the project. The monitoring system of the health status of mangrove forests and swamp forests has been maintained by combining field work with remote sensing techniques. | 7 318 Ha (total area where will be carried out reforestation of mangrove, the restoration of the mangrove ecosystems, and the enrichment of the forested areas inland) Note: the rates of coastal mangroves and wetlands must be nominated in the methodological documents to be developed at the start of the project.
| II. Numbers of people (men and women) with reduced vulnerability due to proximity of functioning mangrove forest and wetland ecosystems. | 17 524 People in 47 communities are directly affected by coastal flooding. | Awareness raising activities about the relevance of coastal ecosystems have been conducted with the local government and inhabitants of local communities. These included coastal flooding, mitigation measures, mangrove forest restoration, and opportunities that the Project can bring to the communities to implement national policies on climate change adaptation. | 21,502 People (of which at least 45% are women) directly benefited from the reduction of coastal flooding.
|  | 270,705 People are indirectly affected by the impacts of the phenomena associated with the CC on economic activities. | Awareness raising activities (about flooding impacts, mitigation measures, the importance of the mangrove restoration, etc) have been conducted in all communities located in the interventions areas of the project. This activities have involved the governments, decision makers of selected productive sectors, and regulatory authorities. Theses actions have contributed to increase the level of risk perception of the people. | 270,705 People (at least 45% are women) benefit indirectly by the reduction of the impact of the phenomena associated with the CC on economic activitie.
| 1.1 Area (ha) of red mangrove is established along shore between Batabanó and Punta Mora. | 533ha | Rehabilitation actions have been developed in 1207.4 ha of red mangrove forest (includes restoration of ditches and canals, management of natural regeneration and sowing of propagules). It represents the 93.5% of final tarjet of the project. | 1290,6 ha of which 85% survived* (1097 ha) *Survival can only be measured 3 years after planting
| 1.2 Cumulative area of mangrove ecosystem restored between Majana and Surgidero de Batabanó. | 144ha | Rehabilitation actions have been developed in 1805 ha of the mangrove ecosystem (includes restoration of ditches and channels, management of natural regeneration and sowing of propagules). It represents the 105.4% of final tarjet of the project. | 1711,9 ha of which 85% survived* (1455,1 ha) *Survival can only be measured 3 years after planting
| 1.3 Cumulative area of landward edge woodlands restored and enriched. | 939 ha | 3558 ha of landward edge woodlands were enriched by planting native species and encouraging natural regeneration. It represents the 82.4% of of final tarjet of the project. | 4315,5 ha of which 85% survived* (3668,2 ha) *Survival can only be measured 3 years after planting
| 1.4 Numbers of IAS management plans developed. | 0 | A Management Plan for 20 invasive alien species is in progress. It contains information on the main characteristics of these species and proposals for control and management measurements for each one. 4 Invasive Alien Species have been eliminating in 47.3 ha of the intervention area. | 1, covering 7,318ha
Outcome Indicator | 2.1 Numbers of provincial and municipal development plans that make specific provision for EBA. | 2 provincial and 6 municipal governments are preparing development plans that do not include EBA. | The EBA approach has been included in 3 management instruments. This approach has been included in the local development strategies in 6 municipalities, in the environmental strategy of the 2 provinces, and in the plan to combat climate change in the 2 provinces and the 6 municipalities. The inclusion of EBAin local plans is done by the government, during biannual meetings. | 2 provincial plans and 6 municipal plans
Outcome Indicator | 2.2 Numbers of provincial and municipal governments with EBA-related knowledge management systems in place. | 0 | Authorities in both provinces are using the project information in decision-making related to the climate change plan; also in the planning and supervisions to the coastal zone, and in the incorporation of EBA actions in the local development strategies and the forestry sector economy plans. Necessary information for decision-making regarding adaptation is being compiled, using the SIAM structure of the BASAL project in other provinces in the country. | 2 provincial and 6 municipal governments
Outcome Indicator | 2.3 Numbers of community members (men and women) belonging to local voluntary groups addressing environmental and adaptation issues. | 0 | 5 working volunteer groups: Guanímar (with 18 members, 10 are women and 8 are men; Surgidero de Batabano (with 16 members, including 9 women); Cajio (with 10 members, including 2 women); Playa Mayabeque (with 25 members, of them 3 women), and Majana beach (with 5 members and 5 boats). These groups support: the inspections and controls carried out on the project, the transfer of the trunks to make the palisades, the dissemination of the work of the project in the area. | 1 group with at least 15 members (of which at least 45% are women) in four municipalities
Outcome Indicator | 2.4 Numbers of local schools with study programmes incorporating adaptation issues. | 0 | 34 schools in the two provinces include CC and EBA issues in the syllabus for 2016-2017 course, of which: 5 are mixed centers, 18 primary schools, 4 secondary schools, 1 pre-university school of basic science, and 6 municipal university centers. These syllabi include practical and theoretical work, books for 5th and 10th grades include information of the project and EBA and CC concepts. In 2019, this will be implemented across the country. | 16 primary schools 15 secondary schools 3 municipal universities 1 teacher training institute
Outcome Indicator | 2.5 Numbers of dissemination and awareness raising materials on adaptation issues, produced by local media | 0 | 12 videos were produced and broadcasted on several occasions by national and local television stations, related to the objectives and advances of the project, the mangroves and the importance of their protection. | 17 audiovisual 3 local television . 5 local radio 2 articles
47 reports were broadcasted by local (26), national (17) and international (4) television stations about the project, its actions, progress and perspectives as well as the importance of mangroves and other coastal wetlands.
39 reports and interviews were disseminated on national (7) and local (32) radio.
18 articles were published in national (4), local (9), web (4) media, and international (1). Many with accceso via internet.
Outcome Indicator | 3.1 Frequency of training and technical support visits carried out by provincial and municipal governments to coastal communities in support of EBA | 0 | 1260 training and technical support actions were carried out with the coastal communities. These activities were conducted by the government, the forest ranger corps and research institutes. | 3 training and technical assistant activities undertaken per year by technical authorities to coastal areas.
Outcome Indicator | 3.2 Frequency of inspection visits to coastal areas by provincial and municipal governments in support of EBA | 0 | Lead by the goverment, 170 comprehensive inspections were carried out in the intervention areas of the project; 6 in the first year, 3 in the second year, 5 in the third year, 156 and in the four year. In these inspections were participating representatives of all the regulatory institutions of each municipality: the CAP and CAM, SEF, CGB, TGF, PNR, and implementation office. | 3 inspection activities undertakern per year by provincial municipal goverment and other regulatorities authorities
313 maritime journeys along the coast (1 during the first year, 83 during the second and 59 during the third year, and 170 in the four year) and 1103 on land (180 during the second year, 375 this third year and 548 in the fourth year) were carried out for the monitoring and protection of natural resources within the Project intervention area for the Forest ranger.
Outcome Indicator | 3.3 Number of studies and methodologies carried out to estimate the cost - benefit from the implementation of the approach EBA, available for planners and policy makers. | 0 | 8 graduate University theses selected. Provincial working groups were updated for the economic evaluation of ecosystem goods and services. Training was developed for Provincial and Municipal Groups in the economic evaluation of ecosystem goods and services. | 3
The validation of the Methodology designed for the economic evaluation was started, the information for the baseline was developed in four municipalities of the two provinces and the economic evaluation of different environmental assets of the mangrove and swamp forest ecosystems was achieved , which allowed to validate the first two steps of the proposed methodology.
The methodology was presented in the Forum of Science and Technology where it was granted an award for provincial-level relevance.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | During this fourth year the main lessons learned have been: - The need to identify areas of the ecosystem that have been indirectly benefited without the need to carry out actions in situ. In the control reports, on the insitutions and implementation office report favorable changes in certain areas as a result of actions linked to the reconfiguration of the hydrodynamic regime, such as the cleaning or closing of channels. - Inclusion of additional research institutions to complement the success indicators of the project: Institute of Marine Sciences (ICIMAR), Institute of Geophysics and Astronomy (IGA), the Institute of Hydraulic Research (CIH) and the Faculty of Geography (FGEO) of the University of Havana. - The need to partner with other projects on information and knowledge management systems. In some municipalities there is a platform in place thanks to another international cooperation-funded project (BASAL). The alliances made this year have been profitable, which allowed us to extend these good practices in the other coastal municipalities and strengthen them with the information generated by th AF project.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There is a significant delay in the financial execution of the project in this period. However, the contribution from the co-financing of the national counterpart was over fulfilled 158,41% (7 991 260.03 $). The execution delay was mainly due to difficulties of the importing agency. A plan of measures to recover this delay was prepared and implemented. This delay did not cause non-compliance in the fulfillment of the project's goals.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | In this period, no changes have been made in the project design nor in the outputs in the logical framework.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | In this fourth year of the project, progress has been reported in gender issues, mainly with women and young people directly and indirectly benefiting from the results of project implementation. In the two EAFs, the workforce was increased, with women and young people in forestry and nursery activities. For the EAF South Coast the average monthly salary was maintained at 1200 cup. This year it increased by 80 technicians and workers, and 6 women are maintained in direct and indirect work. At EAF Mayabeque, the average monthly salary was 865.00 cou. At present, 5 women work in this EAF, which must be increased with two more women, for the activities of the forest nursery. The completion of 5 groups of volunteers was achieved, in 5 locations: Surgidero de Batabanó, Cajío, Majana beach, Guanimar and Mayabeque beach. For a total of 74 volunteers (24 women and 50 men).
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | We have learned that, in the design of future adaptation projects to climate change for the coastal zone, the hydrographic basin approach must be taken into account. In other words, it is necessary to consider the management effects upstream and downstream of the intervention area. In addition, indicators of impact and tasks must be included to ensure the sustainability of the project in the long term.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The measures implemented by the project have a great potential for replication inside and outside the intervention area, because the mangrove has shown a great adaptive capacity and responded positively to the restoration interventions carried out. We recommended to review and update (from the technical and economic point of view) before to execute the rehabilitation actions that will be carried out by the forestry company, because it is a key factor to raise the interest of this productive group. In addition, must be considered that the social resilience is not limited to increasing the protection function that ecosystems offer to face the impacts of climate change, it also incorporates attention in the aspects related to the adaptation and improvement of the livelihoods of local inhabitants.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | The lessons learned are: - The correct application of the principles of ecological restoration in the mangrove ecosystem, taking into account a diagnosis and the preparation of the ecosystem health map. - Constitution of a multidisciplinary team to plan and develop the adaptation actions required by the coastal zone. - Incorporation of adaptation actions in the local development plans.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The project has developed and validated a methodology for the restoration of coastal wetlands, this methodology is available to be applied in other areas of the country. Groups of experts in coastal ecosystems have been set up in the research centers directly linked to the project. The forestry brigades are able to carry out the rehabilitation actions with the required quality. So, the technical conditions to scale the results of the project are created.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The active participation of leaders and coastal communities in activities is a key link to achieve the goals of the project. The training of community leaders on topics such as: climate change, life task, local development and ecosystem services guarantee the sustainability of the project's results. In addition, the involvement of the schools guarantees the environmental education of the young generations in transcendental aspects such as the EBA, and the services provided by the coastal wetlands.
What measures are/have been put in place to ensure sustainability of the project/program results? | Incorporation of adaptation actions in the development plans at the municipal and provincial levels; this ensures the sustainability of the achievements. Incorporation of restoration / rehabilitation actions in technical projects and improvement of control indicators.
What measures are being/could have been put in place to improve project/program results? | It would be beneficial to implement a pilot project with local families to promote beekeeping (with native bee); for obtaining honey and wax (non-wood forest products). In addition, this action could enhance pollination in the biological cycles of mangrove species and swamp forests, contributing to the ecological restoration of coastal wetlands.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The project has made an adequate use of the available information and knowledge. Among the documents and information used are: Annual reports of the Mayabeque and South Coast Companies, the Red List of the Flora of Cuba (2016), the protocols for the control protocols of EEI, the annual reports of the Forest Ranger, the inspections reports, and census data (ONEI). The project updated Forest Management using the SIFOMAP system of the Ministry of Agriculture MINAG
If learning objectives have been established, have they been met? Please describe. | The learnings generated by the project have been included in the development plans of the coastal municipalities, this allows their technical and financial planning. The results of the project are shown in government meetings, this allows decision making as adaptive management. In addition, they are being applied in the development loaves of the rest of the coastal municipalities of both provinces.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | All the information needed has been made available.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | The accumulated experience by the project team motivated the redesign of the Communication Strategy and establish a mechanism to measure the impact of the communication strategy and sense of ownership of the people involved.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 84007
Implementing Entity | United Nations Development Program
Type of implementing entity | MIE
Country | Cuba
Region | Latin America and Caribbean
Sector | Coastal management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 288224 | 17519 | 270705 | Total | 281505 | 10800 | 270705 | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 49% | 48% | 50% | % of female beneficiaries | 41% | 38% | 50% | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 15% | 15% | 14% | % of Youth beneficiaries | 15% | 13% | 14% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  | Coastal flooding | 2: Partially effective | Total |  | Coastal flooding | 4: Effective | Total |  | Coastal flooding | 3: Moderately effective | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Multi-sector | National | 2: Undertaking or updating of assessments in progress | 1 | Multi-sector | Local | 3: Risk and vulnterability assessments completed or updated | 1 | Multi-sector | Regional | 2: Undertaking or updating of assessments in progress
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 3: Dissemination and communication | Geographical coverage | Regional | 1 | 4: Response capability | Geographical coverage | Local | 1 | 4: Response capability | Geographical coverage | Local |  |  | Geographical coverage
|  |  |  | Number of municipalities | 6 |  |  | Number of municipalities | 6 |  |  | Number of municipalities | 6 |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Coastal management | 2: Low capacity | Total | 88 | Coastal management | 4: High capacity | Total | 132 | Coastal management | 4: High capacity | Total
|  | % of female targeted | 0 |  |  | % of female targeted | 25% |  |  | % of female targeted | 40% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Coastal management | land | 4: Effective |  | Coastal management | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 677 | ha rehabilitated | 1: Ineffective | Mangroves | 3002 | ha rehabilitated | 4: Effective | Mangroves | 2047 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 939 | ha rehabilitated | 1: Ineffective | Forests | 4315 | ha rehabilitated | 4: Effective | Forests | 2727 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 |  |  |  | 84 | Natural capital | Coastal management | Mangrove reforestation | 60 | Natural capital | Coastal management | Mangrove reforestation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 5: All (Fully integrated) |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 |  |  |  | 8 | 4: Enforced (Most elements implemented) |  | 4: Effective | 8 | 4: Enforced (Most elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on H113: Tomas Escobar: 84 km de costa rehabilitados
Note on L113: Tomas Escobar: 60 km de costa rehabilitados
Note on H129: Tomas Escobar: 6 municipales y 2 provinciales

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness. 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions. 2.2. Number (men and women and other vulnerable groups). 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses. 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None. 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements). 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved. 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement. 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention. 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.