## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 16 September 2015 - 30 September 2016
| Project Title: | Taking Adaptation to the Ground: A Small Grants Facility for Enabling Local Level Responses to Climate Change
| Project Summary: | The overall goal of the project is to ensure that local communities in the project focal areas have reduced vulnerability and increased resilience to the anticipated impacts of climate change. The objective is to incorporate climate adaptation response strategies into local practices so that assets, livelihoods and ecosystem services are protected from climate induced risks associated with expected droughts, seasonal shifts and storm-related disaster events. To do so, the project seeks to increase climate resilience in productive landscapes and socio-economic systems in communities in two pilot district municipalities (Mopani, and Namakwa) in South Africa, by working directly with local stakeholders and anticipated beneficiaries through a small grant mechanism.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | ZAF/NIE/Multi/2013/2 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | South African National Biodiversity Institute (SANBI) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | South Africa | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Northern Cape Province - Namakwa District Municipality; Limpopo Province - Mopani District Municipality | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-10-10
IE-AFB Agreement Signature Date: |  | 2014-10-28 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-09-16 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2017-09-30
| Terminal Evaluation Date: | 2019-08-31
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | SGF Inception Report; Quarterly Technical and Financial Reports (for Quartes 1, 2, 3 and 4) including six-monthly forecasts of project activities and budget and Environmental and Social Risk Assessments; Four-year and Annual Project Implementation Plans; SGF Eligible Expenditure and Disbursement Guidelines; Minutes from NIE Steering Committee, Project Advisory Group (PAG), Technical Advisory Group (TAG), and Project Management Team (PMT) meetings; Field Trip Reports (Mopani and Namakwa reports); Project Performance Report (PPR); four eNews articles (http://www.sanbi.org/node/11937); three Adaptation Network articles; two Conservation South Africa Veepos articles; one Adaptation Fund Press Release (https://www.adaptation-fund.org/sanbi-project-moving-forward-five-new-small-grant-projects-approved-project-development/); and one peer-reviewed scientific paper (What role for local organisations in climate change adaptation? Insights from South Africa). | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.southsouthnorth.org/uncategorized/small-grants-facility/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Carl Wesselink | Dominican Republic
| Email: | carl@southsouthnorth.org | Ecuador
| Date: |  | Egypt
| Government DA | Department of Environmental Affairs | El Salvador
| Name: | Ms Nosipho Ngcaba | Equatoral Guinea
| Email: | dg@environment.gov.za | Eritrea
| Date: |  | Estonia
| Implementing Entity | SANBI | Ethiopia
| Name: | Mandy Barnett | Fiji
| Email: | m.barnett@sanbi.org.za | Finland
| Date: |  | France
| Executing Entity | SouthSouthNorth Trust | Gambia
| Name: | Carl Wesselink | Georgia
| Email: | carl@southsouthnorth.org | Germany
| Date: |  | Ghana
| Facilitating Agency | Conservation South Africa | Greece
| Name: | Sarah Frazee | Grenada
| Email: | sfrazee@conservation.org | Guatemala
| Date: |  | Guinea
| Facilitating Agency | CHoiCe Trust | Guinea Bissau
| Name: | Nicola Stuart-Thompson | Guyana
| Email: | NIKKI@choicetrust.co.za | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 30 September 2016
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 30 September 2016 | 179725
Add any comments on AF Grant Funds. (word limit=200) | The delivery rate of the project for the first year of implementation of the Small Grants Facility is 31% against the projected annual budget. The lag in spending is as a result of over ambitious planning and the slower than expected appointment of the Small Grant Recipients. At the end of September 2016 nine contracts were signed with Small Grant Recipients and USD 88,977 was disbursed against these contracts with only a modest amount of this being approved as eligible expenditure. Accurate reporting and accounting of the income remains an area of intense supervision of the Small Grant Recipients. To this end, the Small Grant Recipients are supported by the Facilitating Agencies who oversee their reporting and ensure their audit trail is sufficient to allow for accurate and transparent reporting, budgeting and cash flow management. A substantial number of financial reports of the Small Grant Recipients will be validated and finalised during the next quarter and an upswing in the spending for the next quarter is expected to be evident. The NIE reviews and approves the overall project expenditure in line with approved budgets and work plans and disbursements are linked to realistic forecasts with minimum risks.
INVESTMENT INCOME | 59221.63
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1: Adaptation assets strengthened through the implementation of at least 12 small grants (approximately USD 100,000 each) disbursed to at least 12 local institutions in the Mopani and Namakwa District Municipalities | 11699.1841
| Output 2.1: At least 12 local institutions in the Mopani and Namakwa Districts are supported to develop small grant projects for local-level adaptation | 67121.5
| Output 2.2 At least 6 local institutions in the Mopani District are supported to implement integrated climate adaptation responses | 14000.93
| Output 3.1: Training opportunities are provided for Small Grant Recipients | 2425.27
| Output 3.2: Local networks for reducing climate change vulnerability and risk reduction are developed, expanded and strengthened | 1659.1657
| Output 3.3: Case studies and policy recommendations are developed for reflecting on, replicating and scaling up small grant financing approaches | 0
| Project execution cost | 29829.6964
| Implementing Entity project management fee | 52989.4723
| TOTAL | 179725.2185
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Adaptation assets strengthened through the implementation of at least 12 small grants (approximately USD 100,000 each) disbursed to at least 12 local institutions in the Mopani and Namakwa District Municipalities | 542072.37 | 2017-09-30
| Output 2.1: At least 12 local institutions in the Mopani and Namakwa Districts are supported to develop small grant projects for local-level adaptation | 48118.2875 | 2017-09-30
| Output 2.2 MOPANI: At least 6 local institutions in the Mopani District are supported to implement integrated climate adaptation responses | 26571.9381 | 2017-09-30
| Output 3.1: Training opportunities are provided for Small Grant Recipients | 27603.7435 | 2017-09-30
| Output 3.2: Local networks for reducing climate change vulnerability and risk reduction are developed, expanded and strengthened | 17052.1173 | 2017-09-30
| Output 3.3: Case studies and policy recommendations are developed for reflecting on, replicating and scaling up small grant financing approaches | 12092.8339 | 2017-09-30
| Project execution cost | 60993.4853 | 2017-09-30
| Implementing Entity project management fee | 44032.1429 | 2017-09-30
| TOTAL | 778536.9184
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Not Applicable
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | Not Applicable
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | Not Applicable

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
| Identified Risk | Current Status | Steps Taken to Mitigate Risk
Financial | Fluctuations in exchange rate (USD: ZAR) which could affect the funding available for implementation and lead to budgetary constraints. | Medium | To date the NIE has received only one disbursement from the AF. The exchange rate at the time of the disbursement was more favourable than predicted in the project proposal. It is anticipated that the exchange rate of the second disbursement from the AF will be more favourable than that of the first. Despite this, a precautionary approach has been adopted, and planning for Years 3 and 4 is being undertaken using the original rate in the proposal. The EE and the NIE will continue to collaborate closely regarding the exchange rate, and undertake any necessary adaptive management in such a way that the achievement of project outcomes are compromised as little as possible, if at all.
| Ineffective management of project funds affects project implementation. | Low | The rigorous quarterly and technical reporting procedures of the project have ensured that project funds have been managed effectively to date. At the end of quarter, the EE provides the NIE with a technical and financial report. This report is a collation of technical and financial reports received from the Facilitating Agencies, which in turn receive technical and financial reports from the contracted Small Grantees. The technical reports outline activities of the previous quarter against what was forecast, and associated spend against activities, and forecast activities and budget for the coming two quarters. The approval of these forecasts by the NIE includes checks to confirm that funds are forecast to be spent on appropriate activities, and the review of the reports confirms funds were spent as planned. If this was not the case, justifications are provided. The financiall report includes financial statements and ledgers related to the expenses of the previous quarter. This rigorous review and approval process of project activities and associated use of project funds has ensured that funds have not been mismanaged to date, and will continue to do so for the remainder of the project.
| Delays in the disbursement of funds, procurement and institutional inefficiencies (e.g. lengthy approval processes) result in delayed recruitment of project staff and hence project implementation. | Low | The recruitment of project staff has not been delayed because of delays in disbursement of funds, procurement and institutional inefficiencies. The NIE will continue to disburse funds, based on approved technical and financial reports, in a timeous manner so as not to delay any necessary recruitment of project staff.
| Delayed implementation and completion of small grant projects due to unanticipated events | Low | Whilst some delays have been experienced in the contracting of small grant recipients resulting in delays in implementation, this will not affect the overall delivery of the project and its associated adaptation benefits. The delays have resulted from challenges in identifying organisations with the capacity and experience to manage small grants and from additional details being required in the proposals submitted by the prospective small grant recipients, to ensure that the proposals align with the SGF requirements and objectives. However, as most small grant projects are two years long, there is no risk of the projects not finishing in the SGF four year period. Within the contracted projects, there have been no unanticipated events to date that have delayed implementation. For small grant projects still to be contracted, focussed discussions are underway about project pipeline development, and critical path analysis and monitoring through the pre- and post-contract phases will support timely implementation and completion of small grant projects, to the extent that is possible.
Project | Lack of incentives for local communities and Small Grant Recipients to apply for small grants, initially, and failure to create ownership of the projects at the community level once the small grants are awarded. | Low | The Facilitating Agencies have engaged extensively with stakeholders in the two project target areas to communicate the opportunity of accessing funding to build climate resilience. Initially, this engagement included local briefing sessions and climate change adaptation training sessions with a broad group of stakeholders to build capacity and create incentives to apply for small grant funding. This resulted in a great deal of interest from locals communities - as a result of the engagements 74 applications were received from a wide range of local stakeholders. This is an indication of the high levels of interest from local participants. Subsequent engagements have included one-on-one sessions with prospective small grant recipients to support the development project proposals, as well as the implementation of approved projects. This support has assisted in developing a sense of ownership in the project and expected outcomes, which respond to the vulnerabilities as outlined by the small grant recipients. The Facilitating Agencies will continue to work closely with existing and new small grant recipients to ensure that project benefits are realised and sustained, thereby enhancing the sense of ownership in projects.
| Small grant projects under the identified Investment Windows fail to build climate resilience in vulnerable, local communities. | Low | As the projects are in the early stages of implementation, increased resilience as a result of the interventions has not yet been realised. This is expected in the coming year. The Facilitating Agencies will continue to work with small grant recipients to ensure that the projects are implemented as planned, and deliver the adaptation benefits that build local resilience in the target communities.
Institutional | Poor coordination with other climate change projects in the focal areas limits the potential to learn from and build on the experiences of related projects. | Low | The Facilitating Agencies, Technical Advisory Groups, Project Advisory Group, EE and NIE are continually sharing project updates with a database of local and national stakeholders to build cohesion with related initiatives. Part of the Year 2 activities will include establishing local platforms for small grant recipients and other local stakeholders to share lessons learned and innovative project ideas, thereby mutually reinforcing the outcomes of complementary projects.
| Limited capacity of grant recipients to coordinate and deliver project outputs | Meduim | As indicated in the mitigation measures at the Proposal stage, the grant recipient criteria have ensured that all contracted small grant recipients have the necessary capacity to the deliver their proposed projects. This was confirmed through a due diligence assessment undertaken by the EE as part of the proposal assessment. In addition, the Facilitating Agencies are working closely with the small grant recipients to ensure they receive the support they require. The grant recipient criteria will apply to all future small grant applicants, as will the assessment at the proposal stage and the provision of support to contracted recipients. Notwithstanding the above, the challenge of identifing suitably qualified and experienced grant recipients remains, and innovative approaches - such as phased contracting - are being used to support local organisations to build the requisite capacity. This capacity challenge has adversely impacted the rate of contracting of small grant recipients and while 9 grantees have been contracted to date, it is noted that only four of these are for fully developed projects.
| Project governance structures fail to perform effectively and efficiently | Low | Project governance structures have functioned effectively and efficiently during the first year of implementation. When necessary, roles and responsibilities will be updated to ensure this continues for the remainder of the project.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
| Identified Risk | Current Status | Steps Taken to Mitigate Risk
| Limited capacity of applicants in the target areas result in poor quality proposals and delayed approval of small grant projects | Medium | At the proposal stage of the SGF it was acknowledged that the capacity of the prospective small grant applicants to develop projects designed to address climate change vulnerabilities may be limited. In fact, one of the objectives of the SGF was to work with stakeholders new to climate change adaptation, to build capacity in this field. The Facilitating Agencies have held briefing sessions and one-on-one meetings to assist in developing this capacity. To date, nine grantees have been contracted but only four fully developed small grant projects have been developed. This has largely been due to the proposals being submitted being of poor quality and requiring additional information to satisfy the project selection criteria related to the delivery of climate change adaptation benefits. In order to address local challenges associated with project identification and development, a phased approach to contracting has been used for five of the nine contracted projects. In the first phase, a small amount of money (approx. USD 2000) has been provided to assist the applicants to develop the detail that is needed for fully developed project proposals. After this first phase, applicants are required to submit detailed proposals that are then re-assessed against the review criteria. This phased approach will continue to be used, as necessary, until all small grant contracts are awarded, to ensure that (1) organisations are supported to participate in the project and that (2) only projects that deliver relevant climate change adaptation benefits are approved.
| Small grant projects do not deliver the adaptation benefits anticipated under the different Investment Windows | Medium | As described above, notwithstanding challenges that are being faced in the project identification and development processes, stringent measures are in place to ensure that the project delivers the quantum of adaptation benefits that are set out in the project proposal.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
A number of mitigation measures were employed in the first year. These measures are lifted from the table above and listed below. The measures were successful in reducing the risks. As a result, the project has not encountered any significant or ‘High’ risks over the first year. • Risk: Ineffective management of funds Mitigation measure: The project has rigorous quarterly and technical reporting procedures, and these have ensured that project funds have been managed effectively to date • Risk: Limited interest in the project because of a lack of understanding about the adaptation benefits Mitigation measure: The Facilitating Agencies have engaged extensively with stakeholders in the two project target areas to communicate the opportunity of accessing funding to build climate resilience, and to ensure the potential benefits are understood. • Risk: Delays in contracting small grant recipients threaten delivery of project outcomes within the project timeframe Mitigation measure: Facilitating Agencies have been supporting small grant applicants to meet the requirements of the contracting conditions, so that contracts can be signed and small grant project initiated. For small grant projects still in the SGF pipeline (including those for which proposals are being delivered, and those still at the initial ideas phase) focused discussions are underway to provide the necessary support to develop small grant proposals, where appropriate. • Risk: Limited capacity of grant recipients to coordinate and deliver project outputs Mitigation measure: The project has clear grant eligibility criteria that ensure that all contracted small grant recipients have the necessary capacity to the deliver their proposed projects. This is confirmed through an institutional due diligence assessment. Where some additional capacity is required, support is provided initially through a Phased contracting approach. • Risk: Poor co-ordination limits the potential to learn from related experiences Mitigation measure: At a local level, the Facilitating Agencies and Technical Advisory Groups are well connected to local project implementers, and at a national level, the Project Advisory Group, EE and NIE are continually sharing project updates with a database of local and national stakeholders to build cohesion with related initiatives • Risk: Project activities do not comply with the AF’s ESP Mitigation measure: The project’s environmental and social risk management procedures include a quarterly assessment of project activities against the 15 ESP Principles, and a feedback loop is in place which results in management measures being developed, approved by the NIE Steering Committee, and implemented by small grant recipients, where required

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Component 1 1. Small Grant Recipients are contracted and the first disbursements paid. 2. Tangible adaptation benefits are delivered. |  | Component 1 1. Contracts are signed for 12 Small Grant Recipients (six in each target area) and disbursements paid. 2. It is not expected that any tangible adaptation benefits are delivered in the first year of the project. |  | In total, 9 Small Grant Recipient contracts have been signed to date. Four of these are for fully developed and approved projects and a further five are for project development support for grantees whose proposals needed substantial strengthening. Four Namakwa Small Grant Recipients were contracted to start project implementation. The first disbursements were paid to 2 of the 4 Namakwa Small Grant Recipients. Five Mopani Small Grant Recipients were contracted to strengthen the technical design of their Proposals. The first disbursements were paid to four of the five Mopani Small Grant Recipients. A contracting process is in progress for two additional Mopani Small Grant Recipients. All approved projects were subjected to a stringent review process that included at least three separate reviews. These were consolidated into a single review that was put before the project approval group and untimatley the NIE Steering Committee. | Marginally Satisfactory (MS)
| Component 2 1. Facilitating Agencies for each target District are contracted to support local communities. 2. Facilitating Agenicies identify and support Applicants with proposal development. 3. Facilitating Agenicies build the capacity of Small Grant Recipients. |  | Component 2 1. Facilitating Agencies for each target District are contracted to support local communities. 2. Facilitating Agenicies identify and support Applicants with proposal development. 3. Facilitating Agenicies build the capacity of Small Grant Recipients. |  | Facilitating Agencies have been contracted in both of the target Districts, and have provided significant support to grantees. One of the Facilitating Agencies (Conservation South Africa) has substantial experience in the field of Climate Change Adaptation. The other (Choice Trust) has excellent local relationships but little experience in the field of climate change, and was contracted on a short term trial basis. The EE is currently reviewing their progress and the outcomes of this review will inform their future role. 1. Facilitating Agencies for each District, have been contracted to provide ongoing support to Small Grant Recipients during proposal development and project implementation. 2a. The Facilitating Agencies called for proposals through local media networks and held briefing sessions in each District to identify potential Applicants. 2b. To date, the Facilitating Agencies have supported at least 15 Applicants during the proposal development stage. 3. The Facilitating Agencies facilitated capacity building sessions with Applicants and Small Grant Recipients, through briefing sessions, site visits and one-on-one meetings. | Satisfactory (S)
| Component 3 1. Small Grant Recipients are trained. 2. Learning platforms are made available to Small Grant Recipients. 3. Case studies and policy recommendations are produced. |  | Component 3 1. Small Grant Recipients are trained to develop their proposals and have increased capacity to implement climate change adaptation projects. 2. Opportunities for Small Grant Recipients to exchange knowledge and learning are created. 3. It is not expected that case studies and policy recommendations are produced in the first year of the project. |  | The programme of work that was envisaged for Component 3 has only recently been initiated. Delays are not expected to impact on overall delivery of the outputs of the component. 1a. Small Grant Recipients were trained to develop their detailed proposals through one-on-one session at the project sites. 1b. Training needs assessments are currently being conducted to identify specific training need for each Small Grant Recipient, for their project implementation. The actual training is scheduled to take place in the second year of the project. 2. Researchers from local tertiary institutions have been contracted to assist the Small Grant Recipients with capturing their learning processes. Lessons learned are captured through quarterly reports to ensure accurate procedural gathering of lessons learned in the SGF project. | Marginally Satisfactory (MS)
[5 empty] | Overall Rating | Marginally Satisfactory (MS)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Carl Wesselink | Carl Wesselink | Carl Wesselink | Carl Wesselink
| Email: | carl@southsouthnorth.org | carl@southsouthnorth.org | carl@southsouthnorth.org | carl@southsouthnorth.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Progress to date is rated as 'Marginally Satisfactory' from the EE's perspective. While the SGF did not meet its target for contracting 12 Small Grant Recipients to start implementing adaptation projects, plans are in place to address the challenges, which primarily related attracting appropriate adaptation proposals from the target communities (Namakwa and Mopani District). As a result of this challenge it was necessary to provide the majority (five of nine) of the Small Grant Recipients financial support to procure sector and technology experts to assist them with reviewing the technical design of their proposals, before implementation can start. With the expert support provided it is anticipated that the target for contracting 12 Small Grant Recipients will be met by the end of Year 2. It is anticipated that the project will meet its targets. To date, no proposals have been received in some of the anticipated Adaptation asset categories e.g. shelter (livestock, market), forestry and, while the overall quantum of adaptation benefits for the project will be met, the specific asset targets may require adjustment at project mid term.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1 1. Small Grant Recipients are contracted and the first disbursements paid. 2. Tangible adaptation benefits are delivered. |  | Component 1 1. Contracts are signed for 12 Small Grant Recipients (six in each target area) and disbursements paid. 2. It is not expected that any tangible adaptation benefits are delivered in the first year of the project. |  | At the start of project implementation it was anticipated that all small grant projects would be contracted by the end of Year 1. To date, while nine Small Grant Recipient contracts have been signed, only four of those projects are under implementation. The others are being supported through a Phased approach to strengthen proposals and meet contracting conditions. Through this support, it is expected that all Small Grant projects will be contracted and under implementation during Year 2. | Marginally Satisfactory (MS)
| Component 2 1. Facilitating Agencies for each target District are contracted to support local communities. 2. Facilitating Agenicies identify and support Applicants with proposal development. 3. Facilitating Agenicies build the capacity of Small Grant Recipients. |  | Component 2 1. Facilitating Agencies for each target District are contracted to support local communities. 2. Facilitating Agenicies identify and support Applicants with proposal development. 3. Facilitating Agenicies build the capacity of Small Grant Recipients. |  | During Year 1 the Facilitating Agencies have supported local Small Grant applicants to develop initial ideas into project Concept Notes, and, where these have been approved, into Project Proposals. In the Namakwa target area, the Facilitating Agency has supported four Small Grant Recipients with the initiation phase of their projects. Over the first year of the SGF it became evident that local communities and organisations require more support than was initially expected, and the Facilitating Agencies have played an active role in building the required capacity. This capacity building will need to continue into Year 2, for new and existing Small Grant Recipients. | Satisfactory (S)
| Component 3 1. Small Grant Recipients are trained. 2. Learning platforms are made available to Small Grant Recipients. 3. Case studies and policy recommendations are produced. |  | Component 3 1. Small Grant Recipients are trained to develop their proposals and have increased capacity to implement climate change adaptation projects. 2. Opportunities for Small Grant Recipients to exchange knowledge and learning are created. 3. It is not expected that case studies and policy recommendations are produced in the first year of the project. |  | This component of the project has yet to be fully developed. Whilst training needs assessments have been initiated and a draft Knowledge Management Strategy is under development, it is expected that the Learning component of the project will become operational in Year 2. | Marginally Satisfactory (MS)
[5 empty] | Overall Rating | Marginally Satisfactory (MS)
Implementing Agency, on aspects of the project the NIE is responsible for delivering | Governance Mechanism: - mechanism established - mechanism operational (quarterly milestone) |  | By the end of Year 1, it is expected that the governance mechanism of the SGF will be established and fully functional i.e. small grants projects will be presented to the NIE Steering Committee for consideration. |  | The governance mechanism of the SGF has been established and is functional. The NIE Steering Committee has convened four times during the first year. At three of those meetings, small grant projects were presented to the Committee for consideration. The Committee has approved four fully developed projects, and a further five through a phased approach to contracting. Several projects have been rejected. The project governance mechanism continues to fulfill its function in ensuring that only appropriate small grant projects are approved through the SGF. | Satisfactory (S)
| Environmental and Social Safeguard and Gender Screening: - tools and procedures for screening developed - screening process operational (quarterly milestone) |  | By the end of Year 1, it is expected that the tools and procedures for screening small grant project applications against environmental and social safeguards and gender mainstreaming principles will be developed. It is expected that these tools and procedures will be applied quarterly to exiting projects, to ensure that any unintended negative impacts are avoided, or mitigated if necessary. |  | The NIE has developed a "Risk Dashboard" which is used to screen new projects against the 15 Principles of the AF's ESP. One of these Principles relates to Gender mainstreaming. This Dashboard is also applied quarterly to the small grant projects, and the activities of the Facilitating Agencies and EE. The NIE has led this process to date. The NIE applied for a Technical Assistance Grant from the AF to assist in the development of a handbook and procedures to accompany the Dashboard. Once completed, this tool will be used to to facilitate training of the EE and Facilitating Agencies on the ESP Principles to allow them to train the Small Grant Recipients on the use and value of the Dashboard. The Grant was approved, but a service provider is yet to be appointed. This appointment, and the related activities, is scheduled for Year 2 of the SGF. | Satisfactory (S)
| Technical and Financial Risk Management: - reporting and forecasting template developed - funds disbursed based on approved reports (quarterly milestone) |  | By the end of Year 1, it is expected that the technical and financial reporting and forecasting templates will be developed, and that the EE will be reporting to the NIE quarterly (this will, in turn, require the Small Grant Recipients and the Facilitating Agencies to be reporting quarterly to the EE). The reporting will allow the management of technical and financial risks, in that only activities and expenses in line with the project's Annual Plans, and the project's Disbursement and Expenditure Guidelines, will be approved. |  | The NIE has developed technical and financial reporting templates. These templates are completed by the EE quarterly and submitted to the NIE, who review the technical report and report back on activities of the previous quarter and forecast of activities for the coming two quarters, and review the financial report supporting the expenditure of the previous quarter. This review and approval process has allowed the NIE to have oversight of the project and make sure funding is directed towards project activities that are in line with the approved project objectives. However, there have been some delays in the submission of the reports, partly due to management capacity in the EE, and partly due to delays in the EE receiving the required reports from the Facilitating Agencies and Small Grant Recipients. A workshop is planned for the first quarter of the second year, where the reporting, review and approval process and lessons learned from Year 1 will be reflected on, so as to streamline processes in Year 2. | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dr. Mandy Barnett
| Email: | m.barnett@sanbi.org.za
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | N/A
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | N/A
| Email: | N/A
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The overall project progress over the first year of implementation is rated as 'Marginally Satisfactory'. Local, project level and national governance processes are well established, most core project staff are in place, contracting, disbursement and expenditure processes are well established and processes for project identification, development and contracting are in place. The project is well on its way to contracting 12 Small Grant Recipients to implement climate change adaptation responses. Four fully developed projects have been approved, and a further five have been contracted in the phased approach. Three additional projects are in the project pipeline. The main challenges that the project has experienced, that have affected its execution to date are: 1. The complexity associated with establishing the systems that are needed for project implementation, including governance, contracting, disbursement, reporting and project reviews. 2. Challenges associated with the development of locally based projects that meet the stringent eligibility requirements of the SGF, partly linked to capacity constraints of local organisations and partly linked to the capacity of the Facilitating Agencies to provide the envisaged support, and partly linked to what may be an overly complex application process. 3. Challenges associated with staff turnover and building the required project management capacity in the EE. Whilst it was hoped that all Small Grant Projects would be contracted by the end of Year 1, the limitations in ability of Small Grant Applicants to write project proposals that outline adaptation responses to an identified climate vulnerability was not entirely unexpected. As a result of the additional information required at the initial stages, a number of Small Grant Proposals are currently in Phase 1 of a phased approach to contracting. In this Phase 1 the information required to identify climate vulnerabilities and propose relevant adaptation responses is being generated, thereby managing the risk of information-poor proposals. At the same time, new Small Grant Projects are being developed as part of the SGF pipeline. It is anticipated that by the end of Year 2 all Small Grant Projects will be contracted and will be delivering adaptation benefits. Therefore it is expected that there will be an increasing trend in the achievement of project outcomes. The project governance, screening and risk management structures and processes are all functioning well, yet will be streamlined in Year 2.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
NOTE: The targets for Output 1.1 are based on the four Small Grant Projects that have been contracted for full project implementation. These targets will be revised at the end of Year 2 when the remaiming eight fully developed projects are expected to be contracted.
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: Increase climate resilience in production landscapes and socio-economic systems in vulnerable communities in two pilot District Municipalities in South Africa, by working directly with local stakeholders and anticipated beneficiaries through a small granting mechanism | 1. Number of vulnerable community members in project target areas with reduced risk to extreme weather events | 1. 0 women and 0 men | 1. 0 women and 0 men | 1. 300 women and 300 men
| 2. Number of Small Grant Recipients with increased capacity to implement climate change adaptation projects | 2. 0 small grant recipients | 2. 9 small grant recipients | 2. At least 12 small grant recipients
| 3. Number of policy briefs presented to South African National Treasury and domestic Green Fund reflecting on experiences of the Community Adaptation SGF and informing appropriate actions with a view to creating a climate adaptation finance mechanism that supports local level responses | 3. 0 policy briefs | 3. 0 policy briefs. | 3. 1 policy brief
Outcome 1: Small grants support concrete adaptation measures that strengthen livelihood strategies, adaptive capacity and ecosystem resilience in vulnerable communities in two district municipalities in South Africa | Number of vulnerable community members with reduced risk to climate-driven impacts as a result of project interventions | 0 women and 0 men | 0 women and 0 men | 300 women and 300 men
Output 1.1: Adaptation assets strengthened through the implementation of at least 12 small grants (approximately USD 100,000 each) disbursed to at least 12 local institutions in the Mopani and Namakwa District Municipalities **Note: The targets are based on four projects approved for full Project Implementation | 1. Number of agricultural adaptation assets: • number of livestock shelters • number of climate resilient livestock • area (ha) under climate smart grazing • area (ha) under climate smart farming practises • number of climate-resilient food gardens • number of tanks used for rainwater harvesting for small-scale farming • area (ha) under improved soil management • area (ha) under improved agroforestry • area (ha) of improved drought resistant crops | • 0 livestock shelters; • 0 climate resilient livestock; • 0 ha under climate smart grazing • 0 ha under climate smart farming practises • 0 climate-resilient food gardens • 0 tanks used for rainwater harvesting for small-scale farming • 0 ha under improved soil management • 0 ha under improved agroforestry • 0 ha of improved drought resistant crops | • 0 livestock shelters • 0 climate resilient livestock • 0 ha under climate smart grazing • 0 ha under climate smart farming practises • 0 climate-resilient food gardens • 0 tanks used for rainwater harvesting for small-scale farming • 0 ha under improved soil management • 0 ha under improved agroforestry • 0 ha of improved drought resistant crops | • 0 livestock shelters; • 65 climate resilient livestock; • 36,163 ha under climate smart grazing • 100 ha under climate smart farming practises • 5 climate-resilient food gardens • 10 tanks used for rinwater harvesting for small-scale farming • 0 ha under improved soil management • 0 ha under improved agroforestry • 0 ha of improved drought resistant crops
| 2. Number of livelihood adaptation assets: • number of communal market facilities • number of cooling facilities for food traders • number of shelters for vegetable production • number of savings groups | • 0 communal market facilities • 0 cooling facilities for food traders • 0 shelters for vegetable production • 0 savings groups | • 0 communal market facilities • 0 cooling facilities for food traders • 0 shelters for vegetable production • 0 savings groups | • 0 communal market facilities • 0 cooling facilities for food traders • 0 shelters for vegetable production • 5 savings groups
| 3. Number of settlement adaptation assets: • number of houses with improved insulation • number of tanks used for domestic rainwater harvesting • number of installed compost toilets • area (ha) with improved coastal storm protection • number of improved river crossings • area (ha) of rehabilitated wetlands and riparian systems | • 0 houses with improved insulation • 0 tanks used for domestic rainwater harvesting • 0 installed compost toilets • 0 ha with improved coastal storm protection • 0 improved river crossings • 0 ha of rehabilitated wetlands and riparian systems | • 0 houses with improved insulation • 0 tanks used for domestic rainwater harvesting • 0 installed compost toilets • 0 ha with improved coastal storm protection • 0 improved river crossings • 0 ha of rehabilitated wetlands and riparian systems | • 20 houses with improved insulation • 10 tanks used for domestic rainwater harvesting • 8 installed compost toilets • 0 ha with improved coastal storm protection • 0 improved river crossings • 0 ha of rehabilitated wetlands and riparian systems
Outcome 2: Small Grant Recipients and associated institutions are empowered to identify response measures to climate-induced vulnerabilities, and implement relevant climate change adaptation projects | Number of Small Grant Recipients with increased capacity to implement adaptation projects that address risks to extreme weather events | 0 small grant recipients. | 9 small grant recipients. | At least 12 small grant recipients.
Output 2.1: At least 12 local institutions in the Mopani and Namakwa Districts are supported to develop small grant projects for local-level adaptation | 1. Number of Small Grant Recipients with women within the management structures | 1. 0 small grant recipients | 1. 9 small grant recipients | 1. At least 10 small grant recipients
| 2. Number of small grant recipients new to climate change adaptation | 2. 0 small grant recipients | 2. 6 small grant recipients | 2. At least 8 small grant recipients
| 3. Number of small grant recipients lead by civil society | 3. 0 small grant recipients | 3. 9 small grant recipients | 3. At least 8 small grant recipients
| 4. Number of small grant recipients with civil society within the management structures | 4. 0 small grant recipients | 4. 9 small grant recipients | 4. At least 12 small grant recipients
Output 2.2: At least 12 local institutions in the Mopani and Namakwa Districts are supported to implement integrated climate adaptation responses | Number of project site visits by Facilitating Agents | 0 site visits | 52 site visits | 192 site visits
Outcome 3: A methodology for enhancing direct access to climate finance is developed, based on lessons learned, providing recommendations for scaling up and replicating in South Africa and beyond | Number of methodologies for enhanced direct access to climate finance | 0 methodologies | 0 methodologies | 1 methodology
Output 3.1: Training opportunities are provided for Small Grant Recipients Number of training sessions to build local community capacity in inter alia climate change adaptation and financial management skills | Number of training sessions to build local community capacity in inter alia climate change adaptation and financial management skills | 0 training sessions | 3 training sessions | 10 training sessions
Output 3.2: Local networks for reducing climate change vulnerability and risk reduction are developed, expanded and strengthened Number of fora for grant recipients to share experiences at inter- and intra-Municipal levels | Number of fora for grant recipients to share experiences at inter- and intra-Municipal levels | 0 fora | 0 fora | At least 4 fora
Output 3.3: Case studies and policy recommendations are developed for reflecting on, replicating and scaling up small grant financing approaches | 1. Number of fora where project outcomes and relevant policy recommendations are presented | 1. 0 fora | 1. 0 fora | 1. At least 6 fora (4 local, 1 national and 1 international fora)
| 2. Number of case studies capturing beneficiary and grantee experiences | 2. 0 case studies | 2. 0 case studies | 2.At least 8 case studies

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1. It was vital that the participating institutions (the National Implementing Entity - NIE, Executing Entity - EE, and Facilitating Agencies - FAs) were established entities, whose mandates enabled them to commit (or at least advance) their own resources and Institutional commitment towards the establishment of the Small Grants Facility (SGF). If programme set up and management had been based purely on ‘commercial’ relationships, the early challenges would have been multiplied. 2. Embedding the SGF in local community needs was always going to be a key element. Facilitated stakeholder engagement over an extended period of time, including vulnerability assessments, briefing sessions and project concept training workshops proved the need for flexible and skilled facilitation of relationships at local level. The role of the FA’s – known and trusted amongst stakeholders – was vital. 3. The complexity of setting up a new Small Grants Facility supporting climate change adaptation at community level, required collaboration and ability to learn by doing. The combination of government, parastatal and civil society participation provided the necessary level of authority, resourcing, skills, commitment, legitimacy, and flexibility to achieve a largely successful establishment phase. The coming together of civil society and government in a programme of this nature is, however not without complications. Having SANBI (NIE) as interlocutor, who understands both government and civil society systems and approach, ensured that this collaboration was effectively managed, notwithstanding on-going communication and information sharing challenges between the various role-players, including grant applicants. The communication challenge has also extended to decision-making processes as especially in the beginning of the process we required all parties to be included in decisions. We are now developing mechanisms to allow for a more streamlined communication process for decisonmaking depending on the level of engagement required. 4. The call for proposals process, requiring prescribed minimum levels of language and organizational, governance and administrative capacity, excluded a number of possible applicants, including promising new entrants. 5. Notwithstanding the facilitation that preceded the ‘project concept’ application process, almost all applicants struggled to articulate a clear adaptation proposition in response to an identified climate vulnerability. Effective review and sharpening of proposals took time and required specific sector skills and site visits and multiple stakeholder engagements, not necessarily suited to a competitive proposal-based competitive review processes. In review of this we may consider different approaches for future pipeline projects which allows for more time for FA to work closely with potential grantees in developing their concepts to closely align with adaptation fund priorities and guide these processes and ensure capacity development allows for improved applications.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Contracting of the EE and FAs was delayed because of lengthy negotiations and engagement with legal representative to finalise contracting terms. Cascading risk from a multi-million dollar grant contract, to executing, facilitation and implementing organisations proves more and more difficult and less and less appropriate the further one goes along the value chain. The impact of these delays was mitigated through the commitment of the EE and FAs to the process and pre-contractual engagement – focused on public-interest (as apposed to commercial) objectives and the ability to bring their own resources to contribute to the costs during the set-up phase. However, the contracting process continued to cause delays down the line when grant recipients were engaged and the consensus is that the process needs streamlining and the documentation needs to be simplified. The difficulty in attracting well articulated adaptation responses from target communities, and collating and communicating multiple reviews, in the grant assessment and approval process, resulted in delays in the contracting of grantees. As a measure to reduce delays, we have improved communication by agreeing that FAs are the primary contact for communications with Small Grant Recipients and project progress is reported to the Project Management Team (FAs and EE) on a fortnightly basis.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Given the difficulty in attracting high quality proposals, the SGF adopted a two phase process for contracting some applicants. The SGF approved limited funds for projects to complete detailed project design work, with the support of experts – ensuring that project designs could be effectively assessed (and approved) for intended SGF outcomes. In order to introduce additional specialised skills in the assessment process, the SGF made use of both external and internal reviewers in addition to the Technical Advisory Group (TAG) and Project Advisory Group (PAG) processes. Detailed consultation with the beneficiary communities was necessary for some projects, after they were approved, so the SGF allowed flexibility for Small Grant Recipients to motivate for any changes that may be necessary after consultation with the beneficiaries.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender disaggregated attendance registers were kept at the briefing sessions and training days. Slightly more women than men attended – and there was equal participation by men and women. The importance of gender as a consideration of future funded projects was emphasised during the briefing session. Application forms: Gender disaggregated information on the applicants and their organisations; and expected beneficiaries has also been collected on the application forms, and was analysed during the review process done by TAG, EE and FAs to ensure that (a) women were represented within management structures; and (b) women were prioritised as beneficiaries of the project. The outcome of this has been a explicit focus on gender representation and targeting in all approved projects. It is too early to determine lessons on project performance and impact.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | ZAF/NIE/Multi/2013/2
Implementing Entity | South African National Biodiversity Institute
Type of implementing entity | NIE
Country | South Africa
Region | Africa
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 2340 | 600 | 1740 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 51.71% | 50% | 52.29% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 20.21% | 33.33% | 15.69% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | NGO |  | 36 | 50% | NGO
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 2: Partially not aware |  | 600 | 50% | 5: Fully aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Multi-sector | Community-based adaptation | 24 | Physical capital | Multi-sector | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 2: Most not integrated |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | Local | Other policy | 3 | Multi-sector | Local | Other policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.