## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 30/4/2018 - 30/06/19
| Project Title: | Conservation and Management of Coastal Resources as a Potential Adaptation Strategy for Sea Level Rise
| Project Summary: | In India nearly 100 million people living along the coastline are reliant on climate-dependent activities such as agriculture, fishing and aquaculture. The livelihood security of these coastal communities and ecological security of the coastal areas are already under stress due to high population density, urbanization, industrial development, high rate of environmental degradation and frequent occurrence of cyclones and storms. Sea level changes and occurrence of extreme events such as cyclones and storm surges will be aggravating this problem. The predicated sea level rise would lead to inundation of seawater in about 5,700 km2 of land along the coastal states of India and nearly 7 million coastal families could be directly affected if the sea level increases by 1 m by 2100. Farming families, fishermen, aqua farmers and others will bear the brunt of these impacts through less stable livelihoods and rising risks to their health, safety and homes. Many fisheries-dependent communities already live a precarious and vulnerable existence because of poverty, lack of access to social services and lack of essential infrastructure. As indicated above the coastal area of India is highly vulnerable to climate change and the present project is designed to link ecological rehabilitation of degraded mangroves, utilization of saline lands for livelihood development and preparing the communities for facing the climate change challenges through adaptation measures.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | IND/NIE/Coastal/2014/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | National Bank for Agriculture and Rural Development (NABARD) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | India | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Project Location: The project is being implemented in the Krishna delta (lat. 15°44′–16°40′N and long. 80°20′–81°30′E) in the state of Andhra Pradesh on the southeast coast of India. The soil of the coastal tract is sandy, coarse, deep and occasionally saline. About 4.5 million people, depending on agriculture, fisheries and aquaculture, live within the delta. About 5,40,000 ha are irrigated with river water within the delta. In the project area, nearly 17% of the population are poorest of the poor and 37% are poor. The land use pattern indicates that nearly 55% of the land area is under agriculture, 8.7% of the area is under forest. Brackish water aquaculture is practiced in about 4,000 ha. Project Villages: Project is being implemented in three villages namely, Sorlagondi, Nali and Basavanipalem, located in the Krishna deltaic region of Andhra Pradesh. The main occupation of the community in all the three villages is Agriculture, Fishing and aquaculture. The total population of the three villages is about 3,905. There are about 1,104 households in these three villages. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Water body based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone | S.No Major Activity Time line 1 Community mobilization and organization 0-6 months 2 Participatory Rural Appraisal 0-6 months 3 Implementing entry point activities 0-6 months 4 Identification and demarcation of site for mangroves and IMFFS 0-6 months 5 Restoration of mangrove areas for coastal protection 7-24 months 8 Land preparation and development of integrated mangrove fishery farming system (IMFFS) and cage and pen culture for fish culture 7-24 months 9 Planting of mangroves and halophytes in the IMFFS farm and participatory monitoring 7-24 months 10 Fish culture in IMFFS in IMFFS and in cages/pens 18-42 months 11 Capacity building and training programmes 3-42 months 12 Programme management activities including reporting 3-50 months 13 Mid-term monitoring by stakeholder's team 24 months 14 Final evaluation 58 month | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-10-10
IE-AFB Agreement Signature Date: |  | 2014-11-25 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-06-23 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 1900-01-22
| Terminal Evaluation Date: | 30-06-2020(Project period extended)
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Reports: 1. Inception Report 2. Participatory Rural Appraisal 3. Socio-economic survey 4. Micro plan 5. Village Level Institutions 6. Exposure visit to Coringa mangroves 7. Exposure visit to Brahmavar, Karnataka on cage culture 8. Mangrove Nursery 9. Mangrove restoration 10. Entry Point activities of the project. Brochures: 1. Overview of the project 2. Climate change Sea level rise and 3. Mangrove conservation and management. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | NA | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | R.Ramasubramanian, Principal Co-ordinator- Coastal Systems Research M S Swaminathan Research Foundation (MSSRF) | Dominican Republic
| Email: | rramasubramani@rediffmail.com; ramasubramanian@mssrf.res.in | Ecuador
| Date: | 2019-07-23 | Egypt
| Government DA |  | El Salvador
| Name: | Ravi S. Prasad, IAS (Joint Secretary) Ministry of Environment, Forests & Climate Change, Govt. of India | Equatorial Guinea
| Email: | ravis.prasad@nic.in | Eritrea
| Date: | 2019-07-23 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Sunil Kumar (CGM-FSPD) National Bank for Agriculture and Rural Development | Fiji
| Email: | fspd@nabard.org climate.change@nabard.org | Finland
| Date: | 2019-12-04 | France
| Executing Agency |  | Gambia
| Name: | M S Swaminathan Research Foundation | Georgia
| Email: | rramasubramani@rediffmail.com; ramasubramanian@mssrf.res.in | Germany
| Date: | 2019-07-26 | Ghana
| Executing Agency |  | Greece
| Name: | Same as Above | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Same as Above | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial Information: Cumulative from project start to [23/06/15 - 30/06/19]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [30-06-2019] |  |  | 522821 |  |  | In USD
|  |  | 31369240 |  |  | In Indian Rupees at the exchange rate of 1 USD = INR 60
Add any comments on AF Grant Funds. (word limit=200) |  |  | No Comments | [7 empty] | 0
INVESTMENT INCOME |  |  | NABARD maintains one AF Ledger account where all the AF funds are credited and pooled. In view of this, project wise investment income may not be ascertained. The Investment Income, cumulative for all the six AF projects at the end of each financial year, shall be reported separately to AF.
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | Project Components | Expected Outcomes | ITEM / ACTIVITY / ACTION |  | AMOUNT in USD | AMOUNT in INR
| 2.Capacity building for coastal protection and livelihoods | Trained stakeholders on coastal protection and livelihoods | Capacity building for coastal protection and livelihoods
|  |  | Activity 2.2.2.Organizing training on IMFFS |  | 3333.3 | 199998
|  |  | Sub Total |  | 3333.3 | 199998
| 3. Restoration of mangrove areas for coastal protection | Restored and healthy mangrove replanted area contributing to protection of coastal erosion sea level rise | Restoring mangroves for coastal protection
|  |  | Activity 3.1.4.Preparing land for mangrove restoration (Canal digging) |  | 37916.5 | 2274990
|  |  | Activity 3.1.5.Planting mangrove saplings |  | 3333.5 | 200010
|  |  | Activity 3.2.2.Establishing mangrove nursery |  | 3200 | 192000
|  |  | Activity 3.1.6.Monitoring and after care |  | 3167 | 190020
|  |  | Sub Total |  | 47617 | 2857020
| 4. Demonstration of Integrated mangrove based fishery livelihoods | Demonstrated fishery related sustainable livelihoods integrated with mangroves | Demonstration of mangrove dependent fishery
|  |  | Activity 4.1.2 a.Constructing two types of IMFFS farms (Pond preparation) |  | 130000 | 7800000
|  |  | Activity 4.1.2 b.Construction of sluice gates |  | 14583 | 874980 | 874980
|  |  | Activity 4.3.2.Construction of cages and pens |  |  |  | 52020
|  |  | Activity 4.1.3.Raising mangrove plantation in the IMFFS farms |  | 867 | 52020 | 249990
|  |  | Activity 4.2.2.Stocking of fishes/shrimps/crabs |  | 4166.5 | 249990 | 108000 | 10383750 | 209749.5 | 12584970
|  |  | Activity 4.2.3.Monitoring of IMFFS ponds |  | 1800 | 108000
|  |  | Activity 4.3.3.Stocking of fish crab juveniles |  | 5000 | 300000
|  |  | Activity 4.3.4 b.Feed cost |  | 3333 | 199980
|  |  | Sub Total |  | 159749.5 | 9584970 | 300000
| 5. Knowledge Management for Improved Coastal Protection | Prepared and published materials on ways to upscale coastal protection and livelihood systems in mangrove areas | Knowledge Management for improve coastal Protection |  |  |  | 199980
|  |  | Activity 5.1.1.Preparation of resource materials in local language |  | 1666.5 | 99990 | 99990
|  |  | Activity 5.1.2.Preparation of Brochure and Pamphlets |  | 0 | 0 | 300000
|  |  | Activity 5.2.1.Documenting processes |  | 5000 | 300000 | 99990
|  |  | Activity 5.2.1 b.Monitoring of Project activities along with community |  | 1666.5 | 99990
|  |  | Activity 5.2.3.Organizing workshop at district level |  | 0 | 0
|  |  | Activity 5.2.4.Organizing workshop at national level |  | 0 | 0
|  |  | Sub Total |  | 8333 | 499980
|  |  | Total of all the Project Components(1-5) |  | 219032.8 | 13141968
|  |  | Project Execution cost |  | 13033 | 781980
|  |  | TOTAL |  | 232065.8 | 13923948
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period [01/07/2019 to 22/06/2020] | Project Components | Expected Outcomes | ITEM / ACTIVITY / ACTION | PROJECTED COST (In USD) | PROJECTED COST (In INR) | Est. Completion Date | Amt already Released (Agreement Signing Amt) | Requested by EE (1st Year) | As per DPR (Agreement Signing + 1st Year of Project Implementation) in USD | As per DPR (Agreement Signing + 1st Year of Project Implementation) in INR
| Community mobilization and organization |  |  | 0 | 0 |  | 680000 | 866645 | 13333 | 799980
| 2.Capacity building for coastal protection and livelihoods | Trained stakeholders on coastal protection and livelihoods | Activity 2.1.2 Organizing training on mangrove restoration techniques to VLI members | 1500 | 90000
|  |  | Activity 2.1.3 Organizing training on mangrove restoration to NGOs and Self government | 1000 | 60000
|  |  | Activity 2.1.4 Organizing training on mangrove restoration to Government officials | 833 | 49980
|  |  | Activity 2.2.2 Organizing training on IMFFS | 3333.5 | 200010
| Sub-Total |  |  | 6666.5 | 399990
| 3. Restoration of mangrove areas for coastal protection | Restored and healthy mangrove replanted area contributing to protection of coastal erosion sea level rise | Activity 3.1.6.Monitoring and after care | 11750 | 705000 | 2019-12-18
| Sub-Total |  |  | 11750 | 705000 |  | 1195833 | 3095105 | 47583 | 2854980
| 4. Demonstration of Integrated mangrove based fishery livelihoods | Demonstrated fishery related sustainable livelihoods integrated with mangroves | Activity 4.1.3.Raising mangrove plantation in the IMFFS farms | 434 | 26040 | 2019-12-18
|  |  | Activity 4.3.3.Stocking of fish crab juveniles | 16666.6 | 999996 | 2019-12-18
|  |  | Activity 4.3.4b.Feed cost | 6666.7 | 400002 | 2019-12-18
| Sub-Total |  |  | 23767.3 | 1426038
| 5. Knowledge Management for improve coastal Protection | Prepared and published materials on ways to upscale coastal protection and livelihood systems in mangrove areas | Activity 5.1.1 b.Preparation of Brochure and Pamphlets | 3333 | 199980 | 2018-12-18 | 430000 | 541710 | 8334 | 500040
|  |  | Activity 5.2.1b.Monitoring of Project activities along with community | 3333 | 199980 | 2018-12-18
|  |  | Activity 5.2.2.Documenting best practices | 5000 | 300000 | 2018-12-18
|  |  | Activity 5.2.3 Organizing workshop at district level | 8333 | 499980
|  |  | Activity 5.2.4 Organizing workshop at national level | 16667 | 1000020
| Sub-Total |  |  | 36666 | 2199960
| Project Execution cost |  | Research fellows 2 nos. | 16000 | 960000 | 2020-06-30
|  |  | Field Asst. - 1 no | 4000 | 240000 | 2020-06-30
|  |  | Travel | 1400 | 84000 | 2020-06-30
|  |  | Contingency and other office expenses | 2800 | 168000 | 2020-06-30
|  |  | Monitoring and Evaluation | 9366 | 561960 | 2020-06-30
| Sub-Total |  |  | 33566 | 2013960
41355840
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  | TOTAL | 112415.8 | 6744948
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  | 0
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)
NA
NA

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Failure in Community Mobilization to undertake the activities of mangrove-fishery - inertia against change | Low | Community was involved in mangrove restoration trainings and also in the mangrove restoration work which helped them earn livelihood and it also helped in developing sesnse of ownership in the given project. Community ownership has been promoted through development of the village committees.
Not all necessary stakeholders may take part in the process with the capacity and commitment required. Afterwards, there can be resistance from some stakeholders in adopting the proposed measures. | Low | All the major stakeholders viz., Community, Government departments and NGOs have been properly oriented about the project. The organisation of stakeholders workshop and the village level meetings have reduced the risk. The initiation of entry point activities in the respective villages have built the confidence and also rapport with the stakeholders. The government department i.e. the forest department has accorded permission to restore 200 ha. of the degraded area. The forest department is also involved in monitoring the work activities. MSSRF is also periodically updating the progress and also submitting the annual reports to the department.
Financial miss-management | Low | Periodic on-site and off-site Monitoring has been conducted for verification of expenditures both by EE and NIE
Slow progress of the work due to climatic unfavourable factors | Low | Though there was delay in getting permission for mangrove restoration from the forest department, the work has been completed successfully.
Extreme weather events during the project lifetime undermine confidence of local communities in adaptation measures promoted by the project | Medium | The IMFFS fishers and community-based institutions are sensitized on disaster risk reduction and on early warning communication operated by Government Agencies. This in turn has enabled to improve the coping capacity of the local communities to overcome the disasters.
Limited capacity of partner organisations to deliver project outputs | Low | The EE has been implementing Joint Mangrove Management for the last 20 years. It has been working with the local communities and implementing community centric projects with adequate training and capacity building initiatives.
Failure to create ownership of the project at the local level | Low | The project components were evolved after having series of consultations with the community members during the project planning stage. The adaptation strategies are simple, increasing community ownership and building in sustainability to project interventions.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
NA
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
NA

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator (MSSRF): | Community mobilized and organized in 3 villages - Village level institutions formed in each village |  | Development of 3 Village level institutions |  | Gender balanced village level institutions formed in all the 3 project villages viz., in Sorlagondi, Nali and Basavanipalem. Community members including women participating in the VLI meetings, planning and implementation of project activities | HS
| Orientation of the stakeholders in Climate change, Sea level rise and Adaptation strategies |  | Orientation of the 1500 members of the community |  | All the 800 members of the community were Oriented in Climate Change, Sea Level Rise and Adaptation strategies Local community members are channelized for the preparation of the annual micro plans for the optimal utilization of resources | S
| 200 stakeholders to be trained on mangrove restoration |  | 120 members of the community would be trained in mangrove restoration |  | 64 members from Basavanipalem were trained in mangrove restoration activities such as mangrove nursery development, canal alignment, digging and planting of saplings. About 20 forest staff members were trained in mangrove sylviculture activities. Number of women, men and youth would be trained in designing and establishing IMFFS farms | S
| Replanted mangrove area close to 3 villages for future coastal protection |  | 200 ha of mangroves replanted |  | Completed planting in 200 ha and the survival of saplings are about 90%. | HS
| Established central mangrove nursery serving the needs of the 3 project villages |  | 3 lakhs saplings were to be raised in the central mangrove nursery |  | About 180000 saplings were raised in the nursery in first 2 years. In addition more than 3 lakhs seeds were planted directly. More than 4 lakhs saplings are available in the plantation. | HS
| Two models of IMFFS demonstrated with the participation of local community and stakeholders |  | 25 ha area to be demonstrated under two models of IMFFS |  | The IMMFS model demonstrated in 25 ha with the participation of local community and stakeholders. Another 10 ha is being prepared. In October, 2019 remaining 15 ha will be completed. | S
| Cage and Pen Culture established for crabs, fish, clams and cockles |  | 10 cages / pens for fish / crab culture |  | 6 floating cages are fabricated recently and the fish fries will be released in August. Another 4 pens/ cages will be prepared in September 2019. | S
| Resource materials prepared for dissemination among various stakeholders |  | Development of 4 pamphlets as resource material |  | 3 pamphlets as resource material developed and published | HS
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | R Ramasubramanian
| Email: | rramasubramani@rediffmail.com; ramasubramanian@mssrf.res.in
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The activities are being implemented as per the plan. The community members were oriented on the climate change vulnerabilities. Participatory vulnerability assessment was carried out and the coping capacity of the community is mapped. The mobilized community was organized into village level institution to plan, implement and monitor the project. During the first year the mangrove restoration work was not started due to delay in getting the permission from the forest department. Mangrove saplings (1.3 lakhs) were raised in the nursery. Field visits were organized to the degraded area to identify the suitability of the area to restore mangroves. Integrated Mangrove Fishery Farming (IMFFS) activity was completed in 15 ha. Three resource materials were prepared and given to the community.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency (NABARD) | Community mobilized and organized in 3 villages - Village level institutions formed in each village |  | Development of 3 Village level institutions |  | Gender balanced village level institutions formed in all the 3 project villages viz., in Sorlagondi, Nali and Basavanipalem. | S
| Orientation of the stakeholders in Climate change, Sea level rise and Adaptation strategies |  | Orientation of the 1500 members of the community |  | All the 800 members of the community were Oriented in Climate Change, Sea Level Rise and Adaptation strategies in the year 1. In last year another orientation was given in three villages for women and youth in which 300 members participated. | S
| 200 stakeholders trained on mangrove restoration |  | 120 members of the community would be trained in mangrove restoration |  | 64 community members were trained in mangrove restoration work during June 2017. About 20 members of the forest department staff were trained on the sylviculture practices such as mangrove nursery and mangrove restoration. | MS
| Replanted mangrove area close to 3 villages for future coastal protection |  | 200 ha of mangroves replanted |  | 200 ha of mangroves restored. About 1.8 lakh nursery raised saplings and 3 lakhs seeds were planted. Now the saplings are one year old and healthy. | HS
| Established central mangrove nursery serving 3 villages |  | 1.3 lakh saplings to be raised in the central mangrove nursery |  | About 1.8lakh saplings raised during last 2 years. | S
| Two models of IMFFS demonstrated with the participation of local community and stakeholders |  | 25 ha area to be demonstrated under two models of IMFFS |  | The IMMFS model demonstrated in 25 ha with the participation of local community and stakeholders. Now another 10 ha is being done. Another 15 ha area has been identified. | S
| Cage and Pen Culture established for crabs, fish, clams and cockles |  | 10 cages / pens for fish / crab culture |  | 6 floating cages are fabricated in which fish fries will be released in August. Another 4 pens/ cages will be prepared in September 2019. | S
| Resource materials prepared for dissemination among various stakeholders |  | Development of 4 pamphlets as resource material |  | 3 pamphlets as resource material are developed and published. Another one will be prepared. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | SHARONVAS K S
| Email: | sharonvas.ks@nabard.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | NA
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The village level meetings were organised regularly. Discussions were held with the community about the progress of the work and other project related activities in the meeting. The training on mangrove restoration has helped the community to involve better in the mangrove restoration works. They also earned their livelihood in the work. The mangrove plantation work was completed in 200 ha. The survival of saplings in about 80% which is improved this year due to causality replacement and better care. Multiple species is being planted to have rich biodiversity. The villagers are happy about the success of the plantation. The IMFFS activity is completed in 25 ha and another 10 ha is under progress. The villagers are interested to convert the abandoned shrimp farms into IMFFS. The target of 50 ha will be completed. The landless community were oriented for cage culture and 6 cages were installed. Sea bass will be cultured in the cages.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
Project Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc.…)
Component(s) | Type of Indicator | Indicator | Baseline | Progress since Inception | Target for Project End
Component 1: Community mobilization and organization | Outcome 1: Improved community organization to undertake climate change adaptation measures | Number of men and women in 3 villages trained in participatory approaches and micro planning and implementing project activities. Number of stakeholders participating in the VLI meetings, planning and implementation of activities | Very limited awareness about climate change and its impact and possible adaptive measures to reduce vulnerability in the project villages | Almost 40% of the community are aware of Climate Change issues in the coastal area. 15 members of the community directly benefit from the IMFFS ponds | At least 60% people (of which nearly 50% of women) living in the project villages directly benefited from reduced vulnerability to climate change related impacts
| Output 1.1: Gender balanced village level institutions formed in Sorlagondi, Nali and Basavanipalem villages | Frequency of VLI meetings organized with quorum | No VLI institutions in place | 3 gender balanced VLI institutions formed for 3 participating villages | 3 gender balanced VLI institutions formed for 3 participating villages
| Output 1.2: 1,500 people oriented to Climate Change (CC), Sea Level Rise (SLR) and adaptive capacity concepts and measures involving mangroves | Number of orientation meetings organized in the three villages | No orientation on CC, SLR and adaptive capacity | 800 members of the community were oriented in Climate Change concepts in which women are 450 (nearly 60%). "The women participation in the Climate change orientation meetings are about 60%. Women have now well understood the importance of the conservation of coastal resources particularly mangroves for strengthening their livelihood as well as for various ecosystem services particularly for their role as Bio-shield." | 1,500 people including 50% women would be orientated on CC, SLR and adaptive capacity
| Output 1.3: Annual micro plans prepared for optimal utilization of resources | Number of micro plans with detailed activities | No micro plan is available | 3 village level annual micro plans are available | 12 micro plans (3 annual micro plans for each village for 4 years) would be developed
Component 2: Capacity building for coastal protection and livelihoods | Outcome 2: Trained stakeholders on coastal protection and livelihoods | Number of women, men and youth trained on mangrove restoration technique Number of women, men and youth trained in designing and establishing IMFFS farms Number of members of local self-government, government institutions and local NGOs trained on mangrove restoration and IMFFS establishment | No Community members trained in mangrove restoration and IMFFS in 2 villages (Nali and Basavanipalayam) 5% of the stakeholder groups know mangrove restoration techniques | 84 members were tranied (64 community members and 20 forest department staff) were trained in mangrove restoration. It is also planned to provide training to NGOs, forest department staff and the community in September 2019. | At least 50% marginalized and vulnerable members of the community and youth trained. At least 20% members of stakeholders organizations working in coastal resource management and improving adaptive capacity of community to climate change in the project region trained.
| Output 2.1: 200 stakeholders trained on mangrove restoration | Number of training programmes organized with equal women and men trainees | 0 Nos.of community members trained in mangrove restoration | 64 members were trained in mangrove restoration. "Among 64 members of the community trained in mangrove restoration, about 35 were women. (i.e., 54.7%) " | 200 members would be trained on mangrove restoration
| Output 2.2: 50 farmers trained in IMFSS | Number of training organized with equal women and men trainees | 0 Nos. of trained farmers on IMFFs | Beneficiaries have been identified and capacity building trainings are in progress | 50 farmers including at least 20 women trained in IMFFS
Component 3: Restoration of mangrove areas for coastal protection | Outcome 3: Restored and healthy mangrove replanted area, contributing to protection of coastal erosion and sea -level rise | VLI plan for mangrove restoration and protection in each of 3 villages Mangrove restored with 300,000 mangrove saplings Conditions of mangrove plantation: 80% survival of planted saplings and growth rate. | 0 community plan is available for mangrove management 800 ha of degraded mangroves present nearby project villages | Restoration of degraded mangrove forest has commenced. "The delay in getting permission from the state forest department: During the proposal development, the district collector gave permission to restore mangroves. However, while initiating the work, it was found that the area has been handed over to the Forest department, Government of Andhra Pradesh by the Revenue department. The EE has again approached the forest department with a formal request and submitted requisite project related documents. The Forest Department has assessed the request and gave permission after lapse one year. However, the activity has since been completed now. " | Mangrove restoration would be conducted in 200 ha area
| Output 3.1: Replanted mangrove area close to 3 villages for future coastal protection | Area of mangrove restored with multispecies of mangroves | 800 ha of degraded mangrove near project villages was restored under certain other project implemented by the executing entity | 200 ha of mangroves were restored. More than 4 lakhs saplings planted. "About 3 lakhs saplings survived. Causalities will be replaced in Sep/Oct 2019. More than 4 lakhs saplings were planted and the survival was about 80%. The 20% causalities would be replaced to get 100% survival by end of the project period. It was also noted that there has been natural rejuvenation that has helped in maintaining the requisite plant stand." | Mangrove replantation would be conducted in 200 ha area.
| Output 3.2:Established central mangrove nursery serving 3 villages | Number of saplings of different mangrove species raised | No nursery present | 1.8 lakhs saplings were raised during first 2 years. However, more than 4 lakhs saplings were planted including direct planting of seeds. It has more than 3.5 lakhs saplings in the 200 ha of plantation. | One centralized nursery. About 300,000 saplings would be raised.
Component 4: Demonstration of Integrated mangrove based fishery livelihood | Outcome 4: Demonstrated fishery related sustainable livelihoods integrated with mangroves | Village Level Institution (VLI) plan for IMFFS establishment and management Reduction in input costs of shrimp and fish farming compared to conventional aqua farms | 100 ha abandoned shrimp farms present near project villages | 25 ha area of IMFFS and another 10 ha area is under progress. The community is coming forward more areas now. The remaining 15 ha will be taken up in October 2019. 6 cages for fish culture were just installed. The sea bass juveniles from Rajiv Gandhi Centre for Aquaculture will be stocked in August 2019. | IMFFS established in 50 ha in abandoned shrimp farms by participating farmers with a minimum of 600 mangroves plants per ha and 300 kg of prawn per year per ha of IMFFS
| Output 4.1: Two models of IMFFS demonstrated with the participation of local community and stakeholders | Number of IMFFS ponds | No IMFFS farm | Demonstration of IMFFS model for 25 ha area and another 10 ha is under progress | Demonstration of IMFFS model for 50 ha area
| Output 4.2: Two culture of fish or prawn or both undertaken in the IMFFS farms per year | Number of culture by IMFFS farmers | No culture (Abandoned farms) | Three cultures were completed in 15 ha. First culture started in 10 ha of ponds prepared in April/ May 2019. "During the report period 25 ha of IMFFS ponds were established. Of that in 15 ha Ponds three crops were harvested totaling 45 cultures. In the rest i.e. 10 ha one culture has been done. Totally 55 cultures were completed." | Fish/ crab culture in 50 ha of IMFFS farms
| Output 4.3: Cage and pen culture established for culture of crabs, fish, clams and cockles | Number of cages and pens established for culture of fishes | No cages | Preliminary assessment is made. Community members and MSSRF trained in cage culture. Six cages were installed in July 2019. | 10 cages would be established for culture of fishes
Component 5: Knowledge Management for Improved Coastal Protection | Prepared and published material on ways to up-scale coastal protection and livelihood systems in mangrove areas | Awareness materials on CC, SLR, Vulnerability and Adaptive capacity prepared in local language and distributed to community and other stakeholders Number of meetings and workshops held Number of brochures and pamphlets prepared and distributed | No awareness materials were available | Three brochures prepared and distributed to the community living in 3 villages. Another brochure on cage culture and IMFFS is being prepared. | 4 brochures and 2 workshops (one district level and the other at national level)
| Output 5.1: Resource materials prepared for dissemination among various stakeholders | No of pamphlets distributed to various stakeholders | No pamphlets available | 3 brochures were distributed to the stakeholders | 4 brochures would be distributed to the stakeholders
| Output 5.2: Stakeholders brought together and knowledge on CC, SLR, Vulnerability and measures to improve adaptive capacity shared | Number of workshops organized Number of stakeholders participated | N0 workshops organized on CC, Sea Level Rise and vulnerability to CC adaptive capacity | Planned in the December 2019 and March 2020 | 2 workshops - one district level and the other at national level

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Positive factor: One of the Climate Change adaptation strategy, viz., mangrove conservation and management is not new to the local community. The community are experiencing coastal erosion and they want mangroves to be planted to arrest erosion. Communities are also aware that the mangrove restoration activities would increase the fishery production. The aqua farmers also coming forward to adapt IMFFS as it is low input based farming system.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The IMFFS farms were under culture till May 2019. Now the farmers have given 10 ha of land which is being prepared. The other 15 ha will be started in September after harvesting the culture.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | No changes have been made.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Yes. M. S. Swaminathan Research Foundation right from the beginning had involved women and other marginalized communities in all its projects. In all the project villages women are part of the village level institutions and equal opportunity has been given to them in general body and executive body. Drinking water concern identified by women during PRA was addressed in 2 villages as the entry point activity. Large number of women were involved in mangrove nursery development and its management.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | In mangrove restoration activity, mangrove saplings were raised in the nursery close to the sea. The saplings have better adaptation as they were grown in the same saline environment and become accustomed to saltwater environments thereby increasing their overall survival rate. The local community realized that the mangroves will mitigate the sea shore erosion and also help in protecting the village from cyclones as well as sea level rise.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Participatory mangrove restoration through involvement of local communities members, forest departments and other stakeholders helps greatly in achieving the project goals.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Community trainings in mangrove restoration have been held to share techniques for seed collection and storage, canal digging, and planting, managing and monitoring mangroves thereby contributing immensely towards achievement of project objectives. The IMFFS will be completed in 50 ha before December and the cage culture will be also completed in December 2019. The local community now understood these activities as adaptation measures in the event of climate change induced sea level rise.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Raising and planting mangroves helps to reestablish the natural systems to improve protection from floods and erosion. IMFFS, cage culture are the potential areas for expansion. The government at centre and state level are now supporting cages in the brackish water area for fish culture.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Successful participatory resources management with active involvement of Women has been serving as a model to manage the large area of unprotected mangroves located along the other coastal areas of the Krishna district. The planting of mangroves by the community and their better survival has been witnessed by them. They are happy that the mangroves will protect their shore from erosion and also from disasters particularly cyclones.
What measures are/have been put in place to ensure sustainability of the project/program results? | The participating farmers in mangrove restoration have given an undertaking indicating that they would carry on aqua farming in the IMFFS farm and protect the mangrove plantations in the IMFFS beyond the project period thereby reflecting the project sustainability in the future.
What measures are being/could have been put in place to improve project/program results? | During the course of the project, location specific management protocol has been developed jointly by the project aqua farmers, MSSRF, and National Centre for Sustainable Aquaculture, Government of India to improve the project outcomes. The community members were taken to Karnataka to observe the cage culture carried out in the backwaters of Udipi district.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The information on sea level rise and role of mangroves and IMFFS in increasing community adaptive capacity towards Climate Change.
If learning objectives have been established, have they been met? Please describe. | Yes. Learning objectives are met through organization of farmers to farmer learning programme under the project to provide exposure to IMFFS to other aqua farmers in the region of project implementation.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | NA
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes. Learning among aqua farmers has helped in replication of IMFFS through Fisherman Associations, Self Help Groups (SHGs), Individuals, etc.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | IND/NIE/Coastal/2014/1
Implementing Entity | National Bank for Agriculture and Rural Development (NABARD)
Type of implementing entity | NIE
Country | India
Region | Asia-Pacific
Sector | Coastal Management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at Mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 1200 | 1000 | 200 | Total | 800 | 600 | 200 | Total | 1000 | 200 | 800
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 40% | 10% | % of female beneficiaries | 40% | 30% | 10% | % of female beneficiaries | 40% | 10% | 50%
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 15% | 10% | 5% | % of Youth beneficiaries | 10% | 8% | 2% | % of Youth beneficiaries | 10% | 5% | 10%
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Salinization | 3: Moderately effective | Total | 500 | Salinization | 4: Effective | Total | 300 | Salinization | 4: Effective | Total | 500 | Salinization | 4: Effective
|  | % of female targeted | 0% |  |  | % of female targeted | 50% |  |  | % of female targeted | 30% |  |  | % of female targeted | 50%
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Disaster risk reduction | Local | 3: Risk and vulnerability assessments completed or updated | 1 | Disaster risk reduction | Local | 3: Risk and vulnerability assessments completed or updated | 1 | Disaster risk reduction | Local | 3: Risk and vulnerability assessments completed or updated | 1 | Disaster risk reduction | Local | 3: Risk and vulnerability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge
|  | 1 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge
|  | 2 | 4: Response capability | Geographical coverage | Local | 2 | 4: Response capability | Geographical coverage | Local | 1 | 4: Response capability | Geographical coverage | Local | 1 | 4: Response capability | Geographical coverage | Local
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Coastal management | 2: Low capacity | Total | 20 | Coastal management | 4: High capacity | Total | 15 | Coastal management | 4: High capacity | Total | 200 | Disaster risk reduction | 4: High capacity
|  | % of female targeted | 0% |  |  | % of female targeted | 30% |  |  | % of female targeted | 30% |  |  | % of female targeted | 40%
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 20 | 30% |  |  | 15 | 30% | Public |  | 20 | 40% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Coastal management | 2: Low capacity | Public | Local | Coastal management | 4: High capacity | Public | Local | Coastal management | 3: Medium capacity | Public | Local | Disaster risk reduction | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Coastal management |  | 50% |  | Coastal management |  | 40% |  | Coastal management |  | 50 |  | Coastal management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 1: Aware of neither |  | 50 | 40% | 4: Mostly aware |  | 25 | 50% | 4: Mostly aware |  | 120 | 50% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Coastal management | Local | 2: Partially responsive (Lacks most elements) |  | Coastal management | Local | 4: Mostly responsive (Most defined elements) |  | Coastal management | Local | 4: Mostly responsive (Most defined elements) |  | Coastal management | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Coastal management | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved |  | Coastal management | 2: Physical asset (produced/improved/strengthened) | 4: Mostly Improved |  | Coastal management | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved |  | Coastal management | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved |  | Coastal management | 2: Physical asset (produced/improved/strengthened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 3 | Community |  | Coastal management | 3 | Community |  | Coastal management | 2 | Community |  | Coastal management | 3 | Community |  | Coastal management
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Disaster risk reduction | biological assets | 4: Effective |  | Disaster risk reduction | biological assets | 4: Effective |  | Disaster risk reduction | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 200 | ha rehabilitated | 1: Ineffective | Mangroves | 200 | ha rehabilitated | 1: Ineffective | Mangroves | 200 | ha rehabilitated | 2: Partially effective | Mangroves | 200 | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 840 | 15% | 2: Limited improvement |  | 840 | 15% | 3: Moderate improvement |  | 600 | 15% | 3: Moderate improvement |  | 650 | 15% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 840 | 15% | From 1% to 5% | Fishing | 840 | 15% | From 20% to 30% | Fishing | 600 | 15% | From 10% to 20% | Fishing | 650 | 15% | From 30% to 40% | Fishing
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 3 | Natural capital | Coastal management | Supporting livelihoods | 3 | Natural capital | Coastal management | Supporting livelihoods | 3 | Natural capital | Coastal management | Supporting livelihoods | 3 | Natural capital | Coastal management | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income level
|  | 690 | Fishing |  | 90 | 690 | Fishing |  | 150 | 600 | Fishing |  | 120 | 690 | fishing
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 50 | Aquaculture |  | 0 | 50 | Aquaculture |  | 200 | 15 | Aquaculture |  | 200 | 50 | Aquaculture
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most |  |  |  | 4: Most |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 1 | Coastal management | National | Environmental policy | 2 | Coastal management | National | Environmental policy | 1 | Coastal management | Regional | Environmental policy | 1 | Coastal management | Regional
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 1 | 2: Partially not enforced (Most elements not implemented) |  | 2: Partially effective | 1 | 4: Enforced (Most elements implemented) |  | 4: Effective | 1 | 4: Enforced (Most elements implemented) |  | 3: Moderately effective | 1 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | for | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adaptive capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Go Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnerability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strengthened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.