## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | October 2015-October 2016
| Project Title: | REDUCING THE VULNERABILITY BY FOCUSING ON CRITICAL SECTORS (AGRICULTURE, WATER RESOURCES, AND COASTLINES) IN ORDER TO REDUCE THE NEGATIVE IMPACTS OF CLIMATE CHANGE AND IMPROVE THE RESILIENCE OF THESE SECTORS
| Project Summary: | Support the development of Costa Ricas’s adaptation capacity in line with the Plan Nacional de Acción de la Estrategia Nacional de Cambio Climático (National Action Plan of the National Strategy on Climate Change)
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Fundecooperacion para el Desarrollo Sostenible | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | NIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Costa Rica | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Communities. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-11-01
IE-AFB Agreement Signature Date: |  | 2014-12-10 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-10-07 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2018-04-07
| Terminal Evaluation Date: | 2020-10-07
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | #FondodeAdaptaciónCostaRica for Facebook's news. "Acciones a través del Programa País del Fondo de Adaptación" http://www.ambientico.una.ac.cr/pdfs/art/ambientico/A6.pdf "Acciones climáticas" https://www.facebook.com/dccCostaRica/videos/1199098133455184/ "41-fincas-lecheras-modelo-inician-proceso-de-adaptacion-al-cambio-climatico" http://presidencia.go.cr/comunicados/2016/06/41-fincas-lecheras-modelo-inician-proceso-de-adaptacion-al-cambio-climatico/ "El Fondo de Adaptación en Costa Rica" http://larutadelclima.org/2016/04/11/fondo-de-adaptacion-en-costa-rica "NOGAL-juego para conocer de Adaptación al Cambio Climático" "Manual de Buenas Prácticas Bríbris y Cabecar" http://es.calameo.com/read/0047140859c1a66ce6402 "El Fondo de Adaptación en Costa Rica y ACEPESA" https://larutadelclima.org/2016/05/17/el-fondo-de-adaptacion-en-costa-rica-y-acepesa/ Juntos por el Mar- Almanaque, video y audio. | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.fundecooperacion.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Carolina Reyes | Dominican Republic
| Email: | creyes@fundecooperacion.org | Ecuador
| Date: | 2016-10-10 | Egypt
| Government DA |  | El Salvador
| Name: | Andrea Meza | Equatoral Guinea
| Email: | cambioclimatico@minae.go.cr | Eritrea
| Date: | 2016-10-10 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Carolina Reyes | Fiji
| Email: | creyes@fundecooperacion.org | Finland
| Date: | 2016-10-10 | France
PCU coordinator
Marianella Feoli Peña
mfeoli@fundecooperacion.org
2016-10-10
| Executing Agency |  | Gambia
| Name: |  | Georgia
| Email: |  | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 10/10/2016 | 1363681.1393
Add any comments on AF Grant Funds. (word limit=200) | It is important to notice that for every disbursement a bank fee is reduce.
INVESTMENT INCOME | 18139.58
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | 1177368.15
| 1.1 | 444317 |  | 1177368.15
| 1.2. | 20000
| 2.1 | 50672.97 |  | -186312.9893
| 2.2 | 288339
| 2.3 | 115606
| 3.1 | 9834
| 3.2 | 119731.63
| 3.3 | 11811
| EE Fee | 180014.4984
| NIE FEE | 123355.041
| TOTAL | 1363681.1393 | #REF!
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1 | 1368237.6422 | October 2017
| 1.2. | 44800 | June 2017
| 2.1 | 7862 | June 2017
| 2.2 | 433175.4776 | June 2017
| 2.3 | 117765.503 | June 2017
| 3.1 | 91005 | June 2017
| 3.2 | 488290.7987 | October 2017
| 3.3 | 208604.426 | October 2017
| EE Fee | 144631 | October 2017
| NIE FEE | 146682 | October 2017
| TOTAL | 3051053.8475
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | 1015944.12
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 0
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | It is expected a total of $5.500.000 of co-financing by the Terminal Evaluation. The co-financing of the project is in-kind and part in cash..

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Extreme weather events or geophysical events diminish programme benefits or cause major disturbances resulting in delays due to needed emergency and recovery processes. | Low | The implementation has considered the improvement of community preparation and response by developing and consolidating early warning protocols and systems.
Programme beneficiaries resistant to change or weak cooperation at the proposed sites | Low | The development of the project considers the involved of the consultation of different stakeholders such as organizations, public and private institutions, that are implementing projects related to climate change. The processes facilitate an active participation of the beneficiaries in order to reinforce the beneficiaries’ ownership of the project, supporting proactive and community-led initiatives.
Project beneficiaries are unable to properly manage the technologies or measures being promoted, and/or the technologies or measures do not improve operational efficiency | Low | Knowledge transfer and awareness building through capacity building activities are contemplated throughout the programme. Promotes a capacity development approach which is based on participatory assessments. These assessments will contribute to building the beneficiaries’ ownership and enable the analysis of autonomous adaptation approaches.
Stakeholders are not able to perceive reductions in vulnerability over the time-scale determined by programme duration. | Low | Maintain proactive outreach communications strategy throughout the programme. Also, the programme is strengthening local capacity to monitor project indicators through the support of the Executing Entities.
Insufficient collaboration/coordination between participating partners and stakeholders | Low | Establishment of agreements with detailed roles and responsibilities, work plans and team building activities throughout the programme implementation. Up to now has been important the participation of NGO’s, public organization, academia and other organizations and has been possible to create alliances among organizations. Up to today, the projects selected include letters of commitment among the EE and partners/stakeholders. Also we had made meetings with each organization to confirm their participation. Also, the EIN has signed contribution agreements and MOU's with stakeholders and partners; with the interest of formalize their participation with the adaptation Fund Programme in Costa Rica. For example, an agreement was sighed with Fundación CRUSA for over $800.000 for the implementation of actions at the local level and an MOU with the Agriculture Ministry for the technical support of the projects.
Delays in programme implementation | Low | Programme activities have been designed and paced to ensure a reasonable chance of completion over five years. The Programme Management Board will provide required oversight for management of programme inputs.
Limited human resources in Government ministries to support activities. | Low | Promotion of early and consistent engagement of senior government decision makers on programme progress and monitoring. Fundecooperación, as EIN, has signed cooperation agreements with the government ministries (that are related to the components) in order to received technical assistance in the field.
Mismanagement of Resources. | Low | Each of the project Executing Entities reports each semester at the financial and technical level. A project financial evaluation each semester is made by the EIN to each of the project. Depending of this analysis the disbursement are made or not to the EE; if not improvements are should be requested to the EE. An external audit was hire to evaluate monthly the implementation and management of resources of the project by Fundecooperación. Also, by December (at the end of financial year) the EIN will be audited.
Fluctuations in exchange rate | Low | Financial Coordinator monitor exchange rate (USD to Colones) in order to communicate any implication to the PC. It is important to mention the exchange rate has during the last months have been beneficial to the project.
Delays in disbursements affects project progress | Low | In order to avoid delays has been important to anticipate as much as possible and to promote constant coordination among National Implementing Entity, Executing Entities and the Adaptation Fund. However, delays can happen and some of the delays respond to the importance of responding 100% to the requirements at the financial and administrative level.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The inception period allowed to the EIN the arrangements needed to confirm the activities in the field and the priorities in each component.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Programme Implementation Oversight Reunions |  | Framework functioning effectively |  | Reunions with several authorities at the national level, this reunions serve as the main mechanism for the provision of technical and strategic advice. The reunions comprised members from different stakeholders with technical interest and knowledge; including relevant government Ministries representatives, Departments and Agencies, the Private Sector Organization, academia, and NGO partners. There were two (2) meetings held in 2016. Also, EIN has implemented regular meetings with executing partners to support the implementation process. The meetings provide a platform for knowledge sharing and allows collaboration among organizations to interact with and support each other. This meetings serves as a way for systematically identifying and helping to proactively resolve operational bottlenecks. | S
| Promotion and Awareness |  | Implementation Communication actions |  | The Programme was featured in the different media and magazine publications at the local level (Ambientico and magazine Agropecuaria/MAG). Also the programme also participated in/supported awareness initiatives such as "Juntos por el Mar", Congreso Nacional Forrajero 2016, and Congreso PCCMCA, were the adaptation subject has been included. Some of the results: *Appearances in national TV and newspapers promoting the Adaptation Fund in Costa Rica. *More than 16 workshops had been held in different communities. *Participation at the COP 22 in order to present many of the results achieved by the programme at the local level. | S
| Monitoring and field visits |  | Monitoring visits facilitation |  | Each of the Executing Entity must report the financial and technical improvements each semester. Executing Entities reports were reviewed and feedback was provided with recommendations for improvement. Field visits were undertaken by EIN along with partners (more than 15 field visits), to meet with beneficiaries in target communities and also to confirm the implementation of the actions. Monitoring visits allows to gain a better understanding of the actions, verify expenditures made and confirm that work and results are as planned. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Carolina Reyes
| Email: | creyes@fundecooperacion.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The implementation of the programme at this stage has been good; until now there are many results achieved at the local level. It is expected to achieved even more results by the second year.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component1 |  | Increasing the adaptation capacity to climate change in the agricultural sector Some expected results at the first year: -At least 18 agricultural and livestock units has identified technological options -At least 18 plans for adaptation at farm level |  | To date the programme has started almost 12 initiatives that respond to agricultural adaptation needs in each of the communities selected. Up to date the programme has achieved the implementation of adaptation measures in 84 farm units. Each unit with its plans farm plans created. | HS
| Component 2 |  | Improving water resources management in order to increase resilience in coastal communities that are more vulnerable to climate change. Some expected results at the first year: -10 ASADAS have implemented a Water Safety Plan or Watershed Management Plans -At least 3 ASADAS have undertaken a vulnerability assessment -10 hectares of aquifer recharge areas reforested |  | To date the programme has started almost 10 initiatives-projects that respond to water resources and coastal areas adaptation needs in each of the communities selected. Up to date: -4 ASADAS have implemented a Water Safety Plan -4 ASADAS have undertaken a vulnerability assessment -25 hectares of aquifer recharge areas reforested | MS
| Component 3 |  | 1. Implementation of different projects at the local level that respond to the adaptation needs of each community. 2. Improving the capacity of communities, producers, institutions, and stakeholders regarding adaptation to Climate Change. |  | All the projects include, as a cross-cutting theme, the improvement of capacities at the local level. At the same time, specific projects that allow the creation of knowledge tools and the improvement of national frameworks has been supported by the programme. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Marianella Feoli as PCU coordinator
| Email: | gerencia@fundecooperacion.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The rating of S is because, even though the programme started until october 2015, over the last year and the inception period we have achieved several important results at the local level. The main reasons factors has been the coordination with the partner organizations and the executing entities during the inception period. Component 1 has been the component with more implementation at the local level creating specifics examples of adaptation. However, is important to mention that the second component, in specific coastal zones, has started with a slow pace that we consider will improve during the second year of implementation. Fundecooperación continuous working with partners from different sectors to ensure the sustainability of the projects, continuous dialogue with the stakeholders and other initiatives to increase impact and to seek for more opportunities to support adaptation measures and to leveraging existing resources to improve impact and value of the actions. The progress and achievement of concrete results certainly demonstrates the good management and implementation until now. Also, we consider that a better result will be achieved during the upcoming periods.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator: indicators towards Objectives
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
1.1.1. | ZAE maps for selected crops of the Central Region | Last ZAE maps of the country were made in 1980 | 1 | 13
1.1.1. | technological showcases implemented and applying technology options for the adaptation to climate change in Naranjo, Puriscal, Dota and Pacayas. | 0 technological showcases implemented | 0 | 4
1.1.1. | Online platform with updated information on adaptation technologies and zoning scenarios | 0 | 0 | 1
1.1.1. | beneficiaries (50% women and 50% men) | 0 | 0 | 1000
1.1.2 | Agricultural and livestock units has identified technological options | 0 units has identified technological options | 84 | 90
1.1.2 | Plans for adaptation at farm level | 0 Plans for adaptation at farm level | 50 | 90
1.1.3 | beneficiaries (50% women and 50% men) | 0 | 533 | 1000
1.1.3 | Discrete agricultural adaptation practices are demonstrated on-farm. Adaptation practices include: enhanced water management techniques, enhanced soil management practices, planting techniques, post-harvest processing and diversified livestock practices. | 0 | 50 | 90
1.1.3 | Number of farms implementing actions | 0 | 50 | 90
1.1.3 | ha on indigenous territories implementing technical options and methods that enhance their resilience to the effects of climate change | 0 | 0 | 1000
1.2.1 | -At least 10 initiatives per year have access to credit schemes for the implementation of adaptation activities -At least 5 microfinancing institutions include credit products available to local small producers for adaptation to climate change | 2 | 0
2.1.1 | At least 50 ASADAS and 2 municipalities have implemented a Water Safety Plan/ Watershed Management Plans | 0 | 4 | 52
2.1.1 | At least 12 ASADAS have undertaken a vulnerability assessment | 0 | 4 | 12
2.1.1 | At least 3 committees formed by various social actors | 0 | 4 | 3
2.1.1 | At least 25,000 water users beneficiated | 0 | 1604 | 25000
2.1.2 | At least 5 measures implemented for integrated watershed protection | 0 | 94 | 5
2.1.2 | 5000 hectares of the watershed improved directly or indirectly by the implementation of management practices | 0 | 0 | 5000
2.2.1 | At least 50 hectares of aquifer recharge areas reforested | 0 | 25 | 50
2.2.1 | Protection of aquifers | 0 | 25 | 1
2.2.2 | At least 25,000 inhabitants in 50 communities have their water supply and associated infrastructure, improved to manage climate-induced impacts on water supply | 0 | 767 | 25000
2.2.2 | 50 communities have their water supply and associated infrastructure improved | 0 | 0 | 50
2.2.3 | -At least 10 initiatives per year -At least 2 credit products available for adaptation to climate change of local water management associations (ASADAS) and national water systems | 0 | 0 | 10
2.3.1 | At least 500 citizens in coastal zones are prepared and trained to deal with the impacts of climate change | 0 | 314 | 500
2.3.1 | At least 10 coastal communities have implemented at least one adaptation measure | 0 | 2 | 10
2.3.1 | 8 km of coastline and beaches in protected areas, redesigned and reforested | 0 | 0 | 8
2.3.1 | At least 1 Community Coastal Reforestation Program | 0 | 1 | 1
2.3.3 | 25 ha of mangrove reforested in Gandoca (including areas within the National Wildfire Refuge Gandoca Manzanillo) | 0 | 0 | 25
2.3.3 | At least one coastal community implement a mangrove nursery effective to combat coastal erosion | 0 | 2 | 1
3.1.1 | At least one Early Warning System and Emergency Protocol implemented | 0 | 0 | 1
3.1.1 | One management system and incident management for Forest Fires | 0 | 0 | 1
3.1.2 | At least 5 communities trained, involving traditional leaders, women and youth groups | 0 | 5 | 5
3.2 | At least 3,000 beneficiaries trained | 0 | 672 | 3000
3.2 | At least than 50 stakeholders participating in awareness raising events | 0 | 63 | 50
3.2 | At least 1000 policymakers and technical officers exhibit improved levels of understanding of climate risk assessment and planning processes for climate change adaptation. | 0 | 76 | 1000
3.2 | -At least 10 knowledge materials (experience notes, case studies, photo stories, videos, etc.) are generated per year starting from year 2 of the programme | 0 | 7 | 10
3.2 | -A completed and operationally tested “Handbook on Coastal Adaptation”, "Technical Guide for Adaptation to Climate Change for the artisanal fishing sector" and "Handbook on Water Supply Systems Adaptation" is developed by the end of the project | 0 | 6 | 1
3.2 | Internalization of environmental costs of the water suppliers to facilitate their adaptation to climate change in vulnerable areas | 0 | 1 | 1
3.2 | -1 online training course | 0 | 1 | 1
3.3 | 70% of programme beneficiaries make use of improved climate risk information | 0 | 0 | 2100
3.3 | At least 10 properly installed and functioning new meteorological stations and information platforms | 0 | 0 | 10

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Lessons learned: - It is important to promote understanding among the EIN, EE, partners and the community groups in order to implement the project in the most successful way. - The support of allies among the projects are needed in order to increase the impact. However, a follow up from the EIN during the whole process is also needed to obtain results. The programme approach is to build partnerships with key national and local organizations in order to facilitate progress, obtain outputs, implement activities and shared objectives. -The constant coordination among the EE and the EIN is needed. The effective coordination allows transparency and good governance of the implementation process.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Many of the Executing Entities were not ready for complying with the different standards needed for the implementation of the project. This slowed the progress in some of the components. Also, a significant time and effort had to be spent addressing the requirements for the Environmental and Social Policy with each of the projects selected. The coastal sub-component has experience delays due to different challenges with the sector. Measures taken include the promotion of specific adaptive actions from the EIN with specific EE that will be choose considering their experience working with the sector.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | In order to implement actions on the ground the NIE had to: (i)facilitate access to information and data bases through the creation of alliances with the organizations that owns the information needed (ii) approved the engagement of technical staff that were already in the Executing Entities as part of the consultants in each of project (iii) to search for support at the technical level with some of the adaptation actions promoted specifically the ones that involves water. Additionally, there were special workshops with each EE to speed up the implementation.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | It is important to mention that the gender consideration on the programme is more focus from a family perspective; as a result, both men and women have been actively involved in programme activities. However, the programme has made efforts on mainstreaming gender into project implementation. The NIE has assisted Executing Entities to gain a better understanding of the importance of addressing gender issues. And to continue this efforts, Fundecooperación asked for the AF technical grant support in order to implement activities such as workshops, stakeholder sensitization sessions and development of the communications strategy etc. in order to comply with the AF Gender Policy. The composition of the PSC is an excellent example of gender equality as both men and women occupy decision-making positions.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | Fundecooperacion para el Desarrollo Sostenible
Type of implementing entity | NIE
Country | Costa Rica
Region | Latin America and Caribbean
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 4008292 | 1225 | 4007067 | Total |  |  |  | Total
|  | % of female beneficiaries | 0 | 0% | 0% | % of female beneficiaries | 0.8699 | 37% | 49.99% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0 | 0% | 0.003269% | % of Youth beneficiaries | 0.070033 | 7% | 0.003269% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 |  |  |  | 1 | Water management | Local | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  | 1 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities | 1 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 |  |  | Total | 32 | Agriculture | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 53% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0%
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
0%
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% |  |  | 204 | 20% | 3: Partially aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
[6 empty] | Agriculture | Local | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
[6 empty] | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
[6 empty] | 1 | National |  | Water management
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Protected areas/National parks | 23993 | ha protected | 4: Effective | Mangroves | 25 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Coasts | 100 | km protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 8 | km rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer |  | km protected | 1: Ineffective | Catchment area/Watershed/Aquifer | 25 | ha protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
[6 empty] | Cultivated land/Agricultural land | 90 |  | 3: Moderately effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 1: None |  |  |  | 3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Water management | National | Public policy | 1 | Water management | National | Public policy
|  | No. of Policies introduced or adjusted | Sector | Scale | Type | 1 | Urban development | National | Public policy
|  | 0 | Urban development | National | Urban policy | 1 | Other | National | Other policy
|  | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Other | National | Other policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.