## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 23/06/15 - 30/04/17
| Project Title: | Conservation and Management of Coastal Resources as a Potential Adaptation Strategy for Sea Level Rise
| Project Summary: | In India nearly 100 million people living along the coastline are reliant on climate-dependent activities such as agriculture, fishing and aquaculture. The livelihood security of these coastal communities and ecological security of the coastal areas are already under stress due to high population density, urbanization, industrial development, high rate of environmental degradation and frequent occurrence of cyclones and storms. Sea level changes and occurrence of extreme events such as cyclones and storm surges will be aggravating this problem. The predicated sea level rise would lead to inundation of seawater in about 5,700 km2 of land along the coastal states of India and nearly 7 million coastal families could be directly affected if the sea level increases by 1 m by 2100. Farming families, fishermen, aqua farmers and others will bear the full force of these impacts through less stable livelihoods and rising risks to their health, safety and homes. Many fisheries-dependent communities already live a precarious and vulnerable existence because of poverty, lack of access to social services and lack of essential infrastructure. As indicated above the coastal area of India is highly vulnerable to climate change and the present project is designed to link ecological rehabilitation of degraded mangroves, utilization of saline lands for livelihood development and preparing the communities for facing the climate change challenges through adaptation measures.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | IND/NIE/Coastal/2014/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | National Bank for Agriculture and Rural Development (NABARD) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Developmental Bank | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | India | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Project Location: The project is being implemented in the Krishna delta (lat. 15°44′–16°40′N and long. 80°20′–81°30′E) in the state of Andhra Pradesh on the southeast coast of India. The soil of the coastal tract is sandy, coarse, deep and occasionally saline. About 4.5 million people, depending on agriculture, fisheries and aquaculture, live within the delta. About 5,40,000 ha are irrigated with river water within the delta. In the project area, nearly 17% of the population are poorest of the poor and 37% are poor. The land use pattern indicates that nearly 55% of the land area is under agriculture, 8.7% of the area is under forest. Brackish water aquaculture is practiced in about 4,000 ha. Project Villages: Project is being implemented in three villages namely, Sorlagondi, Nali and Basavanipalem, located in the Krishna deltaic region of Andhra Pradesh. The main occupation of the community in all the three villages is Agriculture, Fishing and aquaculture. The total population of the three villages is about 3,905. There are about 1,104 houses in these three villages. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone | S.No Major Activity Time line 1 Community mobilization and organization 0-6 months 2 Participatory Rural Appraisal 0-6 months 3 Implementing entry point activities 0-6 months 4 Identification and demarcation of site for mangroves and IMFFS 0-6 months 5 Restoration of mangrove areas for coastal protection 7-24 months 8 Land preparation and development of integrated mangrove fishery farming system (IMFFS) and cage and pen culture for fish culture 7-24 months 9 Planting of mangroves and halophytes in the IMFFS farm and participatory monitoring 7-24 months | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-10-10
IE-AFB Agreement Signature Date: |  | 2014-11-25 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-06-23 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2017-06-23
| Terminal Evaluation Date: | 2019-06-19
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Reports: 1. Inception Report 2. Participatory Rural Appraisal 3. Socio-economic survey 4. Micro plan 5. Village Level Institutions 6. Exposure visit Brochures: 1. Overview of the project 2. Climate change Sea level rise and 3. Mangrove conservation and management | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | NA | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | R.Ramasubramanian, Principal Co-ordinator- Coastal Systems Research M S Swaminathan Research Foundation (MSSRF) | Dominican Republic
| Email: | rramasubramani@rediffmail.com | Ecuador
| Date: | 2017-08-22 | Egypt
| Government DA |  | El Salvador
| Name: | Ravi S. Prasad, IAS (Joint Secretary) Ministry of Environment, Forests & Climate Change, Govt. of India | Equatorial Guinea
| Email: | ravis.prasad@nic.in | Eritrea
| Date: | 2017-08-22 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Ms. T.S.Raji Gain (CGM) National Bank for Agriculture and Rural Development | Fiji
| Email: | bg.mukhopadhyay@nabard.org | Finland
| Date: | 2017-08-22 | France
| Executing Agency |  | Gambia
| Name: | M S Swaminathan Research Foundation | Georgia
| Email: | rramasubramani@rediffmail.com | Germany
| Date: | 2017-08-22 | Ghana
| Executing Agency |  | Greece
| Name: | Same as Above | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Same as Above | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial Information: Cumulative from project start to [23/06/15 - 30/04/17]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [30-04-2017] |  |  | 148725 |  |  | In USD
|  |  | 8923500 |  |  | In Indian Rupees at the exchange rate of 1 USD = INR 60
Add any comments on AF Grant Funds. (word limit=200) |  |  | Unanticipated delays in project implementation have affected the project disbursement schedule and reasons for delay are mentioned in this report. Efforts are being made to bring project activities and the disbursement schedule in line with the project plan.
INVESTMENT INCOME |  |  | NABARD maintains one RBI account where all the funds are credited and pooled. In view of this, project wise investment income may not be ascertained.
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | Project Components | Expected Outcomes | ITEM / ACTIVITY / ACTION (Expected Outputs) |  | AMOUNT in USD | AMOUNT in INR
| 1. Community mobilization and organization | Improved community organization to undertake climate change adaptation measures | Community mobilization and organization
|  |  | Organizing project orientation meetings to community (in 3 villages) |  | 500 | 30000
|  |  | Sensitizing the community on gender |  | 361.8333 | 21710
|  |  | Organizing exposure visits to successful participatory mangrove, IMFFS and coastal resources mgmt projects |  | 674.6333 | 40478
|  |  | Conducting Participatory Rural Appraisal (PRA) |  | 3851.2833 | 231077
|  |  | Forming village level institutions |  | 79.3333 | 4760
|  |  | Implementing entry point activities |  | 3650 | 219000
|  |  | Organizing orientation meetings on CC, SLR and adaptive capacity |  | 1834.4 | 110064
|  |  | Preparing annual micro plan: |  | 179.1667 | 10750
|  |  | Implementing micro plan and monitoring |  | 202.6833 | 12161
|  |  | Sub Total |  | 11333.3333 | 680000
| 2.Capacity building for coastal protection and livelihoods | Trained stakeholders on coastal protection and livelihoods | Capacity building for coastal protection and livelihoods
|  |  | Organizing training on mangrove restoration techniques to VLI members |  | 2500 | 150000
|  |  | Organizing training on mangrove restoration to NGOs and Self government |  | 1250 | 75000
|  |  | Organizing training on mangrove restoration to Government officials |  | 1250 | 75000
|  |  | Sub Total |  | 5000 | 300000
| 3. Restoration of mangrove areas for coastal protection | Restored and healthy mangrove replanted area contributing to protection of coastal erosion sea level rise | Restoring mangroves for coastal protection
|  |  | Preparing land for mangrove restoration (Canal digging) |  | 15905.55 | 954333
|  |  | Establishing mangrove nursery |  | 4025 | 241500
|  |  | Sub Total |  | 19930.55 | 1195833
| 4. Demonstration of Integrated mangrove based fishery livelihoods | Demonstrated fishery related sustainable livelihoods integrated with mangroves | Demonstration of mangrove dependent fishery
|  |  | Constructing two types of IMFFS farms (Pond preparation) |  | 90702.7833 | 5442167
|  |  | Construction of sluice gates |  | 7000 | 420000
|  |  | Raising mangrove plantation in the IMFFS farms |  | 866.6667 | 52000
|  |  | Sub Total |  | 98569.45 | 5914167
| 5. Knowledge Management for Improved Coastal Protection | Prepared and published materials on ways to upscale coastal protection and livelihood systems in mangrove areas | Knowledge Management for improve coastal Protection
|  |  | Preparation of resource materials in local language |  | 6333.3333 | 380000
|  |  | Monitoring of Project activities along with community |  | 833.3333 | 50000
|  |  | Sub Total |  | 7166.6667 | 430000
|  |  | Project Execution cost |  | 6725 | 403500
|  |  | TOTAL |  | 148725 | 8923500
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | Project Components | Expected Outcomes | ITEM / ACTIVITY / ACTION | PROJECTED COST (In USD) | PROJECTED COST (In INR) | Est. Completion Date | Amt already Released (Agreement Signing Amt) | Requested by EE (1st Year) | As per DPR (Agreement Signing + 1st Year of Project Implementation) in USD | As per DPR (Agreement Signing + 1st Year of Project Implementation) in INR
| 1. Community mobilization and organization | Improved community organization to undertake climate change adaptation measures | Sensitizing the community on gender | 138.1667 | 8290 | 2017-12-01
|  |  | Conducting Participatory Rural Appraisal (PRA) | 474.09 | 28445.4
|  |  | Forming village level institutions | 420.6667 | 25240
|  |  | Implementing entry point activities | 350 | 21000
|  |  | Preparing annual micro plan: | 319.43 | 19165.8
|  |  | Implementing micro plan and monitoring | 297.317 | 17839.02
| Sub Total |  |  | 1999.6667 | 119980 |  | 680000 | 866645 | 13333 | 799980
| 2.Capacity building for coastal protection and livelihoods | Trained stakeholders on coastal protection and livelihoods |  | 0 | 0 | NA
| Sub Total |  |  | 0 | 0
| 3. Restoring mangroves for coastal protection | Restored and healthy mangrove replanted area contributing to protection of coastal erosion sea level rise | Preparing land for mangrove restoration (Canal digging) | 22010.95 | 1320657 | 2017-12-01
|  |  | Establishing mangrove nursery | 1308.5 | 78510
|  |  | Planting mangrove saplings | 1000 | 60000
|  |  | Monitoring and after care | 3333 | 199980
| Sub Total |  |  | 27652.45 | 1659147 |  | 1195833 | 3095105 | 47583 | 2854980
| 4. Demonstration of mangrove dependent fishery | Demonstrated fishery related sustainable livelihoods integrated with mangroves | Pond preparation | 39297.2167 | 2357833 | 2017-12-01
|  |  | Construction of sluice gates | 7583.33 | 454999.8
|  |  | Stocking of fishes/shrimps/crabs | 4166.5 | 249990
|  |  | Monitoring of IMFFS ponds | 1800 | 108000
|  |  | Construction of cages and pens | 58333 | 3499980
| Sub Total |  |  | 111180.05 | 6670803 |  | 5914167 | 10383750 | 209749.5 | 12584970
| 5. Knowledge Management for improve coastal Protection | Prepared and published materials on ways to upscale coastal protection and livelihood systems in mangrove areas | Preparation of resource materials in local language | 333.6667 | 20020 | 2017-12-01
|  |  | Monitoring of Project activities along with community | 833.6667 | 50020
| Sub Total |  |  | 1167.3333 | 70040 |  | 430000 | 541710 | 8334 | 500040
| Project Execution cost |  | Research fellows 2 nos. | 4000 | 240000 | 2017-12-01
|  |  | Field Asst. - 1 no | 1000 | 60000
|  |  | Travel | 350 | 21000
|  |  | Contingency and other office expenses | 700 | 42000
|  |  | Monitoring and Evaluation | 675 | 40500
| Sub Total |  |  | 6725 | 403500 |  | 403500 | 847145 | 13450 | 807000
|  |  | TOTAL | 148724.5 | 8923470 | 2017-12-01 |  | 41355840
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? |  |  | NA
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  | NA
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  | NA

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Failure in Community Mobilization to undertake the activities of mangrove-fishery - inertia against change | Low | Exposure visit to project sites has been conducted to increase awareness about the entry point activities. Community ownership has been promoted through development of the village committees.
Not all necessary stakeholders may take part in the process with the capacity and commitment required. Afterwards, there can be resistance from some stakeholders in adopting the proposed measures. | Low | All the major stakeholders viz., Community, Government departments and NGOs have been oriented about the project. The organisation of stakeholders workshop and the village level meetings have reduced the risk. The initiation of entry point activities in the respective villages have built the confidence and also rapport with the stakeholders. The government department i.e. the forest department has permitted to restore 200 ha of the degraded area.
Financial miss-management | Low | Periodic on-site and off-site Monitoring has been conducted for verification of expenditures both by EE and NIE
Slow progress of the work due to climatic unfavourable factors | Low | The mangrove restoration work was delayed due to delay in getting permission from the forest department. Request letters and the required documents were submitted to get permission. Based on the above documents, the department has now allotted permission to bring 200 ha of project area under mangrove plantation.
Extreme weather events during the project lifetime undermine confidence of local communities in adaptation measures promoted by the project | Medium | The IMFFS fishers and community-based institutions are sensitized on disaster risk reduction and on early warning communication operated by Government Agencies. This in turn is observed to improve the coping capacity of the local communities to overcome the disasters.
Limited capacity of partner organisations to deliver project outputs | Low | The EE has been implementing Joint Mangrove Management for the last 20 years. It has been working with the local communities and implementing community centric projects with adequate training and capacity building initiatives.
Failure to create ownership of the project at the local level | Low | The project components were evolved after having series of consultations with the community members during the project planning stage. The adaptation strategies are simple, increasing community ownership and building in sustainability to project interventions
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
NA
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
NA

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator (MSSRF): | Community mobilized and organized in 3 villages - Village level institutions formed in each village |  | Development of 3 Village level institutions |  | Gender balanced village level institutions formed in all the 3 project villages viz., in Sorlagondi, Nali and Basavanipalem. Community members including women participating in the VLI meetings, planning and implementation of project activities | HS
| Orientation of the stakeholders in Climate change, Sea level rise and Adaptation strategies |  | Orientation of the 500 members of the community |  | All the 500 members of the community were Oriented in Climate Change, Sea Level Rise and Adaptation strategies Local community members are channelized for the preparation of the annual micro plans for the optimal utilization of resources | S
| 200 stakeholders to be trained on mangrove restoration |  | 120 members of the community would be trained in mangrove restoration |  | Not initiated. Will be done in September 2017/after receipt of fund as the permission from Government Authorities for mangrove restoration was obtained in March 2017. Number of women, men and youth would be trained in designing and establishing IMFFS farms | MS
| Replanted mangrove area close to 3 villages for future coastal protection |  | 75 ha of mangroves replanted |  | Initiated in Jan 2017 and will be completed in June 2017 | MS
| Established central mangrove nursery serving the needs of the 3 project villages |  | 1.3 lakhs saplings to be raised in the central mangrove nursery |  | About 1.3 lakhs saplings raised in the central mangrove nursery catering to the needs of 3 project villages | S
| Two models of IMFFS demonstrated with the participation of local community and stakeholders |  | 25 ha area to be demonstrated under two models of IMFFS |  | The IMMFS model demonstrated in 15 ha with the participation of local community and stakeholders | S
| Resource materials prepared for dissemination among various stakeholders |  | Development of 4 pamphlets as resource material |  | 3 pamphlets as resource material developed and published | HS
[5 empty] | Overall Rating | S | Satisfactory (S)
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | R Ramasubramanian
| Email: | rramasubramani@rediffmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The activities are being implemented as per the plan. The community members were oriented on the climate change vulnerabilities. Participatory vulnerability assessment was carried out and the coping capacity of the community is mapped. The mobilized community was organized into village level institution to plan, implement and monitor the project. During the first year the mangrove restoration work was not started due to delay in getting the permission from the forest department. Mangrove saplings (1.3 lakhs) were raised in the nursery. Field visits were organized to the degraded area to identify the suitability of the area to restore mangroves. Integrated Mangrove Fishery Farming (IMFFS) activity was completed in 15 ha. Three resource materials were prepared and given to the community.This has resulted in enhanced awareness among vulnerable communities about sea level rise and ways to adapt to it. The project interventions have made communities more climate resilient through enhanced adaptive capacity.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency (NABARD) | Community mobilized and organized in 3 villages - Village level institutions formed in each village |  | Development of 3 Village level institutions |  | Gender balanced village level institutions formed in all the 3 project villages viz., in Sorlagondi, Nali and Basavanipalem. | S
| Orientation of the stakeholders in Climate change, Sea level rise and Adaptation strategies |  | Orientation of the 500 members of the community |  | All the 500 members of the community were Oriented in Climate Change, Sea Level Rise and Adaptation strategies | S
| 200 stakeholders trained on mangrove restoration |  | 120 members of the community would be trained in mangrove restoration |  | Not initiated. Will be done in May 2017 as the permission for mangrove restoration was obtained in March 2017 | MS
| Replanted mangrove area close to 3 villages for future coastal protection |  | 75 ha of mangroves replanted |  | Initiated in Jan 2017 and will be completed in June 2017 | MS
| Established central mangrove nursery serving 3 villages |  | 1.3 lakhs saplings to be raised in the central mangrove nursery |  | About 1.3 lakhs saplings raised in the central mangrove nursery catering to the needs of 3 project villages | S
| Two models of IMFFS demonstrated with the participation of local community and stakeholders |  | 25 ha area to be demonstrated under two models of IMFFS |  | The IMMFS model demonstrated in 15 ha with the participation of local community and stakeholders | S
| Resource materials prepared for dissemination among various stakeholders |  | Development of 4 pamphlets as resource material |  | 3 pamphlets as resource material are developed and published | S
[5 empty] | Overall Rating | S | Satisfactory (S)
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Kuldeep Singh, Sachin Kamble and Sushil Kumar
| Email: | kuldeep.singh@nabard.org, sacjhin.kamble@nabard.org and sushil.kumar@nabard.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | NA
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The activities are implemented as per the plan except for the mangrove restoration activity. The permission given by the district collector to restore 200 ha of mangroves during the project proposal development was later shifted to the forest department. Fresh permission for restoring the mangroves was sought from the forest department for which all the required documents was submitted to them and subsequently forest department principally agreed to provide the land. Permission from the forest department has been received on 08-03-2017 for carrying out the mangrove restoration. Community mobilisation, Increased awareness among communities about climate stress/sea level rise and alternative means of livelihoods, village level committees and increased participation from women are strong/ positive features of the project. Seeking permission from State Government has been a long processwhich has delayed the project. Two monitoring visits were undertaken by NIE. In addition to this, numbner of trainees under different programmes came to the project site for exposure visit.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
Project Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc.…)
Component(s) | Type of Indicator | Indicator | Baseline | Progress since Inception | Target for Project End
Component 1: Community mobilization and organization | Outcome 1: Improved community organization to undertake climate change adaptation measures | Number of men and women in 3 villages trained in participatory approaches and micro planning and implementing project activities. Number of stakeholders participating in the VLI meetings, planning and implementation of activities | Very limited awareness about climate change and its impact and possible adaptive measures to reduce vulnerability in the project villages | Almost 40% of the community are aware of Climate Change issues in the coastal area. 15 members of the community directly benefit from the IMFFS ponds. | At least 60% people (of which nearly 50% of women) living in the project villages directly benefited from reduced vulnerability to climate change related impacts
| Output 1.1: Gender balanced village level institutions formed in Sorlagondi, Nali and Basavanipalem villages | Frequency of VLI meetings organized with quorum | No VLI institutions in place | 3 gender balanced VLI institutions formed for 3 participating villages | 3 gender balanced VLI institutions formed for 3 participating villages
| Output 1.2: 1,500 people oriented to Climate Change (CC), Sea Level Rise (SLR) and adaptive capacity concepts and measures involving mangroves | Number of orientation meetings organized in the three villages | No orientation on CC, SLR and adaptive capacity | 300 members of the community were oriented in Climate Change concepts | 1,500 people including 50% women would be orientated on CC, SLR and adaptive capacity
| Output 1.3: Annual micro plans prepared for optimal utilization of resources | Number of micro plans with detailed activities | No micro plan is available | 3 village level annual micro plans are available | 12 micro plans (3 annual micro plans for each village for 4 years) would be developed
Component 2: Capacity building for coastal protection and livelihoods | Outcome 2: Trained stakeholders on coastal protection and livelihoods | Number of women, men and youth trained on mangrove restoration technique Number of women, men and youth trained in designing and establishing IMFFS farms Number of members of local self-government, government institutions and local NGOs trained on mangrove restoration and IMFFS establishment | 0 community members trained in mangrove restoration and IMFFS in 2 villages (Nali and Basavanipalayam) 5% of the stakeholder groups know mangrove restoration techniques | Trainings will be organised in September 2017/after receipt of fund as the permission for mangrove restoration was obtained in March 2017 | At least 50% marginalized and vulnerable members of the community and youth trained" and "at least 20% members of stakeholders organizations working in coastal resource management and improving adaptive capacity of community to climate change in the project region tarined"
| Output 2.1: 200 stakeholders trained on mangrove restoration | Number of training programmes organized with equal women and men trainees | 0 community members trained in mangrove restoration | Nil | 200 members would be trained on mangrove restoration
| Output 2.2: 50 farmers trained in IMFSS | Number of training organized with equal women and men trainees | 0 trained farmers on IMFFs | Nil | 50 farmers including at least 20 women trained in IMFFS
Component 3: Restoration of mangrove areas for coastal protection | Outcome 3: Restored and healthy mangrove replanted area, contributing to protection of coastal erosion and sea -level rise | VLI plan for mangrove restoration and protection in each of 3 villages Mangrove restored with 300,000 mangrove saplings Conditions of mangrove plantation: 80% survival of planted saplings and growth rate. | 0 community plan is available for mangrove management 800 ha of degraded mangroves present nearby project villages | Nil | Mangrove restoration would be conducted in 200 ha area
| Output 3.1: Replanted mangrove area close to 3 villages for future coastal protection | Area of mangrove restored with multispecies of mangroves | 800 ha of degraded mangrove near project villages | Permission obtained for 200 ha from the forest department. Canal digging will be initiated from April 2017 | Mangrove replantation would be conducted in 200 ha
| Output 3.2:Established central mangrove nursery serving 3 villages | Number of saplings of different mangrove species raised | No nursery present | 1.3 lakhs saplings available for planting | One centralized nurserywould be established.
Component 4: Demonstration of Integrated mangrove based fishery livelihood | Outcome 4: Demonstrated fishery related sustainable livelihoods integrated with mangroves | Village Level Institution (VLI) plan for IMFFS establishment and management Reduction in input costs of shrimp and fish farming compared to conventional aqua farms | 100 ha abandoned shrimp farms present near project villages | 15 ha of IMFFS | IMFFS established in 50 ha in abandoned shrimp farms by participating farmers with a minimum of 600 mangroves plants per ha" and "300 kg of prawn per year per ha of IMFFS
| Output 4.1: Two models of IMFFS demonstrated with the participation of local community and stakeholders | Number of IMFFS ponds | No IMFFS farm | Demonstration of IMFFS model for 15 ha area | Demonstration of IMFFS model for 50 ha area
| Output 4.2: Two culture of fish or prawn or both undertaken in the IMFFS farms per year | Number of culture by IMFFS farmers | No culture (Abandoned farms) | First culture completed. Crabs were cultivated and the same were harvested | 100 culture in 50 ha of IMFFS farms per year
| Output 4.3: Cage and pen culture established for culture of crabs, fish, clams and cockles | Number of cages and pens established for culture of fishes | No cages | Second year cages will be designed and used for culture | 10 cages would be established for culture of fishes
Component 5: Knowledge Management for Improved Coastal Protection | Prepared and published material on ways to up-scale coastal protection and livelihood systems in mangrove areas | Awareness materials on CC, SLR, Vulnerability and Adaptive capacity prepared in local language and distributed to community and other stakeholders Number of meetings and workshops held Number of brochures and pamphlets prepared and distributed | awareness materials available | Three brochures prepared and distributed to the community living in 3 villages | 4 brochures and 2 workshops (one district level and the other at national level)
| Output 5.1: Resource materials prepared for dissemination among various stakeholders | No of pamphlets distributed to various stakeholders | No pamphlets available | 3 brochures were distributed to the stakeholders | 4 brochures would be distributed to the stakeholders
| Output 5.2: Stakeholders brought together and knowledge on CC, SLR, Vulnerability and measures to improve adaptive capacity shared | Number of workshops organised Number of stakeholders participated | workshops organised on CC., SLR and vulnerability to CC adaptive capacity | Planned in the last year | 2 workshops - one district level and the other at national level

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Positive factor: The communites are experiencing coastal erosion and they want mangroves to be planted to arrest erosion. Communities are also aware that the mangrove restoration activities would increase the fishery production. Community mobilisation, Increased awareness among communities about climate stress/sea level rise and alternative means of livelihoods, village level committees and increased participation from women are strong/ positive features of the project. Seeking permission from State Government has been a long processwhich has delayed the project.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The participatory process has taken slightly more time during the initial phase of the project. Earlier the land for mangrove plantation was with the Revenue department. The district collector had given permission for the Mangrove restoration in that revenue land. But later, rights were given to the forest department and fresh request for granting permission for mangrove restoration was made with all necessary documents. Later, permission was obtained in March 2017 to restore 200 ha of degraded mangroves.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | No.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Yes. M S Swaminathan Research Foundation right from the beginning involved women and other marginalized communities in all its projects. In all the project villages women are part of the village level institutions and equal opportunity has been given to them in general body and executive body. Drinking water concern identified by women during PRA was addressed in 2 villages as the entry point activity. Large number of women were involved in mangrove nursery development and its management.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Not Applicable at this Stage
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Not Applicable at this Stage
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Not Applicable at this Stage
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Not Applicable at this Stage
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | Not Applicable at this Stage
What measures are/have been put in place to ensure sustainability of the project/program results? | Not Applicable at this Stage
What measures are being/could have been put in place to improve project/program results? | Not Applicable at this Stage
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Not Applicable at this Stage
If learning objectives have been established, have they been met? Please describe. | Not Applicable at this Stage
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Not Applicable at this Stage
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Not Applicable at this Stage

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | IND/NIE/Coastal/2014/1
Implementing Entity | National Bank for Agriculture and Rural Development (NABARD)
Type of implementing entity | NIE
Country | India
Region | Asia-Pacific
Sector | Coastal Management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 1000 | 800 | 200 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 40% | 10% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 15% | 10% | 5% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Salinization | 3: Moderately effective | Total | 500 | Salinization | 4: Effective
|  | % of female targeted | 0% |  |  | % of female targeted | 50%
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Disaster risk reduction | Local | 3: Risk and vulnerability assessments completed or updated | 1 | Disaster risk reduction | Local | 3: Risk and vulnerability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Storm surge | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 2 | 4: Response capability | Geographical coverage | Local | 2 | 4: Response capability | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 0 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 20 | Coastal management | 2: Low capacity | Total | 20 | Coastal management | 4: High capacity | Total |  |  |  | Total
|  | % of female targeted | 30% |  |  | % of female targeted | 30% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 20 | 30% | Public |  | 20 | 30%
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Coastal management | 2: Low capacity | Public | Local
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 25% |  | Coastal management |  | 8% |  | Coastal management
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 50 | 50% | 1: Aware of neither |  | 15 | 40% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Coastal management | Local | 2: Partially responsive (Lacks most elements) |  | Coastal management | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Coastal management | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved |  | Coastal management | 2: Physical asset (produced/improved/strengthened) | 4: Mostly Improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 2: Somewhat improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strengthened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 3 | Community |  | Coastal management | 3 | Community |  | Coastal management
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Disaster risk reduction | biological assets | 2: Partially effective |  | Disaster risk reduction | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 200 | ha rehabilitated | 1: Ineffective | Mangroves | 200 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 840 | 15% | 2: Limited improvement |  | 840 | 15% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 840 | 15% | From 1% to 5% | Agriculture | 840 | 15% | From 10% to 20% | Aquaculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 3 | Natural capital | Coastal management | Supporting livelihoods | 3 | Natural capital | Coastal management | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 690 | Fishing |  | 90 | 690 | Fishing |  | 150
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 50 | Aquaculture |  | 0 | 15 | Aquaculture |  | 200
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 100 | Aquaculture |  | 0 | 100 | Aquaculture |  | 150
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 3: Some |  |  |  | 4: Most |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 1 | Coastal management | National | Environmental policy | 2 | Coastal management | National | Environmental policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  |  | 2: Partially not enforced (Most elements not implemented) |  | 2: Partially effective |  | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | for | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defence policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adaptive capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Go Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnerability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strengthened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.