## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 12 November 2015 - 30 September 2016
| Project Title: | Building Resilience in the Greater uMngeni Catchment
| Project Summary: | The overall objective of the uMngeni Resilience Project is to reduce the vulnerability of rural communities and small scale farmers in the uMgungundlovu District Municipality (uMDM) in KwaZulu-Natal, South Africa, to the impacts of climate change. This is to be achieved by increasing climate resilience and adaptive capacity by combining traditional and scientific knowledge in an integrated approach to adaptation. This will be enabled through implementing a suite of complementary gender-sensitive project interventions, focussing on: i) early warning and ward-based disaster response systems; ii) ecological and engineering infrastructure solutions specifically focused on vulnerable communities, including women; iii) integrating the use of climate-resilient crops and climate-smart techniques into new and existing farming systems; and iv) disseminating adaptation lessons learned and policy recommendations, to facilitate scaling up and replication. Four sites were selected as demonstration sites for the project based on the results of a vulnerability assessment, stakeholder consultations, and subsequent short-listing and ground-truthing through site visits. The sites are: i) low-lying high-density settlements; ii) the rural area of Ward 8 of Vulindlela, Msunduzi Local Municipality; iii) the rural farming area of Ward 8 of Swayimane, uMshwathi Local Municipality; and iv) the rural area of Ward 5 of Nhlazuka, Richmond Local Municipality.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | ZAF/NIE/Water/2013/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | South African National Biodiversity Institute (SANBI) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | South Africa | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | uMgungundlovu District Municipality, KwaZulu-Natal: i) low-lying high-density settlements; ii) the rural area of Ward 8 of Vulindlela, Msunduzi Local Municipality; iii) the rural farming area of Ward 8 of Swayimane, uMshwathi Local Municipality; and iv) the rural area of Ward 5 of Nhlazuka, Richmond Local Municipality. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2014-10-10
IE-AFB Agreement Signature Date: |  | 2014-10-28 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-11-12 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2018-11-01
| Terminal Evaluation Date: | 2020-10-01
List documents/ reports/ brochures / articles that have been prepared about the project.
|  | Reports: URP Project Inception Report, Quarterly Technical and Financial Reports (for Quarters 1, 2, 3 and 4) including six-monthly forecasts of project activities and budget and Environmental and Social Risk Assessments; Reports to uMDM Community Services and Economic Development Commitees and Council Project plans: Five-year and Annual Project Implementation Plans; Minutes from meetings: NIE Steering Committee, Project Coodinating Committe (PCC), and Technical Task Team (TTT) meetings; uMDM website articles: International Day for Disaster Reduction, uMDM climate change actions; SANBI NIE eNews articles: Small scale farmers observe yield increases due to the uMngeni Resilience Project (URP) interventions http://www.sanbi.org/sites/default/files/documents/documents/november-2016-linked-enews-article-small-scale-farmers-observe-yield-increases-due-umngeni-resilienc.pdf uMDM Annual reports: 2014-15 and 2015-16 Newspaper reports: Adapting to save the future: A district municipality in KwaZulu-Natal is implementing model adaptation practices to deal with climate changeMail & Guardian 20 March 2015, also http://mg.co.za/article/2015-03-20-00-adapting-to-save-the-future), Climate change taught to rural communities (Maritzburg Fever 21 October 2015, also http://www.news24.com/SouthAfrica/Local/Maritzburg-Fever/Climate-change-taught-to-rural-communities-20151021), Swayimane's New Cloud Watcher (Witness Newspaper 10 November 2016), Newsletters/magazines: UKZN Plays Leading Role in Local Climate Change Project (UKZN Indaba 10 February 2016 V4 I1), Addressing the Impact of Climate Change (UKZN Foundation Annual Report 2015/16), uMngeni Resilience Project off to a great start (UKZN Foundation Magazine, August 2016), National Climate Change Network Ciculations: Adaptation Network (project updates included in 4x newsletters) Guidelines: SANBI Eligible Expenditure and Disbursement Guidelines; SANBI Policies And Processes Manual, Research On SANBI Projects MOU Template, Engaging Stakeholders In The URP Guideline, Methodology For Qualitative Evaluation Guideline, Knowledge Management Guideline, Communication Guideline for URP, URP Complaints Procedure; Templates for URP: Register for community engagements, Capturing Learnings: Asifundisane/Lets Share, capturing Learnings: Stories Of Change (What I did differently), Capturing Learnings: Field Visit Report (for visitors to the project) | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.umdm.gov.za | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Nomalungelo Ndlovu | Dominican Republic
| Email: | Nomalungelo.Ndlovu@umdm.gov.za | Ecuador
| Date: |  | Egypt
| Government DA | Department of Environmental Affairs | El Salvador
| Name: | Nosipho Ngcaba | Equatoral Guinea
| Email: | dg@environment.gov.za | Eritrea
| Date: |  | Estonia
| Implementing Entity | SANBI | Ethiopia
| Name: | Mandy Barnett | Fiji
| Email: | m.barnett@sanbi.org.za | Finland
| Date: |  | France
| Executing Agency | uMgungundlovu District Municipality | Gambia
| Name: | Nomalungelo Ndlovu | Georgia
| Email: | Nomalungelo.Ndlovu@umdm.gov.za | Germany
| Date: |  | Ghana
| Sub Executing Agency | University of KwaZulu-Natal | Greece
| Name: | Albert Modi | Grenada
| Email: | ModiAT@ukzn.ac.za | Guatemala
| Date: |  | Guinea
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 30 September 2016 | 341310
Add any comments on AF Grant Funds. (word limit=200) | To date USD 341,310 of the global budget has been spent, and translates to a delivery rate of 36 % at first year of implementation. This is partly due to the recruiting and appointing processes of some of the project staff, such as the Project Finance Officer and Learning Network Officer, taking longer than anticipated. This has resulted in less spending of the Project Execution Costs and total personnel costs. Some of the planned activities that were envisaged to take place during Year 1 have not commenced. However, detailed scoping is underway that will see these activities commence in the next year of implementation. The EE continues to exercise thorough procurement and financial oversight and manages the expenditure in line with the guidelines provided by the NIE. The NIE reviews and approves the overall project expenditure in line with the approved budget and project implementation plans.
INVESTMENT INCOME | USD 432.75
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Component 1 Coordination and technical support | 0
| 1.1 Hydro-climatological and fire information and warnings supplied timeously in an appropriate format for direct use by communities and relevant disaster response officials | 0
| 1.2 Early warning systems empower municipal officials and local communities to respond timeously to seasonal forecasts and potential disaster events | 0
| 1.3: Access to seasonal weather forecasting improves the resilience of small scale farmers to climate variability | 23165.01
| Component 2 Coordination and technical support | 0
| 2.1: Critical settlement infrastructure, community facilities and homes strengthened and stabilised to buffer vulnerable communities against anticipated climate-induced stresses in rural communities | 0
| 2.2 Restored and protected critical ecosystems that maintain ecosystem resilience, provide buffering from climate change impacts and provide freshwater to local communities downstream | 0
| 2.3: Officials empowered to mainstream climate change adaptation into relevant planning and infrastructure development plans and frameworks | 0
| Component 3 Coordination and technical support | 90418.19
| 3.1: Investments in climate-resilient agricultural practices and physical infrastructure at the farm level mitigate impacts of climate variability and change for small scale farmers | 56948.45
| 3.2: The KZN Provincial Department of Agriculture and Environmental Affairs mainstreams adaptation practices into its extension services and farmer support programmes | 2153.89
| Component 4 Coordination and technical support | 16616.68
| 4.1. Community champions, officials and authorities are empowered to participate in the project's activities | 1455.73
| 4.2 Project knowledge outputs and experiences are shared and captured | 0
| 4.3 Policy recommendations support sustaining, scaling up and replicating project successes. | 0
| Project Execution cost | 75811.87
| Implementing Entity project management fee | 74740.1897
| TOTAL | 341310.0097
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Component 1 Coordination and technical support | 32426.7101 | 2017-09-30
| 1.1 Hydro-climatological and fire information and warnings supplied timeously in an appropriate format for direct use by communities and relevant disaster response officials | 132605.8632 | 2017-09-30
| 1.2 Early warning systems empower municipal officials and local communities to respond timeously to seasonal forecasts and potential disaster events | 407.1661 | 2017-09-30
| 1.3: Access to seasonal weather forecasting improves the resilience of small scale farmers to climate variability | 35489.373 | 2017-09-30
| Component 2 Coordination and technical support | 118159.6091 | 2017-09-30
| 2.1: Critical settlement infrastructure, community facilities and homes strengthened and stabilised to buffer vulnerable communities against anticipated climate-induced stresses in rural communities | 6514.658 | 2017-09-30
| 2.2 Restored and protected critical ecosystems that maintain ecosystem resilience, provide buffering from climate change impacts and provide freshwater to local communities downstream | 112377.8502 | 2017-09-30
| 2.3: Officials empowered to mainstream climate change adaptation into relevant planning and infrastructure development plans and frameworks | 0 | 2017-09-30
| Component 3 Coordination and technical support | 90846.5008 | 2017-09-30
| 3.1: Investments in climate-resilient agricultural practices and physical infrastructure at the farm level mitigate impacts of climate variability and change for small scale farmers | 191886.7125 | 2017-09-30
| 3.2: The KZN Provincial Department of Agriculture and Environmental Affairs mainstreams adaptation practices into its extension services and farmer support programmes | 52568.695 | 2017-09-30
| Component 4 Coordination and technical support | 29666.1238 | 2017-09-30
| 4.1. Community champions, officials and authorities are empowered to participate in the project's activities | 63517.9153 | 2017-09-30
| 4.2 Project knowledge outputs and experiences are shared and captured | 0 | 2017-09-30
| 4.3 Policy recommendations support sustaining, scaling up and replicating project successes. | 0 | 2017-09-30
| Project Execution cost | 156999.3265 | 2017-09-30
| Implementing Entity project management fee | 101661.2143 | 2017-09-30
| TOTAL | 1125127.718
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Not applicable
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | Not applicable
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | Not applicable

## Procurement
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  |  | 41
NOTE: The contracts noted with a ** below (i.e. the NIE and EE) are USD contracts. All other contracts are in South African Rand (ZAR), and converted to USD in the table below using the conversion rate of ZAR12.28 to the USD (the rate at the time the first - and only to date - tranche of funding was received). The contract values will will be adjusted according to applicale exchange rates for future reporting periods.
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signiture Date (Contract start date) | Contract end date | Payment to Date (Aproved expenditure to date) | Remaining Balance
National Implementing Entity ** | South African Natyional Biodiversity Institute | 7495055 | 2014-10-28 | 2020-11-11 | 341310.0097 | 7153744.9903
Personnel - National Implementing Entity | South African National Biodiversity Institute - Strategic Grant Manager | 295715 | 2016-07-01 | 2021-06-30 | 52684.3738 | 243030.6262 | #REF!
Executing Entity** | uMgungundlovu District Municipality (uMDM) | 2352507 | 2015-10-21 | 2020-10-30 | 93884.28 | 2258622.72
Personnel - Executing Entity | uMDM Project Manager | 335550.49 | 2015-07-01 | 2020-06-30 | 57622.43 | 277928.06
Personnel - Executing Entity | uMDM Project Finance Officer | 163861.93 | 2016-09-01 | 2020-09-30 | 2229.75 | 161632.18
Personnel - Component 4 | Component 4 Learning Network Officer | 132680.37 | 2016-04-01 | 2020-09-30 | 16079.06 | 116601.31
Services - Executing Entity | Camel SA | 9674.27 | 2016-06-27 | 2016-07-08 | 9674 | 0.27
Services - Componenent 4.1 | Wildlife and Environment Society of South Africa | 15065.62 | 2016-04-01 | 2016-10-31 | 1455.97 | 13609.65
SubExecuting Entity** | University of KwaZulu-Natal (UKZN) | 1617143 | 2015-10-21 | 2020-10-30 | 172685.55 | 1444457.45
Personnel - SubEE | Project Leader | 114162.62 | 2015-07-01 | 2020-06-30 | 15495.5 | 98667.12
Personnel - SubEE | Project Component Coordinator | 268359.12 | 2015-07-01 | 2020-06-30 | 54967.43 | 213391.69
Personnel - SubEE | Field Assistant 1 | 8550.49 | 2015-07-01 | 2016-12-31 | 7329 | 1221.49
Personnel - SubEE | Field Assistant 2 | 3664.5 | 2016-04-01 | 2016-12-31 | 2443 | 1221.5
Goods - SubEE | Campbell Scientific SA | 14845.74 | 2015-11-01 | 2016-02-29 | 14845.74 | 0
Goods - SubEE | UKZN Electronics | 2824.77 | 2016-01-04 | 2016-05-15 | 2825 | -0.23
Goods - SubEE | Ford | 32492 | 2016-01-04 | 2016-05-25 | 32491.86 | 0.14
Services - SubEE | Agrometeorology at UKZN | 2565.15 | 2015-11-01 | 2016-12-31 | 2565 | 0.15
Services - SubEE | Sihle and Siphelele | 2850.16 | 2015-11-01 | 2015-12-31 | 2850 | 0.16
Goods - SubEE | CMH Pinetown | 12139.44 | 2016-08-01 | 2016-10-31 | 12139 | 0.44
Operations - SubEE | Pannar Seeds | 3118.11 | 2016-08-01 | 2016-10-31 | 3118 | 0.11
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
National Implementing Entity | not applicable | not applicable | 7495055 | The NIE was selected based on the approval of the Building Resilience in the Greater uMngeni Catchment Project proposal by the Adaptation Fund Board.
National Implementing Entity, Strategic Grant Manager, Competitive Recruitment Process | not applicable | not applicable | 295715 | Candidate was shortlisted from a pool of applicants based on submission of CV and motivational letter, and selected for the position based on competence demonstrated in a skills test and panel inreview in accordance with SANBI's procurement processes.
Executing Entity | N/A | N/A | 2352507 | The EE was selected based on the approval of the Building Resilience in the Greater uMngeni Catchment Project proposal by the Adaptation Fund Board.
Executing Entity, Project Manager, Competitive Recruitment Process, 25 March 2015 | N/A | N/A | 335550.49 | Candidate was shortlisted from a pool of applicants based on submission of CV and motivational letter, and selected for the position based on competence demonstrated in a skills test and panel interview in accordance with uMDM's procurement processes.
Executing Entity, Project Finance Officer, Competitive Recruitment Process, 19 Apil 2016 | N/A | N/A | 163861.93 | Candidate was shortlisted from a pool of applicants based on submission of CV and motivational letter, and selected for the position based on competence demonstrated in a skills test and panel interview in accordance with uMDM's procurement processes.
Component 4 Learning Network Officer, Competitive Recruitment Process, 8 December 2015 | N/A |  | 132680.37 | Candidate was shortlisted from a pool of applicants based on submission of CV and motivational letter, and selected for the position based on competence demonstrated in a skills test and panel interview in accordance with uMDM's procurement processes.
Camel SA, Development of MSCOA system of accounts and provision of training, Single Source | Camel SA | 9674 | 9674 | CamelSA was well placed to deliver on the project-specific chart of accounts because they have been working with uMDM to develop its Standard Chart of Accounts and are the only National Treasury approved service provider appointed to the uMDM that was able to deliver on this work
Wildlife and Environment Society of South Africa, Development of tools and templates for collecting information for project reporting, Single Source | WESSA | 15065.62 | 15065.62 | The Wildlife and Environment Society of South Africa (WESSA) has been involved in the development of the (URP) since the stage where a project proposal was submitted to SANBI (the National Implementing Entity- NIE). WESSA hold a lot of historical knowledge relating to the project as well as the skills and expertise required to develop the required tools and templates.
SubExecuting Entity, Project Leader, Single Source | N/A | N/A | 114162.62 | Staff member was an existing employee within the organisation, and was assigned URP responsibilities based on a combination of their skills, experience and knowledge. The contract was approved based on the submission of a Single Source Motivation letter. Detailed procurement records are available on request.
SubExecuting Entity, Project Component Coordinator, Single Source | N/A | N/A | 268359.12 | Staff member was an existing employee within the organisation, and was assigned URP responsibilities based on a combination of their skills, experience and knowledge. The contract was approved based on the submission of a Single Source Motivation letter. Detailed procurement records are available on request.
SubExecuting Entity, Field Assistant 1, Single Source | N/A | N/A | 8550.49 | Staff member was an existing employee within the organisation, and was assigned URP responsibilities based on a combination of their skills, experience and knowledge. The contract was approved based on the submission of a Single Source Motivation letter. Detailed procurement records are available on request.
SubExecuting Entity, Field Assistant 2, Single Source | N/A | N/A | 3664.5 | Staff member was an existing employee within the organisation, and was assigned URP responsibilities based on a combination of their skills, experience and knowledge. The contract was approved based on the submission of a Single Source Motivation letter. Detailed procurement records are available on request.
Campbell Scientific, Supply of automatic weather station, Single Source | Campbel Scientific SA | 14846 | 14846 | Campbell Scientific SA are the only authorised dealer permitted to import the automatic weather station required for the project.
UKZN Electonics, supply of computers for Swayimane HighSchool, three quotes | Dell | 3471 | 2825 | The lowest quote, representing the best value for money, was selected.
| Vuwani | 3042
| UKZN Electronics | 2824.77
Ford, supply of project vehicle for SubEE, three quotes | Toyota | 33420.71 | 32492 | The lowest quote, representing the best value for money, was selected.
| Ford | 32492
| Isuzu | 37699
Agrometeorology at UKZN, maintenance of the Automatic weather station, single source | Agrometeorology at UKZN | 2565 | 2565 | The Agrometeorology Department is well place to deliver on these responsibilities because it has strong capacity in instrumentation, especially setting and maintenance of AWS systems. They have also conducted pioneering work with the AIM system. In addition, the Agrometeorology Department has a strong working relationship with the Project Team. This will allow for seamless collaboration and linking of their effort to the overall project objectives with respect to Component 1.3.
Sihle and Siphelele, Tractor hire for land preperation, single Source | Sihle and Siphelele | 2850 | 2850 | Sihle and Siphele are from the Swayimane community. They were appointed to do the land prep as they own tractors and this will boost local, community upliftment rather than hiring a tractor from outside the project area.
CMH Pinetown, supply of project vehicle for Extension Officers, three quotes | CMH Pinetown | 12139 | 12139 | The lowest quote, representing the best value for money, was selected.
| CMH Pietermaritzburg - | 13477.93
| CMH Durban | 14907.4
Pannar Seeds, supply of maize (SC701), single source | Pannar Seeds | 3118.11 | 3118 | Pannar are the single licenced supplier of SC701 in South Africa. All other suppliers (retailers) buy it from them and then repackage and resell. The farmers in Swayimane and most rural areas in KwaZulu-Natal prefer SC701 as it produces huge cobs which are desirable for the green mealies market which is their primary market..

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Fluctuations in exchange rate (USD: ZAR) which could affect the funding available for implementation and lead to budgetary constraints. | Low | To date the NIE has received only one disbursement from the AF. The exchange rate at the time of the disbursement was more favourable than predicted in the project proposal. It is anticipated that the exchange rate of the second disbursement from the AF will be more favourable than that of the first. Despite this, a precautionary approach has been adopted, and planning for Years 3 and 4 is being undertaken using the rate at the first disbursement. The EE and the NIE will continue to collaborate closely regarding the exchange rate, and undertake any necessary adaptive management in such a way that the achievement of project outcomes are compromised as little as possible, if at all.
Ineffective management of project funds affects project implementation. | Low | The rigorous quarterly and technical reporting procedures of the project have ensured that project funds have been managed effectively to date. At the end of quarter, the EE and sub-EE provide the NIE with a technical and financial report. The technical reports outline activities of the previous quarter against what was forecast, and associated spend against activities, and forecast activities and budget for the coming two quarters. The approval of these forecasts by the NIE includes checks to confirm that funds are forecast to be spent on appropriate activities, and the review of the reports confirms funds were spent as planned. If this was not the case, justifications are provided. The financial report includes financial statements and ledgers related to the expenses of the previous quarter. This rigorous review and approval process of project activities and associated use of project funds has ensured that funds have not been mismanaged to date, and will continue to do so for the remainder of the project.
Delays in the disbursement of funds, procurement and institutional inefficiencies (e.g. lengthy approval processes) result in delayed recruitment of project staff and hence project implementation. | Medium | A major factor affecting disbursement over the reporting period was delays associated with the registration of the UMDM on SANBI's supplier database, due to recent changes to the database and its centralisation with the National Treasury system. This delay has meant that the EE (UMDM) carried all project costs for the first year of implementation. The matter has now been resolved. There have been some delays in the recruitment of project staff based at the EE. In the case of the Project Finance Officer it was not due to delays in disbursements or institutional inefficiencies, but due to challenges recruiting a candidate who met the required skills and experience. The post was advertised four times before an appointment could be made. This delay did not affect project implementation as the NIE has been providing support in the financial oversight for the EE. Component 2.1 was delayed due to local government elections being held in August 2016 and a decision that, in order to minimise the risk of political interference in the project, engagement with local communities should only commence later in the year. There were delays in the starting of the implementation of component 2.2 due to lengthy contract negotiations. These meant that detailed planning could not commence until the contract discussions between the legal teams were at an advanced stage. The detailed planning will take place at the start of Year 2, with the potential implementing entities who have already been identified in order to mitigate any delays that have occurred.
Difficult access to the sites results in logistically challenging implementation of project interventions. | Low | Accessing project sites has not been a challenge thus far.
Failure to involve adequate representation of vulnerable communities, particularly women, and therefore failure to create ownership of the project at the community level at project sites. | Low | The project is approach is one that is bottom-up, where the community is involved in the planning, which ensures that the voices of normally marginalised groups are heard. In Swayimane the majority of farmers involved in the project are women. A youth group has recently been formed that is also going to be participating in the URP. The process to appoint a Gender and Social Expert is currently underway. The Gender and Social Expert will assist in ensuring that vulnerable and marginalised groups are given equitable access to the project.
Lack of incentives for local farmers to participate and cooperate in interventions that do not yield immediate financial value or reduce incomes in the short-term, but aim at longer-term resilience. This may reduce stakeholder engagement and participation. | Low | Sub-EE project staff have established relationships with the small scale farmers in the target area of Ward 8 of Swayimane. Farmers had already seen the benefits of the on-farm crop trials on a limited portion of their lands, and had expressed an interest in expanding the area of climate-resilient crops. The target for number of farmers involved in the URP for Year 1 was surpassed due to other farmers wanting to participate in the URP after seeing how farmers involved in the URP are benefitting. Small scale farmers from Ward 8 of Vulindlela and community home gardeners from Ward 5 of Nhlazuka will visit the Swayimane crop trial sites and speak to farmers, as part of the training provided through the project. This community exchange, as part of a broader capacity building programme, will highlight the benefits of climate-resilient crops, and increase the likelihood of farmer participation and support.
Communities are incapable of managing and maintaining assets and structures built through the project. | Low | Capacity building programmes will include training on maintenance and management techniques. This is particularly relevant to the restored grasslands in Ward 8 of Vulindlela (Output 2.2), where management of grazing livestock will be an important aspect of grassland restoration. A rangeland management plan will be developed with the community which will include an intensive community engagement process to ensure community ownership.
Low capacity, awareness and acceptance of the need to tackle the impacts of climate change among key stakeholders limit the support for the project and limit likelihood of project outputs being mainstreamed into plans and budgets. | Low | The project includes a capacity building programme for community members, councillors, traditional authorities and district and local municipal officials on the importance of mainstreaming adaptation responses into planning, budgeting and policy development processes. This capacity building programme, which will be implemented through Component 4, will build on the awareness generated and the support already raised amongst municipal and district officials, who have been involved in the design of the project. Already there is a level of awareness amongst communities that there are changes in the climate which are causing problems for the communities; but there is often lack of capacity and knowledge on how to address these challenges, which is what the URP is doing.
Poor coordination with other climate change projects in the District and Province limits the potential to learn from and build on the experiences of related projects. | Low | The Project Coordinating Committee (PCC) has been established which includes representatives from various government departments and all the local municipalities. The PCC is responsible for providing relevant contextual information to project implementers; providing guidance on project implementation; ensuring alignment between URP and other projects in province, uMDM area and project areas; and sustaining the outcomes beyond the project and replication into other areas. Furthermore, the EE has joined the Central KwaZulu-Natal Climate Change Compact which brings together municipalities from the central KwaZulu-Natal region with the aim to coordinate efforts, avoid overlap between similar endeavours and ensure that projects deliver complementary and mutually reinforcing outcomes.
Poor coordination and information sharing structures/agreements between project partners and other meteorological and agricultural institutions limits the effectiveness off the flood/storm, fire and agro-meteorological EWSs. | Low | Efforts are being made to engage the relevant partners who have access to data that will benefit the URP. In March 2016 a workshop was held bringing together all the relevant players to discuss the issue of data and find possible synergies and areas for collaboration. Further direct engagements have taken place with partners as a result of that workshop. Developing and strengthening these partnerships is an on-going process.
Limited capacity of project partners to coordinate and deliver project outputs. | Low | The project partners that have been contracted in the first year are highly capacitated and well suited to coordinating and delivering on their programme of work. The University of KwaZulu-Natal, who are contracted to lead Component 3 and 1.3 of the project, are experts in climate-smart agriculture and in engaging and supporting small scale farmers in rural areas. The additional project partners that will be brought onboard for the URP will all have experience in coordinating, implementing and delivering outputs in their relevant spheres of expertise, which will need to be demonstrated by the successful implementation of previous projects. The EE and sub-EE's Supply Chain Management processes are quite rigorous in ensuring that only service providers with the required levels of expertise are appointed to provide services. These have been tested by the due diligence review that was conducted by the NIE prior to signing the contracts for the URP. Additionally, the NIE will play an oversight role, providing further expertise if required
Staff turnover within the UMDM and Local Municipalities, project partners and within the PMU may hamper progress. | Low | Efforts have been made to establish relationships with the institutions involved in the URP, which go beyond the individuals involved, although it is acknowledged that relationships with individuals are also very important. A lot of effort has gone into developing systems for the management of the URP that will ensure that if individuals leave the various institutions, they do not take all the URP knowledge with them and the project is able to continue. During Year 1 the Project Manager took maternity leave for 3.5 months. As these processes had already been developed, and the project implementation plan was developed with this in mind, with additional support from the NIE, the Project Management Unit at the EE was able to function and deliver.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Changes to National Treasury regulations which require all organisations doing business with any government entity to be registered on the Central Suppliers Database, may lead to delays in implementation if current and potential project partners are not already registered. | Medium | National Treasury Department has indicated that municipalities are no longer required to register on the Central Suppliers Database. The EE will continue to engage its Finance Department regarding registration in case Treasury requires that municipalities do register on the CSD at some point. The EE will inform its stakeholders through the various forums that any potential partners to the URP must be registered on the CSD in order be legible to be contracted by either the NIE or the EE.
In August 2016 local government elections took place which resulted in new councils for all the municipalities in the uMDM (EE). There is a risk that the new councils may try to influence the manner in which the URP is managed or implemented. | Low | Engagements with the new councils have begun to explain the need for the URP and its objectives. The existing reporting structures will be used to keep councils informed of the latest developments and reasons for decisions being taken in the URP. It will be important that the management of the URP remains where it is located within Community Services Department as this Department brings together many of the key units required to implement the URP and take on the policy recommendations towards the end of the project that will ensure sustainability and replication.
There are delays in implementation due to potential project partners not meeting the standards and requirements for project and financial management set by the NIE and national legislation. | Low | The due diligence review conducted by the NIE found that one of the project partners did not meet the standards and requirements for project and financial management set by the NIE and national legislation. This has caused delays in the implementation of component 2.1, but contracting them as a sub-EE would have posed a greater risk to the project, based on the findings of the due diligence. The EE has taken over the implementation of this work. Service providers and partners will be appointed to conduct various aspects of component 2.1 in accordance with the new implementation plan.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
A number of mitigation measures were employed in the first year. These measures are lifted from the table above and listed below. The measures were successful in reducing the risks. As a result, the project has not encountered any significant or ‘High’ risks over the first year. • Risk: Ineffective management of funds Mitigation measure: The project has rigorous quarterly and technical reporting procedures, and these have ensured that project funds have been managed effectively to date. • Risk: Local elections interfere with project progress Mitigation measure: The initiation of Component 2.1 was delayed due to local government elections being held in August 2016. At project inception community engagement was planned in the months leading up to August, but in order to minimise the risk of political interference, a decision was taken to engage with communities early in Year 2. Additionally, engagements with the new councils (post elections) have begun. The existing reporting structures will be used to keep councils informed of the latest URP developments. • Risk: Contract negotiations delay implementation Mitigation measure: While the Component 2.2 contract was being negotiated, planning for the implementation of the work continued. In consultation with the sub-EE technical experts, local implementing partners were identified and engaged, so that upon signature, implementation can commence immediately. • Risk: Top-down approach neglects to cater to the needs to vulnerable communities Mitigation measure: The project has adopted a bottom-up approach at all times, that includes the project beneficiaries in the planning, executing and monitoring of project activities. In the agriculture components of the project the sub-EE is in constant contact with farmers in the Swayimane target area, and a considerable amount of effort has gone into building their capacity so they can take ownership of the interventions, and the positive results. • Risk: Women and people from vulnerable and marginalised groups are excluded Mitigation measure: The process to appoint a Gender and Social Expert, who will ensure that vulnerable and marginalised groups are given equitable opportunities to access project benefits, is currently underway. In Swayimane, over 80% of farmers involved in the project are women, and a youth group has been formed. • Risk: Poor co-ordination limits the potential to learn from related experiences Mitigation measure: The Project Coordinating Committee (PCC) has been established and meets quarterly. The PCC includes representatives from various government departments and all the local municipalities, and provides a platform to establish relationships and integrate lessons learned. • Risk: Limited partner capacity results in ineffective implementation Mitigation measure: Due diligence reviews have been undertaken where necessary, to confirm that partners have the capacity to effectively implement the project. Where required, technical specialists are being contracted to assist in initiating project activities. • Risk: Project activities do not comply with the AF’s ESP Mitigation measure: The project’s environmental and social risk management procedures include a quarterly assessment of project activities against the 15 ESP Principles, and a feedback loop is in place which results in management measures being developed, approved by the NIE Steering Committee, and implemented by sub-EEs, where required.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Component 1 |  | 1. Appoint EWS expert to facilitate uMDM review of existing systems, identify gaps and develop detailed implementation plan that links 1.1.1, 1.1.2 & 1.1.3. 2. Appoint a Component 1 Coordinator. 3. Appoint Umgeni Water to: Undertake risk and vulnerability assessments of flooding hotspots, and collect initial data required to configure models. 4. Initiate seasonal weather forecasting activities with partners and farmers in Swayimane, including the following activities: i) Convene launch workshop and undertake institutional analyses; ii) Engage small scale farmers, procure/install AWS at Swayimane High and design integrated crop-climate-GIS modelling system; and iii) Planning and stakeholder engagements on different methodologies. |  | 1. and 2. The process of appointing an early warning systems consultant to facilitate the review of existing systems in the uMDM and the two local municipalities is underway as a competitive bidding process was undertaken. The review will provide direction on the skills requirement and job description for the Component 1 coordinator who will then be appointed in Year 2. 3. A proposal was received from uMngeni Water, but the EE was unable to accept it as there were queries on the implementation plan and system to be developed. The alignment with national government direction was not clear. The review of the early warning systems will include an assessment of the proposal and recommendations for improvement which will enable the appointment of uMngeni Water. 4 i) A stakeholder workshop was held at UKZN in March 2016 which was attended by more than 55 participants from different institutions - many of them experts in agrometeorology and farmer interaction. This also allowed for an assessment of different institutions involved in the collection, generation and dissemination of data. ii) A baseline study was conducted with farmers at Swayimane to understand perceptions to climate change. An AWS was set up and installed at Swayimane High and learners were engaged. The crop-climate-GIS system has been conceptualised and being rolled out in phases. iii) South African Weather Services (SAWS) International Crops Research Institute for the Semi-Arid Tropics (ICRISAT), Climate System Analysis Group (CSAG) based at the University of Cape Town (CSAG), Agricultural Research Council's Institute for Soil, Climate and Water (ARC-ISCW) and KZN-Department of Agriculture and Rural Development (DARD) were engaged with institutional visits undertaken. | Satisfactory (S)
| Component 2 |  | 1. Appoint a Gender and Social expert 2. Develop a plan for the climate proofing of human settlements (2.1) 3. Contract Natural Resource Management (NRM) of Department of Environmental Affairs for the coordination of component 2.2 |  | The Terms of Reference for the Gender and Social Expert (GSE) were developed and approved by the NIE. The competitive bidding process to appoint the GSE is underway. The implementation plan for component 2.1 has been developed. The process to appoint a service provider who will facilitate capacity building with the communities to enable them to participate in a social vulnerability assessment and contribute to the review of interventions for climate-proofing of community facilities, is underway. Contracting of NRM is almost complete as there is now agreement on the contract contents from the legal departments and it is just awaiting signatures. The detailed implementation plan will be developed at the start of Year 2 so that implementation can begin soon thereafter. | Marginally Satisfactory (MS)
| Component 3 |  | 1. Appoint Component Team, Procure equipment and convene launch workshop. 2. Undertake community consultations and develop training programmes for small scale farmers and contribute to the launch of URP in Swayimane. 4. Identify farmer groups in Swayimane. 5. Appoint two extension officers and develop training materials and handbooks. |  | 1. A Project Leader, Component Coordinator and two Field Assistants were appointed and equipment purchased for them. 2. Community consultations were routinely undertaken throughout the year and members of the PMU and other partners were often invited to participate. Training programmes for farmers were implemented and are still on-going. 3. Two farmer groups were identified in Swayimane. A youth group was formed and another youth group was also identified. 4. The recruitment of Extension Officers suffered a minor setback due to KZN-Department of Agriculture and Rural Development (DARD)'s refusal to appoint them within its ranks. Subsequently, UKZN approved the appointment of the Extension Officers within SAEES and this shall now happen in Y2. The development of their training materials is ongoing and will benefit from accessing previously developed materials by the UKZN-SAEES Project Team from other previous external projects. | Highly Satisfactory (HS)
| Component 4 |  | 1. Appoint a Learning Network Officer 2. Develop a plan for knowledge management |  | The Learning Network Officer was appointed at the EE and is performing his duties in a satisfactory manner. The selection of community beneficiaries for accredited training is slightly delayed as a result of delays in the initiation of Components 1 and 2. However, options for the development of a knowledge management strategy and knowledge management portal have been developed. In Year 2 the EE will implement these. A guideline document for community engagement was developed as well as for qualitative assessment of the URP. | Satisfactory (S)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Nomalungelo Ndlovu
| Email: | Nomalungelo.Ndlovu@umdm.gov.za
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Progess to date is rated as 'Satisfactory' from the EE's perspective. The URP has achieved many of the targets set for Year 1, noting that some of these were purposefully delayed at project inception due to anticipated challenges in the receiving environment and with envisaged sub-EEs. It was anticipated that this year would be dedicated to setting up systems, developing detailed plans and contracting the key project partners. In most cases this has been achieved. In Component 1 it was realised that additional technical support will be required to ensure that the proposals for work to be undertaken really do help the URP to achieve its objectives for early warning systems. This has meant that the early flood warning systems area of work could not commence. This delay in starting that work was a necessary step in the management of project risk. The appointment for technical support is underway. The automatic weather station was set up at Swayimane High and the web-page is under development, so the annual target for Component 1.3 was achieved. In Component 2, the sub-EE who had been identified at the project proposal stage to lead the implementation of climate proofing human settlements did not pass the NIE's due diligence. The EE has now taken responsibility for implementing this work. A detailed implementation plan was developed by the EE and implementation will begin in Year 2. Out of the Year 1 target of 50 farmers in Component 3, the URP managed to engage 127 farmers. There were some challenges experienced with reporting cycles and the flow of finances, caused especially by changes in the national regulatory framework - Central Supplier Database. Whilst this delayed certain implementation, important positive lessons were learnt with regards to contingency planning for when there is a delay in accessing project funds. The appointment of Extension Officers suffered a setback when the Provincial Agriculture Department (DARD) was unwilling to appoint them due to their HR policies. However, the EE and NIE allowed for a deviation such that they would be appointed within UKZN-SAEES. This was subsequently approved by UKZN's own Evaluations Committee with two new posts being created. Guidelines for community engagement were developed which will be used by all project partners and will ensure that the URP communities are engaged with in a meaningful manner. The process of developing a knowledge management strategy and portal are well underway.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Component 1 |  | 1. Appoint EWS expert to facilitate uMDM review of existing systems, identify gaps and develop detailed implementation plan that links 1.1.1, 1.1.2 & 1.1.3. 2. Appoint a Component 1 Coordinator. 3. Appoint Umgeni Water to: Undertake risk and vulnerability assessments of flooding hotspots, and collect initial data required to configure models. 4. Initiate seasonal weather forecasting activities with partners and farmers in Swayimane, including the following activities: i) Convene launch workshop and undertake institutional analyses; ii) Engage small scale farmers, procure/install AWS at Swayimane High and design integrated crop-climate-GIS modelling system; and iii) Planning and stakeholder engagements on different methodologies. |  | At the start of project implementation it was expected that during Year 1 a service provider would be appointed to start generating data and enhancing the systems that are required for the Early Warning System to function effectively, and that a coordinator would be appointed to guide the implementation of this programme of work. There have been delays in both these processes. However, these delays are because experts have been contracted to review the planned activities for Component 1 to ensure that they align with national policy processes, and that they can be upscaled to other regions. The findings of the expert assessments will strengthen the project outcomes (without changing the overall objectives). Regarding the agro-meteorological work of Component 1.3, progress has been on target. The Automatic Weather Station has been installed and is operating and generating data, and numerous workshops have been held with school learners and farmers. It is expected that crop models and seasonal forecasting tools will be developed in Year 2. | Marginally Satisfactory (MS)
| Component 2 |  | 1. Appoint a Gender and Social expert 2. Develop a plan for the climate proofing of human settlements (2.1) 3. Contract Natural Resource Management (NRM) of Department of Environmental Affairs for the coordination of component 2.2 |  | Whilst terms of reference for the Gender and Social expert and for the Vulnerability study to inform the human settlements work have been developed, service providers have yet to be contracted. However, detailed plans have been developed for the roll out of the Component 2.1 programme of work, and it is expected that progress against the deliverables will be made in Year 2. For Component 2.2 (Ecological Infrastructure), the contract with the relevant national department has been finalised, but has yet to be signed. However, detailed discussion having been taking place in parallel to the contracting process, and a field visit with all project partners to develop the implementation plan will happen in the first quarter of Year 2. | Marginally Satisfactory (MS)
| Component 3 |  | 1. Appoint Component Team, Procure equipment and convene launch workshop. 2. Undertake community consultations and develop training programmes for small scale farmers and contribute to the launch of URP in Swayimane. 4. Identify farmer groups in Swayimane. 5. Appoint two extension officers and develop training materials and handbooks. |  | Progress on the agricultural component of the project has been very pleasing and the Year 1 targets have been exceeded. At the start of the project the aim was for 50 farmers (40 women) to be benefitting from project activities in the first year. At the end of Year 1, 127 farmers are benefitting (106 women) from support from the project in the Swayimane area. This has resulted in increased yields from the areas they are farming. In Year 2, this support will extend to the remaining two target areas and the project team and project Extension Officers will work with KZN-Department of Agriculture and Rural Development (DARD) to train the DARD Extension Officers on the benefits of the approaches used in the project. | Highly Satisfactory (HS)
| Component 4 |  | 1. Appoint a Learning Network Officer 2. Develop a plan for knowledge management |  | At the start of Year 1 it was expected that some of the beneficiaries of Component 1 and 2 would have been identified, and that a service provider would be contracted to develop / update the accredited training material. Delays in Components 1 and 2 have meant delays in Component 4. However, the Learning Network Officer has been appointed and a number of guideline documents have been developed, including those covering community engagement, and knowledge management and sharing of lessons learned. | Marginally Satisfactory (MS)
[5 empty] | Overall Rating | Marginally Satisfactory (MS)
Implementing Agency, on aspects of the project the NIE is responsible for delivering | Governance Mechanism: - mechanism established - mechanism operational (quarterly milestone) |  | By the end of Year 1, it is expected that the governance mechanism of the uMngeni Resilience Project will be established and fully functional i.e. the Project Management Unit will be operational, and will report into the Project Coordinating Committee and the NIE Secretariat and Steering Committee. |  | The governance mechanism of the uMngeni Resilience Project has been established and is functional. The Project Management Unit (PMU) is operational and includes three full-time staff members: a Project Manager, a Project Finance Officer and a Learning Network Officer. The PMU reports into the Project Coordinating Committee (PCC) which is made up of a wide range of project partners, local and national government as well as non-government stakeholders. The PCC has met four times and has an overall role of guiding project actions, align these with related initiatives and activities being implemented in the District and Nationally, and sustaining the outcomes of the project. Decisions made at the PCC meetings are ultimately approved by the NIE Steering Committee, which is updated on project progress by the Project Manager at its quarterly meetings. | Satisfactory (S)
| Environmental and Social Safeguard and Gender Screening: - tools and procedures for screening developed - screening process operational (quarterly milestone) |  | By the end of Year 1, it is expected that the tools and procedures for screening all project activities against environmental and social safeguards and gender mainstreaming principles will be developed. It is expected that these tools and procedures will be applied quarterly to project activities, to ensure that any unintended negative impacts are avoided, or mitigated if necessary. |  | The NIE has developed a "Risk Dashboard" which is used to screen project activities against the 15 Principles of the AF's ESP. One of these Principles relates to Gender mainstreaming. This Risk Dashboard is completed quarterly by the EE and Sub-EEs that are implementing project actions. The NIE reviews these activities, which are presented to the NIE Steering Committee. Recommendations are then sent back to the EE, who share them with the relevant Sub-EEs. The NIE has applied for a Technical Assistance Grant from the AF to assist in the development of a handbook and procedures to accompany the Dashboard. Once completed, this tool will be used to facilitate training of the EE and Sub-EEs on the ESP Principles. The Grant was approved, but a service provider is yet to be appointed. This appointment, and the related activities, is scheduled for early in 2017. | Satisfactory (S)
| Technical and Financial Risk Management: - reporting and forecasting template developed - funds disbursed based on approved reports (quarterly milestone) |  | By the end of Year 1, it is expected that the technical and financial reporting and forecasting templates will be developed, and that the EE and relevant Sub-EEs will be reporting to the NIE quarterly (Sub-EE reporting is via the EE). The reporting will allow the management of technical and financial risks, in that only activities and expenses in line with the project's Annual Plans, and the project's Disbursement and Expenditure Guidelines, will be approved. |  | The NIE has developed technical and financial reporting templates. These templates are completed by the EE and relevant Sub-EEs quarterly and submitted to the NIE (Sub-EE report is submitted via the EE), who review the technical report and report back on activities of the previous quarter and forecast of activities for the coming two quarters, and review the financial report supporting the expenditure of the previous quarter. This review and approval process has allowed the NIE to have oversight of the project and make sure funding is directed towards project activities that are in line with the approved project objectives. | Satisfactory (S)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dr. Mandy Barnett
| Email: | m.barnett@sanbi.org.za
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | N/A
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The overall project progress over the first year of implementation is rated as 'Marginally Satisfactory'. We note the differences in the EE's and NIE's rating of project progress i.e. in Components 1 and 4 and for the overall rating. This difference is primarily due to the adaptive management outlook and approach of the EE - where challenges have arisen, corrective actions have been undertaken to the extent that is possible, and the EE has been satisfied with the outcome of these actions and the progress of the project. While the NIE is fully supportive of this approach, the NIE feels that progress has been slightly delayed relative to what was anticipated at the start of project implementation, hence Marginally Satisfactory rating. Local, project level and national governance processes are well established, the Project Management Unit is fully staffed and functioning effectively, reporting and expenditure approval processes are in place, and monitoring & evaluation of project activities and management of environmental and social risk is occurring efficiently for the components that are active in the target areas. At the inception of the project it was anticipated that Year 1 would be dedicated to setting up systems, developing detailed plans and contracting the implementing partners (Sub-EEs). For Components 1 (Early Warning System), 2.1 (Built Environment) and 2.2 (Ecological Infrastructure) Sub-EEs have yet to be contracted. However, technical support is being procured to assist with the technical studies required before the Sub-EEs for Components 1 and 2.1 can be contracted, and processes are well underway to contract with the Sub-EE and implementing partners for 2.2. For Component 4 (Capacity Building and Knowledge Management), an implementing partner was contracted in the short-term to develop Guidelines for Community Engagement as well as a Knowledge Management Strategy. Once the on-the-ground beneficiaries are being engaged by all the components, Component 4 capacity building activities will commence. The progress of Component 3 (Climate Smart Agriculture) is very pleasing. The Sub-EE (the University of KwaZulu-Natal) has used the uMngeni Resilience Project to build on earlier engagements with farmers in the Swayimane target area. This continued interaction and focus on climate-smart techniques and crops has seen the targets for Year 1 exceeded in this component, with 127 farmers (over 80% of whom are female) benefiting from project interventions (the target was 50 farmers). Increased yields have been measured, and farmers have reported that they have been able to use the additional income from the sale of agricultural produce to undertake activities that build climate resilience, such as strengthening their houses to withstand storms of increasing intensity. Towards the end of Year 1 the expansion of activities to the two other target areas was being planned, as well as the upscaling of activities in the Swayimane target area. The main challenges that the project has experienced in Year 1 are: 1. Delays in the contracting of implementing partners in Components 1 and 2 of the project. However, as described above, this is being managed through the support of technical experts, and it expected that in year 2 all Sub-EEs and relevant implementing partners will be contracted. 2. Challenges associated with the disbursement of funds to the EE. This was related to the contracting of the Project Finance Officer, and to the registration of the Municipality on a national database (which is required for entities to receive funding from Government agencies). However, both challenges have now been resolved. As a result of the measures to manage the challenges noted above, and because the project governance, reporting and disbursement, screening and risk management structures and processes are all functioning well and will be further streamlined, it is expected that there will be an increasing trend in the achievement of project outcomes in Year 2.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: Reduce climate vulnerability and increase the resilience and adaptive capacity of vulnerable and small scale farmers in production landscapes in the uMgungundlovu District that are threatened by climate variability and change, through an integrated adaptation approach | Number of people with reduced risk to climate change-driven floods, storms, fires and drought, as a result of project interventions | 0 women and 0 men | 106 women and 21 men | 13,414 women and 12,226 men
Outcome 1: Number of early warning systems benefiting vulnerable communities and small scale farmers. | Number of early warning systems benefiting vulnerable communities and small scale farmers. | 0 early warning systems in place | 0 early warning systems in place | 1 early warnings system: agro-meteorological
Output 1.1: Hydro-climatological and fire information and warnings supplied timeously in an appropriate format for direct use by communities and relevant disaster response officials | 1. Flood/storms: Area of the UMDM covered by improved monitoring network, to allow early detection of flooding threats to vulnerable communities. | 0% of the uMDM is covered by an improved monitoring network | 0% of the uMDM is covered by an improved monitoring network | High-level/course configuration: 100% of the UMDM; detailed configuration: 75 km of the prioritised rivers in UMDM
| 2. Wildland fire: Number of PPPs in place between the relevant FPAs, the Ingonyama Trust Board and the Local Authorities. | 0 PPPs with FPAs, ITB and local authorities | 0 PPPs with FPAs, ITB and local authorities | 1 PPP between the relevant FPAs, the Ingonyama Trust Board and the Local Authorities
Output 1.2: Early warning systems empower municipal officials and local communities and small scale farmers to respond timeously to seasonal forecasts and potential disaster | 1. Number of ward-based disaster management systems piloted in project target areas. | 0 ward-based disaster management systems have been piloted in the project target areas | 0 ward-based disaster management systems have been piloted in the project target areas | 3 ward-based disaster management systems; one each for the low-lying high-density site, Ward 8 of Vulindlela and Ward 5 of Nhlazuka
| 2. Number of community members benefiting from ward-based disaster management systems. | 0 community members (0 women and 0 men) in the low-lying high-density site; ward 8 of Vulindlela and ward 5 of Nhlazuka | 0 community members (0 women and 0 men) in the low-lying high-density site; ward 8 of Vulindlela and ward 5 of Nhlazuka | At least: 500 women in the low-lying high-density site; 7,962 women in Ward 8 of Vulindlela; 4,852 women in Ward 5 of Nhlazuka; 500 men in the low-lying high-density site; 7,327 men in Ward 8 of Vulindlela; 4,014 men in Ward 5 of Nhlazuka.
| 3. Number of community-based fire risk management programmes pilot in project target areas. | 0 community-based fire risk management programmes. | 0 community-based fire risk management programmes. | 1 community-based fire rsik management programme in Nhlazuka
| 4. Number of trainees directly benefiting community-based fire risk management programme. | 0 women and 0 men in Ward 5 of Nhlazuka. | 0 women and 0 men in Ward 5 of Nhlazuka. | 30 women and 30 men in Ward 5 of Nhlazuka
Output 1.3: Access to seasonal weather forecasting improves the resilience of small scale farmers to climate variability. | Number of small scale farmers in Ward 8 of Swayimane benefitting from improved agro-meteorological forecasts at the farm level. | 0 women and 0 men in Ward 8 of Swayimane. | 106 women and 21 men in Ward 8 of Swayimane currently benefitting. An AWS was installed at Swayimane, a stakeholder workshop was conducted in March 2016, RTMC software for the AIM system was purchased, and a youth group was formed at Swayimane. | 300 women and 100 men in Ward 8 of Swayimane
Outcome 2: Built and ecological infrastructure enhances resilience and reduces vulnerability to risks associated with climate variability and change. | 1. Number of rural physical assets strengthened or constructed to withstand conditions resulting from climate change-driven floods, storms, fires and drought. | 0 houses; 0km of stormwater drainage channels; and 0pedestrian bridge at project start | 0 houses; 0 km of stormwater drainage channels; and 0 pedestrian bridge at project start | 300 houses; 10 km of stormwater drainage channels; and 5 pedestrian bridges.
| 2. Area and type of natural resource assets maintained and improved to withstand conditions resulting from climate change-driven floods, storms, fires and drought. | 0ha of restored grassland; 0km of rehabilitated riparian zones; 0ha of alien vegetation removed to prevent bush encroachment; and 0 km of firebreaks at project start | 0 ha of restored grassland; 0 km of rehabilitated riparian zones; 0 ha of alien vegetation removed to prevent bush encroachment; and 0 km of firebreaks | 200 ha of restored grassland; 12 km of rehabilitated riparian zones; 100 ha of alien vegetation removed to prevent bush encroachment; and 100 km of firebreaks.
| 3. Number of policy revisions recommendations developed to include adaptation considerations as a result of knowledge gained through the project. | 0 policy revision recommendations | 0 policy revision recommendations | 3. At least 3 policy revision recommendations, for the inclusion of adaptation considerations into each of: • rural settlement planning processes/SPLUMA; • South Africa’s Extended Public Works Programme; and • peri-urban and urban settlement design and upgrade processes/SPLUMA
Output 2.1: Critical settlement infrastructure, community facilities and homes strengthened and stabilised to buffer vulnerable communities against anticipated climate-induced stresses in rural communities. | Number rural structures with strengthened climate resilience in the target area, in direct response to participatory vulnerability mapping of the project. | 0 houses; 0 km of stormwater drainage channels; and 0 pedestrian bridges. | 0 houses; 0 km of stormwater drainage channels; and 0 pedestrian bridges. | 300 houses; 10 km of stormwater drainage channels; and 5 pedestrian bridges.
Output 2.2: Restored and protected critical ecosystems that maintain ecosystem resilience, provide buffering from climate change impacts and provide freshwater to local communities downstream. | Area of target ecosystems within target areas with improved climate resilience | 0 ha of restored grassland; 0 km of rehabilitated riparian zones; 0 ha of alien vegetation removed to prevent bush encroachment; and 0 km of firebreaks at project start | 0 ha of restored grassland; 0 km of rehabilitated riparian zones; 0 ha of alien vegetation removed to prevent bush encroachment; and 0 km of firebreaks | 200 ha of restored grassland; 12 km of rehabilitated riparian zones; 100 ha of alien vegetation removed to prevent bush encroachment; and 100 km of firebreaks.
Output 2.3: Officials empowered to mainstream climate change adaptation into relevant planning and infrastructure development plans and frameworks. | 1. Number of tools for mainstreaming climate change adaptation considerations/ standards into informal settlement upgrade planning in the UMDM. | 0 climate change adaptation mainstreaming tools | 0 climate change adaptation mainstreaming tools | At least 1 climate change mainstreaming tool, for the UMDM
| 2. Number of training sessions to build the capacity of relevant officials to mainstream climate change adaptation in policies and plans. | 0 training sessions | 0 training sessions | 15 output driven training and workshops with relevant officials
Outcome 3: Productive landscape resilience increased through the installation of farm-level infrastructure and the integration of climate change responses into agricultural practices. | 1. Increase in yield from climate-resilient farms/community homegardens as a result of project interventions. | Average of 0.3-1 t/ha for maize and 0.1-0.5 t/ha for dry beans from current farms in target areas. | Maize = 1.2 t/ha, Beans = 0.5 t/ha, Soybean = 0.6 t/ha | Average of at least 3-5 t/ha maize and 0.75-1.5 t/ha for dry beans from climate-resilient farms/community homegardens in target areas
| 2. Increase in access to markets for farmers in Ward 8 of Swayimane as a result of project interventions. | 0% increase in access | 0% increase in access | 50-100 % increase in access to markets for farmers in Ward 8 of Swayimane.
Output 3.1: Investments in climate-resilient agricultural practices and physical infrastructure at the farm level mitigate impacts of climate variability and change for small scale farmers. | 1. Number of farms/community homegardens in target areas on which climate-resilient project interventions are being implemented. | 0 farms/community gardens in target areas. | 127 farms (households) / 2 community gardens | Swayimane Ward 8: 200 farms; Vulindlela Ward 8: 200 farms; and Nhlazuka Ward 5: 5 community homegardens.
| 2. Area of farms/community homegardens in target areas in which climate-resilient project interventions are being implemented | 0 ha | 123.38 ha | Swayimane Ward 8: 2,000 ha of farm land; Vulindlela Ward 8: of 1,000 ha farm land; and Nhlazuka Ward 5: 2.5 ha of community homegardens .
| 3. Number of small scale farmers in target areas benefitting from climate-resilient agricultural practices introduced through the project. | Swayimane Ward 8: 0 women and 0 men farmers; Vulindlela Ward 8: 0 women and 0 men farmers. | Swayimane Ward 8: 106 women and 21 men | Swayimane Ward 8: 300 women and 100 men farmers; Vulindlela Ward 8: 300 women and 100 men farmers; and Nhlazuka Ward 5: 100 women and 50 men community home gardeners.
Output 3.2: The KZN Provincial Department of Agriculture and Environmental Affairs mainstreams adaptation practices into its extension | 1. Number of trained1 extension officers placed in project target areas. | 0 trained extension officers in target areas. | 0 trained extension officers in target areas. | 2 trained extension officers (1 in each of Swayimane Ward 8 and Vulindlela Ward 8).
| 2. Number of trained extension officers in UMDM. | 0 Extension officers trained in UMDM | 0 Extension officers trained in UMDM | 100 % of DAEA extension officers in UMDM trained17
Outcome 4: Adaptation practices integrated in relevant climate variability and change policies at the municipal level, in targeted sectors and beyond | 1. Percentage of community members in target areas with increased awareness, as a result of the project, of climate change adaptation and options to enhance climate resilience. | 0% at project start | 0% of community members | 80 % (for both women and men) of beneficiaries with increased knowledge on climate change adaptation and options to enhance climate resilience
| 2. Number of development strategies that incorporate adaptation considerations as a result of knowledge generated through the project. | 0 at project start | 0 development strategies | 3 development strategy revision recommendations: agriculture; human settlements; and disaster response
Output 4.1. Community champions, officials and authorities are empowered to participate in the project's activities. | 1. Number of project beneficiaries trained on climate change adaptation and options to enhance climate resilience. | 0 at project start | community champions: 0 women and 0 men councillors: 0; and officials: 0 | 48 NQF certificates obtained
| 2. Percentage beneficiaries with improved knowledge of climate change adaptation and options to enhance climate resilience. | 0% at project start | 0% of beneficiaries | 80 % (for both women and men) of beneficiaries with increased knowledge on climate change adaptation and options to enhance climate resilience
Output 4.2: Project outputs and experiences are captured and support integrated learning. | Number of platforms to share project outputs and experiences. | 0 platforms at project start | 0 reflection workshops; 0 learning exchanges; and 0 conferences | 8 reflection workshops; 3 learning exchanges; and 3 conferences
Output 4.3: Policy recommendations support sustaining, scaling up and replicating project successes. | Number of national policy conferences and scaling up workshops based on project lessons learned. | 0 at project start | 0 national policy conferences; and 0 scaling up workshops | 3 national policy conferences; and 3 scaling up workshops

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1. Communication and consultation with stakeholders is very important. This project has been characterised by lengthy in-depth engagement with stakeholders. While these types of processes do take time, they are critical. The EE has developed a detailed stakeholder map which has identified all stakeholders who need to be engaged with. The use of existing structures and forums has ensured that stakeholders receive regular updates on the project. However, it must be noted that there are many forums both within and outside the EE and that the Project Manager is not always able to get to them all. There are also stakeholders that don’t participate in any forums that need to be engaged with separately. The Project Coordinating Committee has helped bring some of these stakeholders together. However, where there are no direct benefits for the PCC members, it is difficult to maintain their commitment and participation in the PCC. The current format of the PCC will be reviewed during Year 2. 2. The process of contracting is detailed and lengthy. It has taken a substantial amount of time to finalise the key project contracts. This process has involved several drafts, with legal teams from all sides providing comments and suggesting changes in wording before all parties were satisfied and the final documents were approved. 3. The due diligence review is a valuable tool and it should be conducted with all key partners and sub-EEs. Through the due diligence we were able to identify that there were concerns with the financial management structures at one of the organisations that had been involved in the development of the project and were potential project partners. As a result of the due diligence, a decision was taken not to continue with that organisation. This has meant that a new plan for implementation of that component is now the responsibility of the EE. The lesson learned is that the due diligence is important and should take place much earlier in the process - as soon as the project is approved. 4. There were delays in the transfer of funds due to changes instituted by the National Treasury that required the EE and sub-EE to be registered on the Central Suppliers Database (CSD). As a University, the sub-EE was able to resolve these relatively quickly, however as local government it was more complicated for the EE and a lot of time and effort was spent trying to resolve the matter. Subsequently, National Treasury has indicated that municipalities are no longer required to register on the CSD. The lesson learned is that the sub-EE must use its internal mechanisms for bridging funds as a stop gap measure where it is anticipated that there will be delays with the transfer of funds from the NIE. 5. During this period the Project Manager took maternity leave for 3.5 months. The scheduling of project activities that specifically required the Project Manager's input was revised and the NIE provided additional support to the EE during this time.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | 1. The contracting of key partners took a long time. The implementation plan has taken this into account and it will not have an impact on the achievement of the URP targets. 2. There were also delays in the appointment of the Finance Officer for the EE as finding the candidate that met the requirements for skills and experience was a challenge. During this time, the NIE provided support in reviewing the financial reports of the sub-EE. 3. The EE did not receive project funds, as the appointment of a Finance Office was one of the pre-conditions in the funding agreement between the EE and the NIE. National government made it a requirement that any entity receiving funds from a government entity was required to be registered on the Central Suppliers Database. The registration for municipalities was very challenging. This has meant that the EE was using its own funds for the project during this period. Subsequently, National Treasury has indicated that municipalities are no longer required to register on the CSD. 4. The community consultative meetings that were planned for one of the project areas (Vulindlela in Msunduzi Municipality) could not take place as the municipality wanted to conduct its own consultations before the URP could meet with the community, and also wanted this to happen after local government elections. The URP is engaging the municipality to ensure that the community meetings take place early in Year 2.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | 1. Changes have been made to Component 2.1 where the EE has taken over the planning and implementation of this component, following the due diligence review facilitated by the NIE. A community vulnerability assessment will now be conducted as the first step in implementing 2.1. 2. The target for Component 3 was 50 farmers in Year 1. However, when 127 farmers expressed an interest to participate, the decision was taken to accommodate all the farmers. This placed a strain on budgeted seed and inputs. The farmers also expressed an interest in establishing a community vegetable garden. The URP decided to agree to this as it will add to the diversification of crops and help increase the farmers' resilience. 3. The original plan was to appoint two Extension Officers (EOs) within KZN Department of Agriculture and Rural Development (DARD). However, DARD senior management indicated that their Human Resources Policy would not allow for that. The URP decided to appoint the EOs within the sub-EE and an addendum to the existing MoU between the sub-EE and KZN DARD was developed and approved by the NIE which will allow the EOs to work with DARD and for DARD officials to receive training on climate smart agriculture. These changes will not alter the URP targets but it is believed that they may lead to a more effective delivery of the targets.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | 1. The participation of female farmers and youth has been encouraged in the project. Of the three key leaders of the farmer groups, two are women. There are currently 127 farmers participating in the URP and 106 of them are women. To date, the inclusion of both women and men as well as allowing women to lead has allowed more progress to be made as women are more at home than men and thus able to participate in farming activities. The participation of female farmers and youths continues to be encouraged in the project. 2. In the recruitment of the project staff in the EE, the EE's Employment Equity Policy has been applied. The policy states that "special attention will be given to the disadvantaged, e.g. women and the disabled…in order to achieve employment equity".
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | ZAF/NIE/Water/2013/1
Implementing Entity | South African National Biodiversity Institute (SANBI)
Type of implementing entity | NIE
Country | South Africa
Region | Africa
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 25640 | 3855 | 21785 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 52% | 55% | 52% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 8% | 10% | 8% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 2: Monitoring and warning service | Geographical coverage | Regional | 1 | 2: Monitoring and warning service | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 2 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Wind | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Local | 1 | 1: Risk knowledge | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 2 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Local | 1 | 3: Dissemination and communication | Geographical coverage | Local |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 2 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 2: Partially not aware |  | 25640 | 52% | 5: Fully aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
|  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
|  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Multi-sector | 2: Physical asset (produced/improved/strenghtened) | 5: Fully improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Rangelands |  | ha rehabilitated | 1: Ineffective | Rangelands | 200 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer |  | ha rehabilitated | 1: Ineffective | Catchment area/Watershed/Aquifer | 100 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer |  | km rehabilitated | 1: Ineffective | Catchment area/Watershed/Aquifer | 12 | km rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Natural capital | Agriculture | Livelihoods | 405 | Natural capital | Agriculture | Livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 200 | Agriculture |  | 76 | 200 | Agriculture |  | 228
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Multi-sector | National | Other policy | 3 | Multi-sector | National | Other policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 3 | 3: Partially enforced (Some elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.