## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | Mars 2013 - Août 2013
| Project Title: | Adaptation to coastal erosion in vulnerable areas
| Project Summary: | “Adaptation to coastal erosion in vulnerable areas” is a 2 years (2011 / 2012) project financed with 8 619 000 USD by the Adaptation Fund through a one-step approval process. The project document was approved during the 11th meeting of the AF Board (16-17 September 2010) in Bonn and the MOU was signed in 11th November 2010. The main focus of the project is the development of adaptation capacities of communities the most vulnerable to coastal erosion and sea level rising in 3 regions of Senegal, located along the coastline. The principal promoter of the project is the Directorate of Environment, with a strong involvement of CSO (GREEN Senegal and Dynamique Femme) The main components of the project are: - Training and awareness rising - Building up of coastal protection facilities in the areas of Rufisque and Saly - Building an anti-salt dike in Joal - Strengthening of the protection and development of the littoral: beach, fish processing areas - Development, strengthening, and implementation of the regulation on coastal protection and the adaptation to climate change - Communication - Follow-up/Evaluation/Monitoring
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Centre de Suivi Ecologique (CSE) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Senegal | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Senegal | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 17th September 2010
IE-AFB Agreement Signature Date: |  | 11th November 2010 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 21st January 2011 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | October 2012
| Terminal Evaluation Date: | End of project
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: |  | Dominican Republic
| Email: |  | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Ndeye Fatou Guène | Equatoral Guinea
| Email: | mactarguen@yahoo.fr | Eritrea
| Date: | 2010-07-29 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Directorate of the Environment | Fiji
| Email: | marilinediara@yahoo.fr | Finland
| Date: | 2011-01-04 | France
| Executing Agency |  | Gambia
| Name: | GREEN Senegal | Georgia
| Email: | greensenegal@orange.sn | Germany
| Date: | 2011-01-05 | Ghana
| Executing Agency |  | Greece
| Name: | Dynamique Femme | Grenada
| Email: | dynfemme@yahoo.fr | Guatemala
| Date: | 2011-01-10 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 13 September 2013
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 1 March 2012 | 6843995
Add any comments on AF Grant Funds. (word limit=200)
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT DOLLAR
| Action 1.1 : Environmental Impact Assessment for the design of the coastal protection facilities in the area of Rufisque-Est (Thiawlene) | 0
| Action 1.2: Building up of the coastal protection facilities in the areas of Rufisque. The target areas host houses, economic and cultural infrastructure (Fish processing areas, fishing docks, cemeteries, etc.) | 464479.7412
| Action 1.3 :Cleaning-up of channels, including awareness raising and training activities (Thiawlene) | 23959.555
| Action 2.1: Carry out and validate the detailed technical feasibility studies for the design of the protection facilities of the coastal areas of Saly | 0
| Action 2.2 : Set up the protection facilities of the vulnerable areas covering hotels, people, poor villages, as well as the fishing docks | 200614.1355
| Action 2.3: Assistance in the development of the fishing dock and the fich processing area in Saly | 14052.2125
| Action 3.1: Study and achieve the anti-salt barriers in the rice-growing areas of Joal and the other agricultural crops. | 29254.5722
| Action 3.2: Protect and develop beaches and fish processing areas. | 116832.5011
| Action 3.3: Restore the cleanliness of the beaches | 23574.4204
| Action 3.4: awarness and training programme | 0
| Action 4.1: Design, fine tune, and strengthen the regulation pertaining to the management of the littoral, by taking into account the CC dimension: Environment Code, other codes and regulations | 0
Action 4.2: Dissemination of the elaborated texts
| Action 5.1: Design and implement the awareness and training programme | 20770.4039
| Action 5.2: Fine tune and share the suitable communication tools | 13550.7817
| Action 5.3: Inform, sensitize, and train people on the adaptation techniques to climate change in coastal areas | 0
| Action 5.4: Train the different target groups on the new regulations on adaptation | 47431.3648
| Action 6.1: Monitoring/ Follow up | 5498.7455
| Action 6.2: External Evaluation and audit | 0
| Action 6.3: Controle of realisation | 23353.5852
| N.I.E. | 50000
| TOTAL | 1033372.0192
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST EN DOLLAR | Est. Completion Date
| Action 1.1: Update the technical and detailed feasibility studies for the design of the protection facilities in the areas of Rufisque | -320.99 | Completed
| Action 1.2: Building up of the coastal protection facilities in the area of Rufisque. | 40399.66 | Completed. (The remainder of the budget in line 4.2 has been added to the remainder of this line to be used for complementary works around the seawall of Thiawlene (sanitation facilities))
| Action 1.3: Cleaning up of the channels and connection with the sea | 13003.58 | November 2013
| Action 2.1: Rehabilitation of the fishing dock at Saly Coulang | 0 | Completed
| Action 2.2: Building the protection facilities of the vulnerable areas in Saly | 987437.36 | January 2014
| Action 2.3: Assistance in the developpement of the fishing dock and the fish processing area | 9481.94 | November 2013
| Action 3.1: Building the anti-salt dike in Joal | 266750.16 | December 2013
| Action 3.2: Works on the fish processing area in Joal | 165224.54 | November 2013
| Action 3.3: Restore the cleanliness of the beaches | 45548.71 | November 2013
| Action 3.4: awarness and training programme | 10260.84 | November 2013
| Action 4.1: Design, fine tune and strenghten the regulation pertaining to the management of the littoral (Littoral law and environment Code) | -508.5 | Completed
| Action 4.2: Dissemination of the elaborated texts | 124045.23 | Despite all efforts devlopped towards national authorities, there is no guarantee that the texts will be voted before januaray 2013. Thus, the remainder of the budget in this line 4.2 has been added to the remainder of line1.2 to be used for complementary works around the seawall of Thiawlene (sanitation facilities)
| Action 5.1: Information and training workshops on climate change | 58531.37 | December 2013
| Action 5.2: Fine tune and share the suitable communication tools | -1081.65 | Completed
| Action 5.3: Inform, sensitize, and train people on the adaptation techniques to climate change in coastal areas | 3.26 | Completed
| Action 5.4: Train the different target groups on the new regulations on adaptation | 1383.26 | Completed
| Action 6.1: Monitoring/ Follow up | -7.15 | The resources for this activity are over. USD 6211 have been taken from line 5.1 to allow monitoring activties for the remaining time.
| Action 6.2: External Evaluation and audit | 43778.15 | End of project
| Action 6.3: Controle of realisation | 10958.62 | End of project
| Programme document formulation | 0 | Completed
| Translation into English | 0 | Completed
| N.I.E. | 0 | Completed
| TOTAL | 1774888.39
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  | 4
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date (USD) | Remaining Balance (USD)
Intellectual services |  | 6220.7108 | Sept. 19, 2012 | 6220.7108 | 0
Intellectual services |  | 6220.7108 | Sept. 19, 2012 | 6220.7108 | 0
Intellectual services |  | 4147.1405 | Oct. 8, 2012 | 4147.1405 | 0
Intellectual services |  | 16588.5622 | Sept. 19, 2012 | 16588.5622 | 0
Intellectual services |  | 9331.0662 | Dec. 19, 2012 | 9331.0662 | 0
Intellectual services |  | 10316.0121 | Jan. 5, 2012 | 10316.0121 | 0
Intellectual services |  | 46655.3311 | Dec. 1, 2010 | 46655.3311 | 0
Intellectual services |  | 46655.3311 | Dec. 1, 2010 | 46655.3311 | 0
Intellectual services |  | 15966.4911 | March 1, 2011 | 15966.4911 | 0
Intellectual services |  | 100041.4714 | Apr 18, 2011 | 90475.0549 | 0
Intellectual services |  | 29859.4119 | Jan 21, 2011 | 29859.4119 | 0
Intellectual services |  | 32347.6963 | Jan 21, 2011 | 32347.6963 | 0
Intellectual services |  | 14929.706 | Jan 21, 2011 | 14929.706 | 0
Intellectual services |  | 24882.8433 | Dec. 1, 2010 | 24882.8433 | 0
Service delegation contract (Saly) |  | 92000 | Sept. 1, 2011 | 70879.7329 | 21120.2671
Lease work Saly |  | 2073570.2733 | Sept. 1, 2011 | 1029107.7137 | 1044462.5596
Works Saly |  | 1872120.9182 | Nov. 28, 2012 | 964878.8745 | 907242.0437
Intellectual services |  | 59946.9166 | June 20, 2012 | 29973.4583 | 0
Control of works Saly |  | 61170.3231 | March 14, 2013 | 34255.3809 | 26914.9421
Works (Joal) |  | 456848.6003 | Nov. 21, 2011 | 286759.1341 | 170089.4663
Intellectual services |  | 134429.7267 | Sept. 1, 2011 | 124144.7352 | 10284.9915
Intellectual services |  | 59946.9166 | June 20, 2012 | 29973.4583 | 0
Intellectual services |  | 22809.273 | Dec. 20, 2011 | 22809.273 | 0
Intellectual services |  | 16588.5622 | Nov. 10, 2011 | 16588.5622 | 0
Intellectual services |  | 22809.273 | Jan. 17, 2012 | 22809.273 | 0
Service agreement |  | 41471.4055 | Dec. 21, 2011 | 41471.4055 | 0
Service agreement (amendment to the contract) |  | 6220.7108 | Nov. 28, 2012 | 4147.1405 | 2073.5703
Service delegation contract (Thiawlene/Rufisque) |  | 2378385.1035 | Jan. 2012 | 2378385.1035 | 0
Service agreement |  | 28627.7112 | Jan. 18, 2012 | 28627.71 | 0.0011931
Intellectual services |  | 22021.3163 | March 29, 2012 | 22021.3163 | 0
Works Joal |  | 207340.6275 | Feb. 7, 2012 | 185764.5337 | 21576.0938
Works Joal (amendment to the contract, for painting the fishing dock's hangar) |  | 25116.5346 | Jan. 14, 2013 | 8790.7871 | 16325.7475
Works_Joal |  | 493749.3261 | Aug. 24, 2012 | 372580.4213 | 121168.9047
Control of works at the Khelcom fish processing area (Joal) |  | 11451.0845 | Feb. 13, 2013 | 9733.4218 | 1717.6627
Construction of a fith deck |  | 10030.7096 | Aug. 2, 2013 | 10030.71 | 0
Making tee-shirt |  | 2799.3199 | May 28, 2013 | 2799.3199 | 0
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (CFA) | Selection Justification for the Winner
Agreement to delegate implementation for the coastal protection works in Saly, 25 March 2011 |  | 0.04 | 92000 | Best answer, from both the technical and financial point of view (quality of references, skills of proposed experts, experience in the field of coastal works)
0.06
0.05
Financial offer depends on total cost of the works
Preliminary design (coastal protection in Saly), 03 August 2011 |  | 22809.273 | 22809.27 | Best answer, from both the technical and financial point of view
25919.6284
Did not provide a financial bid
Construction works for the anti-salt-dike in Joal / 28 September 2011 |  | 524121.2147 |  | Good experience in hydro-agricultural development activities L'entreprise at national level; a detailed organization of site personnel shwoing the division of responsibilities, which facilitates accountability.
|  | 457053.8838 | 457053.88
654042.8814
Control of realization, 13 October 2011 |  | 41471.4055 | 41471.41 | The selection method is based on the pre-defined budget, set at 41471 USD). The firm selected (28 Core) has proposed a relevant and consistent methodology.
Detail design studies and elaboration of the tender dossier (coastal protection in Saly), 2 November 2011 |  | 20735.7027 |  | Best answer, from both the technical and financial point of view
19698.9176
|  | 16588.5622 | 16588.56
Environnemental Impact Assessment coastal protection in Saly), 19 December 2011 |  | 22809.273 | 22809.27 | Best answer, from both the technical and financial point of view
Did not provide a financial bid
27993.1987
Control of works for the anti-salt dike in Joal, 26 December 2011 |  | Did not provide a financial bid
Did not provide a financial bid
|  | 28627.7112 | 28627.71 | Most complete bid, and best technical and financial bids
Agreement to delegate implementation for the coastal protection works in Thiawlene (Rufisque), January 2012 |  | 2378385.1035 | 2378385.1 | The building of the protection dike of Thiawlene (Rufisque-Est) will be carried out in synergy with two other projects relating to the same sector and sharing the same aim, namely the initiative of the West African Economic and Monetary Union (WAEMU) and the INTAC project. The firm (public works execution agency) was already selected as project owner agent for the whole programme in this area.
Intellectual services, 9 May 2012 |  | 82942.8109 |  | Best answer, from both the technical and financial point of view
The technical bid submited by the firm X did not reach the required minimum score for further evaluation of the financial bid. Then, the financial bid was not opened
|  | 59946.9166 | 59946.92
Protection works for the fish unloading dock in Joal-Fadiouth, 29 November 2011 |  | 207340.6275 | 207340.63 | The firm gave a good description of its working methodology, with consistency in the description of its organization and work planning. In addition, LSI meets the essentiel criteria for qualifications.
151011.0646
Control of the protection works for the fish unloading dock in Joal-Fadiouth, 7 February 2012 |  | 29055.9035 |  | The firm has a good experience of dock and road works. In addition, this firm offered the lowest financial bid
|  | 22021.3163 | 22021.32
22265.9976
Works (rehabilitation of the fish processing area at Khelcom (Joal), 29 May 2012 |  | 1320621.54 |  | Good technical bid and good planning of works. The profile of the staff and the logistic caracetristics match very well the criterai defined in the tender dossier
645384.16
|  | 493749.33 | 493749.33
500429.68
Construction works for the coastal protection in Saly, 1st August 2012 |  | 1872120.92 | 1872120.92 | Best answer, from both the technical and financial point of view. Lower bid
1956682.53
7011932.11
3576384.11
3385389.51
3519966.96
Control of the works for the developement of the fish processing area, 1 October 2012 |  | 12527.68 |  | The firm has a good experience of dock and road works. In addition, this firm offered the lowest financial bid
|  | 11451.08 | 11451.08
13946.83
Diagnostic of the accounting and financial organization of the executing and implementing entities,13 August 2012 |  | 16588.56 | 16588.56 | Cabinet accredited by the association of chartered accountants, good work approach and lower bid
17521.67
17729.03
26956.41
Realization of the fith regulating structure and of the fifth deck for the anti-salt dike in Joal, 30 May 2013 |  | 17749.7615
11634.8028
|  | 10030.7096 | 10030.7096 | Best answer, from both the technical and financial point of view. Lower bid
Control of coastal protection works in saly, 2 February 2013 |  | 43544.9757
|  | 51839.2568 | 51839.2568 | Most complete offer and lower bid
Score below 70 points; the tender has not been opened
Note on H20: Aissata B SALL The contract was terminated and the reaminder was used for communication activities

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Efficiency of technical measures adopted to fight coastal erosion | Low | Feasibility studies were realized prior to each contract, clear technical specifications were given in the tender and a stringent control is performed during the realization, both from executing agencies and from the implementing entity.
Management of the project heavily dependent on subcontracting | No longer relevant | It was decided that contract award processes are subject to the procedures of the CSE, and no to the ones of the Public Procurement Regulation Agency which is more time consuming. To this end, the manual of procedures of the CSE was updated with the inclusion of an annex on “contracting procedures”. In addition, delegate project managers were hired to assist the project owner (the excuting entities) in the procurement.
Conflict over the management and maintenance of the built infrastructures between local communities, private companies, extension services | Low | Many information and sensitization activities were undertaken toward the different stakeholders, a database on households and their assets is also under elaboration. In addition, many meetings were organized between neighboring local government units in the area of impact of the anti-salt dike to discuss the management of the land resources.
Local communities do not fully participate to the project | No longer relevant | The information, sentitization and mobilization activities were very successfull and local communities are highly committed an involved
Local governments do not accept the project | Low | The local governments are fully associated to the implementation of the activities. They play an imoportant role in mobilising populations and taking decision a bout the location of the facilities. They will aslo be involved in the monitoring and the maintenance of these facilities
Low consciousness of the populations and decision makers with regards to climate change | No longer relevant | The project has implemented an intense comunication and awareness raising programme, targeting all categories of stakeloders and addressing all issues relating to climate change and its impacts
Low impact/application of the Coastal Act | Medium | It is planned to disseminate the new regulations and the Coastal Act provide for the setting up of a national body for the management of the littoral. One of the mandates of this body will be to ensure the application of the law
Lack of coordination among the executing entities | Low | Regular technical committee meetings are organized to coordinate the interventions, as well as national and local steering committee meetings.
Budget forecasts not adequate, under estimation of the projected line items allocations | medium | Re-adjustments have been operated by the end of the project implementation between line items allocations, using remainders from certain lines to consolidate others.
Delays in the disbursement of funds, due to length of the chain | Low | There is a good collaboration framework established with the AF Secretariat and a good follow-up after reports are sent, to give any requested clarifications and make sure the disbusrements are done at due time.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Building of the protection facility and related works dependent on the synergy of interventions with the West African Economic and Monetary Union (WAEMU) | Low | Regular meetings with WAEMU staff, DNA and implementing entities
Difficulties to mobilize populations because of elections scheduled for February 2012 | Medium | Schedule most of the mobilization activities out of the critical period
Conflict between the executing entity and a portion of the population about the site of implantation of the structures in Joal | Low | Sensitization activities and advocacy in the relevant areas
Risks associated with the complexity of maritime works | Low | Take fullest advantage of the dry season and of the calm sea period
The installation of a new Parliament still impedes the adoption of the Littoral law and Environment code, resulting in delays in the training and dissemination programme | High | Despite all initiatives aiming to sensitize parlementarians and public authorities, there is a high risk thta this activity will not be completed befote the end of the project.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator:
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Building coastal protection facility in Thiawlene (Rufisque-Est) |  | Works were supposed to be completed |  | Works completed and the facility was inaugurated on July 31 by the Minister of Environment and the Chair of the WAEMU | HS
| Building coastal protection facility in Saly |  | Works were supposed to be launched since December 2011 |  | Works in progress | MS
| Rehabilitation of fish processing areas in Saly Coulang |  | Completed |  | Completed | S
| Building anti-salt-dike in Joal |  | Works were supposed to be completed |  | Works in a final stage. | S
| Developement of the fish processing area and fishing dock in Joal |  | Works were supposed to be completed |  | Works completed for the fishing dock, in a final stage for the fish processing area. | S
| Formulation of the law on littoral and revision of the Environmental Code |  | Was supposed to be completed during the first year |  | The littoral law and the Environmental Code already passed the stage of the Supreme Court. It is still awaiting examination before the Parliament. The founding of a new parliament has frozen the process so far. | MS
| Awareness raising |  | Good knowledge of the project, its objectives and its activities in the areas of intervention |  | Good level of implementation | HS
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completing the Rating section
| Name: | Assize Toure
| Email: | assize@cse.sn
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Assize Toure
| Email: | assize@cse.sn
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | To date, the awareness raising activities have been implemented with a good rythm. The construction works were launched in the 3 areas of intervention and most of them are completed or in a final stage (rehabilitation and protection of the fishing dock in Joal, building the anti-salt dike in Joal, rehabilitation of the fish processinh area in Saly). The rehabilitation of the fish processing area of Khelcom (Joal) is well advanced and the provisional acceptance has been done. There are some delays in the adoption of the new regulations and the protection works in Saly. In Joal, after the extreme weather events in August and September 2013, there are unpredictable damages affecting the anti-salt dike, the protection dike and the hangar of the fishing dock. The project management is preparing an exit strategy aiming to make the achievements sustainable and to fill gaps.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
| Indicator 1.1: number of study report | One study report validated for Rufisque | Completed | The detailed technical feasibility studies for the protection of the coastal areas of Rufisque are updated
| Indicator 1.2: Length of protected coast (in linear meter) | 6,000 square kilometres of areas threatened by flood | 73 m of seawall built (381 linear meter of wall built through the Adaptation Fund ). Facility inaugurated. | The protection facility of the coastal areas of Rufisque are built (381 linear meter of wall built through the Adaptation Fund )
| indicator.1. 3: Linear number of cleaned up channels | Coastal facilities and human settlements facing high threats | Cleaning of the shoreline, clearing of conduits (400 linear meters), removing waste materials | The waste ways of rainwater are cleaned up and connected to the sea
| Indicator 2.1: Study Reports | No study made | Completed | The detailed technical feasibility studies for the protection of the coastal areas of Saly are completed and validated
| Indicator: 2.2. Length of the coast protected (in linear metre) | 3 square kilometres of areas threatened by flood | One breakwater completed and one under construction | The protection works of the coastal areas of Saly are completed
| Indicator 2. 3 Existence of a sound fishing dock and a good fish processing area | Destruction of fishing docks and fish processing areas due to sea-level rise | Works completed | The development of the fishing dock and the fish processing area in Saly is done
| Indicator 3.1. Study reports, number of curbs and dikes built | Rice-growing activities affected by intrusion of saline waters; drainage of rice growing areas difficult | Provisional acceptance done, concerns stated by the supervising office are being addressed by the firm in charge of works before a final acceptance | The technical studies and the dikes to prevent salt intrusion into the rice-growing areas of Joal are done
| Indicator: 3.2.1. The curbs for protected beaches and the fish processing areas are developed | The beach is used as lavatory and the waste management system is very poor | Provisional acceptance done | The protection and development of beaches and fish processing areas are completed
Indicator 3.2.2. The setting up of a rational and effective waste management programme in the beach is completed
| Indicator 4.1. Number and nature of the legal materials drawn up and in force | No (or inadequate) legal materials dealing with the management of the littoral and taking into account the CC | The littoral law and the Environmental Code already passed the stage of the Supreme Court. It is awaiting adoption by the Council of Ministers and the examination before the Parliament. The Environment Code was already discussed by the relevant authorities and is awaiting and examination in plenary at the Secretariat of the Government and consideration by the Supreme Court. The texts have been reviewed at the request of the new authorities. | The legal materials dealing with the management of the littoral and taking into account the CC dimension are drawn up
| Indicator 4.2. Number of popularization sessions and participants | Peoples in these areas have very few information about the legal materials | A trainer's booklet was developed, but the popularization sessions will not take place, because the text will probably not be adopted by the parliament before the end of the project | The texts drawn up are popularized
| Indicator 5.1. Study Report | Education on adaptation is still a national priority | Regional committees for adaptation to climate change (COMREC) were estabilished by Order of the Governors and the capacity building neeeds were identified. Training sessions were organized in7 Regions benefiting to 500 peoples (Fatick, Thiès, Louga, Saint-Louis, Kaolack, Kolda et Tambacounda) | A training and sensitization programme is designed and carried out
| Indicator 5.2. Number and nature of the communication tools developed | Adaptation programmes/projects are still devoided of adequate tools for taking up and disseminating learned lessons on community adaptation | A communication strategy was elaborated, a web site developed and 1 film produced. Press visits were organized on the project's sites. | Adequate communication tools are developed and shared
| Indicator 5. 3. Number of sensitization sessions/workshops held or participants | Cross learning mechanisms are little_known | Social mobilization in Joal, Saly and Rufisque; site visits with the environmental NGOs | People are informed, sensitized and trained on the adaptation techniques to climate change en coastal areas
| Indicator 5. 4. Number of training sessions/workshops or participants | Cross learning mechanisms are little_known | 3 training sessions organized (training of journalists on environmental issues, training on organizational dynamic and gender applied to AIDS and STD, technical training on quality, hygiene, processing and conservation of fishery products) | The different target groups are trained in the new regulations on the adaptation

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Synergy with other projects can be beneficial, but it can also be source of difficulties in implementing with different procedures. The other actors in Rufisque have fundings from donors with different procedures and different requirements. During critical times, theses specificities could generate some blockages
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The protection works in Saly are delayed and safeguard measures are under preparation through the exit strategy under developement. This exit strategy is developed in collaboration with the executing agencies, the experts and the national authorities.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts?
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | When designing a protection facility, it is important to take into account extreme weather events. In addition, feasibilty studies are key steps in the implementation of such projects. Without a good feasibility study, it is diifciult to ensure the sustainability of the facilities.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | At national level, the expectations are very high from the Government and local communities for the replication and scaling up of the project activities in many parts of the coastal areas, dealing with the same issue.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | When designing a protection facility, it is important to take into account extreme weather events. In addition, feasibilty studies are key steps in the implementation of such projects. Without a good feasibility study, it is diifciult to ensure the sustainability of the facilities.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | At national level, the expectations are very high from the Government and local communities for the replication and scaling up of the project activities in many parts of the coastal areas, dealing with the same issue.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The most successful aspect for the target communities is the protection of houses and social infrastructure, but also the set up of a network of the actors of the littoral. Moreover, reclaiming the rice growing land was a great achievement for the women in Joal
What measures are/have been put in place to ensure sustainability of the project/program results? | Setting up neighborhood comittees and facilities management committees ensures a greater ownership and then, the sustainability. Maintenance guides have been also developed in order to facilitate the work of these committees. The elaboration of an exit strategy will also contribute to this sustainability
What measures are being/could have been put in place to improve project/program results? | Thanks to the information and awareness-raising activities, national and local authorities are committed to consolidate the projects achievements.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Scientific data and local knowledge have been intensely used during the project developement and implementation. These data or information were used to decide about the most appropriate technology.
If learning objectives have been established, have they been met? Please describe. | The programme has identified lessons learned that were compiled as a compendium of best practices.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | A continuous process of action learning was set up and lessons learned at each step helped improve the achievements in the next steps

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1: Implement the actions to protect the coastal areas of Rufisque, Saly, and Joal against erosion, with the aim to protect houses and the economic infrastructures threatened by the erosion including fish processing areas, fishing docks, tourism or cultural infrastructures, and restore lost or threatened activities
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 4 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 4.2 | 5 | 1 (Nothing in Saly and a very rudimentary stone dyke in Rufisque) | 360 m of coast protected in Rufisque-Est (Seawall), the fishing dock of Joal protected with a 310 m protection facility
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 4 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 4.2 | 3 coastal protection facilities | 0 protection facility in Saly and Joal, 1 rudimentary stone dyke in Rufisque-Est | 1 protection facility built in Joal
OBJECTIVE 2: Implement the actions to fight the salinization of agricultural lands used to grow rice in Joal, with the construction of anti-salt dikes
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 4 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 4.2 | 5 | 1 (Rice-growing araes abandoned due to salinization) | Approximately 240 hecatres of land reclaimed
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 4 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 4.2 | 5 | No salinity control works | 1 anti-salt dyke built in Joal
OBJECTIVE 3: Assist local communities of the coastal area of Joal and Saly, especially women, in handling fish processing areas of the districts located along the littoral and to conduct awareness programme and training related to adaptation and its adverse effects
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 6 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 6.1 | 4 | 1 | The fish processing area isn Saly rehabilitated, securing the main source of income for about 100 people.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 6 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 6.1 | 2 fish processing areas developed, one fishing dock restored, several awareness raising sessions held | 1 artisanal fish processing area, 1 fish processing area and 1 fishing dock in poor condition, low awareness of climate change effects and adapattaion strategies | 1 fish pocessing area developed
OBJECTIVE 4: Communicate on the adaptation, sensitize and train local people on climate change adaptation techniques in coastal areas and on good practices, to avoid an aggravation of the various situations encountered
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 3 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 3.1 | 4 | 2 | Approximately 5000 people targeted with awareness raising activities, improving their understanding of climate change impacts and adaptation to climate change
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 3 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 3.1 | A training and sensitization programme is designed and carried out Adequate communication tools are developed and shared. People are informed, sensitized and trained on the adaptation techniques to climate change en coastal areas The different target groups are trained in the new regulations on the adaptation. | Education on adaptation is still a national priority Adaptation programmes/projects are still devoided of adequate tools for taking up and disseminating learned lessons on community adaptation Cross learning mechanisms are little_known | 812 sensitization sessions organized, 104 radio programs produced in 3 radios located in the sites
OBJECTIVE 5: Develop and implement the appropriate regulations for the management of coastal areas
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 7 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 7 | 4 | 2 | The new littoral law and the updated environment code have passed the stage of the supreme court.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 7 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 7.1 | The Environmental Code updated; the littoral law elaborated; the texts are popularized | No (or inadequate) legal materials dealing with the management of the littoral and taking into account the CC Peoples in these areas have very few information about the legal materials | 2 texts elaborated

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.