## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 1 June 2013 - 31 May 2014
| Project Title: | Ecosystem Based Adaptation Approach to Maintaining Water Security in Critical Water Catchments in Mongolia
| Project Summary: | The Project's objective is to “maintain the water provisioning services supplied by mountain and steppe ecosystems by internalizing climate change risks within land and water resource management regimes.” This project applies the principles of Ecosystem-based Adaptation (EBA) to increase climate change resilience at a landscape level. EBA is broadly defined as “a range of local and landscape scale strategies for managing ecosystems to increase resilience and maintain essential ecosystem services and reduce the vulnerability of people, their livelihoods and nature in the face of climate change” (UNFCCC) Project investments will alleviate vulnerabilities and dismantle identified barriers by implementing three interconnected components: Component I: Integrated Strategies/Management Plans for target landscapes/river basins developed and under implementation. Component II: Implementing landscape level adaptation techniques to maintain ecosystem integrity and water security under conditions of climate change. Component III: Strengthening capacities/Institutions to support EbA strategies and integrated river basin management, their replication and mainstreaming in sector policies.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | 4505 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme - UNDP | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | MIE | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Mongolia | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | 1. The Altai Mountains and Great Lakes Basin Eco-region: Turgen/ Kharkhiraa Sub River Basins -Turgen, Ulaangom, Sagil, Bukhmurun, Khovd, Tarialan, Naranbulag soums of Uvs aimag 2. The Eastern Steppe Eco- region: Ulz River Basin- Chuluunkhoroot, Dashbalbar, Bayndun, Bayn-Uul, Gurvanzagal, Choibalsan, Sergelen soums of Dornod aimag, Bayn-Adarga, Batnorov, Norovlin soums of Khentii aimag | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2011-06-22
IE-AFB Agreement Signature Date: |  | 2011-11-03 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2012-06-14 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2014-10-14
| Terminal Evaluation Date: | 3 months prior to the final Project Board Meeting
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. Reports: a) Quarterly reports, b) Annual report, c) Annual report to MEGD, d) Vulverability and risk assessment report for two target areas, e) Economic valuation study report for two target areas under the climate change condition f) EbA strategy report for two target areas, j) Feasibility study repots for two target areas, | Czech Republic
2. Advocacy materials: Quarterly Newsletters, Eco bags with project logo and message words, Table calendar 2014, wall planner 2014, wall calendar 2014&2015 that presents main findings and recommendations of study and assessments conducted in project target areas, Two wall posters on EbA strategy and IWRM respectively for public and community groups of two target areas
3. Handbook: a) The handbook on Physical measures of EBA at local level, and associated training modules designed for different knowledge-level users was re-printed due to high demand of local project stakeholders b) Handbook on tree planting techniques comparised of 6 series including seabackthorn, elm, poplar, salix, larch and khargana species which are considered native plants of 2 target river basins
4. Policy documents a) EbA strategy framework providing guidelines for adaptation measures implementation in Steppe and Mountain areas b ) IWRM Plans for the Turgen/Kharkhiraa Subriver Basin and Ulz River Basin
| List the Website address (URL) of project. | 5. Regulations: In accordance with the Article 10.1.6 of the Law on Water and the Article 6.2 of Law on Water Pollution Fee, two relevant regulations were developed with the aim to promote an efficient and proper water use, and encourage individuals (consumers) and economic entities (users) to apply environmentally sound technology. | Democratic People's Republic of Korea
|  | http://www.climatechange.gov.mn/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Tuya Tserenbataa | Dominican Republic
| Email: | tuya.tserenbataa@undp.org | Ecuador
| Date: | 09. May 2014 | Egypt
| Government DA |  | El Salvador
| Name: | Dagvadorj. D, Special Envoy for Climate Change, Director, Climate Change Coordination Office of MEGD | Equatoral Guinea
| Email: | damdin.davgadorj@gmail.com; dagvadorj@mne.gov.mn | Eritrea
| Date: | 09. May 2014 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Chimeg Junai, Programme Officer | Fiji
| Email: | chimeg.junai@undp.org | Finland
| Date: | 09. May 2014 | France
| Executing Agency |  | Gambia
| Name: | Oyun. S, Parliament member, Minister of Environment and Green Development | Georgia
| Email: | oyun@mne.gov.mn | Germany
| Date: | 09. May 2014 | Ghana
| Executing Agency |  | Greece
| Name: | Dagvadorj. D, Special Envoy for Climate Change, Director, Climate Change Coordination Office of MEGD | Grenada
| Email: | damdin.davgadorj@gmail.com; dagvadorj@mne.gov.mn | Guatemala
| Date: | 09. May 2014 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from 01 Jun 2013 to 31 May 2014
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 31 May 2013 | 1052673
Add any comments on AF Grant Funds. (word limit=200) | Out of the total grant received from the AF to date $2,243,000 , approximately 71% ($ 1,594,633) has been spent as of May 31, 2014. Delivery of the first two years was lower than planned because of the following reasons: 1. The main reason for the low disbursement of the allocated AF funding is that the project used almost all remaining committed UNDP cofinancing in 2013 totalling USD 483,878.30. In the next years only AF funding will be spent, which will accelerate delivery of AF financing. 2. The Project office set up including recruitment of both central and local level staff was only complete towards end of 2012 (due to shortage of national specialists) contributing to lower delivery. 3. Effective implementation of the Project was only partly ensured after the inception workshop in June 2012. In addition, the re-structural and organizational changes of the Ministries and Agencies after Parliamentary election in June 2012 forced a re-establishment of the Project Board delaying arrangement of key procurements and workshops/ meetings.
EXPENDITURE DATA
List item / activity / action and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION |  | AMOUNT
| Component 1. Integrated Strategies/Management Plans for target landscapes/river basins developed and under implementation |  | 149863.65
| Output 1.1 Strategic environmental assessment, including climate change considerations, conducted for target landscapes to document threats to ecosystem function and resilience and provide recommendations for avoiding and mitigating impacts. |  | 18967.18
| Output 1.2 Economic valuations completed summarizing landscape level costs and benefits of EBA. |  | 0
| Output 1.3 Ecosystem-based Adaptation integrated within land use and water resources monitoring and decision-making system in two eco-regions. |  | 130896.47
| Component 2. Implementing landscape level adaptation techniques to maintain ecosystem integrity and water security under conditions of climate change |  | 408019.08
| Output 2.1 Capacities of rural communities for monitoring natural resources and climate change impacts and for adaptive management in two watersheds strenghtened. |  | 113894.37
| Output 2.2 EbA management plan at landscape level in two critical watersheds developed and operational. |  | 14064
| Output 2.3 Suite of adaptation techniques to improve ecosystem resilience established in two critical watersheds. |  | 280060.71
| Component 3. Strengthening capacities/Institutions to support EbA strategies and integrated river basin management, their replication and mainstreaming in sector policies |  | 172754.47
| Output 3.1 Ecosystem-based adaptation approaches/integrated river basin management, mainstreamed in natural resource use planning and implementation mechanisms in sector policies |  | 44147.13
| Output 3.2 Institutional structure for river basin management integrating climate change risks (Administration and Council) established and operation in target areas as model for replication. |  | 49962.73
| Output 3.3 Best practices are identified and programme for up-scaling best practices developed and implemented. |  | 78644.61
| Project Management |  | 92587.23
| Exchange loss |  | 24640.61
| NEX advances as of May 2014 |  | 204808.05
| TOTAL |  | 1052673.09
PLANNED DISBURSEMENT SCHEDULE
List item / activity / action planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Component 1. Integrated Strategies/Management Plans for target landscapes/river basins developed and under implementation | 164843.2205 | 2015-05-31
| Output 1.1 Strategic environmental assessment, including climate change considerations, conducted for target landscapes to document threats to ecosystem function and resilience and provide recommendations for avoiding and mitigating impacts. | 71201.0073
| Output 1.2 Economic valuations completed summarizing landscape level costs and benefits of EBA. | 0
| Output 1.3 Ecosystem-based Adaptation integrated within land use and water resources monitoring and decision-making system in two eco-regions. | 93642.2132
| Component 2. Implementing landscape level adaptation techniques to maintain ecosystem integrity and water security under conditions of climate change | 715715 | 2015-05-31
| Output 2.1 Capacities of rural communities for monitoring natural resources and climate change impacts and for adaptive management in two watersheds strenghtened. | 146187.5
| Output 2.2 EbA management plan at landscape level in two critical watersheds developed and operational. | 74031.25
| Output 2.3 Suite of adaptation techniques to improve ecosystem resilience established in two critical watersheds. | 495496.25
| Component 3. Strengthening capacities/Institutions to support EbA strategies and integrated river basin management, their replication and mainstreaming in sector policies | 213635.3369 | 2015-05-31
| Output 3.1 Ecosystem-based adaptation approaches/integrated river basin management, mainstreamed in natural resource use planning and implementation mechanisms in sector policies | 122075.3369
| Output 3.2 Institutional structure for river basin management integrating climate change risks (Administration and Council) established and operation in target areas as model for replication. | 68150
| Output 3.3 Best practices are identified and programme for up-scaling best practices developed and implemented. | 83810
| Project Management | 99196.3733 | 2015-05-31
| TOTAL | 1193389.9307
ACTUAL CO-FINANCING
How much of the total co-financing as committed in the Project Document has actually been realized? | Government co-financing is all in kind contribution and 0.5 mln USD has been contributed by UNDP. During the reporting period all remaining committed funds of a total of USD 483,878.30 from UNDP regiular resources and appx. 25% of the total Government in-kind contribution was allocated/disbursed. UNDP co-financing contributed to completion of several assessments including Economic Valuation Study, Vulnerability and Risk Assessment. Goverment in-kind contribution has been realized in the form of office service including space, heat and electricity, logistic support, expert consultation at both federal & provincial level and adaptation local measures by Aimag and Soum governments, agencies.
If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Procurement
PROCUREMENT DATA-from 01 June 2013 to 30 April 2014
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
| Contract Type | Agency / Contracted party | Amount | Signature Date
| Purchase Order |  | 1441.00 lump sum | 2013-05-14
| Purchase Order |  | 1400.76 lump sum | 2013-06-11
| Purchase Order |  | 3085.99 lump sum | 2013-06-11
| Purchase Order |  | 1516.99 lump sum | 2013-06-17
| Purchase Order |  | 4632.84 lump sum | 2013-06-17
| Purchase Order |  | 2582.67 lump sum | 2013-06-17
| Purchase Order |  | 8742.79 lump sum | 2013-06-17
| Purchase Order |  | 1253.28 lump sum | 2013-06-17
| Purchase Order |  | 3331.02 lump sum | 2013-06-14
| Purchase Order |  | 251.21 lump sum | 2013-06-17
| Purchase Order |  | 351.49 lump sum | 2013-06-27
| Purchase Order |  | 587.0 lump sum | 2013-07-09
| Purchase Order |  | 13,207.55 lump sum | 2013-06-27
| Purchase Order |  | 11,006.29 lump sum | 2013-06-24
| Purchase Order |  | 1210.67 lump sum | 2013-07-10
| Purchase Order |  | 2266.89 lump sum | 2013-05-14
| Purchase Order |  | 14,073.65 lump sum | 2013-06-11
| Purchase Order |  | 827.07 lump sum | 2013-09-24
| Purchase Order |  | 3076.92 lump sum | 2013-10-07
| Purchase Order |  | 2009.32 lump sum | 2013-10-24
| Purchase Order |  | 1269.23 lump sum | 2013-11-06
| Purchase Order |  | 442.89 lump sum | 2013-11-06
| Purchase Order |  | 786.66 lump sum | 2013-11-13
| Purchase Order |  | 745.80 lump sum | 2013-11-21
| Purchase Order |  | 517.49 lump sum | 2013-11-21
| Purchase Order |  | 2769.49 lump sum | 2013-11-21
| Purchase Order |  | 1903.85 lump sum | 2013-11-28
| Purchase Order |  | 5737.45 lump sum | 2013-11-28
| Purchase Order |  | 804.20 lump sum | 2013-11-28
| Purchase Order |  | 617.63 lump sum | 2013-12-05
| Purchase Order |  | 503.72 lump sum | 2013-12-02
| Purchase Order |  | 3022.32 lump sum | 2013-12-09
| Purchase Order |  | 314.83 lump sum | 2013-12-09
| Purchase Order |  | 643.96 lump sum | 2013-12-11
| Purchase Order |  | 1047.22 lump sum | 2013-12-10
| Purchase Order |  | 452.55 lump sum | 2013-12-13
| Purchase Order |  | 973.10 lump sum | 2013-12-09
| Purchase Order |  | 1718.95 lump sum | 2013-12-11
| Purchase Order |  | 661.13 lump sum | 2013-12-23
| Purchase Order |  | 6468.23 lump sum | 2013-12-24
| Purchase Order |  | 301.27 lump sum | 2013-12-24
| Purchase Order |  | 252.32 lump sum | 2013-12-26
| Purchase Order |  | 6353.75 lump sum | 2013-12-26
| Purchase Order |  | 6625.50 lump sum | 2013-12-26
| Purchase Order |  | 1395.91 lump sum | 2013-12-26
| Purchase Order |  | 1287.92 lump sum | 2013-12-23
| Purchase Order |  | 14,581.00 lump sum | 2013-12-26
| Purchase Order |  | 1886.53 lump sum | 2014-03-04
| Purchase Order |  | 737.84 lump sum | 2014-03-04
| Purchase Order |  | 2411.86 lump sum | 2014-04-16
| Purchase Order |  | 7834.36 lump sum | 2014-04-04
| Purchase Order |  | 660.00 lump sum | 2014-04-09
| Purchase Order |  | 2966.98 lump sum | 2014-04-16
| Purchase Order |  | 4678.23 lump sum | 2014-04-16
| Purchase Order |  | 2640.02 lump sum | 2014-03-24
| Purchase Order |  | 17,783.68 lump sum | 2014-03-24
| Purchase Order |  | 12,952.55 lump sum | 2014-03-18
| Purchase Order |  | 14,474.01 lump sum | 2014-03-18
| Purchase Order |  | 16,435.44 lump sum
| Purchase Order |  | 13,346.39 lump sum | 2014-04-16
| Purchase Order |  | 9720.67 lump sum | 2014-05-06
| Service Contract |  | 1890.00 per month | 2014-01-01
| Service Contract |  | 1680 per month | 2014-01-01
| Service Contract |  | 1680 per month | 2014-01-01
| Service Contract |  | 600 per month | 2014-01-01
| Service Contract |  | 700 per month | 2014-01-01
| Contract for services |  | 1515 per month | 2013-06-10
| Contract for services |  | 700 per month | 2013-06-10
| Contract for services |  | 930 lump sum | 2013-08-01
| Contract for services |  | 17.47 per day | 2013-07-24
| Contract for services |  | 0.8 per km | 2013-07-26
| Contract for services |  | 770 per month | 2013-08-08
| Contract for services |  | 0.68 per km | 2013-08-01
| Contract for services |  | 5.83 per page | 2013-11-26
| Contract for services |  | 81.45 per day | 2013-09-16
| Contract for services |  | 23.31 per page | 2013-11-27
| Contract for services |  | 25.06 per hour | 2013-09-16
| Contract for services |  | 8900 lump sum | 2013-12-04
| Contract for services |  | 5.72 per page | 2013-12-10
| Contract for services |  | 5.72 per page | 2013-12-10
| Contract for services |  | 5.72 per page | 2013-12-10
| Contract for services |  | 31.48 per page | 2013-12-03
| Contract for services |  | 770 per month | 2013-09-08
| Contract for services |  | 15.09 per page | 2014-03-10
| Contract for services |  | 6230 lump sum | 2014-03-04
| Contract for services |  | 3.91 per page | 2014-03-13
| Contract for services |  | 850 per month | 2014-04-01
| Contract for services |  | 1150 per month | 2014-04-01
| Contract for services |  | 2797.98 lump sum | 2014-04-07
| Contract for services |  | 1300 lump sum | 2014-04-07
| Contract for services |  | 1250 lump sum | 2014-04-07
| Contract for services |  | 1000 lump sum | 2014-04-07
| Contract for services |  | 1000 lump sum | 2014-04-07
| Contract for services |  | 1398.99 lump sum | 2014-04-07
| Contract for services |  | 1000 per month | 2014-04-15
| Contract for services |  | 0.84 per km | 2014-04-14
| Contract for services |  | 0.84 per km | 2014-04-14
| Contract for services |  | 1400 per month | 2014-04-15
| Contract for services |  | 1200 per month | 2014-04-15
| Contract for services |  | 850 per month | 2014-04-25
| Contract for services |  | 5000 lump sum | 2014-05-05
| Contract for services |  | 111.73 lump sum | 2014-05-05
| Contract for services |  | 1200 per month | 2014-05-05
| Contract for services |  | 750 per month | 2014-05-05
| Contract for services |  | 3200 lump sum | 2014-05-10
| Contract for services |  | 11,111.17 lump sum | 2013-06-17
| Contract for services |  | 5256.41 lump sum | 2013-11-05
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT | Submitted Bids |  | Bid amount | Justification | Winning Bid
Methodology to estimate damage to water resource and compensation amount; 08 May 2013 |  |  | 12131.7
|  |  | 15787.3 | Scored the highest in technical evaluation
Ecosystem-based adaptation strategy development to be conducted in the Altai mountains / Great Lakes depression and eastern steppe/Mongol Daguur; 22 Jul 2013 |  |  | 17932.4
|  |  | 24074.3 | Scored the highest in technical evaluation
Detailed research for Integrated Water Resource Management plan development in the Kharkhiraa/ Turgen rivers sub-basin; 29 Jul 2013 |  |  | 17341.84
16842.57
|  |  | 14895.27 | Scored the highest in technical & financial evaluations
Detailed research for Integrated Water Resource Management plan development in the Ulz river basin; 29 Jul 2013 |  |  | 15314.81 | Although the X NGO scored the highest for the both assignments for two watersheds, the Y NGO, the second best candidate was selected for the development of IWRM Plan for Ulz river basin. The main reason for this selection was the time constraints for completion of IWRM Plans for both watersheds within the set timeline of 3 months due to i) the distance between the two target sites (approx. 2500 kms) located in far East the and the far West of Mongolia, that makes impossible to meet the deadline; ii) The scope of assignment was broad including multiple tasks such as to hold local needs assessment, consultative and participatory workshops, survey, development of IWRM plans and its approval of Citizens Representative Khural. In addition it was required to develop compendium of Baseline studies and creation of Atlas (maps) for the watershed.
16900.68
|  |  | 13833.11 | Scored the highest in technical & financial evaluations. However, the selection for this assignment was for the second best candidate considering the workload of the company being selected for IWRM plan development for Kharkhiraa/Turgen sub - river basin. see above.
Feasibility study of EBA techniques to be undertaken in project target soums / Ulz river basin; 26 Aug 2013 |  |  | 17678.57 | Scored the highest in technical & financial evaluations
|  |  | not opened | insufficient technical proposal
92120
Feasibility study of EBA techniques to be undertaken in project target soums / Kharkhiraa-Turgen river basin; 26 Aug 2013 |  |  | 17919.8 | Scored the highest in technical & financial evaluations
40797.9
To develop a guidebook on water saving and harvesting techniques and organize regional trainings for public and community groups of target areas; 28 Mar 2014 |  |  | not opened | insufficient technical proposal
|  |  | not opened | insufficient technical proposal
Scored the highest in technical & financial evaluations
|  |  | not opened | insufficient technical proposal
|  |  | not opened | insufficient technical proposal
To develop the climate change and EBA education curriculum and incorporate it into the environmental study program of Mongolian universities; 28 Mar 2014
Initiate permafrost study in Mongolia; Mar 2014
Development of IWRM Plan for Uvs Lake and Tes River Basin

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them (word limit = 200)
Identified Risk | Current Status | Steps Taken to Mitigate Risk (as identified in the Prodoc)
Policy makers prioritize economic benefits over sustainable and resilient ecosystems | Impact: Moderately high (4); Probability: Low (1) | In order to ensure the government's understanding on climate change risk on ecosystem services and its impact on the economy, the Project conducted economic valuation study quantifying the economic impacts of envisaged ecological changes under the climate change conditions. It will be finalized by the end of Q2, with measurement of the economic costs and benefits of alternative adaptation strategies to cope with these changes. Policy documents -Integrated Water Resources Management Plans (IWRM Plan) and EbA measures strategy framework for two target river basins were developed basing on the study findings on CC, ecosystem change effects on the supply and demand of water and land. The policy documents, the IWRM Plans and the EbA strategy framework are adopted by the local governments (three aimags) through respective Aimag Parliament Resolutions and their implementation started. The project continous capacity building of government officals and stakeholders at national and local levels through various tools of knowledge management.
Ineffective mitigation of nonclimate drivers of ecosystem alteration | Impact: Moderately high (4); Probability: Low (1) | The government and UNDP have been working closely with the complementary Projects supported by GEF and bilateral donors, in order to ensure that non-climatic drivers of ecosystem alterations are sufficiently addressed. The policy documents, IWRM plans and EbA strategy framework inform other ecosystem management initiatives, and/or act as incentives for reducing nonclimatic threats to ecosystems. Capacity building for EbA practices at community level directly contributes to addressing nonclimatic drivers such as grazing pressure, hydropower, mining and agricultural planning. During the reporting period, the project cooperated with the MEGD in developing of 2 relevant regulations (in addition to 3 regulation development in 2013) in accordance with the Article 10.1.6 of the Law on Water and the Article 6.2 of Law on Water Pollution Fee with the aim to promote an efficient and proper water use, and encourage individuals (consumers) and economic entities (users) to apply environmentally sound technology. These legal documents are expected to serve as an useful means to build a proper mindset for a sustainable use of natural resources.
Extreme natural disasters affect confidence of local community to adaptation measures | Impact: Moderate (3); Probability: Moderately low (2) | As a part of adaptation measures, the project initiated already a proven approach of community-based disaster risk management, thus reducing the vulnerability of communities to natural disasters. The primary units are the herder groups or community organizations joining the efforts. Local level demonstrations provide incentives for the local communities to cooperate towards a long-term resilience.
Capacity of Aimag and Soum level stakeholders will no match project activity demands | Impact: Moderate (3); Probability: Low (1) | The probablility rating has been upgraded from moderately low (2) to low (1) Implementing the earlier developed "Local level capcity building programme", a series of capacity building activities on data collection, analysis, and use for better planning and policy development are initiated. For instance: GIS-based land management, easy to use and refer google-based micro data base on EbA (soon be able to give the link here), CC planning and EbA principles and practices.
Adaptation measures increase inequity | Impact: Moderate (3); Probability: Moderately low (2) | The project ensures that the adaptation measures are sensitive to gender and vulnerable population groups (disabled and of low income). The project will also ensure that demonstration activities at the local level do not limit the participation of women and the disabled as beneficiaries.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
No critical risks identified.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
N/A

## Rating_2013
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
|  | Progress on Key Milestones | Expected Progress | Progress to Date | Rating
Project Manager / Coordinator: |  | Project Objective is to maintain the water provisioning services supplied by mountain and steppe ecosystems by internalizing climate change risks within land and water resource management regimes.
Outcome 1: Landscape level integrated land use and water resources monitoring and planning system focused upon reduction of ecosystem vulnerability to climate change.
|  | 1.1 Baseline inventory/assessment (ecological and socio-economic) as a basis for the development of Ecosystem-based Adaptation Strategies for the target landscapes and River Basin Management Plans are completed and enriched the database | 1.1.1 Data on surface/ground water quality, soil sample examination for two target eco-regions to enrich database of state of ecological and socio-economic conditions as of 2013 and 2014 completed. | Water chemistry analyses were carried out to identify chemical components and properties of the ground and surface water in 17 soums of the target areas. These include pH, suspended solids and ammonium, permanganate value, phosphate and iron etc. A total of 22 water samples were collected from the two river basins during the last summer, including 7 samples from upstream, mid and downstream of Kharkhiraa, Turgen and Ulz rivers, 3 samples from lakes in Ulz river basin, and 12 samples were taken from wells in targeted soum centers. In addition to that total of 26 soil samples collected from the areas used for agriculture, pasture, and haymaking in the basins of the two river basins. All the sampling points were located on slopes or plains, covering regions with different parent materials as a comparison and with a wide variety of annual precipitation. Soil sampling can be used in the “demonstration” site of the Project that are visually different or with consistent low yields when compared to the healthy field. This activity will be updated each year during the Project to enrich the database and keep records indicating where samples are taken and the state of soil. | S
|  |  | 1.1.2 Capacity building of local Government Organizations (LGO)/ Environmental Units, RBAs were improved on application of GIS/Remote Sensing in natural resource planning (forest, water, soil, plant) in Uvs, Khentii, Dornod aimags. | The major objective of the training (conducted in April - May 2014 in two target areas) is to apply remote sensing technology to surveying the natural resources and monitoring the environment and natural hazards in the project areas. It encouraged the satellite data for applications in various natural resources and, provided data and services to LGO engaged in development of database and policy-making activities. Total number of 115 LGO/Environmental Units (ranger, environmental inspector, meteorologist etc.) and RBAs participated in those trainings. As a result, trainees gained skills on remote sensing science/ GIS for better planning of land management.
|  |  | 1.1.3 Vulnerability and Risk Assessment as a basis for developing EBA Strategies for the target landscapes and estimate balance surface and groundwater use balance in target catchments for developing RBMPs were finalized. | Vulnerability assessments conducted analyzing the expected impacts, risks and the adaptive capacity of natural resources (water resources, pasture, soil, forest, wildlife) and socio-economical (livestock, agriculture, human health and livelihood) sectors to the effects of the climate change using basic principles guided by the IPCC and based on the results of the RCM with spatial resolution of 30 km under A1B GHG scenario. In case of risk assessments, the estimation based on the combination of consequences (damage) and likelihood, and scores based on the experts’ analyses for above mentioned sectors were determined. In addition, vulnerability and sensitivity maps that depict the temporal and spatial distribution of different aspects or determinants of vulnerability were processed. The outcomes of the assessments fed into to the policy documents as EbA measures guidelines and IWRM plans. Highlights of the summary of vulnerability: Water is the most vulnerable natural resource in these two eco-regions. The wildlife and animal husbandry sectors are more vulnerable compared with other natural resources and socio-economic sectors in both ecoregions. Summary of risk: It is predicted by the current climatic condition and 2011-2030 climate change projection that husbandry, wildlife, mining and water sectors in the east, whereas sectors of water, forest, livelihood and agriculture are at more risk in the west respectively. During the periods of 2046-2065 and 2080-2099, wildlife, animal husbandry and public health are likely to be at the highest risk in Altai Mountain/ Great lake Depression regions due to water scarcity. Grasland ecosystem and animal husbandry, wildlife and agricultural sectors in the Eastern Steppe landscapes/ Mongol Daguur will likely be at higher risk. Water use balance was estimated with inclusion of surface and groundwater resources of the basin using existing outputs of baseline studies.
|  | 1.2 Economic valuations completed summarizing landscape level costs and benefits of EBA. | 1.2.1 Project's initial economic valuations finalized comparing the landscape level costs and benefits of EBA approaches. The purpose of the study is to propose adaptation options that internalize the risks posed on the livestock, agricultural, water and forestry sectors, in addition to the wellbeing of wildlife and humans. | The first stage of the study including construction of a set of climate change projections in two eco-regions of Mongolia, the Great Lakes Depression in the West and Eastern Steppes in the East for the periods of 2011-2030, 2046-2065 and 2081-2099 using 3 GCMs under different greenhouse gas (GHG) scenarios and the regional climate model under A1B GHG scenarios is completed. Through this analysis, the study tried to examine the A1B emission scenario to estimate potential outcomes in the case of absense of green house gas mitigation over the next century. Model outcomes predicted warmer and less snowy winter and hot and dry summer in Altai mountain/ Great lakes depression and Kharkhiraa, Turgen sub river basin /compared to Eastern steppe eco region/ Ulz river basin. For each climate scenario, the climate change variables such as extreme events, temperature, precipitation and evaporation, etc. and their effects on natural resources, trends of water (glacier), soil, forest and wildlife are predicted. Further step is to apply these data in economic analysis. Lastly, by analyzing the changes in climate change, the study predicted how the income of local residents and the value of natural resources would ultimately be affected in 2020, 2050 and 2080. According to result of this research work, the optimal adaptation strategies to climate change in the near and long terms are identified. Recommendations of the valuation will be used for next cost and benefit analyses on EbA adaptation measures and submitted to relevant ministries and reflected in the development of the policy documents.
|  |  | 1.2.2 Review of Economic valuation studies of natural resources under climate change | In fact, this type of studies has not been conducted earlier in a sufficient number in Mongolia to be able to accumulate an adequate pool of data. By focusing on ecosystem services expressed in economic term, the value and multiple benefits of functioning ecosystems will be recognized and the conservation of natural resources will be implicit as an effective means of maintaining sustainable and healthy life, while responding to climate change. Therefore, necessity to reexamine and review again economic study section definitely does arise. In this regard, it requires inputs of additional expertise/international consultancy to fulfill the knowledge gap of the ecosystem valuation skills by provision of training to national team. Especially, assessment of the economic part and recommendations on adaptation options to support ecosystem integrity and its services based on outcomes are needed to be reviewed.
|  |  | 1.2.3 Series of cost and benefit analyses initiated (CBA) to assess impacts of ecosystem based adaptation measures. | 1st series of CBAs focus on 3 topic; Household drip irrigation in the west site, Protection of wetland or along river bed in the east site and Efficiency of heating stoves for hospitals and soum administration offices in 3 Soums of East site. International consultant on Economic Evaluation will provide methodological advice on CBA as well.
|  | 1.3. Support in improving and implementing Ecosystem-based Adaptation strategies for the target landscapes (Great Lakes Depression, Daurian Steppe), and River Basin Management Plans for the River Basins (Kharkhiraa/Turgen and Ulz). | 1.3.1 Ecosystem-based Adaptation (EbA) guidelines in two ecoregions were finalized with plans to implement a suitable version for implementation of climate resilience measures and to build the resilience of habitat and communities to climate change impacts. | EbA measures' guidelines which was developed with support from the project now serve as a reference for implementing priority adaptation measures in target areas since the baseline/ benchmark assessments, including baseline survey, vulnerability and risk assessments and economic valuation study all fed into them. The guidelines consider the current and future climate change, variability and associated disaster risks focusing steppe and high mountain ecoregions which are replicable in similar ecosystems in the country as well. They promote also interactive solutions in other sectors such as animal husbandry, land management and socio-economic sectors. EbA measures were determined according to the 6 principles recommended by UNDP aimed to adopt integrated policy on EbA. These principles are: i) Maintain ecosystem resilience, ii) Support ecosystem services, iii) Support adaptation capacity of sectors, iv) Reduce disaster risks, v) Develop appropriate infrastructure, vi) Reduce negative impact for adaptation. Sets of adaptation measures are divided into 7 types; (i)Water; (ii) Pasture; (iii) Forest ecosystems, (iv) Riparian areas, (v) Policy to support implementation, (vi) Esthetic and educational values of ecosystems; and (vii) Ecosystems resilience and further separated into activities. | HS
|  |  | 1.3.2 The IWRM plans for Kharkhiraa/ Turgen sub-river basin and Ulz river basin were developed and finalized as a policy documents | Two IWRM Plans for Kharkhiraa/ Turgen sub-river basin and Ulz river basin are now operational since end of 2013, starting with the 2013 water census. The newly established River Basin Administrations in target areas and all stakeholders (water consumers, users, RB Councils) of the Basins are implementing the Plans, which reflect priority measures on water use, protection and restoration with consideration of regions' vulnerability and risks in context of climate change and principles of EbA. During the preparation period, a survey on needs of the water management was carried out including 300 herders and other key stakeholders, extensive discussions were held upstream, midstream and downstream of the rivers to collect comments of local governments. The Plans were drafted reflecting their recommendations and feedbacks and discussed further at Ulaanbaatar involving all level stakeholders to introduce initial results and receive comments for finalization. Then they were submitted to Aimag Governments for discussion and approval by the Citizen’s Representative Khural (Aimag Parliament) of Uvs, Khentii and Dornod aimags in November 2013. Finally, the IWRM plans were approved by the Minister of Environment and Green Development following to the Article 4.8 of the “Law on Water”, which specify that river basin management plans shall be approved by the Government officially in charge of the environmental issues.
Outcome 2: Landscape level adaptation techniques maintaining ecosystem integrity and water security under conditions of climate change.
|  | 2.1: Capacities of rural communities for monitoring natural resources and climate change impacts and for adaptive management in two watersheds strenghtened. | 2.1.1 Conduct local regional training to prepare local level trainers on CBNRM and CLIM in target river basins | A regional training on Community based natural resource management (CBNRM) and Community led impact monitoring (CLIM) techniques have been organized in Uvs and Dornod respectively. As a result, local project coordinators and environmental, agricultural, and land officers of target soums as well as school teachers gained adequate knowledge on CBNRM issues and basic skills to work with local communities through participatory tools and techniques. In addition, participants learned on basic techniques for river water quality monitoring. An advanced guidance to the communities in formation and capacity development is provided by local coordinators on a regular basis. | S
|  |  | 2.1.2 Establishment of 3 surface water monitoring posts in upstream of Kharkhiraa River (Tarialan) and upper and midstream of Ulz River (Norovlin and Dashbalbar) to collect a set of indicators to monitor the effectiveness of the Project implementation | Due to limited financial and human resources, the local meteorological and hydrological units still face challenges related to equipments to carry out surface and ground water quality monitoring and assessment. Considering this, the project supplied required equipments with specifications including portable water lab, current meters, data loggers and thermometers to local meteorological units in order to improve data collection capacity. Considering lack of capacity to properly use of newly received equipments, relevant technical officers of local meteorological units have been invited to UB for a day practical training. The training was organized in cooperation with NAMEM involving 12 local officers to be responsible for operatioin and maintenance of newly provided equipments. The training consisted of two sections including seminar and practical works. During the practical session, the participants visited Tuul river and conducted on-site measurements. As a result, the trainees gained sufficient practical skills to properly utilize the equipments for more effective water monitoring. | HS
|  |  | 2.1.3 Establish ~10m2 sized energy efficient dwelling for Glacier Base Camp in the Kharkhiraa Mountain, Uvs Aimag for monitoring of glacier and ice melts ( visits to define appropriate site, install automatic weather station, purchase dwelling and transportation cost) | The project provided support to construction work of a dwelling for Glacier Base Camp in the Turgen Mountain as a part of capacity building efforts to NAMEM. An energy efficient building with floor size of 12 m2 was constructed by applying Canadian timber-frame technology at the 3500m above the sea level. The site was selected by the experts of IHME in advance. UNDP’s GEF-funded “Building Energy efficiency project” provided support on selection of structural design, construction company, construction works as well as quality controlling the construction process. Horses and camels, as the only capable transportation means have widely been used to transport relevant parts and details of the building to get to the Base Camp which became the 3rd camp in Altai Mountain. An Automatic Weather Station (AWS) which collects observation data with 10 minute frequency was assembled and installed nearby the dwelling as a complimentary unit. The both dwelling and weather station are expected to enable national researchers and scientists to accurately define meteorological factors affecting melting of glacier in this changing climate context. The data sets have been two times collected by the local meteorologist and forwarded to the Project and NAMEM since establishment of the Glacier Base Camp. This year's data will serve as a benchmark for the long term monitoring of glacial melting and observation. | S
|  | 2.2. Suite of adaptation techniques to improve ecosystem resilience established in two critical watersheds. | 2.2.1 Develop landscape level EbA program for each target soum in Kharkhiraa-Turgen and Ulz river basins | Within the EbA strategy framework, the Project is planning to develop landscape level EbA program for each target 17 soums. The national team's recruitment process is initiated and the soum programs/plans will be finalized by October, 2014. The EBA program is closely linked with the economic and social factors that govern the ecosystems services and benefits especially on pasture and land use, and will address identified issues and challenges, such as environmental, socio-economic, cultural, organizational issues, urbanization and the overall well-being of local people | S | output description and progress simply changed between 2.2 and 2.3. the mistake happened when we changed the numbers last time.
|  |  | 2.2.2 Conduct assessment on expansion of protected area in order to maintain ecosystem integrity and services in Kharkhiraa/Turgen and Ulz river basin | The Assessment for Expansion of Protected Areas (PAs) in the Project target areas will start in June and is expected to be complete by October, 2014. The aim of the assessment is to work out the scientific basis for expansion of protected area in order to maintain ecosystem integrity and services within the boundaries of targeted river basins. The expedition is expected to result in development of proposals on new areas (rivers upstream, expand Mongol Daurian Strictly PA etc.) for expansion of PAs following on legal requirements of expansion of PA system and recommendations on improvement of community based tourism and lessen mining impacts to PAs .
|  | 2.3. EbA management plan at landscape level in two critical watersheds developed and operational. | 2.3.1 Undertake a Feasibility Study in Kharkhiraa/Turgen River sub-basin to dentify priority areas to implement EBA techniques and explore suitable natural techniques for EbA implementation | The objective of the Feasibility study (FS) was to determine the most suitable techniques for ecosystem based adaptation measures taking into account of hydrological and ecological conditions of each target soum. The main findings of the FS were presented to and highly appreciated by the Project Technical Committee. The results and technical recommendations from this assignment are being used as important references and guidance for further planning of the project activities. More specifically adaptation techniques regarding renewable energy, clean technology, sustainable land, forest and water management were defined and to be reflected workplans for further project lifetime. . | S
|  |  | 2.3.2 Install measuring and monitoring devices on heat-only boilers and conduct on-site training | As recommended by the Feasibiltiy Study, the project is planning to implement follow-up activities to improve energy efficiency of heating systems in project target soums, in order to decrease challenges towards deforestation due to logging for the central heating system for public buildings including soum governance office, kindergardens, schools and hospitals etc. that use woods as fuel. In addition, most of the heat-only boilers do not have a system to control and ensure adequate energy efficiency. For the reporting period 75 technicians were trained in installing and using automatic instruments including thermometers and manometers to ensure and monitor proper heating mode of central systems for fuel efficiency. During the training, 40 heating systems for public buildings were equipped with automatic instruments under professional assistance of project trainer in order to ensure efficiency. As a result, wood consumption for heating is expected to be reduced by 30-40 percent in target areas.
Outcome 3: Institutional and policy capacity strengthened to support Ecosystembased Adaption replication, monitoring, and enforcement for critical watersheds
|  | 3.1 Ecosystem-based adaptation approaches/integrated river basin management, mainstreamed in natural resource use planning and implementation mechanisms in sector policies | 3.1.1 Conduct training for Soum land officers of two target areas | In May 2014, training for the land officers involving 28 participants from target aimags and soums was organized in cooperation with the National Agency for the land management, geodesy and cartography. The objective of the training was to strengthen land officers’ capacity to reflect EbA and sustainable pasture use principles into land management planning of their localities. As a consequence, trained land officers are committed to have the increased area with an adequate pasture management. In addition, these officers are expected to be resource persons for development and implementation of Soum level EbA management plans in their soums. These resource officers will be cooperating with the national team to develop landscape level EbA Soum Plans in 17 soums of the Project. Their inputs will be to ensure synergies in reflection of EbA measures in land use plans including Soum pasture management plan at their Soums by providing expertise and thematic maps on pasture, agricultural fields, soum residential and administrative areas, protected areas, infrastructure and mining areas etc. They will also be resource people to reflect participatory approach and principles into land use planning and management. | S
|  |  | 3.1.2 Cooperate with MEGD to develop relevant regulations in accordance with the Law on Water and Law on Water Pollution Fee | Mongolia is considered as a country with scarce water resource. However, water consumption is increasing every year. On the other hand, water resource is threatened by the improper water use and inadequate natural resource exploitation leading to water shortage. Taking account of this, the project provided support to MEGD in developing 2 regulations associated with the Law on Water and Law on Water Pollution Fee. The objective of one of the regulations is to ensure a proper fee system to promote an efficient water use, and encourage consumers and economic entities to apply environmentally sound technology while another is focused more on compensation for the damage to water resources. These regulations are expected to be useful legal means to build a proper mindset for a sustainable use of water resources, encourage to implement users pay and polluters pay principles and improve and introduce new technology on water saving.
|  |  | 3.1.3 Support the CCCO to hold series of discussions on Climate Change adaptation policy to be reflected in the Aimag development plans in western and central Aimags (Uvs and Selenge aimags) and to introduce EbA options and measures. | Two regional training sessions on “Climate change policy and response” were co-organized with the CCCO of the MEGD in Selenge aimag and in Uvs aimag in 2013. A totall of 85 participants including officers of Aimag Environmental Offices and representatives from other sectors such as industry, health and education etc obtained knowledge about climate change, mitigation and adaptation options, especially one best adaptation options–EbA; climate change policy in Mongolia and skills to implement climate change policy at a local level. As a result, trainees are now in charge of reflection of climate change adaptation issues/EbA in their Aimag development planning and policy of sectors. As the next step the project will support the Climate Change Coordination Office (CCCO) in organization of trainers' training for all 21 Aimags with collaboration of the German Technical Cooperation (GIZ). The curriculum will include reflection of climate change issues in planning and policy development in all Soums (315). The CCCO will also coordinate events to discuss Climate change adaptation and mitigation measures and strategic planning in Agricultural, Water Resources and Forest sectors with consideration of EbA involving national level stakeholders.
|  |  | 3.1.4 Support national institutions to attend the Climate Change Conference COP19 in Warshaw, Poland with involvement of experts and the Project level representation and organize Side event in association with the Government of Japan | The Project participated in the Side event titled "Financing Climate Adaptation: Innovation from Direct Access Through Project Implementation” organized by AF, and involved in panel discussions. During the event mostly experiences that various implementing organizations are having in each phase of the Adaptation Fund’s financing processes have been presented to give insights about tangible climate adaptation interventions from Africa to Mongolia to Honduras. As one of the 5 presenters, the Mongolia project presented its work under the title "IWRM as one of options of EbA measures and its implementation arrangements". The presentation gave insights into conducting concrete water sector climate adaptation interventions. Attendance of Side events and Panel meetings on Climate change adaptations in Mountains, in Water sector and Mitigations; Low Carbon Societies etc. was benefitial to learn and share latest reports and cases on technology, needs, planning of Adaptation and Mitigation. A separate side event was independently co-organized by Mongolian and Japanese government to exchange views on further extending cooperation on Joint Credit Mechanisms. Outputs of the attendance the COP 19 were as follows: • The Joint Crediting Mechanism (JCM) to be implemented between Mongolia and Japan was decided to expand • Cooperative initiatives of the Mongolian Government on the climate change adaptation with other countries were more cleared • The project information, including the IWRM interventions was introduced as one of options of EbA measures and its implementation arrangements • Became familiar with latest reports and cases on technology, needs, planning of Adaptation and Mitigation and shared new information and knowledge with the MEGD and project staff
|  |  | 3.1.5 Raise public awareness on EbA and climate change using all means of media (newspaper, journal, radio, TV) | During the reporting period 3 editions of the Quarterly Newspaper were published in cooperation with the CCCO of the MEGD and distributed to the key stakeholders, project field staff, decision makers and officials of relevant ministries and agencies. The 3th edition was titled “Climate change mitigation, possibility and measures to reduce green house emission”; the 4th edition of the Quarterly newspaper was prepared in English as a special edition; the 5th edition was titled “Inventory and estimation of green house emission” and the 6th was published under “Overview of project activity in 2013”.Totally, more than 3000 readers including national and local level decision makers, and project stakeholders received the latest issues in regarding to climate change and project activities. Two series of TV program were produced and broadcasted on MNBTV. The first one introduced the public about the Project rationale and EbA concepts. In this program, interviews with relevant experts such as climate change researcher, hydrologist, soil scientist, ecologist and biologist about the current challenges underlying climate change were included. Also, university students who participated the essay competition joined the program, sharing their ideas concerning climate change and response actions to take. The second TV talk show aimed to introduce main findings and recommendations of the studies and assessments conducted by the project and key principles of the EbA strategic framework and the rationale of the IWRM plans to the project stakeholders and decision makers as well as the public. This program was broadcasted during the peak time of MNB. As per the monitoring survey conducted by the Press Institute team, 20 percent of total viewers watched the program, approximately 420 000 people including urban and rural population. No official monitoring has been done on influencing perception to environmental protection and restoration or behavior of locals, but positive attitudes and understandings noticed by especially on cooperative actions on local adaptation measures. It is assumed their contribution as willingness of labor or their active participation in trainings or provision of their contribution materials, equipments, buildings etc.
|  |  | 3.1.6 Organize public awareness activities during the International events such as World Environment Day (June 5), World Water Day (March 22) | The Project organized an essay competition titled “What can we do to mitigate and adapt to climate change?” among Mongolian university students in cooperation with the CCCO of the MEGD between April 19 and May 20, 2013 prior to the "World Environment Day 2013" hosted by Mongolia. The purpose of this competition was to improve public awareness of the importance of each individual’s contribution to climate change mitigation and adaptation, and promote the active public involvement. All successful participants came up with important new messages about “what kind of actions should be taken and how to mitigate further climate change and implement adaptation actions in Mongolia. A WMO booklet titled “We care for our climate” was translated and duplicated with the aim to provide children with easily understandable and attractive basic materials. • Eco bags with project logo and message words reflecting EbA& its principles
|  |  | 3.1.7 Cooperate with CCCO of MEGD to develop advocacy materials on EbA and climate change (DVD, poster, table and wall calendar, eco bag etc) | The following advocacy materials were produced in the period of the report: • A 5 minute GIZ animation titled “We know enough about climate change” was translated and broadcasted during the “Open Doors Day” of MEGD held on June 03, 2013 with the aim to call attention of the decision makers and the public for involving in the climate change mitigation and adaptation actions, decision making towards it. • Table calendar 2014, wall planner 2014, wall calendar 2014&2015 that presents main findings and recommendations of study and assessments conducted in project target areas and some key messages on EbA measures in connection with IWRM plans to the key stakeholders and decision makers as well as the public. • Two wall posters on EbA strategy and IWRM respectively produced and disseminated to public and community groups of two target areas All project advocacy materials will be used for further educational, promotional and publicity purposes.
|  | 3.2 Institutional structure for river basin management integrating climate change risks (Administration and Council) established and operational in target areas as model for replication. | 3.2.1 Support in establishment of River Basin Administrations (RBA) of Uvs lake-Tes river (which includes the target Kharkhiraa, Turgen rivers sub-basin) and Ulz river basin for technical capacity building | The Uvs Lake-Tes RBA and Ulz RBA were established in June 2013 after RBAs’ directors were recruited by the MEGD. The western project target area, Kharkhiraa, Turgen river basin belongs to the Uvs Lake-Tes river basin. In July, 2013, the project supported the newly established RBAs in their capacity building by providing with office equipments (personal computer, printer, UPS, GPS, photo and video camera, and some office furniture etc). Moreover, two Russian Vans were handed out to these RBAs. As a result, two target RBAs are fully operational in terms of infrastructure and equipment. | HS
|  |  | 3.2.2 Organize a training for newly established RBAs on ecology, hydrology, policy, IWRM and Adaptation Strategies in cooperation with the MEGD | Scaling up the capacity development interventions, the project cooperated with the MEGD (Division of River basin management) in organization of a regional training titled “Implementing IWRM planning in a river basin” for western aimag RBA officeres on September 20, 2013 in Zavkhan aimag. A total of 70 participants were involved in this training, including experts of RBAs (“Khar lake-Khovd river”,“Khirgas lake-Zavkhan river” and “Uvs lake-Tes river”) as well as decision makers of 5 western aimags, Bayan-Ulgii, Khovd, Uvs, Zavkhan and Govi-Altai. They obtained comprehesive knowledge on Climate change adaptation, EbA, IWRM, water and nature conservation, in addition to that participants gained detailed information on the amendments to the newly approved Package of Environmental Laws (10 laws).
| Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500) |  |  | Overall Rating | S
|  | Name: | Tuya Tserenbataa, National Project Coordinator
|  | Email: | tuya.tserenbataa@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The Project has completed its 1st stage to create ecological and socio-economic benchmarks and baseline data that were essential for policy documents such as River Basin Management Plans (RBMP) in three River basins and EbA strategic framework including implementation guidelines in two ecoregions. They successfully serve as references for implementing local adaptation measures in relation to River Basin Management and Climate change adaptation in 17 soums of 3 Aimags. Coverage area and number of Soums in target area will be expanded since the development process of Uvs Lake and Tes River Management Plan in west site is initiated. Data base for measuring impacts of adaptation measures was set up and became operational. The nationwide monitoring network was expanded by establishment of 3 more Surface water monitoring posts along river beds in Ulz and Kharkhiraa and 1 Glacial observation post in the Kharkhiraa and Turgen Mountains. As a result of it, Aimag and Soum Meteorology offices/ posts improved data quality and effiecency with fixed frequency and less labor forces. Local level pilot adaptation measures were initiated on riparian area with interventions in terms of springs protection and restoration, sustainable farming, reforestation, efficient heating and support of small scale productions for livelihood diversifications and demonstration of best practices. In parallel, on site trainings on technologies and methods were provided to target groups on drip irrigation, tree and vegetable planting and fire prevention and fighting with provision of seedlings and equipments. Series of capacity development activities arranged for local decision makers, environmental agencies and RBAs on better planning and policy development with inclusion of climate change and EBA principles and practices with cooperation of CCCO and MEGD. To enable effective implementation of Water Law and Law on Fees on Water Pollution , 2 regulations were developed with the technical support of the Project with the aim to promote an efficient and proper water use, and encourage individuals (consumers) and economic entities (users) to apply environmentally sound technology. These legal documents are expected to be useful means to build a proper mindset for a sustainable use of natural resources.There is no negative progress so far observed.
|  | Progress on Key Milestones | Expected Progress | Progress to Date | Rating
Implementing Agency |  | Outcome 1: Landscape level integrated land use and water resources monitoring and planning system focused upon reduction of ecosystem vulnerability to climate change. | Creation of benchmarks/ baseline stage completed including baseline survey, vulnerability and risk assessments and economic valuation study in order to ensure a strong base for the development of Ecosystem-based Adaptation measures gudelines/ strategies for the target landscapes and IWRM plans. These policy documents were finalized through contracting of experts teams to carry out assessments with wide discussions and carry out learning by doing and experience sharing trainings. Extended Consultative Workshop was held in Ulaanbaatar city on November 28 and 29, 2013 to introduce outcomes of key studies, assessments and policy documents in Project targeted landscapes (vulnerability and risk, economic valuations, IWRM plan and EbA directions) for all stakeholders of the Project. | 1. Climate change vulnerability and risk assessment were finalized which started in August 2013 in Altai Mountains/Great Lakes Depression and Eastern Steppe Landscapes/Mongol Daguur, along with the estimation of the catchments’ water use balance. The outcomes of the assessments fed into to the EbA strategy framework including adaptation measures implementation guidelines and supported the development of the IWRM plans. For validation of the findings of the study and assessments as well as finalization of the policy documents (vulnerability and risk assessment, economic valuations, IWRM plans and EbA directions), extended consultative workshop was held in Ulaanbaatar in November 2013 presenting outcomes for broad discussion and comments by key stakeholders of the Project. These policy documents advise systemized strategic planning and assess adaptation options within the context of climate change. The implementation guideline for Ecosystem-based adaptation (EbA) measures in the Altai Mountains/Great Lakes Depression and Eastern steppe/Mongol Daguur identified six key directions/objectives broken down into several sub-objectives and activities covering the timeframe between 2014 and 2021. The guideline serves as a key hands-on tool for local governments in the target ecoregion. Implementation of the IWRM attributed to the integration of social and ecological adaptation capacity and increased knowledge into climate change adaptation and expected to have significant positive impact on proper use and conservation of water resources in Mongolia where challenges of water quantity and quality issues are serious concern. 2. 1st round of Economic Valuation Study for Kharkhiraa/Turgen and Ulz river basins w+D42as finalized. The study was examined the impact of climate change on the economies of two disparate river basins in Mongolia. Team of scientists have used ecological models to project the future conditions of the climatic F48and hydrological regimes. Subsequently, this information has been used to forecast the conditions of pastureland, agricultural land, forest land and habitat for wildlife in 2020, 2050 and 2080. According to result of this research work, identified the optimal adaptation strategies to climate change in the near and long terms. 3. Through establishment of surface water monitoring posts, (3) glacier bas camp (1) and local water monitoring groups (17) and provision of series of trainings, the capacity in target two ecoregions for landscape level integrated land use and water resources monitoring improved. So the Environmental Unit members, including rangers, environmental inspectors, meteorologists and land management officers, as well as local surface water monitoring groups, officials in the surface water monitoring posts and glacier base camp are able to apply remote sensing science/ GIS technology and skilled quality monitoring and to work with the Project EbA micro-database. At the soum level the considerations on EbA strategy and appropriate measures in the soum land use planning is progress in all 17 target soums. | S
|  | Outcome 2: Landscape level adaptation techniques maintaining ecosystem integrity and water security under conditions of climate change. | Two RBMPs and two EbA strategies developed and implemented | The official adoption of the IWRM Plans by all three target Aimag Parliament in 2013 and the two EbA strategy framework enabled inititation of pilot adaptation measures to support the locals, ecosystems and economic development of the 17 soums with the aim to producing good practices for further replication in the region and nationwide. All the guiding documents and plans including Feasibility study of Adaptation measures used as references to select most suitable techniques (drip irrigation system, water meters, solar energy resources for deep wells etc.) of ecosystem based adaptation taking into account of hydrological and ecological conditions of each target soum and for further planning of the project activities. | S
|  | Outcome 3: Institutional and policy capacity strengthened to support Ecosystembased Adaption replication, monitoring, and enforcement for critical watersheds Institutional and policy improvements | Capacity of target and relevant stakeholders strengthened to develop and implement EbA strategies and River Basin Management Plans at two target areas. | Two RBAs were supported in establishment and capacity building both in terms of infrastructure and technical capacity. With the policy documents including EbA strategy framework and IWRM Plans for two project target basins, the Aimag and Soum government, as well as key stakeholders are enabled for appropriate planning and implementation of development with consideration of climate change challenges. Series and sets of advocacy and capacity building activities and products were provided to the target site institutions and key stakeholders. | S
|  |  |  | Overall Rating | S
|  | Name: | Chimeg Junai, Programme Analyst
|  | Email: | chimeg.junai@undp.org
|  | Progress on Key Milestones | Expected Progress | Progress to Date | Rating
Other |  | See above.
Overall Rating
Name:
Email:
|  | Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words | Overall, the project achievements were satisfactory in terms of products and outcomes planned in the reporting period. The main reason for the low disbursement of the allocated AF funding (71%) is that the project used almost all remaining committed TRAC funds in 2013 totalling to USD 483,878.30. That will mean that in the next years until end of the project, only AF funding will be spent. Major studies and assessments including baseline survey, vulnerability and risk assessments and economic valuation study were conducted, finally setting the benchmarks and completing the baseline stage. Key findings of the studies and assessments built solid base for development of the River Basin Management Plans at two River Basins and EbA Strategies for target ecoregions. The IWRM Plans are officially adopted by all 3 target Aimag Parliaments enabling funds allocation by the central and local governments for immediate implementation of the plans. A total of USD 3.3 million were committed by the target aimags and soums, showing local ownership for and adding value to the adaptation interventions. Nationwide hydrological monitoring network expanded as a result of establishment and capacity building of 2 RBAs, 3 new posts for surface water monitoring and 1 glacier base camp (the 3d in the country), as well as through data gathering systems and data base improvement with the support of the project, and broad involvement of local communities in the monitoring activities (17 monitoring groups) . In general, the quality and relialibility of water and glacial data collection have been significantly increased compared to previous years, as acknowledged by relevant experts of NAMEN. A national level policy document mainstreaming climate change adaptation/EbA in sectoral decision-making and policy frameworks will be developed in 2015 based on the recommendations from the series of discussion workshops on climate change mitigation, adaptation measures and strategic planning with the involvement of i) Agricultural sector, ii) Water resource sector, iii) Forest sector which will be held in second half 2014. 1st round of Economic Valuation Study for Kharkhiraa/Turgen and Ulz river basins was finalized, assessing the impact of climate change on the economies of two disparate river basins in Mongolia. Team of scientists have used ecological models to project the future conditions of the climatic and hydrological regimes. Subsequently, this information has been used to forecast the conditions of pastureland, agricultural land, forest land and habitat for wildlife in 2020, 2050 and 2080 respectively. However, the study report is not complete yet due to insufficient experience of the national team in the field of economic valuation of ecosystem servises, EbA and cost benefit analysis with consideration of CC. With facilitation of the RBAP and the regional Technical Advisor, completion of the study and finalization of the report is continued under guidance of Ms. Wang, Professor and Deputy Director, Center for Chinese Agricultural Policy, Chinese Academy of Sciences. The report is expected to be finalized in the next months and considered to serve as a template for similar coming efforts from ECCA’s other 10 countries.
Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major objectives/outcomes for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Project actions/activities planned for current reporting period are progressing on track to achieve most of its major objectives/outcomes with only minor shortcomings.
Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant objectives/outcomes, but with either significant shortcomings or modest overall relevance.
Project actions/activities planned for current reporting period are not progressing on track to achieve major objectives/outcomes with major shortcomings or is expected to achieve only some of its major objectives/outcomes.
Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major objectives/outcomes.
Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its objectives/outcomes.

## Rating-2012 (hidden)
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager / Coordinator: |  | Project Objective is to maintain the water provisioning services supplied by mountain and steppe ecosystems by internalizing climate change risks within land and water resource management regimes.
|  | Inception Phase of the Project completed |  | Inception Phase activities commenced in April, 2012. Within this phase, recruitment of the Project staff at both at Ulaanbaatar and local levels, the Inception workshop and Local stakeholder consultations were held. |  | Inception Phase activities commenced in April 2012 with establishment of the Project office and recruitment of team. As the implementing agency of the Project, the Ministry for Nature, Environment and Tourism (former MEGD) made a room available for the Project office. The Project was successfully organized the Inception Workshop on June 15, 2012 in the capital city, Ulaanbaatar, Mongolia. More than 90 participants representing the Government, relevant NGOs, and key stakeholders of the Project target areas were attended. In addition to the workshop, Local stakeholder consultations were held in both target landscapes between May 20 and June 3, 2012. The objective was to introduce the project design and underlying concepts of Ecosystem based Adaptation and provide background information on the status of water resources, ecosystem vulnerability to climate change impacts as well as the Adaptation Fund in the context of global climate finance mechanisms. | S
Outcome 1: Landscape level integrated land use and water resources monitoring and planning system focused upon reduction of ecosystem vulnerability to climate change.
|  | Strategic environmental assessment, including climate change considerations, conducted for target landscapes to document threats to ecosystem function and resilience and provide recommendations for avoiding and mitigating impacts. |  | 1. Baseline inventory/assessment (ecological and socio-economic) as a basis for the development of Ecosystem-based Adaptation Strategies for the target landscapes and River Basin Management Plans were completed. Apart from that, in cooperation with the National Agency of Meteorology and Environmental Monitoring (NAMEM), the Project has gathered all the required data as a basis of long term of environmental monitoring at target regions. 2. Vulnerability and Risk Assessment as a basis for developing EBA Strategies for the target landscapes and estimate the catchment surface and groundwater use balance in target River basins for developing RBMP are progressed. |  | 1. Baseline studies were conducted during the period from September 2012 to April 2013. The report on baseline studies includes collection, analysis of all related information and data and compilation reflecting the current situation on: (i) ecological condition including information on surface and ground water quantity and quality, wildlife, grassland, soil, forest, climate and geography; (ii) socio-economic condition including institutional capacity, policy and legislation framework. A data base with more than 170 indicators of the ecological and socio-economic sectors in targeted sites of the Project were being evaluated. From this a number of potential indicators were identified. The results of these studies will feed into development EbA landscape Strategy and RBMP. 2.The Project initiated Vulnerability and Risk assessments as a basis for development of EbA Strategy and RBMP as well as clarification of national capacity needs, which are keys to successful implementation of adaptation techniques in target areas. The assessment will be done compliant with the national environmental legislation and standards and use of environmental impact assessment methodologies, statistical analysis tools such as checklist, matrix analysis, and dynamic models (HBV, Century DAYCENT, NICHE, DSSAT, Maxcent ) and GIS system tools. The assessment will cover major components such as ecological vulnerabilities and risks, socio-economic vulnerabilities, the water use balance calculation and Climate change risk assessment (CCRA) of ecological and socio-economic sectors. Water use balance will be estimated with Vulneravility and Risk assessment with inclusion of surface and groundwater resources of the basin using existing outputs of baseline studies. | S
|  | Economic valuations completed summarizing landscape level costs and benefits of EBA. |  | Project's initial economic valuations initiated comparing the landscape level costs and benefits of EBA approaches. The purpose of the study is to assist in identification of the economically efficient adaptation strategies to climate change taking into full account the value of ecosystem services and biodiversity and will be a flatform to prioritize EBA local level strategies. |  | Hence the evaluation requires cohesive approach and expertise using existing and newly simulated climate prediction and ecological models, the national experts are involved on-job training, learning by doing and wide discussions. International expert shared and trained national experts and relevant stakeholders on cost and benefit principles, practices, data collection, processing and interpretation of results. Regional climate simulation has completely finished over targeted river basins using A1B scenario with 10km spatial resolution for the periods 2011-2030, 2046-2065 and 2081-2100 through the dynamic interpretation on the outputs of the 3 GCMs. Initial output estimates of ecological models (MAXENT, CENTURY, HBV and Snow melt runoff model ) are generated using the climate simulated data on soil, forest, water and wildlife analysis (distribution, size/quantity and quality with regard of human settlements and influences etc.). Therewith, the Project was recruited Economics consultant (EC). The EC will work with the International expert, Climate Modeling expert (CME) and the local team to work on models of the economic values of ecosystem services under alternative potential development scenarios, based on the ecological analysis of the CME. EC is drafted a meteodology of economic analysis. Questionnaires in different types of research design such as water use, forest, wildlife and pasture/ livestock were prepared by experts of the study as inputs to the economic models. Relevant interviews were conducted by soum coordinators over target landscapes of the Project between April and May, 2013. Totally 1800 questionnaires were collected with the aid of a structured questionnaires on production inputs and output will be analyzed using descriptive statistics. The economic model would then evaluate the outcome of using the current management strategy in each future climate. | S
|  | Ecosystem-based Adaptation integrated within land use and water resources monitoring and decision-making system in two eco-regions. |  | The Project provided the NAMEM with technical support with aim to expand the monitoring network. |  | 1. Within the framework, the Project initiated procurement of required equipments such as Automatic Weather Station, ice drill, portable water lab, current meter with synthetic propeller, water-level sensor in order to improve the quality and accuracy of monitoing works for glaciers run-off, and surface and ground water measurements. 2. Constructing 12 m2 sized energy efficient dwelling for Glacier Base Camp in Kharkhiraa mountain is in progress. In cooperation with the GEF funded "Building Energy Efficient" Project implemented by UNDP, suitable design and technology for construction was identified. The site to construct dwelling is expected to be defined by HAMEM researchers in June, 2013. | S
Outcome 2: Landscape level adaptation techniques maintaining ecosystem integrity and water security under conditions of climate change.
|  | Local level climate change adaptation assessment and monitoring implemented in two target watersheds. |  | Soum level capacity assessment was carried out by a professional team. |  | With this assessment, local capacity with regard to EBA and IWRM activities was identified by categorized target groups such as soum and aimag level officers, herders, and NGO-s. Based on this, needs of trainings were identified. The assessment indicates that the knowledge and skills of local community is limited to undertake local level measures of EBA in a sustainable manner. In addition, the assessment pointed out that existing terms of references for soum level officials did not clearly state the duties and responsibilities concerning effective application of EBA concepts and participatory approaches for their works. Therefore, in cooperation with Aimag governments, the Project will develop Soum level EbA plans which will allow to revise and update of the existing terms of references for officials in charge of agriculture, environment and land management in order to reflect the above. | S
|  | Integrated landscape level Ecosystem-based Adaptation management action plans operational within two target watersheds. |  | 1. As preperation phase, based on Soum level capacity assessment, "Local level capacity building program" was developed to be realized throughout the Project lifetime. 2. Soum level project coordinators were trained on principles and practices of EBA and IWRM 3. A national consultant for conducting training on community based natural resource management and community-led impact monitoring techniques is selected on a competivie basis. |  | 1. In accordance with the programme, the Project intends to prepare local level trainers (resource persons) specialized in EbA and IWRM planning. Environmental Units (ranger, officer in charge of land use, environmental inspector, meteorologist, veterinarian etc.) and the Project Soum Coordinators will be trained as trainers, who are expected to take a lead in the implementation of landscape level adaptation techniques at Soum level. 2. For building technical capacity of Soum level project coordinators, a training event took place in March, 2013 at the PIU in Ulaanbaatar. The main objective of the training was to build skills and knowledge of all soum coordinators in EbA strategy and IWRM principles and practices, and develop detailed workplan for year of 2013 on main activities of the Project. As a result of the training, trainees gained advanced level knowledge and skills on EBA and IWRM approaches and applications that have internationally and nationally been recognized and became familiar with participatory approaches as vital tools and techniques to motivate and mobilize local community for better collaborative actions and enhanced natural resource management. In addition, the participants were able to update their knowlegde and advanced skills on EBA and IWRM concepts and techniques. The trainees have been provided with all the necessary hand-outs and printed materials and will serve as trainers in their localities when necessary. 3. According to a ToR, the recruited consultant is expected to start duties starting from June, 2013 with objective of preparing local level trainers in Community Management Natural Management and Community-led Impact Monitoring. Main benefitiares will be environmental units, middle school teachers, environmental NGOs and Soum coordinators who in return train locals, students , farmers and herders. | S
|  | Suite of physical techniques to improve ecosystem resilience established in two target watersheds. |  | Feasibility study of physical techniques to improve ecosystem resilience to climate change will be conducted in 2013. Based on the study, required actions will be undertaken step by step. |  | TOR on feasibility study was drafted for recruitment process. The study will start in August, 2013. | S
|  | Regulatory and financial management techniques for improving climate change resilience implemented within two target watersheds. |  | As a preparation work, specific trainings on best practices on EbA at international and national levels, IWRM and sustainability of Community-based Natural Resources Management will be organized in 2013. After implementing these capacity building activities, actual EbA measures will be initiated in 2014 through implementing Small Grants Programme in target soums. |  | Training on funding mechanisms of Small projects for establishment of EbA groups and mobilization of existing cooperatives/ nuhurluls (Forest User Groups, Pasture User Groups, Herder Groups) will be held in July, 2013 with combination of training on Community-based Natural Resource Management and CLIM. Associated legal environment on establishment of cooperatives/nuhurluls, its sustainability, rights and responsibilities of members and monitoring will be introduced to the targeted trainers. | S
Outcome 3: Institutional and policy capacity strengthened to support Ecosystembased Adaption replication, monitoring, and enforcement for critical watersheds
|  | Ecosystem-based adaptation approaches mainstreamed in national resource use planning and implementation mechanisms. |  | Assessment of Institutional Capacity for mainstreaming EBA approaches into development policy and planning of key agencies was completed. With the project support, capacities of several institutions including Ministry of Environment and Green Development, National Committee on Climate Change, Climate Change Coordination Office and Agency of Meteorology and Hydrology were assessed. Based on the assessment, specific recommendations were developed for ensuring better Instiututional capacity to mainstream EBA approaches into state policy and coordination. Furthermore, Capacity building programme was developed. |  | Technical and human capacities of relevant state institutions with strong engagement in climate change issues were assessed. In additon, relevant laws and national programs (The Laws on Environmental Protection, Forest, Fauna, Water, Air, Environmental Impact Assessment) were reviewed for further refinements in order to incorporate EBA concepts. Based on provided recommendations, the Project is cooperating with the MEGD to refine several significant regulations including water and forest use fee to ensure improving mentality for natural resource users. Finally, a draft Capacity building program was developed and submitted to the Minister of Environment and Green development for further consideration. | S
|  | Institutional support for integrating climate change risks in land and water resource management planning. |  | Public Awareness Programme disseminating EBA knowledge and information to general public was developed. Within the Programme, handbooks on EbA and IWRM were developed by professionals. As a complimentary part of the handbooks, training modules/ curriculums reflecting specific topics and delivering approaches were included to be used for different knowledge level users and trainers. These user friendly handbooks and associated training modules will be used as reference materials for further trainings. |  | Ways and methods to foster general public education with regard to EBA were identified and recommended. This will be used as a basic document to be considered and followed up to deal with public awareness raising issues within the Project objective. The program includes specific topics and activities designed for different knowlegde-level users. Implementation mechanisms and form of engagement of responsible parties to be considered were defined in detail and recommended. This is a basis for futher public awareness activities of the Project. As follow up activities of Public Awareness Programme, the products are designed as set of training packages including handbooks and training modules. The handbooks include general concepts and principles of EBA and IWRM and clear exapmles of national and international best practices, and pilot activities. Those activities can be underaken in the Project target soums. | S
|  |  |  | According to the Assessment of Institutional Capacity of key agencies, it is stated that it is necessary to improve relevant regulations of some Laws in order to mainstream EbA approaches into development policy and planning. Regarding this demand, totally 6 regulations of relevant Laws was newly developed and/or reformulated. |  | Set of Environmental Laws were revised and newly developed and approved by the Parliament of Mongolia in 2012. The project supported the development of following regulations in order to enhance the enforcement of newly approved Laws. Overall aim of these regulations is to promote economic entities that apply environmental sound technology and efficient use of water through provision of incentives. The regulations are expected to be a useful means to build proper mindset for sustainable us of natural resources. For implementation of Law on Water Pollution Fee: following 3 Regulations were reformulated and/or newly introduced: 1. Regulation on Household waste water tariff (consumers) 2. Regulation on setting water pollution charge 3. Regulation on Discount and excemption of water use charge and economic entity and organizations to be benefited from discount or excemption, and Setting of discount percentage: For implementation of Law on Forest: following 3 Regulations were reformulated and/or newly introduced: 1. Proposal for Regulation of procedure for the payment to owner for forest protection, restoration and nursery in case of timbering woods according to the permission of state authorized organization. 2. Proposal for Regulation on commercial activities undertaken in special purpose forest area of the State. 3. Proposal for common regulation of incentives | S
|  | Program for up-scaling best practices developed and implemented. |  | Development of Climate change website for distributing climate change and EbA related information with the aim to improve public awareness on climate change and EbA. |  | The Climate change coordination office (CCCO) had the webpage that was out-of-date, difficult to access and hard to modify. Therefore, a fully functional and easy to access web page was crucial to design which now became important tool and platform to share and disseminate information, knowledge and experience sharing, as well as to publicize CCCO and the Project activities and achievements to the public. The Climate change coordination office (CCCO) website is now accessible beginning on December 25, 2012 | S
| Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500) |  |  |  |  | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
|  | Name: | Tuya Tserenbataa, National Project Coordinator
|  | Email: | tuya.tserenbataa@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The Project has initiated to establish ecological and socio-economic benchmarks and baseline data as inputs for further planning and policy development documents such as River Basin Management Plans (RBMP) and EbA strategies. Programs and Action Plans for institutional and human capacity development, and public awareness and advocacy will be used further as significant guidance to implement a series of trainings with relevant topic and targeted stakeholders during the Project cycle. For the reporting period, training guidelines on RBMP, EbA principles and practices at local level were developed to increase knowledge and experience of stakeholders and used for training of trainers in target areas. In accordance with set of Environmental Laws newly amended and approved in 2012, the relevant 3 regulations of Law on water pollution fee and 3 regulations of Law on Forest were developed with the technical support of the Project. Overall aim of these regulations is to promote economic entities that apply environmental sound technology and efficient use of water, protection of trees and restoration of forest through provision of incentives. The regulations are expected to be a useful means to build proper mindset for sustainable use of natural resources. There is no negative progress so far observed.
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency |  | Outcome 1: Landscape level integrated land use and water resources monitoring and planning system focused upon reduction of ecosystem vulnerability to climate change. |  | Inception phase including initiation of establishment benchmarks as a basis for the development of Ecosystem-based Adaptation Strategies for the target landscapes and River Basin Management Plans are completed through contracting of experts teams to carry out assessments with wide discussions and carry out learning by doing and experience sharing trainings. Apart from that, preparation of establishment of additional surface water monitoring posts in 3 sites of the river basins and 1 glacial observation post in Western area was initiated in cooperation with the National Agency of Meteorology and Environmental Monitoring (NAMEM) for the purpose expansion of existing environmental monitoring network. Economic valuation of the targeted landscapes in two water sheds was progressed. |  | 1. The baseline study on ecology and socio-economic conditions of the two River basins was completed, final report submitted in March/April 2013 that allowed to revise and update the Project indicators in the Logical framework as well. 2. Economic valuation is underway and it requires cohesive approach to complete. The national consultants are progressing and benefiting with learning by doing, class room and on-job training and discussions and sharing experiences. Basing on completed climate simulation the cost and benefit analysis of the water, soil, pasture, forest and wildlife will be completed in 2013 by use of ecological models. 3. The Project support in expansion of environmental monitoring network was conducted by initiation of procurement of equipments; authomatic weather station, portable laboratories for water quality, small house and measuring tools/equipments. NAMEM included in its plan to establish a new station at Uvs Lake in 2013, which will delegate personnel for the water and glacial observation posts in western target area. | S
|  | Outcome 2: Landscape level adaptation techniques maintaining ecosystem integrity and water security under conditions of climate change. Baseline and benchmarks for the development of the River Basin Management Plans at two River Basins and EbA Strategies at target ecoregions completed. |  | Two RBMPs and two EbA strategies will be developed and implemented |  | Preparatory works for development and implementation of the RBMPs and EbA strategies are aligned with planning of MEGD to establish and operate River Basin Administrations (RBA) at Ulz river and Turgen/Kharkhiraa rivers with consultations. As a result of it and Capacity development needs plan, series of trainings on IWRM, EbA strategy, hydrology, ecology and environmental policy for the staff of newly established RBAs and technical assistance on water and environmental monitoring are planned in 2013. Compilation of ecological and socio-economic conditions and series of discussions with relevant parties resulted progress report that was used in update of the Project Indicators as well. | S
|  | Outcome 3: Institutional and policy capacity strengthened to support Ecosystembased Adaption replication, monitoring, and enforcement for critical watersheds Institutional and policy improvements |  | Capacity of target and relevant stakeholders strengthened to develop and implement EbA strategies and River Basin Management Plans at two target areas. |  | A number of public awareness materials on EBA and River Basin Management principles and practices and climate change adaptation produced and disseminated, as a booklets/handouts and through CCCO website. A total of 6 regulations that support enforcement of 2012 amended/approved Laws on Fees on Water pollution and Law on Forest and were developed with the technical support of the Project. | S
|  | Inception phase completed |  | Local needs assessment and adaptive management conducted. Recruitment of Project staff and set up of office completed. The Inception workshop held with participation of relevant stakeholders. |  | The Project launching was succefully conducted with participation of relevant stakeholders to introduce the Project goals and objectives and its implementation mechanisms; oversight, monitoring and Logical framework with indicators. The Project staff were fully recruited at Ulaanbaatar and local levels. 3 aimag coordinators were appointed and 9 Soum coordinators and 9 Soum drivers were recruited. Administrative Offices of Aimag and Soum Governments cooperate on implementation of the Project and provided work spaces for the Soum Coordinators. The Project Board and Techical Committee were established and the First Project Board Meeting was held to introduce Project Board (PB) roles and responsibilities and the progress of the Project and to get PB comments on 2013 Annual work plan. Technical Committee was called to meet three times to review and comment on progress of baseline studies and economic evaluation. | S
[6 empty] | Overall Rating | S+
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
|  | Name: | Chimeg Junai, Programme Analyst
|  | Email: | chimeg.junai@undp.org
|  | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other |  | See above.
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
|  | Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | In overall, the Project achievements were satisfactory in terms of products and outcomes planned in the reporting period. It was important to set up the Project office with full staff both at central and local level to ensure smooth run of the implementation. Priority actions were to collect and compile baseline data on ecology and socio-economic conditions of the target areas. Other preparatory works such human and technical capacity building, and public awareness programs were completed. Training guidelines were developed for stakeholders who will play a main role in development of the RBMP and EbA strategies. Moreover, advocacy of the Project was done with active involvement of relevant bodies of MEGD. During the reporting period, few challenges were encountered to Project team. These were structural and organizational changes of the Ministries and agencies after Parliamentary election that resulted delays of some processes namely Project Board establishment as well as organizing meetings, workshops and discussions within the planned timeframe.
Rating Definitions
[5 empty] | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major objectives/outcomes for given reporting period, without major shortcomings. The project can be presented as “good practice”.
[5 empty] | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major objectives/outcomes with only minor shortcomings.
[5 empty] | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant objectives/outcomes, but with either significant shortcomings or modest overall relevance.
[5 empty] | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major objectives/outcomes with major shortcomings or is expected to achieve only some of its major objectives/outcomes.
[5 empty] | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major objectives/outcomes.
[5 empty] | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its objectives/outcomes.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator |  | Baseline | [7 empty] | Progress since inception | [6 empty] | Target for Project End
Project overall Indicator | Mean annual in-stream summer 30-day base flow maintained (not decreased) in two project sites (Kharkhiraa/Turgen, Ulz) |  |  | Turgen River: |  | Kharkhiraa River: |  | Ulz River: (the current monitoring station (Chuluunkhoroot) for the Ulz river is located at a channel without water.) |  |  | Turgen River: |  | Kharkhiraa River: |  | Ulz River: (the current monitoring station (Chuluunkhoroot) for the Ulz river is located at a channel without water.) |  |  | Kharkhiraa River: 2.43 m3/sec
|  |  | Years | 2012* |  | 2012 |  | 2012 |  |  | 2013 |  | 2013 |  | 2013 |  |  | Turgen River: 1.98 m3/sec
|  |  | Summer minimum discharge, m3/s | 1.67 m3/s |  | 4.53 m3/s |  | 0 m3/s |  |  | 1.57 m3/s |  | 4.4 m3/s |  | 0 m3/s |  |  | Ulz River: 0.10 m3/sec (at Chuluunkhoroot)
Mean annual in-stream summer 30-day discharge in Kharkhiraa/ Turgen and Ulz River basin is determined by National Agency of Meteorology, Environment and Monitoring. The Ulz river started to flow again at Chuluunkhoroot soum on 10th September, 2013, due to rainy years in 2012 and 2013. Its discharge was 0.3m3/sec.
| Surface water quality improved or maintained in two project sites (Kharkhiraa/Turgen, Ulz) |  | Water chemical analysis (long term average) | Turgen River |  | Kharkhiraa River |  | Ulz River |  |  | Turgen River |  | Kharkhiraa River |  | Ulz River |  |  | 5% improvement on average
|  |  |  | Sep,2012 |  | Sep,2012 |  | Sep,2012 |  |  | Sep,2013 |  | Sep,2013 |  | Sep,2013
|  |  | Suspended solids (mg/l) | 16 |  | 40 |  | 8.5 |  |  | 10 |  | 14 |  | 8.7
|  |  | Permanganate COD (mg/l) | 1.4 |  | 7 |  | 5.28 |  |  | 0.6 |  | 0.8 |  | 15.5
|  |  | NH+4 (mg/l) | 0.42 |  | 0.54 |  | 0.083 |  |  | 0.22 |  | 0.07 |  | 0.42
|  |  | Total mineral P (g/l) | 0.34 |  | 0.45 |  | 0.79 |  |  | 0.008 |  | 0.006 |  | 0.033
|  |  | Total Fe (mg/l) | 0.23 |  | 0.14 |  | 0 |  |  | 0.02 |  | 0.06 |  | 0
Annual surface water quality and composition in Kharkhiraa/ Turgen and Ulz Rivers were audited through Local Meteorological Office in 2013. Data are collected annually at same sampling spots, and the emerging average is expected to be compared with the baseline.
|  |  | Soil nutrient, organic carbon (matter) pool | Turgen/ Kharkhiraa Rivers basin |  |  | Ulz River basin |  |  |  | Turgen/ Kharkhiraa Rivers basin |  |  | Ulz River basin
|  |  | Place name | [7 empty] | Ulaangom soum | Khovd soum | Naranbulag soum | Choibalsan soum |  | Dashbalbar soum | Gurbanzagal soum
|  |  | Years | 2012 |  |  | 2012 |  |  |  | 2013 |  |  | 2013
|  |  | Type of soil name | Dry steppe pale-brown soil | Swampy soil brown soil | Saline soil | Dark kastanozem soil |  | Light kastanozem soil |  | Dark | Dark brown | Pail brown | Meadow |  | Dark brown | Saliny
|  |  | Depth, cm | 0-20 | 0-20 | 0-20 | 0-20 |  | 0-20 |  | 5-15 cm | 5-15 cm | 5-15 cm | 5-15 cm |  | 5-15 cm | 5-15 cm
|  |  | Humus % | 0.8 | 22.1 | 5.8 | 5.6 |  | 3.2 |  | 8.2 | 4.6 | 0.4 | 2.1 |  | 2.6 | 2.9
|  |  | pH | - | - | - | - |  | - |  | 3 | 6.5 | 3 | 7.4 |  | 1.3 | 0
Total of 6 pilot sites were selected in 6 target soums that are visually different or with comparably lower yield than the healthy fields. Regular monitoring are conducted identifying chemical components and properties of soil characteristics. The demonstration activities/ adaptation local measures related with reforestation, decrease of degraded spots and or improvement of overloaded pasture, and sustainable farming at household level are expected to improve soil conditions in terms of contents of organic matter and fertility. Trends of soil composition and quality can be used to demonsrate the changes/ improvement that are resulted from the above measures. The soil data is updated on an annuall basis to enrich the database.
|  |  | Biological indicators, e.g., insect | Turgen/ Kharkhiraa Rivers basin |  |  |  | Ulz River basin |  |  | Turgen/ Kharkhiraa Rivers basin |  |  |  | Ulz River basin
|  |  |  | Type of indicators | Indicators name | Year | Population number | Indicators name | Year | Population number | Type of indicators | Indicators name | Year | Population number | Indicators name | Year | Population number
|  |  |  | Insects | (Ephemeroptera)- Ameletus inopinatus Eaton, 1887 | 2012 | ++ | (Ephemeroptera)- Baetidae-Baetis sp. | 2012 | ++ | Insects | (Ephemeroptera)- Ameletus inopinatus Eaton, 1887 | 2013 | ++ | (Ephemeroptera)- Baetidae-Baetis sp. | 2013 | ++
[5 empty] | (Plecoptera)- Isoperla sp. | 2012 | ++ | (Plecoptera)- Perlidae-Agnetina sp. | 2012 | ++ |  | (Plecoptera)- Isoperla sp. | 2013 | ++ | (Plecoptera)- Perlidae-Agnetina sp. | 2013 | ++
|  |  | Remarks | Status: +-rare; ++ normal; +++- abundant | [6 empty] | Status: +-rare; ++ normal; +++- abundant
In order to encourage locals and students participation in water quility monitoring, 17 local monitoring groups are established with support of the project in 17 soums in the 2 target basins, in addition to the 8 surface water monitoring posts. The monitoring groups obtained knowldegde to carry out water quality tests using easy to apply guide developed by the Asia Foundation through series of trainings. The test kits base on experimenting on easy to determine insects and larvaes live in polluted or fresh water, pH, density etc.
|  |  |  | Turgen River |  | Kharkhiraa River |  | Ulz River |  |  | Turgen River |  | Kharkhiraa River |  | Ulz River
|  |  | Years | Sep, 2012 |  | Sep, 2012 |  | Sep, 2012 |  |  | Sep, 2013 |  | Sep, 2013 |  | Sep, 2013
|  |  | Surface water temperature (Celsius) | 13 |  | 12 |  | 20.5 |  |  | 14 |  | 12.5 |  |  | 19
Data on surface water temperature taken in September 2013 is provided by each target Aimag Meteorological offices in 2013 and this will be repeated each following years.
|  |  | Glacier Base Camp in the Turgen Mountain (at the 3500m above the sea level) | [7 empty] | Glacier Base Camp in the Turgen Mountain (at the 3500m above the sea level)
|  |  | Years | [7 empty] | Data measured by 27 Oct 2013
|  |  |  | Pile | Altitude (m) | Glacier depth (m) |  | Snow depth (m) |  |  | Pile | Altitude (m) | Glacier depth (m) |  | Snow depth (m)
|  |  | I direction | I glacier pile | - | - |  | - |  |  | I glacier pile | 3024 | 1,28 |  | 0,48
|  |  |  | II glacier pile | - | - |  | - |  |  | II glacier pile | 3048 | 1,48 |  | 0,48
|  |  | II direction | I glacier pile | - | - |  | - |  |  | I glacier pile | 3124 | 1,19 |  | 0,28
|  |  |  | II glacier pile | - | - |  | - |  |  | II glacier pile | 3124 | 1,26 |  | 0,21
|  |  | III direction | I glacier pile | - | - |  | - |  |  | I glacier pile | 3172 | 1,40 |  | 0,46
|  |  |  | II glacier pile | - | - |  | - |  |  | II glacier pile | 3188 | 1,74 |  | 0,68
|  |  | IV direction | I glacier pile | - | - |  | - |  |  | I glacier pile | 3254 | 1,66 |  | 0,67
Glacier monitoring camp has been established in summer 2013 with support of the project in the southern part of the Turgen mountain, at the altitude of approx. 3000 meters. First measurements are taken twice in July and October 2013. In 2014, the mesurements will be done on a monthly basis between July and October.
Indicator of outcomes | 1.1 Number of integrated strategies/ management plans for river basins approved and adopted by National and Aimag Governments |  | Operational integrated strategies/management plans for river basins(or sub-basins) | [5 empty] | Baseline: 0 |  | 2 Ecosystem-based adaptation (EbA) strategy framework developed providing guidelines for adaptation measures on the ground for the Altai Mountains/Great Lakes Depression and Eastern steppe/Mongol Daguur and is submitted to the MEGD for endorsement. 2 Integrated Water Resource Management (IWRM) plans officially adopted by all 3 target Aimags (approval by Uvs Parliament on November 7, 2013 and by Khentii and Dornod aimags on 11 and 12 of November 2013 respectively) and implementation initiated from the end of 2013. IWRM plan of Ulz will be endorsed by the Minister of Environment and Green Development (MEGD) in compliance with the Article 4.8 of the “Law on water”. |  |  |  |  | Progress: 4 |  | at least 2
| 1.2 Number of Aimag governments monitoring, assessing, and reporting to MEGD and relevant agencies (water authority, National Climate Change Coordination Office) on integrated river basin management measures |  | Number Aimag Governments implementing integrated strategies/management plans for river basins: | [5 empty] | Baseline: 0 |  | 2 River Basin Administrations (RBA) in the two target basins report to MEGD (to RBA Division) on all related measures on water users and consumers following the Law on Water, Article 7.5 to update the national level water database. 3 target aimag Meteorology and Hydrology Agencies and aimag Environmental protection departments report to MEGD on actions taken in relation to meteorlogy and hydrology within the integrated river basin management. |  |  |  |  | Progress: 5 |  | at least 3
| 1.3 Total hectares included within protected areas system in the two project sites (Kharkhira/Turgen, Ulz) |  | Altai Mountains / GLB: | [5 empty] | 37,420 km² |  | No changes during the reporting period. However, the Project initiated an assessment on potential expansion of protected area in order to maintain ecosystem integrity and services in Kharkhiraa/Turgen and Ulz river basin in 2014. This assessment will explore possibilities to expand the specially protected areas and mining impact to PAs, and improving community based tourism. |  |  |  |  | 37,420 km² |  | Altai Mountains / GLB: 39,420 km²
|  |  | Kharkhiraa/Turgen Watershed: | [5 empty] | 800 km² | [6 empty] | 800 km² |  | Kharkhiraa/Turgen: 1,000 km²
|  |  | Eastern Steppe: | [5 empty] | 42,676 km² | [6 empty] | 42,676 km² |  | Eastern Steppe: 44,676 km²
|  |  | Ulz Watershed: | [5 empty] | 3,120 km² | [6 empty] | 3,120 km² |  | Ulz: 3,750 km2
| 2.1 Number of Soums in target area considering EBA measures/Integrated River Basin Management into their annual land-use planning and in Soum development plans and strategies. |  | Total number of Soums in target area considering integrated River Basin Management/ EbA measures in their annual land-use planning and in Soum development plans and strategies: | [5 empty] | Baseline: 0 |  | 17 soums in target river basins considered Integrated River Basin Management in their Soum development plans including issues of provision of safe drinking water, water sources' protection and restoration. The principles and practices of Ecosystem-based adaptation measures are already reflected in Aimag level planning in regard to areas such as Water, Pasture, Forest, Riparian area, Implementation arrangement, Ecosystem cultural services and Rehabilitation of ecosystems and resilience. At the soum level the consideration of EbA measures in the soum land use planning is in progress in all 17 target soums by developing Soum level landscape EbA plan. In order to strengthen the human and technical capacity of Soum and Aimag Land management officers (26) two level trainings were organized by provision of Geodesy and GIS methodology and practical experiences in May, 2014 in cooperation of State Agency of Land Affairs, Geodesy and Cartography and National University of Science and Technology of Mongolia. Besides that it provided new concepts of landscape based land use planning including sustainable pasture use, restoration and rehabilitation of degraded pasture lands. |  |  |  |  | Progress: 17 |  | 17
| 2.2 Water use efficiency improved to maintain ecosystem integrity as measured by: | 2.2.1 Amount of surface water extracted for irrigation in project sites (cubic meter) | Kharkhiraa/Turgen River basin: | [5 empty] | 0 |  | Currently, drip irrigation systems are being installed in 9 project sites in order to improve efficiency of water usage for agricultural irrigation. Water meters will be installed in order to enable comparison between drip and regular irrigation systems, thus the amount of water saved through drip irrigation. |  |  |  |  | 0 |  | Total extraction approx. 20% decreased (while maintaining sustainable agricultural practices through appropriate irrigation technology )
|  |  | Ulz River basin: | [5 empty] | 0 | [6 empty] | 0
|  | 2.2.2 Number of monitored wells increasing ground-water consumption efficiency in project sites | Kharkhiraa/Turgen River basin: | [5 empty] | Baseline: 0 |  | A total of 20 wells (location and name) to be repaired and monitored were identified by Feasibily study. Out of these, 5 specific wells' were prioritized to be repaired and monitored. The selection was based on the importance of the location for Demoiselle Crane and Mongolian Gazelle habitat. Training of the trainers will be conducted in June 2014 covering issues of ground water importance, GW resource saving technologies. |  |  |  |  | Progress: 3 |  | 12
|  |  | Ulz River basin: | [5 empty] | Baseline: 0 | [6 empty] | Progress: 2 |  | 70
|  | 2.2.3 Small scale Rain and snow melt Water harvesting | No water harvesting activities | [5 empty] | 0 |  | Detailed design drawing of construction (DDDC) of small scale rain and snow melt water harvesting to be established in Kharkhiraa, Turgen river basin will be conducted in June -July, 2014. The actual construction is expected to be completed in November 2014. |  |  |  |  | 0 |  | Number of small scale water harvesting reservoirs
| 2.3 Land use practices and climate change resilience improved as indicated by: | 2.3.1 Total hectares of riparian and wetland habitat restored with native vegetation within project sites | Kharkhiraa/Turgen River basin: | [5 empty] | Baseline: 0 |  | The areas and sites to be rehabilitated were identified by the Feasibility study (FS). Relevant field level activities are commenced in 2014, starting with small scale tree nurseries in Kharkhiraa, Turgen and Ulz river basins covering 10 ha of riparian area. Local communities are being provided with native seed and seedlings and on the site trainings on tree nursery. Local communities will collect native seeds in autumn for the next season planting under professional guidance of a national consultant. |  |  |  |  | Progress: 10 ha |  | 1,250 ha
|  |  | Ulz River basin: | [5 empty] | Baseline: 0 | [6 empty] | Progress: 10 ha |  | 2,250 ha
|  | 2.3.2 Springs protected with livestock exclosures, Livestock watering and access to creeks managed with appropriate facilities/fencing | Kharkhiraa/Turgen River basin: | [5 empty] | Baseline: 0 |  | As identified by the Feasibility Study, 9 springs out of proposed 30 are planned to be protected in 2014 applying EbA principles and environmentally sound techniques for increased and safe drinking water supply for local population and livestock. Simple desing and other technical estimations will be completed by June to enable demonstration training to be held in July. |  |  |  |  | 0 |  | approx. 30% increase
|  |  | Ulz River basin: | [5 empty] | Baseline: 0 | [6 empty] | 0
|  | 2.3.3 Total area with improved pasture land management | Kharkhiraa/Turgen River basin: | [5 empty] | Baseline: 0 |  | In May 2014, a training for the land officers involving 28 participants from target aimags and soums was organized in cooperation with the National Agency for the land management, geodesy and cartography. The objective of the training was to strengthen land officers’ capacity to reflect EbA and sustainable pasture use principles into land management planning of their localities. As a consequence, a substtrained land officers are committed to have the increased area with an adequate pasture management. |  |  |  |  | 0 |  | 1,500 km2
|  |  | Ulz River basin: | [5 empty] | Baseline: 0 | [6 empty] | 0 |  | 12,000km2
|  | 2.3.4 Areas with Reforestation and improved forest management in Western target areas | 226 ha | [5 empty] | Baseline: 226 ha |  | The current area, 226 ha, includes forest areas with reforestation and area of cleaning and thinning. In 2014, reforested and improved forest management area will be increased by additional 10 ha, totaling 236 ha. |  |  |  |  | Progress: 236 ha |  | Western target areas: 236 ha (approx. 10% increase)
| 2.4 Decrease in average Rural Poverty rate for 17 Soums within the target watersheds. |  | Current poverty rate: Kharkhiraa/Turgen basin: | [5 empty] | 0.495 |  | No changes observed during the reporting period. The project is planning to initiate Small Grant Program in 2014 to enable livelihood diversification within target population. As a preparation phase, the required procedure and regulation is being developed by project team. In addition, on-site trainings including vegetable gardening and wool production with the aim to support value added production and developing business entrepreneur skills of low income locals. |  |  |  |  | 0.495 |  | Approx. 10% average decrease | Are you still working on this?/updated
|  |  | Average Poverty headcount for Ulz basin: | [5 empty] | 0.433 | [6 empty] | 0.433
| 2.5 Number of Small Enterprises established and operating successfully |  | Kharkhiraa/Turgen River basin: | [5 empty] | 312* |  | Currently, within the framework of project pilot activities, 9 local communities are engaging in tree nursery and sustainable agricultural business. Series of trainings and day to day guidance will be provided by the local coordinators in order to enable the target enterprices to get operational and financially sustainable. |  |  |  |  | 317* |  | 570 Small Enterprises at both project sites (appr. 5% increase).
|  |  | Ulz River basin: | [5 empty] | 237* | [6 empty] | 241*
| 2.6 Hydrological monitoring is strengthened |  | Monitoring posts for glacial run-off in Western project area: | [5 empty] | Baseline: 0 |  | One Glacier Observation Post was established in Turgen Mountains. Since the establishment of the post, observation data is being collected twice a year for snow melting monitoring and meso-scale climate study. According to relevant experts of NAMEN, quality and reliability of data collection have been significantly increased compared to previous years. In total, 3 surface water monitoring posts (1 in Kharkhiraaa, the west, 2 in Ulz, eastern target area) newly established with support of the project in addition to existing ones (in the west 3, in the east 3) in 2013. The operation staff (10) of the posts are accordingly trained. Project provided equipment including data logger, current meters and thermometers to 6 surface water monitoring posts (to 3 posts in the west and 3 posts in the east, including existing and newly established posts) and adequate training to the staff (totally 12 person) on the operation of the monitoring equipments. |  |  |  |  | Progress: 1 |  | At least 1 in Western target area; at least 2 surface water monitoring post in Eastern target area
|  |  | Kharkhiraa/Turgen River basin: | [5 empty] | Baseline: 0 | [6 empty] | Progress: 2
|  |  | Ulz River basin: | [5 empty] | Baseline: 0 | [6 empty] | Progress: 4
| 3.1 Number of River Basin Administrations (RBA) established and strengthened in target two watersheds |  | Operational RBAs: | [5 empty] | Baseline: 0 |  | Two RBAs, the Uvs Lake-Tes RBA and Ulz RBA, were established in 2013. The capacity of the RBAs are substantially improved through project support i) IWRM plan development; ii) provision of equipments; iii) provision of series of trainings to the staff |  |  |  |  | Progress: 2 |  | 2
| 3.2 Number of River Basin Councils (RBC) established and strengthened in target two watersheds |  | None of operational RBCs in target two watersheds | [5 empty] | Baseline: 0 |  | In 2013, 3 RBCs were established under the Water Law of Mongolia. These are the first 3 RBCs established in Mongolia. |  |  |  |  | Progress: 3 |  | 3
| 3.3 Number of staffs of relevant agencies and local governments trained in river basin management guidelines |  | 0 | [5 empty] | Baseline: 0 |  | The regional training titled “Implementing IWRM planning in a river basin” involved 70 participants, including experts of RBAs of “Khar lake-Khovd river”,“Khyargas lake-Zavkhan river” and “Uvs lake-Tes river” as well as decision makers of western 5 western aimags, Bayan-Ulgii, Khovd, Uvs, Zavkhan and Govi-Altai. |  |  |  |  | Progress: 70 experts |  | at least 21 experts including staffs of relevant agencies in each 21 aimags (provinces), and members of RBAs and RBCs.
| 3.4 Number of Soums replicating EBA measures and integrated river basin management principles and practices within the target eco-regions |  | 0 | [5 empty] | Baseline: 0 |  | The EbA measures guidelines for each 17 target soums will be developed by end of 2014. |  |  |  |  | Progress: 0 |  | at least 20
| 3.5 National mainstreaming of EBA as indicated by: | 3.5.1 Number of official government policy documents adopting EBA principles/practices | 0 | [5 empty] | Baseline: 0 |  | Four Policy documents, EbA strategy framework for two target basins including guidelines on adaptation measures implementation (2) and IWRM Plans (2) for 2 target river basins were developed in 2013. |  |  |  |  | Progress: 4 |  | at least 7
|  | 3.5.2 Amount of annual government spending to support application of EBA principles and practices nationally | Total national annual investment in EBA: | [5 empty] | Baseline: 0 |  | The target aimag and soums committed a total of USD 3.3 million (2.8 for Ulz, 0.5 in Kharkhiraa/Turgen) for implementation of EbA pilot measures reflected in the IWRM Plans. These amounts constitute 2.8% and 19.1% of the total proposed budget of IWRM Plans for Kharkhiraa, Turgen sub-river basin and Ulz river basin respectively. |  |  |  |  | Progress: 0 |  | 100000
|  | 3.5.3 Number of National Climate Change Authority EBA policy documents mainstreaming EBA within sectoral decision-making frameworks. | Number of National Climate Change Authority Policy Documents: | [5 empty] | 0 |  | The national level policy document mainstreaming climate change adaptation/EbA within sectoral decision-making frameworks will be developed in 2015 based on the recommendations from the series of discussion workshops on climate change mitigation, adaptation measures and strategic planning with the involvement of a. Agricultural sector, b. Water resource sector, c. Forest sector which will be held in 2014. |  |  |  |  | Progress: 0 |  | at least 3

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please Complete the following section every reporting period |  | -
Implementation and Adaptive Management | Response
Describe any implementation issues/lessons affecting progress (positive and negative)
Were there any delays in implementation? If so, include any causes of delays. What are the measures taken to reduce delays? | Were there any delays in implementation? If so, include any causes of delays: i) There is slight delay in procurement of professional servises in 2014 due to the shift to the NIM (National Implementaiton Modality) from the old equivalent of NEX (National Excution) which was used for this project in the beginning. Although the modalities are essentailly the same (national implementaiton), the counterparts from the Implementing partner as well as relevant project staff were required to undergo a certified training on procurement to obtain a certification enabling to handle procurement management according to the Mongolian legislation. ii) Finalization of Economic Valuation Study for Kharkhiraa/Turgen and Ulz river basins is delayed mainly due to insufficient experience of the national team in the field of economic valuation of ecosystem servises, EbA and cost benefit analysis with consideration of CC. What are the measures taken to reduce delays?: i) Both MEGD and UNDP CO supported PIU and Climate Change Coordination Office's relevant staff to obtain needed knowledge and acquire certification to arrange procurements (work, equipment and special services) in accordance to Procurement law and its regulations of the Government. This allowed the project procurement activities run smoothly with small delay in implementation. ii) With facilitation of the RBAP and the regional Technical Advisor, the report has been reviewed and commented by Prof. Mendelson, Yale University. Addressing the comments given by RTA and the Prof. Mendlson, the completion of the study and finalization of the report is continued under guidance of Ms. Wang, Professor and Deputy Director, Center for Chinese Agricultural Policy, Chinese Academy of Sciences. The report is expected to be finalized in the next months and considered to serve as a template for similar coming efforts from ECCA’s other 10 countries.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | None
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender consideration was taken into account in all training, workshop and other activities during the reporting period depending on nature, topic and specifics. Natural resource policy expert (Component III) of the project is the focal point for gender issues keeping records on participation of stakeholders by ensuring gender ratio, inclusion of disabled and low income locals. Especially, for trainings targeted to local communities, the Project attempts to keep gender equality. For instance: In the small scale farming and tree planting training / activities an equal participation of gender were participated, while in livelihood diversification trainings; wool processing and making woolen products almost 100% participants were female, and in fire prevention training 80% were male particpants. For development of policy documents involving multi stakeholders, 65% of participants were males mostly due to that majority at the decision making level consist from men. For instance: Discussions organized in 3 aimags (Khentii, Dornod and Uvs) and 124 representatives (of which 89 male and 35 female participants) from 17 different soums governments, river basin area administrations’ offices, over 10 sectors, government staff at soum and provincial levels, NGO’s and private sectors. For the development of IWRM Plan series of consultative workshops were held in specific areas including upstream, mid and down streams. For consultations involving a total of 172 (in the western basin: 147 were male and 25 female participants) and 233 persons (eastern sites 168 were male and 65 female participants respectively) were invited representing relevant aimag and soum authorities.
Please Complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilent Measures
Please Describe the Climate Resilent measures being undertaken by the project/programme.
Which of these masures has been most effective and why?
Which have been least effective and why?
Concrete Adaptaiton Interventions
Please desribe the concrete adaptation measures being undertaken by the project/programme
What are/were the most difficult aspects of implementing such measures?
What are/were the most successful aspects of the implementation of the interventions?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
Describe what kind and how existing information/data/knowledge has been used to inform the development and the implementation of the project.
If Learning Objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what why have they contributed?
What have been the major lessons learned that would add to the knowledge base for dissemination within and beyond the project area?

## AF Tracking Tool
Tracking Tool for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following Results Framework and Baseline Guidance (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Please select the relevant Fund level Outcome and Output indicators that allign with the project objectives and outcomes
OBJECTIVE 1: Integrated Strategies/Management Plans for target landscapes/river basins developed and under implementation.
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) |  | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 3 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 3.1 | With the project support, EbA strategy and RBMPs for targeted basins will have been developed and implemented with engagement of local authority and community. Approximately, 90 percent of targeted populaton will be aware of predicted adverse impacts of climate change and of appropriate responses. More than 20 percent of the targeted population will have been trained and involved in community-led environmental impact monitoring and Communtiy based Adaptation. |  | Awareness and ownership of EbA and climate risk reduction processes at local level are insufficient. No actions are taken to dissiminate information on adverse impacts of climate change and appropriate responses. Local level authorities have limited experience and skills to develop and implement special programs and strategies with the aim of providing local community with required ecological education on EbA.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement (see Units in next sheet) |  | Baseline (see Units in next sheet) | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 3 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 3.1 | Basic surveys and ( Baseline study, vulnerability and risk assessment and Economic valuation) have been initiated in the target sites. Findings of these studies will be used as a platform for EbA strategy and RBMPs. Participatory approaches will be widely used for development of the strategy. 90 percent of the population will be provided with information on the strategy. |  | Awareness and ownership of EbA and climate risk reduction processes at local level are insufficient. No actions are taken to dissiminate information on adverse impacts of climate change and appropriate responses. Local level authorities have limited experience and skills to develop and implement special programs and strategies with the aim of providing local community with required ecological education on EbA.
OBJECTIVE 2: Implementing landscape level adaptation techniques to maintain ecosystem integrity and water security under conditions of climate change.
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement |  | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 5 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 5 | Land use practices and climate change resilience improved as indicated by: • Total hectares of riparian and wetland habitat restored with native vegetation within project sites • Total number of hectares with EBA friendly livestock management practices in two project sites Total hectares restored riparian/wetland: Targets are: 1) Total hectares restored riparian/wetland: • Kharkhiraa/Turgen: 1,250 ha • Ulz: 2,250 ha 2) Total hectares with EBA grazing practices: • Kharkhiraa/Turgen: 1,500 km2 • Ulz: 12,000 km2 Mean annual in-stream summer 30-day base flow maintained in two project sites Kharkhiraa River: 2.43 cubicmeter/second Turgen River:1.98 cubicmeter/second Ulz River: 0.10 cubicmeter/second (at Chuluunkhoroot) By the end of the Project, approximately 12,000 persons will have been trained and involved in Ecosystem based Adaptation (EbA) measures at 17 target soums. |  | Local communities in target area has little knowledge about the notion of ecosystem resilience. Overgrazing is widespread leading to land and water resource degradation, which is exacerbated by climate change. Therefore there in no progressive techniques and physical measures implemented to improve ecosystem resilence. 1) Total hectares restored riparian/wetland: • Kharkhiraa/Turgen: 0 ha • Ulz: 0 ha 2)Total hectares with EBA grazing practices: • Kharkhiraa/Turgen: 0 ha • Ulz: 0 ha Mean annual in-stream summer 30-day base flow at baseline: Kharkhiraa River: 2.43 cubicmeter/second Turgen River: 1.98 cubicmeter/second Ulz River: 0.10 cubicmeter/second
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement |  | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 5 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 5 | During the project implementation, the target area communities will be provided with opportunities to apply the obtained knowledge and skills for better adapting to climate change. At least 5 demonstration activies to increase ecosystem resillience in responce to climate change will be undertaken in each soum. With support of the project, a number of physical interventions designed to enhance climate change resilience of ecosystems within each target watersheds. Physical interventions will include: On the basis of verified feasibility, establishment of small-scale rain and snow water harvetsing structures Degraded land rehabilitation activities including sustainable grassland management; Sustainable forest management including reforestation, forest conservation with engagement of local community: Integrated water resource management; Utilization of alternative energy sources; Introducing of ecologically oriented agriculture practices to reduce water consumption etc., Actual amount (size) and type of above activities will be specified by Feasibiliy study to be conducted in August / September, 2013 in each soum. |  | Knowledge and skills of project stakeholders including local authorities and communities are very limited with regard to increasing ecosystem resilience in response to climate change and sustainable natural resource management.In this regard, there is no progressive techniques and physical measures implemented to improve ecosystem resilence.
OBJECTIVE 3: Strengthening capacities/Institutions to support EbA strategies and integrated river basin management, their replication and mainstreaming in sector policies.
Fund Outcome | Please select from dropdown menu below | Fund Outcome Indicator | Please select from dropdown menu below | Target at CEO Endorsement |  | Baseline | Mid-term Results | Terminal Results
Outcome 1: Reduced exposure at national level to climate-related hazards and threats Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level Outcome 4: Increased adaptive capacity within relevant development and natural resource sectors Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Outcome 7: Improved policies and regulations that promote and enforce resilience measures | 7 | 1. Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis 2.1. No. and type of targeted institutions with increased capacity to minimize exposure to climate variability risks 2.2. Number of people with reduced risk to extreme weather events 3.1. Percentage of targeted population aware of predicted adverse impacts of climate change, and of appropriate responses 3.2. Modification in behavior of targeted population 4.1. Development sectors' services responsive to evolving needs from changing and variable climate 4.2. Physical infrastructure improved to withstand climate change and variability-induced stress 5. Ecosystem services and natural assets maintained or improved under climate change and variability-induced stress 6.1. Percentage of households and communities having more secure (increased) access to livelihood assets 6.2. Percentage of targeted population with sustained climate-resilient livelihoods 7. Climate change priorities are integrated into national development strategy | 7 | By the end of the project, EbA are intergrated and mainstreamed into National Policy and regulations. More specifically, EbA approaches will be nationally recognized and applied for any decisions related to environment and climate change issues. |  | National and local level policies and regulations to promote EbA measures are extremely weak. National Action Plan on Climate Change is approved by The Government of Mongolia. However, it does not explicitly reflect EBA approaches that suited to Mongolian economic and ecological conditions.
Fund Output | Please select from dropdown menu below | Fund Output Indicator | Please select from dropdown menu below | Target at CEO Endorsement |  | Baseline | Mid-term Results | Terminal Results
Output 1: Risk and vulnerability assessments conducted and updated at a national level Output 2.1: Strengthened capacity of national and regional centres and networks to respond rapidly to extreme weather events Output 2.2: Targeted population groups covered by adequate risk reduction systems Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities Output 4: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 5: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability Output 7: Improved integration of climate-resilience strategies into country development plans | 7 | 1.1. No. and type of projects that conduct and update risk and vulnerability assessments 1.2. Development of early warning systems 2.1.1. No. of staff trained to respond to, and mitigate impacts of, climate-related events 2.1.2. Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased 2.2.1. Percentage of population covered by adequate risk-reduction systems 2.2.2. No. of people affected by climate variability 3.1 No. and type of risk reduction actions or strategies introduced at local level 3.2 No. of news outlets in the local press and media that have covered the topic 4.1. No. and type of health or social infrastructure developed or modified to respond to new conditions resulting from climate variability and change (by type) 4. 2. No. of physical assets strengthened or constructed to withstand conditions resulting from climate variability and change (by asset types) 5. No. and type of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability and change (by type of assets) 6.1. No. and type of adaptation assets (physical as well as knowledge) created in support of individualor community-livelihood strategies 6.2. Type of income sources for households generated under climate change scenario 7.1. No., type, and sector of policies introduced or adjusted to address climate change risks 7.2. No. or targeted development strategies with incorporated climate change priorities enforced | 7.1 |  | By the end of the project, totally 2 River Basin Administrations (RBAs) and 2 River Basin Councils (RBCs) are established and strengthened in two target watersheds. | Currently, RBAs and RBCs in two target project watersheds are not established and operational yet . In accordance with newly approved Law on Water, these structures are expected to be establised in 2013. Therefore, there is an urgent need for project technical assisstance to the RBAs and RBCs to be established.
[5 empty] | By the end of the project, staffs of relevant agencies and local governments in target regions will be trained and obtained necessary knowledge and skills through a series of systematic trainings organized by the project. As a result, sustainability of new RBAs and RBCs are ensured beyond the project termination. | Currently, RBAs and RBCs in two target project watersheds are not established and operational yet . In accordance with newly approved Law on Water, these structures are expected to be establised in 2013. Therefore, there is an urgent need for project technical assisstance to the RBAs and RBCs to be established.
[5 empty] | By the end of the project, more than 10 relevant regulations with regard to water and forest recourses will be amended and approved which reflect EbA concept and principles. | The Set of Environmental Laws were amended and approved by the Parliament of Mongolia in 2012. In relation to this, there is a need for refinement on relevant regulations in order to ensure favorable legal environment for EbA.

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.