## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | August 18, 2017 to August 18, 2018
| Project Title: | Improving the resilience to climate change of small-scale agriculture in the O'Higgins region of Chile
| Project Summary: | Increase the resilience capacity of rural agricultural communities in the coastal and inland secano of the O'Higgins Region with respect to current climate variability and future climate changes. The project lasts four years and the amount allocated is USD 9,960,000. We will work with a number close to 2,000 small farmers and their families, to create resilience capacities in these communities vulnerable to climate variation, with respect to livestock, cultivation, water and soil management, for this we will have machinery and implements that will be available to farmers for the improvement of agricultural practices. In addition, a number greater than 500 farmers will be subsidized with the implementation of rainwater harvesters, storage tanks and a small greenhouse for vegetables, which will allow them to have better water supply and have additional income. The project in turn will improve the agroclimatic information of the sector which will be available to small farmers, which will improve their agricultural management in the face of climate variations. A component of training focused on professionals from the sector, the Ministry of Agriculture and rural communities is also considered.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | CHL/NIE/Agri/2013/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Chilean International Cooperation Agency for Development (AGCID) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Government Cooperation Agency | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Chile | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Chile is a tri-continental country, with a territory that extends along the southwestern part of South America and includes Easter Island, in Oceania, as well as part of Antarctica to the south. Continental Chile, is located between 17 ° 30 'and 56 ° 30' Latitude South, while the Chilean Antarctic Territory covers the area between 53 ° and 90 ° west longitude and the South Pole. It is bordered by the Pacific Ocean along 8,000 kilometers of coastline. Its administrative capital is Santiago and the country is subdivided into 16 administrative regions. The total registered population is around 17.5 million people. Due to its geographical condition and variability of climatic regions, Chile is considered a country vulnerable to climate change: low-altitude coastal zones, arid and semi-arid zones, forested areas and areas exposed to deforestation and fragile ecosystems in coastal and Andean regions. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | November 13, 2015
IE-AFB Agreement Signature Date: |  | November 13, 2015 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | August 18, 2017 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | August 18, 2019
| Terminal Evaluation Date: | August 18, 2021
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. Agreement between the Board of the Adaptation Fund and the Agency for International Cooperation for Development. On November 13, 2015 the Agreement that grants financing to the country for an amount of USDD 9,960,000 was signed. On July 1, 2016, the Office of the Comptroller General of the Republic Takes Reason 2. Agreement between the Chilean International Cooperation Agency for Development (AGCID), the Ministry of Agriculture (MINAGRI) and the Ministry of the Environment (MMA). of September 2016 the Agreement is signed and on December 2, 2016 the General Comptroller of the Republic takes Reason. They agree to transfer USD 9,460,000 to the Ministry of Agriculture 3. Agreement between the Undersecretary of Agriculture and the Institute of Agricultural Research (INIA). On September 3, 2017, the Agreement is signed and on February 6, 2018, the Office of the Comptroller General of the Republic takes Reason. They agree to transfer to INIA the sum of USD 4,558,259 - The Home Workshop held in the O'Higgins region on August 18, 2017. - POA 2018 and 2019 approved by the Steering Committee - Quarterly progress reports of the Project, (have been presented or 4 reports for the following periods: Sept 2017- Nov 2017, Dec 2017 - Feb 2018, Mar 2018 - May 2018 and Jun - Aug 2018). | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Joaquin Arriagada Mujica (Director del Proyecto) | Dominican Republic
| Email: | joaquin.arriagada@minagri.gob.cl | Ecuador
| Date: | 10 de marzo de 2018 | Egypt
| Name: | Jorge Carrasco Jimenez (Coordinador Técnico) | Dominican Republic
| Email: | jcarrasc@inia.cl | Ecuador
| Date: | 6 de Febrero de 2018 | Egypt
| Name: | Fernando Baeriswyl Rada (Coordinador entidad Implementadora - AGCID) | Dominican Republic
| Email: | fernando.baeriswyl@minagri.gob.cl | Ecuador
| Date: | 03 de Nov 2017 | Egypt
| Government DA |  | El Salvador
| Name: | Iván Mertens Galle (Coordinador Sectorial - AGCID) | Equatoral Guinea
| Email: | imertens@agci.gob.cl | Eritrea
| Date: | 25 de septiembre de 2013 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Juan Pablo Lira Bianchi (Director AGCID) | Fiji
| Email: | jlira@agci.gob.cl | Finland
| Date: | 08 de agosto de 2016 | France
| Executing Agency |  | Gambia
| Name: | Alfonso Vargas Lyng (Subsecretario de Agricultura) | Georgia
| Email: | contacto@minagri.gob.cl | Germany
| Date: | 10 de marzo de 2018 | Ghana
| Executing Agency |  | Greece
| Name: | Felipe Riesco Eyzaguirre (Subsecretario de Medio Ambiente) | Grenada
| Email: |  | Guatemala
| Date: | 19 de junio de 2018 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [18/08/2018]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [18-08-2018] | 635639
Add any comments on AF Grant Funds. (word limit=200) | The start of the project had the difficulties of administrative processes and consolidation of professional teams. However, these drawbacks have already been overcome and the project is currently in full execution. Below we will comment on the main situations presented to date: In the summer of 2017 the country suffered one of the largest fires in its history and burned to the order of 600,000 hectares, many of which were located in the geographical area of ​​the project . This meant that the government and its institutions focused on the emergency and on the subsequent assistance processes for the victims, leaving pending in this case the start-up of the project. There were delays in the administrative processes, specifically in the agreement between the Ministry of Agriculture and the Institute of Agricultural Research (INIA), because in Chile the system of control of all documentation and agreements that involve financing is very strict. Lastly, in Chile there was a change of government in March 2018, which meant several months of inaction, while the new authorities and particularly in our case, the Project Director was internalized of the details.
INVESTMENT INCOME | N/A
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| 1.1.1. Creation of training and advisory teams for agro-technology transfer for each one of the 8 municipalities of the project area, coordinated and supervised by local INIA experts | 89044.19
| 1.1.2 Implementation of 9 demonstration fields for the transfer of agro-technology, including its infrastructure and equipment: 4 - 5 hectares in each of the 8 communes plus one in INIA land. | 29149.14
| 1.1.3 Implementation of demonstration plot and acquisition of agricultural machinery for the 9 demonstration fields. | 57782.98
| 1.1.4 Training in sustainable soil management: plowing practices, fertilizing practices, soil fertility recovering practices, holistic soil management. | 30924.91
| 1.1.5 Training in the management of crops, fodder, fruit and livestock, tolerant to climate variability and climate change including the acquisition of seeds, plants and animals. | 29404.45
| 1.1.6 Training in efficient water management on the demonstration fields (including the acquisition of the equipment) through the application of irrigation technology powered by renewable energy resources (sun, wind) | 29361.95
| 1.2.7 Installation of rainwater and surface run-off harvesters in 558 lots, including training and acquisition of materials and equipment. | 117269.01
| 1.2.8 Capacity building through knowledge sharing and good practice demonstrations | 8.79
| 2.1.1 Strengthening of the existing network of automatic meteorological stations in the project area. | 9811.98
| 2.1.2 Capacity building in weather and climate data analysis and its integration in meaningful decision-making for farm management | 26123.35
| Execution costs (EC) | 131726.81
| Implementing entity cost (AGCID) | 85031.22
| TOTAL | 635638.78
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| 1.1.1. Creation of training and advisory teams for agro-technology transfer for each one of the 8 municipalities of the project area, coordinated and supervised by local INIA experts | 176555 | 2019-08-18
| 1.1.2 Implementation of 9 demonstration fields for the transfer of agro-technology, including its infrastructure and equipment: 4 - 5 hectares in each of the 8 communes plus one in INIA land. | 131895 | 2019-08-18
| 1.1.3 Implementation of demonstration plot and acquisition of agricultural machinery for the 9 demonstration fields. | 1619723 | 2019-08-18
| 1.1.4 Training in sustainable soil management: plowing practices, fertilizing practices, soil fertility recovering practices, holistic soil management. | 162467 | 2019-08-18
| 1.1.5 Training in the management of crops, fodder, fruit and livestock, tolerant to climate variability and climate change including the acquisition of seeds, plants and animals. | 183241 | 2019-08-18
| 1.1.6 Training in efficient water management on the demonstration fields (including the acquisition of the equipment) through the application of irrigation technology powered by renewable energy resources (sun, wind) | 157627 | 2019-08-18
| 1.2.7 Installation of rainwater and surface run-off harvesters in 558 lots, including training and acquisition of materials and equipment. | 946081 | 2019-08-18
| 1.2.8 Capacity building through knowledge sharing and good practice demonstrations | 59319 | 2019-08-18
| 2.1.1 Strengthening of the existing network of automatic meteorological stations in the project area. | 53681 | 2019-08-18
| 2.1.2 Capacity building in weather and climate data analysis and its integration in meaningful decision-making for farm management | 76637 | 2019-08-18
| Execution costs (EC) | 127400 | 2019-08-18
| Implementing entity cost (AGCID) | 135601 | 2019-08-18
| TOTAL | 3830227
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | There is no co-financing
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | 0
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Climate change manifests differently or with greater intensity than projected by the analyzes and studies | Medium: To date there is no information that modifies the initial diagnosis of the project | The MMA and MINAGRI are attentive through their information and monitoring systems, regarding any modification that may occur with climate change at the country level. Before any special situation, the actions of the project in the mid-term evaluation will be reviewed
Beneficiaries resist changes in practices | Medium: the risk is maintained because the project has not yet carried out all training and support activities for farmers, which will be aimed at a change of consciousness regarding the need to improve traditional practices that are not adequate to resilience in the face of climate change. As a data we must consider that the average age of the farmers is high and could affect in some way the future changes in their productive system. The project will address important awareness raising actions with the students of the agricultural schools of the sector, to favor changes at the family level. | A survey was carried out with 600 farmers who provided valuable information as a diagnosis of the current situation and will serve as a basis for the training programs. The annual survey will allow monitoring the changes that the project aims to achieve in the farmers of the project area.
Government or institutions do not assign sufficient priority to the program | Very Low: The project is a high priority for current government authorities. The Director of the project that is the Seremi of agriculture of the O'Higgins region has placed first priority in its plans for the next 4 years | The Project Advisory Committee has had a high participation due to the number of meetings and the presence of all the institutions involved. This Committee is directed by the Seremi de Agricultura and has been attentive to solve problems and monitor the commitments of government entities.
Lack of incentives or economic capacity of the beneficiaries to invest in restoration or improvement can lead to inefficient results in land use and other expected results. | Low: this topic will be made visible in a better way once the project is fully operational and with a greater number of farmers participating. There are not enough actions yet for a better evaluation of this risk | All measures are being taken to mitigate this risk through the training scheduled for year 2, in addition to the support with the use of machinery, equipment and subsidies to increase the benefits to farmers with water harvesters and greenhouses.
The CLP / US $ exchange rate falls below $ 550 | Low: The exchange rate has remained on average above $ 600 | AGCID has kept the Advisory Committee permanently informed about the projections of the exchange rate and will review the project's actions in the mid-term evaluation on the year 2 of the project.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Change of Government and / or authorities: New authorities must assume the direction of a project that they do not know and that requires several months of learning for a normal and efficient management | Low: In March 2018, a new government was elected in the country and will remain unchanged for the remainder of the project. Except for specific situations of cabinet change that could affect the direction of the project. | No changes are projected in the near future
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Yes, measures were taken for the change of Government. The new authorities were instructed and provided with project information in a timely manner, so that the period in which the authorities took over and took control of the project was reduced to a minimum and there were no major difficulties.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Product 1.1.1.- Creation of training and advisory teams for agro-technology transfer for each one of the 8 municipalities of the project area, coordinated and supervised by local INIA experts |  | Hiring of 4 professionals and 9 technicians for demonstration units and field work. Hiring of the team of the Project Management Unit (1 coordinator, 1 secretary, 1 in charge of finance). Classification and study of land. Claificacion, studies and acquisition of equipment for soil classification. |  | A professional team was hired to advise on the agro-technological transfer for each municipality in the area of influence of the project. Four professionals were hired (1 coordinator, 1 secretary and 2 administrative managers), as well as a communications team to the development of an adequate communication with the different objective publics of the program, the necessary equipment was acquired for the classification and characterization of soils, these tasks are in full execution. | HS
| Product 1.1.2.- Implementation of 9 demonstration fields for the transfer of agro-technology, including its infrastructure and equipment: 4 - 5 hectares in each of the 8 communes plus one in INIA land. |  | Field diagnosis of the demonstration fields and their final selection, Acquisition of materials for the implementation and operation of the units. Analysis of soil fertility, Physical analysis of soils, Scarification or subsoiling of soils |  | At present, the 9 demonstration fields for agro-technology transfer are being implemented and in operation, in which crops have been established and the committed tasks have been carried out. The selection of these fields was made based on a diagnostic survey that was carried out. I apply to about 600 people from the different communes of the area of influence of the project. | S
| Product 1.1.3.- Acquisition (including maintenance and operating costs) of agricultural machinery for the 9 demonstration fields: Tractors, Pasture regenerator, zero-till planters, plow, Chisel plow, Subsoiler plow. |  | Public bidding for agricultural machinery and equipment. Acquisition of truck and truck by INIA. Acquisition of containers to enable laboratory flooring and office habilitation. Construction of warehouses |  | In the execution of the annual plan of the first year of operation of the project, the purchase of a truck and a truck was executed with the objective of installing the demonstration fields, as well as the rainwater harvesting units, these activities committed by the team program manager were executed according to the established planning. | S
| Output 1.1.4: Training in sustainable soil management: plowing practices, fertilizing practices, soil fertility recovering practices, holistic soil management. |  | Technical training in soil and water conservation. Development of 8 days of fields on use of harrowing scarifier subsoiler. Technical visits abroad. Development of 8 soil management workshops. Scaled soil prairie service. Development of 1 bee production workshop |  | Because for reasons of seasonality, many of the training activities committed should be considered for the second year of execution of the project, due to the delay in the approval of the agreement between the Undersecretary of Agriculture and INIA. Even so, basic technical assistance was given to the 64 farmers who were favored with the installation of water harvesters, accumulation ponds and greenhouses. In addition, 468 people were trained through 15 activities that included, home workshop, work in local committees, induction to technical teams and organization of seminars. | MS
| Product 1.1.5.- Training in the management of crops (wheat, quinoa, buckwheat, chickpeas), fodder crops (legumes, grasses), fruit trees (olive trees, nuts) and livestock (sheep), tolerant to variability of climate and climate change, including the acquisition of seeds, plants and animals |  | Development of courses: 3 on production of Quinoa and Buckwheat in areas of Secano. 3 courses on establishment and management of meadows for rainfed areas. 3 courses on hydroponic green forage production. 3 courses on sheep management, under rainfed conditions. Workshop development: 8 soil management workshops for the establishment of rainfed crops. 4 bee production workshops under rainfed conditions. 8 workshops or seminars on concepts of climate change and its effect on rainfed agriculture. Comic release day on climate change. |  | Like product 1.1.4, the planned activities had the same delay explained previously. Despite the setbacks, it is estimated that the results of this product will be optimally reflected for the second project report. | MS
| Product 1.1.6.- Training in the efficient management of water in the demonstration fields (including the acquisition of equipment) through the application of irrigation technology powered by renewable energies (solar radiation and wind) |  | Purchase and installation of photovoltaic panels in each beneficiary property. Purchase and installation of wind systems for the production of electrical energy in demonstration units. Completion of courses: 8 of rainwater harvesting systems. 8 on the use of photovoltaic panels in agriculture. |  | We proceeded with the hiring of a consulting company to determine the requirements of each farmer, sizing the real requirements we expect that during the second year of the project the bids and purchases of the equipment will be made, which will be dimensioned to the reality of the property of each small farmer. Regarding the wind systems for the 9 demonstration units, their acquisition and installation are scheduled for the second year of the project. With respect to rainwater harvesting system courses and the use of photovoltaic panels, they are scheduled for the second year, however, in the 64 units of water harvesters installed in the first year, basic training was carried out each of the small farmers beneficiaries. | MS
| Product 1.2.7: Installation of rainwater harvesters and surface run-off facilities for use in 558 properties including the training and acquisition of materials and equipment (roofing materials, rain pipes, mobile water tanks, pumps fed by sources of renewable energy (sun, wind), greenhouse installation) |  | Construction and installation: collection units, accumulation and use of rainwater. Purchase and construction of greenhouses. Purchase of technified irrigation materials for the establishment of a greenhouse irrigation system. Training on rainwater harvesting systems. |  | According to what was committed for the execution of the first year of the project, 64 rainwater harvesters were built with their respective greenhouses, equipped with irrigation systems, and the beneficiaries were duly trained in handling the harvesters and the greenhouses. | HS
| Output 1.2.8: Capacity building through the exchange of knowledge and demonstrations of good practices. |  | Visits from foreign experts. Trips of team members to countries of interest. Field day in the Hidando unit. Implementation of communications unit. |  | The first year of the project was attended by foreign specialists; Ms. Deissy Martínez Barón, Regional Coordinator of the Research Program on Climate Change, Agriculture and Food Security (CCAFS), for Latin America - International Center for Tropical Agriculture (CIAT), Colombia, Mr. Julián Ramírez-Villegas, Lead Scientist, of the Climate and Agriculture Modeling Team of the Policy Analysis Research Area (DAPA), of the International Center for Tropical Agriculture (CIAT) and Mr. José Miguel del Cid, specialist of the Agroenvironment and Climate Change Unit of the Secretariat of Agriculture and Livestock, Honduras and Mr. Enrique Saavedra, Agronomist, Plant Health Specialist, Master of Agricultural Sciences; Adviser to FEDEARROZ, Colombia, who participated in the Seminar "Risk Management: New Technologies and Methodologies for the Use of Agroclimatic Information in Agricultural Activity" and that allowed the implementation of the first Agrometeorological Participatory Roundtable in the municipality of Marchigue. The trips scheduled for the first year will be held in the second year due to the reasons explained above, and the same regarding the field days: Regarding the implementation of a communications unit, this year professionals such as visual audio communicator, designer were hired and communication specialists who have worked on a Media Plan and dissemination. | MS
| Producto 2.1.1. Fortalecimiento de la red existente de estaciones meteorológicas automáticas (AMS) en el área del proyecto: |  | Acquisition of E.M.A. for Christmas commune. Acquisition of other measuring equipment (sensors / stations). Expert consulting in agroclimatic information. Construction OAR O'Higgins. Dissemination of the regional Agroclimatic Observatory. Acquisition server for repository automatic processing database. Software library installation. |  | Significant progress has been made in achieving the installation of the Agroclimatic Observatory in MINAGRI units, and work is being carried out on its dissemination and implementation at the territorial level. In addition, progress has been made in defining, both technically and practically, the best location of the EMA, which will provide important data from the agroclimatic point of view. | MS
| Producto 2.1.2. Creación de capacidades de análisis de datos y su integración en la toma de decisiones significativas para el manejo agrícola |  | Expert consultancy for the design, architecture and implementation of the OAR. Hiring an international consultant for agroclimatic monitoring. Drones flight service. Advice on the preparation of a rural communication plan. Training course for farmers and technicians. Purchase of computer, camera, color printer |  | National Consultancy Agronomist / Information Engineer with specialization in agrometeorological information management, knowledge in modeling and construction of agroclimatic indicators. Work has been carried out with specialists from the Regional Water Center for Arid and Semi-Arid Zones of Latin America and the Caribbean (CAZALAC) for the implementation of the new server, supported by professionals from the International Research Institute for Climate and Society (IRI-U of Columbia) | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Joaquin Arriagada Mujica (Project Director)
| Email: | joaquin.arriagada@minagri.gob.cl
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Considering that due to the necessary procedures for its implementation the start date of the project, which generated a significant backlog in its start-up and implementation stage, and that management times had to be optimized, in general it can be said that there has been a commitment of all the members of the project, that despite the little real time to execute, the commitments have been fulfilled, which have constituted important milestones such as laying the foundations for the constitution of the Priemar Participatory Agromeyeorological Table, the integration of the actors local through the Local Committees and something unprecedented in many projects the generation of a communicational Estraegia, so that the technical effort is really reflected in the community as a whole. Therefore compliance is considered Satisfactory
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Product 1.1.1.- Creation of training and advisory teams for agro-technology transfer for each one of the 8 municipalities of the project area, coordinated and supervised by local INIA experts |  | Hiring of 4 professionals and 9 technicians for demonstration units and field work. Hiring of the team of the Project Management Unit (1 coordinator, 1 secretary, 1 in charge of finance). Classification and study of land. Claificacion, studies and acquisition of equipment for soil classification. |  | Hiring of 3 professionals and 8 technicians for the demonstration units and field work. Hiring the team of the entire Project Management Unit. Work related to soil study and classification began, including satisfactory analyzes. | HS
| Product 1.1.2.- Implementation of 9 demonstration fields for the transfer of agro-technology, including its infrastructure and equipment: 4 - 5 hectares in each of the 8 communes plus one in INIA land. |  | Field diagnosis of the demonstration fields and their final selection, Acquisition of materials for the implementation and operation of the units. Analysis of soil fertility, Physical analysis of soils, Scarification or subsoiling of soils |  | A survey was carried out to 600 farmers, which allowed to choose the 8 properties that had the best characteristics for the implementation as a demonstration unit. In this first stage, soil tillage services were contracted with the use of techniques such as subsoiling plow, to favor the incorporation of rainwater into the ground. Soil classification and fertility analyzes were also carried out, using field and laboratory equipment acquired for the project, and later sowings of species and varieties mainly forages were carried out, to show the behavior and yields in the coastal dry land conditions. the region. Further implementation and other trials are scheduled to be carried out in the second year of the project (strawberry cultivation, bee management, greenhouse cultivation, etc.) | S
| Product 1.1.3.- Acquisition (including maintenance and operating costs) of agricultural machinery for the 9 demonstration fields: Tractors, Pasture regenerator, zero-till planters, plow, Chisel plow, Subsoiler plow. |  | Public bidding for agricultural machinery and equipment. Acquisition of truck and truck by INIA. Acquisition of containers to enable laboratory flooring and office habilitation. Construction of warehouses |  | According to the Annual Operating Program (POA 2018), in the matter of equipment acquisition, the truck and truck were acquired, which allowed supporting the first stage of installation of water harvesters, accumulation tanks and greenhouses of the farmers; in addition to the implementation tasks of the demonstration fields. All the acquisition of the machinery and equipment of the land are scheduled for year 2, established in the POA 2019. | S
| Output 1.1.4: Training in sustainable soil management: plowing practices, fertilizing practices, soil fertility recovering practices, holistic soil management. |  | Technical training in soil and water conservation. Development of 8 days of fields on use of harrowing scarifier subsoiler. Technical visits abroad. Development of 8 soil management workshops. Scaled soil prairie service. Development of 1 bee production workshop |  | The training program that had been originally planned, had to be moved to the second year of the project because the activities must be carried out in a specific period of the agricultural season, which was delayed due to the delay in the approval of the agreement between the Undersecretary of Agriculture and the INIA. Nevertheless, with the technical team of the project, training and basic technical assistance were developed for the 64 farmers who were favored with the installation of water harvesters, storage tanks and greenhouses. In addition, 468 people were trained through 15 activities that included, home workshop, work in the local committees, induction to the technical teams and organization of seminars. In the following agricultural season it will be possible to develop the own activities of soil tillage, applying the new technologies. | MS
| Product 1.1.5.- Training in the management of crops (wheat, quinoa, buckwheat, chickpeas), fodder crops (legumes, grasses), fruit trees (olive trees, nuts) and livestock (sheep), tolerant to variability of climate and climate change, including the acquisition of seeds, plants and animals |  | Development of courses: 3 on production of Quinoa and Buckwheat in areas of Secano. 3 courses on establishment and management of meadows for rainfed areas. 3 courses on hydroponic green forage production. 3 courses on sheep management, under rainfed conditions. Workshop development: 8 soil management workshops for the establishment of rainfed crops. 4 bee production workshops under rainfed conditions. 8 workshops or seminars on concepts of climate change and its effect on rainfed agriculture. Comic release day on climate change. |  | As in product 1.1.4, the planned activities had the same delay explained previously. Despite the setbacks, it is estimated that the results of this product will be optimally reflected for the second project report. | MS
| Product 1.1.6.- Training in the efficient management of water in the demonstration fields (including the acquisition of equipment) through the application of irrigation technology powered by renewable energies (solar radiation and wind) |  | Purchase and installation of photovoltaic panels in each beneficiary property. Purchase and installation of wind systems for the production of electrical energy in demonstration units. Completion of courses: 8 of rainwater harvesting systems. 8 on the use of photovoltaic panels in agriculture. |  | There have been 39 meetings with the INDD PRODESAL-SAT work teams in the 8 communes. These meetings have been very important for the planning and work that is going to be done with the farmers since the majority of the beneficiaries of the project are small farmers, who are being supported with INDAP programs. A consulting company was hired to determine the requirements of each farmer, in the requirement of photovoltaic panels, sizing the real requirements so that during the second year of the project the bidding and purchases of the equipment will be carried out, which will be dimensioned to the reality of the property of each small farmer. Regarding the wind systems for the 9 demonstration units, their acquisition and installation are scheduled for the second year of the project. With respect to rainwater harvesting system courses and the use of photovoltaic panels, they are scheduled for the second year, however, in the 64 units of water harvesters installed in the first year, basic training was carried out each of the small farmers beneficiaries. | S
| Product 1.2.7: Installation of rainwater harvesters and surface run-off facilities for use in 558 properties including the training and acquisition of materials and equipment (roofing materials, rain pipes, mobile water tanks, pumps fed by sources of renewable energy (sun, wind), greenhouse installation) |  | Construction and installation: collection units, accumulation and use of rainwater. Purchase and construction of greenhouses. Purchase of technified irrigation materials for the establishment of a greenhouse irrigation system. Training on rainwater harvesting systems. |  | In the first year of the project the established goal (64 units) was met in terms of the installation of collection units, accumulation and use of rainwater, including the construction of a small greenhouse. Each small farmer was advised and received basic training on the use and maintenance of water harvesting systems, as well as the use of crops under plastics in an irrigation environment and controlled temperature. | HS
| Output 1.2.8: Capacity building through the exchange of knowledge and demonstrations of good practices. |  | Visits from foreign experts. Trips of team members to countries of interest. Field day in the Hidando unit. Implementation of communications unit. |  | In this product, most of the activities will be carried out in the second year of the project. In terms of communication, the professionals in charge of the communications unit were contracted, those who have developed a media plan and are working on the elaboration of a communication strategy where all those responsible for communicating the services and Ministries involved will participate. in the project. The objectives of this strategy will be directed to different levels, which will include a work at the local level (communes and farmers), regional (the entire O'Higgins region) and national (all regions of the country) | MS
| Producto 2.1.1. Fortalecimiento de la red existente de estaciones meteorológicas automáticas (AMS) en el área del proyecto: |  | Acquisition of E.M.A. for Christmas commune. Acquisition of other measuring equipment (sensors / stations). Expert consulting in agroclimatic information. Construction OAR O'Higgins. Dissemination of the regional Agroclimatic Observatory. Acquisition server for repository automatic processing database. Software library installation. |  | The terms of reference for the acquisition of the EMA were prepared, whose bidding process is currently in process. The physical place where it will be installed was defined, corresponding to the premises of a small farmer of the Christmas commune. In terms of external consultancy, an international specialist was hired to train professionals from the Ministry of Agriculture and related services, with agroclimatology, use of software (IT). The server and the software were acquired, completing the agroclimatic database. Likewise, numerous meetings have been held to create the regional observatory of O'Higgins, with the participation of Ministries, services, universities and NGOs. | S
| Producto 2.1.2. Creación de capacidades de análisis de datos y su integración en la toma de decisiones significativas para el manejo agrícola |  | Expert consultancy for the design, architecture and implementation of the OAR. International consultant hiring for agroclimatic monitoring. Drones flight service. Advice on the preparation of a rural communication plan. Training course for farmers and technicians. Purchase of Computer, camera, color printer |  | Two OAR meetings have been held with the participation of public services and NGOs that are currently working on agroclimatology in the O'Higgins region. To date, the information handled by each of the institutions has been compiled to avoid duplication and there is a complement of studies and diagnoses. In the meetings of the local committees, a SEGRA professional has participated, who has developed training and extension in the field of agrometeorology to small farmers. | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Fernando Baeriswyl Rada (Implementing Entity Coordinator - AGCID)
| Email: | fernando.baeriswyl@minagri.gob.cl
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | On average it is considered that the result of the milestones of the project is Satisfactory. There are some highly satisfactory milestones and some fairly satisfactory ones. Regarding the latter, the planning of the activities for the second year indicate that they will improve their score, given that the difficulties that prevented a larger budgeted advance have already been resolved. One of the greatest difficulties was having the authorization of the Undersecretariat of Agriculture - INIA agreement for the transfer of funds, which occurred only on February 6, 2018.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Note on C8: Jessica Farias Ibarra: Gerente de Proyecto /Coordinador:

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
| Number and type of institutions with the best capacity to minimize exposure to the risks of climate variability. Number of people with lower risk of extreme weather events | Degradation of agricultural land and livestock, for improper practices. The younger generation migrates from family farms to cities in search of better economic and working conditions and better quality of life | The start-up of the project and the beginning of the planned activities, has meant assuming a commitment of coordinated work with 13 institutions (5 Services of the Ministry of Agriculture and 8 Municipalities). Beyond the three institutions that make up the Steering Committee (MINAGRI, AGCID, Ministry of the Environment), these 13 institutions correspond firstly to the coastal drylands of the O'Higgins Region, with the Municipalities of Paredones, Pichilemu, Marchigue, La Estrella, Litueche, Christmas, Lolol and Pumanque. Likewise, it is necessary to mention the Ministry of Agriculture with five dependent Services: INDAP through its support program for small farmers PRODESAL; the SEGRA Agricultural Emergencies Section; the INIA Rayentué Experimental Station; the National Forestry Corporation CONAF and the ODEPA planning office that is in charge of coordinating climate change matters in the Ministry. All these institutions are interacting at the level of the 4 Project Committees: (1) Steering Committee, (2) Executive Committee, (3) Regional Committee and (4) Local Committees. Finally, as representative of the undersecretary is the SEREMI of Agriculture of the O'Higgins Region, together with its staff of professionals and technicians, who is in charge of the Project Management. | Soil degradation is reduced by the application of soil conservation techniques and appropriate soil, water and vegetation cover management practices. • 13 institutions with the greatest capacity to minimize exposure to the risks of climate variability. • At least 255 officials from 13 institutions trained to minimize exposure to the risks of climate variability. • 558 owners (direct beneficiaries, at least 318 women) with a lower risk of extreme weather events. 20,000 liters of water per year available per holder. Household income increased by at least USD 1,000 / year. • At least 2208 farmers (direct beneficiaries, at least 691 women) with greater access to machinery and technical assistance. At least 5,000 hectares with better soil quality. Household income increased by at least USD 1,000 / year. • At least 4988 owners (100% of the farming population, direct beneficiaries, at least 1562 women) with a lower risk of extreme weather events (EWS 0-> 3). • At least 5343 (direct beneficiaries, at least 1673 women) trained farmers.
Componente 1 | 13 institutions (5 Ministry of Agriculture Services and 8 municipalities) with greater capacity to minimize exposure to the risks of climate variability | Arable land in the O'Higgins region will be reduced by 44% and 68% respectively (scenario A2). The most vulnerable group of farmers (under 20 ha) includes 4988 farmers (1562 women) and their families | The scenario included in the design stage of the project predicted a reduction of the cultivated surface due to the climatic variability that is leading to a lack of water in the growing periods. In this sense the project from year 2 has planned to acquire specialized agricultural machinery to be available to small farmers. This machinery will allow to apply agronomic practices that favor the capture of water in the terrain, perform minor tillage (zero tillage), and avoid erosion by surface curing. In addition, seeds of new varieties that better adapt to rainfed crops will be incorporated, changing them for deciduous varieties that no longer respond adequately to periods of lack of water. All this will improve the capacities for management of soils, livestock, water and crops, which will stop the progressive decline of cultivated areas that has been occurring in recent decades and whose process has accelerated in recent years due to longer droughts than they register in the country. Currently, the demonstration units that are an important part to show farmers different types of soil management and different varieties adapted to climate change were established. From these demonstration units are intended to improve all those technical falencas that are destined to the failure of not mediate a technological change in the short term. At least 5,000 hectares with soil improvement are committed at the end of the project, which will begin to be executed by the year 2. | Greater capacities for soil, livestock, water and crop management. Community access to machines for soil management • 13 institutions (5 Ministry of Agriculture services and 8 municipalities) with greater capacity to minimize exposure to the risks of climate variability. • At least 255 officials from 13 institutions (5 Ministry of Agriculture services and 8 municipalities) trained to minimize exposure to the risks of climate variability. • 558 owners (direct beneficiaries, at least 318 women) with a lower risk of extreme weather events. 20,000 liters of water per year available per holder. Household income increased by at least USD 1,000 / year. • At least 2208 farmers (direct beneficiaries, at least 691 women) with greater access to machinery and technical assistance. At least 5,000 hectares with better soil quality. Household income increased by at least USD 1,000 / year. • At least 5343 (direct beneficiaries, at least 1673 women) trained farmers.
Resultado 1.1 | Number of officials trained to respond and mitigate impacts of climate events Staff capacity of selected institutions to respond and mitigate impacts of increased climate events | Low level of access to technical and financial assistance. Low level of connection with the agro-industrial value chain and low participation in organizations | In this first year of installation of the project, a professional and technical team was consolidated that is at the service of the benefited farmers. 4 professionals and 9 technicians were hired to be in charge of the work in all the communes (in total 8). The demonstration units installed in each Commune are in charge of an agricultural technician and the support of a professional in charge of 2 communes each. This team of permanent terrain has joined the specialists of INIA, experts in rainfed crops, specialists in irrigation and water management, specialist in sheep management and animal production, specialist in rainfed meadows, specialist in agricultural machinery, specialist in soil and soil science, and finally a specialist in rainfed productive systems. The training in the first stage has focused on the professionals and technicians of the project team, who in visits to the farmers have been training for new crop techniques, especially the 64 farmers benefited with the water harvesters and greenhouses, where the work of cultivation under plastic is a novelty and requires to deliver the appropriate knowledge to the beneficiaries. All these institutions that are interacting in different levels of decision, the officials surpass the 200 people (in total 255 are projected), who during the ejecusión of the project have begun training to minimize exposure to the risks of climate variability | • At least 255 officials from 13 institutions (5 Ministry of Agriculture services and 8 municipalities) trained to minimize exposure to the risks of climate variability. • At least 2208 farmers (direct beneficiaries, at least 691 women) with greater access to machinery and technical assistance. At least 5,000 hectares with better soil quality. Household income increased by at least USD 1,000 / year. • At least 4988 holders of (100% of the farmer population, direct beneficiaries, at least 1562 women) with a lower risk of extreme weather events (EWS 0-> 3). • At least 5343 (direct beneficiaries, at least 1673 women) trained farmers.
Resultado 1.2 | Number of people affected by climate variability | Limited productive capacity Small farmers face water shortages from November to April. They receive water in cisterns of the municipalities, but in insufficient quantity for the maintenance of agricultural activity | The first year, as previously reported, subsidized 64 small farmers with the installation of water harvesters by gutters from the roofs, a system of conduction to an accumulator tank and a greenhouse, installing technified irrigation for the cultivation of vegetables. . At the end of the project, 558 small farmers will benefit from the water harvesting, accumulation and greenhouse equipment, including 318 women, with an expected increase in income of at least US $ 1,000 / year. So far the system has been working well within the assessments that have been made, using water from the few rains that have been recorded this season. During the second year of operation there will be more information to evaluate their results, but to date they have worked well and farmers have had an extra income for their crops under plastic. In addition to the direct beneficiaries with the subsidy, 2,208 farmers will be considered directly supported by the project, which added to the indirect ones (2,780) would add a total of 4,988 small producers. | • At least 4988 holders of (100% of the farmer population, direct beneficiaries, at least 1562 women) with a lower risk of extreme weather events (EWS 0-> 3). • 558 owners (direct beneficiaries, at least 318 women) with a lower risk of extreme weather events. 20,000 liters of water per year available per holder. Household income increased by at least USD 1,000 / year. • At least 255 officials from 13 institutions (5 Ministry of Agriculture services and 8 municipalities) trained to minimize exposure to the risks of climate variability.
Componente 2 | Percentage of population covered by adequate risk reduction systems | Small farmers lack agro-climatic information and capacities for agricultural decision-making in changing and extreme environments | During the first year of the project the installation of an EMA (automatic meteorological station) was evaluated, whose decision fell on the Christmas commune. This EMA is going to join the agrometeorology network that runs the SEGRA office (formerly UNEA) of MINAGRI, completing with information throughout the rainfed sector of the project. It is projected for the second year to begin the extension stage to small farmers, through courses, lectures and radio programs, so that farmers can use these forecasting tools to reduce the risks of extreme weather events, as well as reduce minimize exposure to the risks of climate variability. Through mass dissemination by local communication media, it is intended to reach the total population of the area of influence of the project, estimated at around 50,000 people. | The appropriate information is generated and disseminated through the appropriate means. Together with the training, it improves decision making. • At least 4988 farmers (100% of the farmer population, direct beneficiaries, at least 1562 women) with a lower risk of extreme weather events (EWS 0-> 3). • 13 institutions (5 Ministry of Agriculture services and 8 municipalities) with greater capacity to minimize exposure to the risks of climate variability
Resultado 2.1 | Percentage of population covered by adequate risk reduction systems | Small farmers lack agro-climatic information and capacities for agricultural decision-making in changing and extreme environments | During the reporting period, significant progress has been made in the installation of the Agroclimatic Observatory in the MINAGRI units and work is being carried out to disseminate and implement it at a territorial level, and progress has also been made in defining the EMA site (automated meteorological station), that will deliver important data from the agroclimatic point of view. A permanent working table has also been created (Hydrological Table) with professionals from different entities at national and regional level (Universities: PUC, U de Concepción), state services (INIA, Chilean Meteorological Directorate, General Water Directorate, National Commission of Irrigation, Indap, Odepa, Ciren, CSIRO, among others) that have allowed to dimension the problem of drought in the territory and the scarce information and monitoring of groundwater, which are strongly affected by climate change conditions , climatic variability, shortage of rains and finally generating hydrological droughts. Currently, the project is in a position to start in year 2 the strategic implementation of transfer of agroclimatic information to at least 4988 farmers in the coastal dryland communes of the O'Higgins region. Through the information that is delivered by different means, it will allow the decision making that will reduce the risks of crop losses. Through the mass dissemination by local communication media, it is intended to advance the goal of reaching the total population of the area of ​​influence of the project, estimated at close to 50,000 people. | The appropriate information is generated and disseminated through the appropriate means. Together with the training, it improves decision making. • At least 4988 farmers (100% of the farmer population, direct beneficiaries, at least 1562 women) with a lower risk of extreme weather events (EWS 0-> 3). • 13 institutions (5 Ministry of Agriculture services and 8 municipalities) with greater capacity to minimize exposure to the risks of climate variability.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | The project generates lessons learned continuously, since it is the first initiative in Chile that deals with climate change,. The project has generated a strong commitment from national institutions, which work together to achieve the results of the project. The Government of Chile will take into account all results and best practices in new initiatives. The project implies a great experience at the Regional and National level
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There were delays in the administrative processes, specifically in the agreement between the Ministry of Agriculture and the Institute of Agricultural Research (INIA), because in Chile the system of control of all documentation and agreements that involve financing is very strict. Lastly, in Chile there was a change of government in March 2018, which meant several months of inaction, while the new authorities and in our case in particular the Project Director were internalized of the details. To remedy this situation, measures were taken. For example, the new authorities were instructed and provided with project information in a timely manner, so that the period in which the authorities took over and took control of the project was reduced to a minimum and there were no major difficulties.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Proposals for some changes will be made for the mid-term evaluation to improve the results in the field
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | As the project is just beginning, in terms of gender is working on the development of a good baseline to have an adequate diagnosis. There is already an initial survey in 600 farms to learn about gender equity issues and during the second year specific proposals will be worked on in the matter. The hiring of specialists to guide the work of the project is planned.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | The lessons learned are several, among which we can mention being able to access a short list of consultants specializing in this type of project, with proper management and criteria of the minimum list of feasible and necessary activities in a project type of adaptation to climate change . Take into account the administrative processes of internal approval in each State administration, since it can take up to 20 or 30% of the time of the project. Include with more force the activities of visibility of the project, as a powerful tool for disseminating good practices. Establish a "light" administration structure that allows parallel reviews in order to shorten the processes of issuing financial reports. Ensure direct dependence between the Project Director and the Technical Director and the Administration team in order to maintain agility in the processes.
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | The products are still in process most of them, so we still have no experience in its practical use in the terms proposed. If the different aspects are considered such as gender, training (which are in process), very important social and environmental aspects that will account for changes in crops, rotations, etc. that involve changes in uses and working customs maintained for decades.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | In our opinion, we still need to advance even more in the development of the project, in order to have an opinion regarding the lessons learned that would be relevant for future programs. These (the lessons) will be more evident as soon as progress is made in the development of the project. It is premature to draw lessons from a process that is still in full application.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Our perspective, as well as the selection of actions and territories of the project, is that it is replicable and sustainable over time, through its incorporation into the usual programs of accompaniment and promotion of agricultural activities developed by the permanent organisms of the State, which They are responsible for providing direct technical assistance to the farmers. The strength of this project lies precisely in working from the permanent institutions of the State, implementing a model and a change in the productive perspective.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | In the community, the greatest impact is the possibility of having additional water by means of rainwater collection and accumulation systems, allowing for innovative economic activities, such as greenhouse crops, as well as the improvement of their outdoor crops by the application of water accumulation techniques at the subsoil level.
What measures are/have been put in place to ensure sustainability of the project/program results? | The awareness of small farmers to face the effects of climate change is the main objective of the activities that will be developed in the 4 years of the project.
What measures are being/could have been put in place to improve project/program results? | It is a discussion that will be addressed in the mid-term evaluation
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | For this purpose, the diagnostic information included in the project design was included and an exhaustive survey was carried out (600 small farmers), which has served as a basis for improving knowledge. There is still more intervention in the field to improve the reality of the beneficiaries
If learning objectives have been established, have they been met? Please describe. | At this stage of the project it is too early to give answers to this question.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | In the project area there are other related activities, which are executed by other public services. Coordination with these entities has been slow, but measures are being taken to facilitate joint work and the transfer of information.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | In this stage of the project it is too early to give answers to this question
Note on C22: Jessica Farias Ibarra: ¿Cuál es el potencial para que las intervenciones concretas de adaptación emprendidas por el proyecto / programa se repliquen y amplíen tanto dentro como fuera del área del proyecto?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | CHL/NIE/Agri/2013/1
Implementing Entity | Ministry of agriculture (MINAGRI)
Type of implementing entity | Chilean International Cooperation Agency for Development (AGCID)
Country | Chile
Region | Latin America and Caribbean
Sector | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 4988 | 2208 | 2780 | Total | 51655 | 10331 | 41324 | Total |  |  |  | Total
|  | % of female beneficiaries | 31% | 31% | 31% | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 255 | Multi-sector | 3: Medium capacity | Total | 255 | Multi-sector | 3: Medium capacity | Total |  |  |  | Total | 1673
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted | 31%
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 255 |  | Public |  | 255 |  | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Multi-sector | 3: Medium capacity | Public | Regional | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 4988 | 31% | 2: Partially not aware |  | 4988 | 31% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.