## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 4 March 2019 to 4 March 2020
| Project Title: | Programme Support for Climate Change Adaptation in the vulnerable regions of Mopti and Timbuktu
| Project Summary: | The main objective of the programme is to increase the resilience of vulnerable communities and their adaptive capacity to climate change in the Regions of Mopti and Timbuctu including the Faguibine system zone. The programme has three components with the following specific outcomes: Component 1: Enhanced water control measures in vulnerable water buffer zones. Outcome 1: Increased climate change resilience of local water systems in Mopti and Timbuctu Regions. Component 2: Resilience in subsistence livelihoods of vulnerable communities. Outcome 2: The production of local livelihood systems such as agriculture, fisheries, livestock, and forest enhanced under climate change Component 3: Capacity-building and knowledge generation for adaptation Outcome 3: Enhanced capacity of local institutions and of communities to better adapt to climate change.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS No 4789 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme (UNDP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | UNDP as Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Mali | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Communes of Mopti Region : Bamba, Pelou, Kendé, Tédié, Koubewel-koundia, Gandamia, Dangol-Boré, Pondori and Togoro-Kotia. Communes of Timbuctu Region : Alafia, Hanzakoma, Haribomo, Goundam, Gargando, Bintagoungou, Essakane, Kondi, Arham, Tindirma, and Binga; | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 30/03/2015
IE-AFB Agreement Signature Date: |  | 04 November 2015 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 04 March 2016 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2018-06-01
| Terminal Evaluation Date: | 2020-04-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Reports: • Program Launch Report • Report on the situation of reference in Mopti and Timbuktu 2016 • PPR 2016, 2017 and 2018 • Quarterly and annuel Reports 2016, 2017, 2018 and 2019 to UNDP CO (Progress Report/Financial Reports/Quarterly Work Plan/Annual Work Plan) • Report of the Steering Committee 2016, 2017, 2018 and 2019 • Report of the extraordinary Steering Committee in 2018 • Project Website • Study report on the carbon sequestration rate of agroforestry parks in the project intervention zone. • Photos of construction sites and documentary films from 2017 to 2020 • Revision report on programme indicators and targets 2017 • Monitoring reports of naturally assisted regeneration and training of farmers in Agroforestery parks Of the communities of Bamba, Kendé and Dangol-Boré 2017, 2018 and 2019 • Farmers training report on improved seed cultivation techniques and improved seed monitoring (2017 and 2018 Aand 2019) • Farmers training report on agroforestry techniques adapted to climate change (2017 and 2018 and 2019) • Documentary film of project investments in Mopti in 2019 • Training report for Community counsellors and civil society on the institutional management of climate change (2017) • Training report for prefects, sub-prefects and technical agents of the State on taking into account SDOs in the management of climate change in the circles of Diré, Timbuktu, Bandiagara and Djenné in 2019. • Report on the training of farmers and elected officials on climatic and meteorological applications (2018) • Communication Plan Document of the programme 2018 • Work Plans and annual Budgets (2016, 2017, 2018, 2019 and 2020) • Status of implementation of the recommendations of the first, second, third and fourth session of the Programme Steering Committee • Report and Maps on land-use dynamics in relation to climate change in 20 communes • Project brochure for 2019 • Report set up and capacity building of investment management structures in the 8 communes of Mopti in 2018 • Mid-term evaluation report for 2018 • Training report of pilot farmers on conservation techniques for improved seed varieties in 2017, 2018 and 2019 • Study reports for 2016, 2017 and 2018 • Control and monitoring of works reports for 2017, 2018 and 2019 • 16 PDESC des communes revisés incluant les actions des changements climatiques et les ODD • Photo albums of the launch of the project and the steering committees | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.pacvmt-mali.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Balougo TELLY | Dominican Republic
| Email: | balougotelly@yahoo.fr | Ecuador
| Date: | 2020-02-20 | Egypt
| Government DA |  | El Salvador
| Name: | Boureima CAMARA | Equatoral Guinea
| Email: | bouricamara@gmail.com, Tel: +22366805756 | Eritrea
| Date: | 2020-02-20 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | United Nations Development Programme (UNDP) | Fiji
| Email: | oumar.tamboura@undp.org | Finland
| Date: | 2020-02-20 | France
| Executing Agency |  | Gambia
| Name: | Environment and Sustainable Development Agency (AEDD) | Georgia
| Email: | aedd@enironnement.gov.ml | Germany
| Date: | 2020-02-20 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 4 March 2020
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 04/03/2020 | $ 7 453 785,75
Add any comments on AF Grant Funds. (word limit=200) | The project has a cumulative disbursement to date of US$ 7 453 785,75 in March 2020 (4 years of implementation) and represents 95 % of the total funding. This cumulative total expenditure represents 95% of the cumulative disbursed amount (US $ 7 864 838) by UNDP from 2015 to 2019. The three disbursements planned in PRODOC were granted to UNDP (i) in June 2015 at the time of the agreement, (ii) in 2017 and (iii) in November 2019. The project is in its last year of implementation, closing in September 2020, with the final evaluation conducted in March-April 2020.
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT SPENT | AMOUNT COMMITTED | BALANCE
| Outcome 1: Increased climate change resilience of local water systems in Mopti and Timbuctu Regions. | 1102064.78 | 779072.7148 | -322992.0652
| Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 20 km silted channels and obstructed ponds | 286368.4451 | 115423.2036 | -170945.2415
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems | 815696.3349 | 663649.5112 | -152046.8237
| Outcome 2: The production of local livelihood systems such as agriculture, fisheries, livestock, and forest enhanced under climate change | 742256.5 | 905665.0454 | 163408.5454
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities | 515184.0839 | 617336.5652 | 102152.4812
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change | 130282.8148 | 228486.1661 | 98203.3513
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities | 96789.6013 | 59842.3141 | -36947.2871
| Outcome 3: Enhanced capacity of local institutions and of communities to better adapt to climate change. | 122294.74 | 232732.156 | 110437.416
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) | 106939.8379 | 106476.9287 | -462.9092
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) | 3551.4832 | 25037.9565 | 21486.4733
| Output 3.3 Local institutional capacity strengthened in 20 communities in establishing micro-credit schemes, cereal banks etc. and in managing | 11803.4189 | 101217.2709 | 89413.8519 |  |  | 0
| Project Execution Costs | 215304.19 | 198976.7715 | -16327.4185
| TOTAL AF | 2181920.21 | 2116446.6878 | -65473.5222 |  | 0
| COFINANCEMENT UNDP | 275136.41 | 275136.4142 | 0.0042422
| TOTAL AF and UNDP | 2457056.62 | 2391583.102 | -65473.518
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Outcome 1: Increased climate change resilience of local water systems in Mopti and Timbuctu Regions. | 219706.0793
| Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 50 km silted channels and obstructed ponds | 8138.2237 | March 2020 |  | 0 | 0
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems | 211567.8555 | March 2020
| Outcome 2: The production of local livelihood systems such as agriculture, fisheries, livestock, and forest enhanced under climate change | 243971.1637
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities | 186010.9581 | March 2019
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change | 33561.5161 | December 2019
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities | 24398.6895 | December 2019
| Outcome 3: Enhanced capacity of local institutions and of communities to better adapt to climate change. | 213088.9913
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) | 37290.5735 | March 2020
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) | 82571.9841 | December 2019
| Output 3.3 Local institutional capacity strengthened in 20 communities in establishing micro-credit schemes, cereal banks etc. and in managing | 93226.4337 | March 2020
| Project Execution Costs | 242868.9911
| TOTAL | 919635.2254
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | The total co-financing realized during this reporting period is estimated at US$ 275136,41 The cumulative realized co-financing since the start of the project is estimated at US$ 794,463.95 of which U$ 453 463,93 by UNDP and U$ 361,000,00 by the Government (for a total commitment of US$ 1,000,000) |  |  |  | 0
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | The cumulative co-financing as verified during Mid-term Review (MTR) in 2018 is estimated at USS 384,452.00 of which U$134,452,00 by UNDP and U$ 250,000.00 by the Government
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | Under the in kind co-financing of the Government of Mali, a building was made available for the project team. The Government also finances the cost of electricity, water and security services.The contribution for this reporting period is estimated at US$ 111,000.00 The co-financing of UNDP in 2019 is US 275136,41 which represents 55% of its co-financing planned over the total duration of the project. Since the project was extended at no cost, the co-financing of the UNDP will be much solicited, especially for the consolidation actions in terms of capacity building and project closure. The co-financing of UNDP was carried out by TRAC payment.
0
Note on F28: Microsoft: Les 450,84 constitue le salire d'un chauffeur
Note on H29: Microsoft: Ce depassement du PTBA est du (i) à la non maîtrise de l'évolution des travaux qui determine aussi l'engagement des paiements directs au niveau du PNUD. (iii) A noté aussi que 75% des chantiers engagés en 2019 ont été entièrement achevés et cela contrairement aux autres années et (iii) le PPR est à cheval sur le PTBA de l'année N et celui de l'année N+1. Par ailleurs, il faut signaler qu'au quatrième trimestre 2019, le projet était en rupture de fonds et en ce moment plusieurs paiements directs se trouvaient au niveu du PNUD. Ces paiements ont été tous engagés à l'arrivée de la dernière tranche en novembre 2019.
Note on F30: Microsoft: Les 1190,56 sont les fria de transport des petits matériels pour les périmètres maraichers.
Note on H30: Microsoft: En 2019, le PNUD a été fortement sollicité pour financer l'OMVF qui intervient dans les communes d'intervention du PACV-MT au niveau du Système Faguibine notamment la dotation des populations en intrants agricoles, leur formation sur les techniqus culturales et la sensibilisation par rapport à l'entretien des chenaux

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 50 km silted channels and obstructed ponds |  | Overburrowing of 2 channels 2.4 km from kondori and 3.8 km from youmna |  | 6.2 km of overburrow channels, including the 2.4 km long Kondori Channel (Photo in Appendix 3) and the 3.8 km long Youmna Channel. Work on these channels began in 2018 and was completed and handed over in 2019. | Satisfactory (S)
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems |  | Completion of 2 micro-dams (Engré in the Kendé , Orobane commune and,in Bamba commune ) |  | The Engré micro-dam was definitively built and developed by 400 farmers through the exploitation of about 2 ha of off-season market gardening and the irrigation of about 1.5 ha of rice plots downstream. Work on the Orobane micro-dam is at 70% and the company's contract has been terminated because the area around the site is still blocked by jihadists. Despite the incomplete completion of the works, the population is satisfied with the level of execution of the works and the impact is very visible on agricultural and pastoral activities. The micro-dam retains water upstream in the major riverbed, which forms a depression. The mini-dam has also promoted the supply of water tables in the catch basins that are used to water plots of squash, watermelon, gourds, cassava and sweet potato. The pond is also supplied with water to promote plant and animal biodiversity. The pond is also supplied with water to promote plant and animal biodiversity. In addition to agricultural activities, there are many depressions that contain fish . The watering of animals is made possible. | Satisfactory (S)
|  |  | Construction of 5 news summary water conveyances (AES) and completion of 9 old AES (Djera, Kendé, Wedié, Andji,Mougui, Dembely, Boré, Birol-Adioda and Fedji Hoye) |  | 5 new AESs are executed (Gomitgo, Dantiandé, Mougui-Dembely, Kel Antessar II and Hanzagoungou) at 100% and received. 7 old AES are completed and definitively received (Djera, Kendé, Wedié, Andji, Mougui, Dembely and Boré). All these AES are intended to provide drinking water to the population. The Fedji Hye borehole flow rate is low (1 cubic meter per hour) and that of Birol Adioda is considered negative. A negative borehole (no trace of water) and a low flow rate borehole (1m3/h in our case) are all considered negative as they cannot be equipped. So they are abandoned to look for another site. The company's contract has been terminated and it is paid on a prorota basis for the work carried out. | Marginaly Satisfactory (S)
|  |  | Installation of 2 floating cages of 180 m3 for 20,000 fry on behalf of a fishermen's association of 35 members including 9 women. |  | 2 floating cages installed with the technical support of the local fishing service of Diré and stocked with 20,000 fry of Tilapia species in the Binga commune for 35 people including 7 women from the fishermen's association of Bougouberi. | Highly Satisfactory (HS)
|  |  | Development of the Toupéré pond (1) and completion of 4 ponds (Orobane, Pelou, Tabaco, Adia, etc.). |  | The works on the Toupéré pond are 90% completed and the banks are reforested with 1,300 feet of eucalyptus. The Orobane pond has been received Les travaux des mares de Pelou, Tabaco et Adia sont à environ 65% Work on the Pelou, Tabaco and Adia ponds are at about 65%. | Satisfactory (MS)
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities |  | Training of 468 pilot farmers, including 318 on cowpea cultivation technical itineraries and 150 pilot farmers on cowpea seed conservation techniques |  | 468 farmers trained, 318 of whom have mastered cowpea cultivation techniques and 150 have mastered improved cowpea seed conservation techniques by the Koporo-pen agricultural research station. | Highly Satisfactory (HS)
|  |  | Granting of 5,800 kg of improved and adapted varieties including 2,800 kg of cowpeas to 318 pilot farmers in 07 communes and 3,000 kg of rice to 15 farmers of the Togoro-Kotia commune . |  | 5,800 kg granted, including 1,400 kg of KOROBALEN cowpea, 1,400 kg of WULIBALI cowpea and 3,000 kg of Gambiaka rice. | Highly Satisfactory (HS)
|  |  | Completion of 9 market gardening areas (Déguéré, Gomitogo, Kandé, Toya, Goundam, Arham, Bugouberi, Bangadria and Goungoume) and development of 4 market gardening areas (Togoro sarré, Sossolbé, Guinédia and Irebane). |  | 11 market gardening perimeters completely completed, 6 of which have been received definitively (Déguéré, Gomitogo, Kandé Bougouberi, Bangadria and Goungoume) and 5 of which have been received provisionally (Toya, Arham and Goundam). The 2 market gardening perimeters are at a 60% execution rate in a highly insecure area. These are the market gardening perimeters of Guinédia and Irebane in the Bamba commune , Mopti circle, Mopti region. The completion concerns the works started in 2018, with some finishing work to be carried out in 2019 for final acceptance. The development concerns the construction sites started in 2019. | Satisfactory (S)
|  |  | Repair of the fence of 2 market gardening perimeters (Obé and Saourakom) |  | 2 fences repaired | Highly Satisfactory (HS)
|  |  | Construction of a storage warehouse for market gardening products for the women of Goundam |  | The store was entirely built and handed over in June 2019 for 76 women who operate the market gardening perimeter. | Highly Satisfactory (HS)
|  |  | Granting of 115.5 kg of improved garden seeds to 1,305 women from 8 market gardening perimeters set up in Mopti to 11 market gardening perimeters |  | Granting of 115.5 kg of improved seeds (onion, tomato, carrots, potatoes, apple, beet, salad and okra) for 1318 women. | Highly Satisfactory (HS)
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change |  | Training and equipment of 350 farmers on anti-erosion techniques through stony cords. |  | 350 pilot farmers, including 25 women, are trained and have mastered the techniques for building stone cords, either 100% completion rate. | Highly Satisfactory (HS)
|  |  | Training of 180 farmers on Assisted Natural Regeneration (ANR) techniques in the Bamba, Kendé and Dangol-Boré.communes |  | 180 farmers master the techniques of the ANR in the Tédié, Koubewel-Koundia and Dangol-Boré and Pondori communes . | Highly Satisfactory (HS)
|  |  | Support of agroforestry workers in the monitoring of assisted natural regenerations |  | The monitoring of assisted natural regeneration in the agroforestry parks was carried out in three phases: July, September and December. This monitoring allowed us to observe that the number of young shoots (0-50 cm) in the agroforestry parks decreased by 41% in the seno and 13% on the plateau, while the situation is stationary in the flood zone. It is planned to organize workshops to capitalize on these experiences at the level of each commune in order to reach the populations. A total of 7 agroforests, including 3 in the Seno area, 2 on the Dogon tray and 2 in the flood zone are supported. Two agents specialized in agroforestry from the Tropical Ecology Laboratory of the Faculty of Science and Technology of Bamako provided support to the 7 agroforestry workers. | Highly Satisfactory (HS)
|  |  | Development of land-use dynamics in the face of climate change from 1986 to 2016 for 13 communes |  | 13 land occupation dynamics between 1986 and 2016 are established for 13 communes (7 in Timbuktu and 6 in Mopti) on the recommendation of the National Steering Committee, held in Mopti on 26 December 2018. The use made or to make of this exercise was largely explained in the PPR 2018 | Highly Satisfactory (HS)
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities |  | Support and supervision of women for the exploitation of 6 ha of market gardening perimeters in Timbuktu of Goundam, Arham and Alafia. |  | Memorandum of understanding with the Timbuktu Regional Directorate of Agriculture to supervise the support of the NGO ADIL, which provides support and supervision to 424 farmers, 399 of whom are women. This supervision covers the market gardening campaign and ends in April 2019. The NGO coaches women on cultivation techniques, pest control techniques, and capacity building of the management committee on maintenance and repair of facilities. | Satisfactory (S)
|  |  | Granting of a batch of small materials consisting of 30 units of daba, hoes, watering cans and buckets and 20 units of shovel, spades and wheelbarrows for the three (03) market gardening perimeters of women in Timbuktu |  | Granting of a batch of small materials consisting of 30 units of daba, hoes, watering cans and buckets and 20 units of shovels, spades and wheelbarrows to the market gardening perimeters of Alafia, Goundam, and Arham for 424 farmers including 399 women | Highly Satisfactory (HS)
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) |  | Training of 135 technical services officers including the prefect and sub-prefects of the project communes |  | 101 agents trained in Bandiagara, Djenné, Diré, Goundam and Timbuktu circles | Satisfactory (S)
|  |  | Revision of 15 communal PDESC by integrating adaptation options |  | 11 communal PDESC of Timbuktu are revised by integrating adaptation options to climate change | Marginaly Satisfactory (MS)
|  |  | Support for the access of 20 communes to meteorological and agro-climatic information |  | 20 communes are regularly informed about weather forecasts through bulletins provided to local radio stations by the National Meteorological Agency MALI-METEO. This information allows farmers to better understand the course of the agricultural season (month of arrival of the first rains, sowing period, rainfall cessation, etc.). | Satisfactory (S)
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) |  | Realization of 2 films and photo libraries on the investments (Mopti and Timbuktu) |  | 01 30-minute film and photo library were made on certain investments by Mopti and broadcast on ORTM television. The Timbuktu project is currently underway. It is planned to make a complete film capitalizing on the achievements of the project in the two regions with interviews (Beneficiaries, project team, Elected officials, Technical services, administration, UNDP, AEDD, MEADD) | Marginally satisfactory (MS)
|  |  | Monitoring of the first cycle of the fattening of 380 small ruminants by 570 women from 38 associations in the 11 communes of Timbuktu. |  | The first cycle ended in March-April 2019. The cost price per head at the end of the cycle is 54.875 FCFA minimum and 56.020 FCFA maximum. The profit per capita is 6.410 FCFA minimum and 8.365 FCFA maximum. There was a 2% loss (8 heads). | Satisfactory (S)
| Output 3.3 Local institutional capacity strengthened in 20 communities in establishing micro-credit schemes, cereal banks etc. and in managing |  | Supply of 25 tonnes of cereals to 4 cereal banks in the Bamba, Togoro-Kotia, Bintagoungou and Gandamia communes |  | 3 cereal banks supplied with 15 tonnes of cereals in the Bintagoungou, Gandamia and Togoro-Kotia communes, | Satisfactory (S)
| Project Execution Costs |  | Operation of 3 offices including 1 national and 2 regional offices with a staff of 6 agents including 2 drivers. |  | 3 offices including 1 national and 2 regional with a staff of 6 agents including 2 drivers is functional | Satisfactory (S)
|  |  | Organization of 10 supervision missions and 8 joint missions for the acceptance of works by the Regional Directorates of Technical Services and 1 annual meeting of COPIL members |  | 8 supervision missions carried out by the STDs and 5 joint works acceptance missions carried out by the STDs and the project team | Satisfactory (S)
|  |  | Organization and holding of the third session of the steering committee |  | The fourth session of the steering committee was held on December 26, 2019 and 04 recommendations were made, namely:  Complete the investments in the course of the case study of the 3 municipalities of the Mopti region;  Consolidate the achievements of the project, especially in terms of repairing certain investments and strengthening their level of functionality;  Hold a steering committee in June, before the end of the project in September 2020;  Increase the PTBA 2020 in agreement with the UNDP. | Highly Satisfactory (HS)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Balougo TELLY
| Email: | balougotelly@yahoo.fr
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
In 2019, certain activities could not be carried out. These are: (i) supplying the cereal bank of the commune of Bamba in the KORO circle because of insecurity. The Mayor was not able to negotiate with the Famas and Dogon hunters and this led to a reluctance of suppliers to transport cereals (ii) the adjustment of the 4 remaining CESDPs in the Mopti region could not also be carried out because of insecurity. This situation did not favour the regrouping of village delegates in the chief towns of the communes concerned and finally (iii) the failure to make a film on the project's achievements in Timbuktu. For more visibility, it was decided with the Mayors to make this film in January 2020 where women are active in the market gardening campaign. Apart from these activities, the other planned activities were carried out correctly and on time. Considering that project activities planned for current reporting period are progressing on track to achieve most of the project's major outcomes with only minor shortcomings, the project can be rated as satisfactory
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 50 km silted channels and obstructed ponds |  | Overburrowing of 2 channels 2.4 km from kondori and 3.8 km from youmna |  | The overburrowing of these two channels has favoured the gravity-fed irrigation of about 500 ha of rice plots in the Kondi and Arham communes in the Timbuktu region. | satisfactory (S)
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems |  | Completion of 2 micro-dams (Engré in the Kendé , Orobane commune and,in Bamba commune ) |  | All water supply were 100% completed but the product was not satisfactory at Fedji-Hoye (low flow drilling) and Biro-Adioda (negative drilling). In spite of the satisfaction of the population, the works of the Orobane micro-dam are not completed due to insecurity. | ,
Construction of 5 news summary water conveyances (AES) and completion of 9 old AES (Djera, Kendé, Wedié, Andji,Mougui, Dembely, Boré, Birol-Adioda and Fedji Hoye)
Development of the Toupéré pond (1) and completion of 4 ponds (Orobane, Pelou, Tabaco, Adia, etc.).
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities |  | Training of 468 pilot farmers, including 318 on cowpea cultivation technical itineraries and 150 pilot farmers on cowpea seed conservation techniques |  | Agricultural production in the face of climate change has been secured and improved through the provision of 5,800 kg of improved seeds to 333 farmers. The 11 market gardening perimeters contracted were fully implemented and this has effectively empowered more than 1,000 women to increase their income and improve family nutrition. | satisfactory (S)
Granting of 5,800 kg of improved and adapted varieties including 2,800 kg of cowpeas to 318 pilot farmers in 07 communes and 3,000 kg of rice to 15 farmers of the Togoro-Kotia commune .
Completion of 9 market gardening areas (Déguéré, Gomitogo, Kandé, Toya, Goundam, Arham, Bugouberi, Bangadria and Goungoume) and development of 4 market gardening areas (Togoro sarré, Sossolbé, Guinédia and Irebane).
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change |  | Training and equipment of 350 farmers on anti-erosion techniques through stony cords. |  | Capacity building of farmers on water and soil conservation techniques, particularly anti-erosion control through stone cords and agroforestry practices adapted to climate change, will help to secure cropland, improve the vegetation cover of agroforestry parks and agricultural production., | Satisfactory (S)
Training of 180 farmers on Assisted Natural Regeneration (ANR) techniques in the Bamba, Kendé and Dangol-Boré.communes
Support of agroforestry workers in the monitoring of assisted natural regenerations
Development of land-use dynamics in the face of climate change from 1986 to 2016 for 13 communes
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities |  | Support and supervision of women for the exploitation of 6 ha of market gardening perimeters in Timbuktu of Goundam, Arham and Alafia. |  | The women have been provided with small gardening equipment and their technical support and guidance for the operation of market gardening perimeters is effective thanks to the memoranda of understanding signed with the Regional Directorates of Agriculture in Mopti and Timbuktu. Women in the Mopti Region have more experience in market gardening than those in Timbuktu. so, in Timbuktu, an NGO has been recruited to supervise women. | Satisfactory (MS)
Granting of a batch of small materials consisting of 30 units of daba, hoes, watering cans and buckets and 20 units of shovel, spades and wheelbarrows for the three (03) market gardening perimeters of women in Timbuktu
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) |  | Training of 135 technical services officers including the prefect and sub-prefects of the project communes |  | 57 elected officials, including 11 women, and 140 farmers, including 50 women, participated in the process of revising the PDESC and their capacities were strengthened to integrate risk management into communal plans. Mali Météo provides regular agro-climatic and meteorological information bulletins. Through local radio stations, farmers are regularly informed for better planning of communal development. | Satisfactory (MS)
Revision of 15 communal PDESC by integrating adaptation options
Support for the access of 20 communes to meteorological and agro-climatic information
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) |  | Monitoring of the first cycle of the fattening of 380 small ruminants by 570 women from 38 associations in the 11 communes of Timbuktu. |  | This first cycle of fattening enabled the women to make a profit through the sale of the animals. Having always the capital at their disposal, they continue the activity to significantly improve their income. | Satisfactory (MS)
Realization of 2 films and photo libraries on the investments (Mopti and Timbuktu)
| Output 3.3 Local institutional capacity strengthened in 20 communities in establishing micro-credit schemes, cereal banks etc. and in managing |  | Supply of 25 tonnes of cereals to 4 cereal banks in the Bamba, Togoro-Kotia, Bintagoungou and Gandamia communes |  | Out of 4 cereal banks, 3 have been supplied in order to make the cereal accessible to the population during the lean season and field work.
| Project Execution Costs |  | Operation of 3 offices including 1 national and 2 regional offices with a staff of 6 agents including 2 drivers. |  | The monitoring and supervision missions were normally carried out thanks to the involvement of the Regional Directorates through memoranda of understanding. In addition, the ordinary steering committee made 4 recommendations, the most important of which concerns the consolidation of achievements. | Satisfactory (S)
Organization of 10 supervision missions and 8 joint missions for the acceptance of works by the Regional Directorates of Technical Services and 1 annual meeting of COPIL members
Organization and holding of the third session of the steering committee
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | United Nations Development Programme (UNDP)
Oumar TAMBOURA
| Email: | oumar.tamboura@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
At output 1.1, the overburrowing work has been carried out correctly. Most of the investments initiated in relation to access to water at output 1.2 level have been completed, accepted and officially handed over to the beneficiaries. The design of market gardening schemes for women has been completed in the two regions of output 2.1, which also determines the capacity building of women in output 2.3. In addition, it should be noted that the supply of cereals to a highly food insecure bank in output 3.3 was not possible due to insecurity. The number of adjusted FHDPs (output 3.1) is acceptable (80% of revised PDSEC) but 4 PDSEC remain to be revised. There also remains the making of the film on Timbuktu's achievements.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
| Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 50 km silted channels and obstructed ponds |  | Overburrowing of 2 channels 2.4 km from kondori and 3.8 km from youmna |  | The work is of very good quality. These functional channels will contribute to the food self-sufficiency of the beneficiaries through the exploitation of the rice plains. | Higtly Satisfactory (HS)
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems |  | Completion of 2 micro-dams (Engré in the Kendé , Orobane commune and,in Bamba commune ) |  | The project has made huge investments that improve access to water for multiple uses. The Orobane micro-dam, 60% of which has been completed, remains incomplete due to insecurity but is functional according to the populations. In addition, 2 summary water supply in the Gandamia Commune are negative and cannot provide water. | Marginaly Satisfactory (MS)
Construction of 5 news summary water conveyances (AES) and completion of 9 old AES (Djera, Kendé, Wedié, Andji,Mougui, Dembely, Boré, Birol-Adioda and Fedji Hoye)
Development of the Toupéré pond (1) and completion of 4 ponds (Orobane, Pelou, Tabaco, Adia, etc.).
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities |  | Training of 468 pilot farmers, including 318 on cowpea cultivation technical itineraries and 150 pilot farmers on cowpea seed conservation techniques |  | The adaptation of agricultural production systems at the level of farmers is made possible through the provision of improved seeds and training on cultivation techniques. Gender considerations are well integrated, with more than 10 market gardening perimeters entirely exploited and managed by women and their children. This time men are considered indirect beneficiaries. Because of the insecurity, the market gardening perimeters of Guinédia and Irebane in the Bamba commune, Koro circle is still in progress with the hope of completing them by the end of May 2020. | Satisfactory (S)
Granting of 5,800 kg of improved and adapted varieties including 2,800 kg of cowpeas to 318 pilot farmers in 07 communes and 3,000 kg of rice to 15 farmers of the Togoro-Kotia commune .
Completion of 9 market gardening areas (Déguéré, Gomitogo, Kandé, Toya, Goundam, Arham, Bugouberi, Bangadria and Goungoume) and development of 4 market gardening areas (Togoro sarré, Sossolbé, Guinédia and Irebane).
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change |  | Training and equipment of 350 farmers on anti-erosion techniques through stony cords. |  | All the activities planned in terms of capacity building have been executed with satisfaction | Satisfactory (S)
Training of 180 farmers on Assisted Natural Regeneration (ANR) techniques in the Bamba, Kendé and Dangol-Boré.communes
Support of agroforestry workers in the monitoring of assisted natural regenerations
Development of land-use dynamics in the face of climate change from 1986 to 2016 for 13 communes
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities |  | Support and supervision of women for the exploitation of 6 ha of market gardening perimeters in Timbuktu of Goundam, Arham and Alafia. |  | In Mopti and Timbuktu, the project has signed memoranda of understanding with the technical services of the State, particularly the agricultural sector, to provide support and advice to women in the exploitation and management of market gardening perimeters. The involvement of these state services in project implementation is a major asset for the sustainability of the project's achievements. | Higtly Satisfactory (HS)
Granting of a batch of small materials consisting of 30 units of daba, hoes, watering cans and buckets and 20 units of shovel, spades and wheelbarrows for the three (03) market gardening perimeters of women in Timbuktu
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) |  | Training of 135 technical services officers including the prefect and sub-prefects of the project communes |  | The revision process of the PDESC was completed in 11 communes of Timbuktu in 2019. Because of the growing insecurity in the center, the process in the 4 communes of Mopti could not be carried out | Satisfactory (S)
Revision of 15 communal PDESC by integrating adaptation options
Support for the access of 20 communes to meteorological and agro-climatic information
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) |  | Monitoring of the first cycle of the fattening of 380 small ruminants by 570 women from 38 associations in the 11 communes of Timbuktu. |  | Such actions are encouraging to improve women's income and especially their self-promotion. | Satisfactory (S)
| Output 3.3 Local institutional capacity strengthened in 20 communities in establishing micro-credit schemes, cereal banks etc. and in managing |  | Supply of 25 tonnes of cereals to 4 cereal banks in the Bamba, Togoro-Kotia, Bintagoungou and Gandamia communes |  | 75% of the banks planned for 2019 have been supplied with cereals. However, the communes must demonstrate good stock management in a situation of insecurity. | Satisfactory (S)
| Project Execution Costs |  | Operation of 3 offices including 1 national and 2 regional offices with a staff of 6 agents including 2 drivers. |  | Monitoring missions at the national level were possible thanks to the supervision missions of the Regional Directorates. The 2019 steering committee was held and the members strongly appreciated the results obtained by the project. | Satisfactory (S)
Organization of 10 supervision missions and 8 joint missions for the acceptance of works by the Regional Directorates of Technical Services and 1 annual meeting of COPIL members
Organization and holding of the third session of the steering committee
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Environment and Sustainable Development Agency (AEDD)
Boureima CAMARA
| Email: | bouricamara@gmail.com, Tel: +22366805756
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | During 2019, the execution rate of the PTBA was satisfactory, with 97.26% of targets achieved. Despite the security situation, the programme was able to implement several activities in the 10 communes of the Great Green Wall, which is a multi-year programme of the Government. The greatest satisfaction was that contrary to previous years, 75% of the investments committed in 2019 were fully implemented and received thanks to the involvement of local companies. This situation was the immediate effect of the implementation of one of the recommendations of the 2018 steering committee "Give priority to local companies for the execution of works in the communes". The year 2020 will be mainly devoted to the consolidation of the achievements, the completion of the committed investments, the final evaluation of the project and the closing of the project.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
L
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Armed conflict that has recently escalated and engulfed the Northern region of Mali | Medium | In recent months, there has been a decrease in violence in the regions of North Mali. The situation is also in slight decline in the centre of the country. However, the tree should not hide the forest, as sporadic exactions against civilians and civilian positions of our armed forces are noted. The Government of Mali has engaged in dialogue with the two major figures of terrorism in the Sahel-Saharan strip. Mali is gradually recovering its territorial integrity, in particular through the deployment of the reconstituted army in all regions of the North, including KIDAL, which for the past six years has been outside the control of the Malian State. In Mopti, the security situation is on the rise in the commune of Bamba. In this commune, the development of two market gardening perimeters is underway. The Enterprise team used the plateau and cliff corridor instead of the Seno River to transport staff and small equipment. Regarding the drilling workshop, the Mayor of Bamba and the Company are negotiating with a workshop of the Armed Forces to go and drill the two perimeters. The end of this work is expected by March 30, 2020. In Timbuktu, we signed a memorandum of understanding with the NGO ADIL6Mali to supervise women in the exploitation of market gardening areas. Concerning the supervision of works, several protocols were signed with the Regional Directorates of State Technical Services in Mopti and Timbuktu. They concern agriculture, water and forestry, fishing in Timbuktu, rural engineering in Mopti and hydraulics in Mopti.
Delays in project inception impacts the achievment of the outputs and outcomes and reduces the scope to deliver the project as outlined in proposal | Highly Low | The 18-month extension will have enabled the project to achieve the results and targets set out in the PRODOC. By the end of May, we expect to close all the project commitments (receipt of all the investments made, payment of the companies) with the service providers and also to carry out the final evaluation of the project. The consolidation of the assets has already started and will continue until the end of the project. Before the withdrawal of project, the women will be provided with improved seeds for gardening for the 2020-2021 market gardening season.
A poor collaboration between programme partners | Highly Low | All project stakeholders (UNDP, AEDD, Governors of the 2 regions, Ministries and their technical services members of the steering committee, communal authorities and beneficiary populations, partners and NGOs working in the same area) are strongly involved in the implementation of the project and collaboration at all levels is fruitful.
A poor understanding of the objectives by the programme team | Highly Low | The project team has a perfect command of the project (implementation strategy, administrative, institutional and financial management, targets and expected results and issues) as well as risk management.
Low mobilization of the target group caused by a poor understanding of climate change issues | Low | As mentioned in previous RPPs, the mobilization of beneficiary populations does not pose a problem. All that is needed is to plan the activity well with the elected municipal officials, particularly the mayor. This year, the grouping of beneficiaries has allowed the revision of 11 PDESC in Timbuktu, the training of technical services on climate change in Mopti and Timbuktu, the training of pilot farmers on water and soil conservation techniques and the meeting on the assessment of the improved seeds campaign.
Lack of sufficiently qualified partners | Highly Low | There is no lack of skills and qualifications in the project areas. It is only necessary to take them into account at the beginning of the project in the procurement process. The proof is that, on the recommendation of the 2018 steering committee, we gave more contracts to local companies in 2019 and all these local companies received 100% of the work before the winterization. This is the first time since the start of the project that contracts from the same year have been fully executed. Some of the 2017 contracts executed by Bamako companies are completed in 2019 at the same time as those of local companies. The type and procedure of procurement contributes to 40% of the level of activity implementation for projects that make investments.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The long national procurement procedure applied to investments delays the project implementation | Neant | The lengthy procurement procedure is no longer a risk with the recommendation of the 2018 steering committee "Give priority to local companies for the execution of works in the communes" and the transfer of project ownership to the communes for studies and capacity building.
Le communiqué du Chef d'Etat Major Général de Armées du 01 février 2018 qui limite le déplacement du projet dans la region de Mopti | Neant | The press release of the Chief of staff General of the Armies of 1 February 2018, which limits the movement of the project in the Mopti region.. This press release has been lifted.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
Concerning the monitoring and technical supervision of the works in 2019, the protocols of formal collaboration with the local technical services in the 2 regions which was one of the recommendations of the steering committee of 2018 compensated the monitoring mission of the members of the steering committee and contributed to the quality of the works

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Indicators towards Outcome 1 | % increase in functional waterways and channels in the targeted communes | Only about 15% of the waterways and channels are functional or 25 in total | 5 channels (Dialamba, Dialal, Bintagoungou-Essakane, Goundam-TV and Bintagoungou-Issabery in the faguibine sytem) and 3 waterways (water supply waterways of the Boré, Kondori and Youmna pond) are functional; A total of 33 chanels and waterways are now functional, taking into consideration the baseline, reaching 94.28% of achievement. | Functional waterways and channels increased by about 40 % or 35 in total
| Km increase of cleared water channel | Currently about 50 km of the water channels are cleared | 43.125 km of canals are unblocked by the project, of which 2.9 km irrigate 150 ha of rice fields in the commune of Togoro-Kotia, 12 km supply a chain of ponds including Boré pond and secure certain riverside villages against flooding. 22.025 km feed a series of ponds and lakes in the Faguibine system. 2.4 km from the Kondori channel and 3.8 km from Youmna respectively in the commune of Kondi and Arham protect around 200 ha of rice plains against flooding. A total 93,125 km of unlocked canals are cleared, taking into consideration the baselien, reaching 86.25% of achievement. | 100 km increase of cleared water channel
Indicators towards Outcome 2 | Number of developed market gardening perimeters of at least 0.5 Ha each and managed by women. | There are presently few market gardens and no community fish farms. | 16 market gardening perimeters (Obè, Saourakom, Adia, Gomitogo, Kande, Déguéré, Dialloubé, Goungoumé, Bougouberi, Bangadria, Alafia, Goundam, Arham, Togoro-Sarré, Feindoukaina, Sossobè), covering at least 25.5 ha, were introduced. In addition, 2 market gardening perimeters are being developed (Irebane and Bamba) and 1 market gardening perimeter (perimeter of the NIMALYA association) is being secured. | 20 périmètres maraîchers d’au moins 10 ha.
| Number of fish farms developed and managed by the community. | There are presently no community fish farms. | 12 fish farms including (5 fish ponds in the municipalities of Tindirma on behalf of the association ISSABOIREY, 05 fish ponds (Koirabery, Orobane, Pelou , Adia and Touperé) were installed and are functional and 02 fish cages functionnal. This output has been completed at around 60%. | 20 community fish farms established
| Number of communal nurseries of local land species. | Few communities benefit from community managed tree nurseries | 15 nurseries including 8 community nurseries in the Mopti region are being developed and 7 individual nurseries in the Timbuktu Region have been set up. A total of 231 people, including 176 in Mopti and 55 in Timbuktu, are trained in plant production techniques and equipped with small equipment (pots and watering cans) to encourage community reforestation activities.The final target was achieved. | At least fifteen (15) communal nurseries.
Indicators towards Outcome 3 | Number of local official trained in institutional management of climate change | No local councilors trained to enhance their institutional capacity to adapt to climate change | 274 elected representatives (including 38 women), 40 people from civil society (of which 20 women) and 101 state technical agents are trained on the management of climate change, a total of 415 people, including 58 women. The final target was achieved. | 100 local councilors and 40 civil society people including 40 women are trained
| Number of PDESC revised in including climate change management | Just about 6 PDESC currently include climate change management | 11 PDESC (communes of Pondori, Pelou, Kendé, Koubewel-Koundia, Tédié, Alafia, Goundam, Kondi, Arham, Binga, Tindirma, Essakane, Bintagoungou, Gargando, Hanzakoma and Haribomo) have been revised by integrating the CC adaptation options. A total of 390 farmers, 109 of whom were women, were trained to better take into account climate change adaptation in the planning and budgeting of development actions. The final target, including the baseline, was reached oat around 80%. | 20 local community plans will be developed to include climate change management

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | During 2019, we learned two good lessons that very positively affected the results of the project, namely: (i) the priority given to local companies for the completion of the works to enable 100% of the works to be carried out and (ii) formal memoranda of agreement for monitoring and supervising work with the Regional Directorates of Technical Services, which are the legal representatives of the member structures of the steering committee.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | As announced in the PPR 2018, the works contracts of 3 companies of Bamako have been terminated and the works will be completed in concert with the Mayors, giving priority to local companies.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The only change is that the contracts of the 2 focal points ended in December 2019 due to insufficient financial resources on the project's operating line. Today in each of the regions of intervention, we rely on the memoranda of understanding with the technical services to ensure the monitoring of activities. The protocols are in line with their regalian competencies and the communes in the context of decentralization can always ask for their support and accompaniment.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | To date, 16 market gardening perimeters are functional and exclusively managed by women in the regions of Mopti and Timbuktu. The project still places special emphasis on gender and this was welcomed by the members of the steering committee on 26 December 2019 held in Bamako. The representative of the Ministry in charge of Women, Children and Family asked the project to share the results on gender at the level of his department for a wide dissemination at the national level. The results obtained are as follows: (i) 12,133 women have seen their capacity strengthened with inputs, equipment and training with a view to relaunching AGRS, including 11,563 women working on 28.3 ha of market gardens and 570 women fattening small ruminants, (ii) 59,337 women have seen their access to drinking water improved, (iii) 481 women have seen their fish production improved, (iv) 1, 362 young people and 92 women are trained in agro-sylvo-pastoral production techniques and yield improvement, particularly agro-forestry, water and soil conservation techniques, plant production and adapted cultivation techniques, and (v)109 women, including 16 elected women and 93 women farmers, are trained in techniques for revising Economic, Social and Cultural Development Plans (PDESC) using the climate profing tool. Family health has improved with clean drinking water as well as the nutritional quality of households. Strengthened solidarity among the women of the village, as they share the responsibility for managing investments, particularly market gardening perimeters and drinking water points.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | In addition to the 5 points highlighted in the PPR 2018, two other relevant measures will have to be added, namely (i) having a flexible procurement procedure reflecting the realities and conditions in which the project operates and (ii) exploiting local expertise, in particular through the recruitment of local companies to carry out the investments.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | ,In addition to the dynamics of land use in the face of climate change, labour-based work and the integration of adaptation actions into the PDESC, we can also mention the communal project management supported by the project.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Use ways and means to avoid the long DGMP procedure and especially to favour local companies in the procurement of works contracts. At the beginning of the project, when it is launched, the type of contracting authority must be precise to avoid disagreement between the supervisory authority and the project team. Each time the tutorship gets in front of the contracting process, the projects have difficulty in managing the contracts. It is technically easier and more efficient to manage the contracts of local companies than those in Bamako. Local companies have a better command of the field and are closer to the work. Bamako companies are mostly represented by agents who do not tell them the realities of the construction site and this leads to discrepancies with the control.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The populations of central and northern Mali were very vulnerable before the crisis. Today, despite the various interventions, the crisis has increased their vulnerability with regard to access to drinking water, the empowerment of women in production through the development of vast market gardening perimeters and the creation of ponds for watering animals. Much will need to be done to orient women and young people towards production. The administrative authorities in the project's area of intervention all state that the project has had a very positive impact on the living conditions of the populations despite the security situation. They would like the project to be replicated by broadening the scale of activities and the intervention zone. They suggest the idea of a unifying programme based on the strategies and achievements of this project.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | In addition to access to water for multiple uses (water conveyance, development of market gardening perimeters, development of ponds, construction of micro-dams, overburrowing of channels), the RNA and the adjustment of the PDESC, we can add anti-erosion control. Contrairement à beaucoup de projets changements climatiques qui mettent en avant les technologies, ce projet dans sa particularité a comme porte d'entrée "l'accès à l'eau" qui est une condition sine-quanum pour les autres activités de résilience (agriculture, Foresterie, Elevage, Pêche). Les RNA et la lutte anti-érosive sont des techniques qui permettent à priori la stabilité du sol en augmentant sa capacité de retention de l'eau à travrers l'infiltration des précipitations avec des effets induits tels que la resturation du couvert végétal et la fertilité du sol. La planification du développement communal dans le contexte de cchangements climatqiues passe obligatoirement ar le renforcement de capacité des acteurs à adapter les PDESC. Unlike many climate change projects that focus on technology, this particular project has as its entry point "access to water" which is a sine-quanum condition for other resilience activities (agriculture, forestry, livestock, fisheries). RNA and anti-erosion are techniques that a priori allow the stability of the soil by increasing its capacity to retain water through the infiltration of rainfall with induced effects such as restoring the plant cover and soil fertility. The planning of municipal development in the context of climate change necessarily involves strengthening the capacity of the actors to adapt the PDESC.
What measures are/have been put in place to ensure sustainability of the project/program results? | In addition to the management committees, the involvement of the Regional Directorates of Technical Services facilitates the integration of the monitoring of achievements in their regalian function even after the project. The management committees are structures which are the direct beneficiaries of the project's achievements and which will benefit from the support of the commune through the implementation of future PDESC. The communes also benefit from the technical support and supervision of the decentralized technical services of the State.
What measures are being/could have been put in place to improve project/program results? | Local management committees for all investments are set up and the Mayors ensure their functionality. By March 2020, a service provider will visit all municipalities to capitalise on the level of functionality of these structures.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The information bulletins provided by Mali-Météo are broadcast by certain radio stations in the project's intervention zone.
If learning objectives have been established, have they been met? Please describe. | 350 farmers, including 28 women, are trained in anti-erosion techniques through stone cords. Cultivated land are threatened by water erosion and in order to fix the soil and promote water infiltration, the farmers build dikes in the fields. This action, combined with assisted natural regeneration, is a technique for making croplands resilient to climate change. Natural regeneration and anti-erosion are local practices. With these trainings, the technique of these practices is adapted to the context of climate change. Farmers know above all which species to save and protect and which are more resistant to the effects of climate change and the need to build up a green cover of soil for the dry season.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | Nothing
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | 101 technical services officers and prefects were trained on the management of climate change and the integration of ODD into the PDESC of municipalities. This training further strengthens the capacities of State agents in their regulatory function of supporting and accompanying municipalities in the design, planning and implementation of development actions. The communes benefit and will always benefit from the support accompaniment the deconcentrated State services in the planning of communal development. improving their level of knowledge about climate change only strengthens the quality of the support to be provided.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 81072 (PIMS 4789)
Implementing Entity | PNUD
Type of implementing entity | MIE
Country | Mali
Region | Africa
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion Performance de la cible à l'achèvement |  |  |  | Performance at mid-term |  |  |  | Performance at completion Performance à l'achèvement
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total | 213758 | 23949 | 189809 | Total | 337675 | 214265 | 123410 | Total
|  | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries
|  | % of Youth beneficiaries | 49% | 49% | 49% | % of Youth beneficiaries | 49% | 49% | 49% | % of Youth beneficiaries | 49% | 49% | 49% | % of Youth beneficiaries
0
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats. | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis. | Number of targeted stakeholders. |  | Hazards information generated and disseminated. | Overall effectiveness. | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  | Drought | 4: Effective | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted | 0% |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated. | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments. | No. of projects/programmes that conduct and update risk and vulnerability assessments. | Sector | Scale. | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems. | Core Indicator 1.2: No. of Early Warning Systems. | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  |  | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  | 2 |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  | 1 |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses. | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased. | Number of staff targeted. |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events. | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events. | Total staff trained. | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 10% | Private |  | 400 | 10% | Private |  | 415 | 7% | Private
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks. | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Disaster risk reduction | 2: Low capacity | Public | Local | Disaster risk reduction | 4: High capacity | Public | Local | Disaster risk reduction | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes. | Indicator 3.1: Increase in application of appropriate adaptation responses. | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  |  |  | 30% |  |  |  | 25%
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities. | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate . | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0% | 0% | 1: Aware of neither |  | 3000 | 50% | 4: Mostly aware |  | 4210 | 47.7% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets. | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate. | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened. | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability. | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change. | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Water management | 40 | Community |  | Water management | 146 | Community |  | Water management
|  | 0 | Community |  | Agriculture | 60 | Community |  | Agriculture | 36 | Community |  | Agriculture
[10 empty] | 9 | Community |  | Food security
[10 empty] | 101 | Community |  | Multi-sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress. | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated. | Natural asset or Ecosystem (type). | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets. | No. of targeted households. | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 2: Limited improvement |  | 3000 | 50% | 4: High improvement |  | 20827 | 30% | 3: Moderate improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods . | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies. | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies
| Core Indicator 6.1.2: Increased income, or avoided decrease in income. | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  |  | 2000 | Agriculture |  |  | 5271 | Agriculture
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agribusiness |  |  | 500 | Agribusiness |  |  | 2933 | Agribusiness
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Forestry |  |  | 300 | Forestry |  |  | 11683 | Forestry
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Fishing |  |  | 200 | Fishing |  |  | 940 | Fishing
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy. | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks. | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced. | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on N21: Microsoft: Deduction faite de Irebane, Guinedia, Fedji hoye Et Birol Adioda)
Note on I89: Microsoft: 5ha de terres recupérée par commune sur le plateau soit 30 Ha plus 2ha de parcs agroforestiers ocbjet de champs ecoles paysans plus éha de pépinières protégées par commune

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.