## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 18 November 2015 to 31 October 2016
| Project Title: | Building Adaptive Capacities of Small Inland Fishers for Climate Resilience and Livelihood Security, Madhya Pradesh
| Project Summary: | The Project is to make the fishery sector (captive inland fishery) adaptive to climate variability and enhance the adaptive capacity of the fish farmers to ensure their livelihood security. Project Objective: Climate Change Adaptation in the inland fishery sector for secured livelihoods of small and marginal farmers Scope: The Project will work on 60 ponds each with an area less than 10 ha in the Jhabua Agro Climatic Zone of the districts of Jhabua, Alirajpur and Dhar in the state of Madhya Pradesh. Specific Main Outcomes: The project has following specific outcomes: Outcome 1: Increasing water retention capacity of the tanks as an adaptive measure to address rainfall variability by modifying technical specifications; Outcome 2: Diversification of fish species and temperature regulation of ponds as adaptive measures to a warmer climatic regime; Outcome 3: Making small pond fisheries climate adaptation resilient through productivity enhancement by capacity building and institutional linkages; Outcome 4: Preparing and disseminating evidence-based resilient climate change adaptation strategies for inland fisheries for small pond fish farming.
|  |  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | IND/NIE/Food/2013/1 |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | NABARD |  | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | National |  | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | India |  | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Geographic areas where project is being implemented: Jhabua, Rama, Ranapur blocks of Jhabua district; Udaigarh, Alirajpur and Jobat blocks of Alirajpur district; and Manawar, Gandhwani, Kukchi and Bagh blocks of Dhar district. List of Villages where project will have impact: Dhar District: Banedia, Kawadia Kheda, Bhutiyapura, Panwa, Pantha, Ratakot, Baledi, Bhimpura, Chikli, Sustipura, Awaldaman, Banda; Jhabua District: Dudhikheda, Wagnera, Badkua, Para, BagaiBadi, Dhamni katara, Khedli, Waglawat, Panki, Doompada, Gopalpura,Kalapan and Alirajpur District:Lakshmani, Sejgaon Girala, Machhliya, Kharkuwan, Kharkhedi, Badi Hirapur, Ublad, Baladmoong, Kanda, Behadva, Bardala, Badi Juari,Ricchvi, Aali, Khutaja. |  | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[9 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [7 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2015-04-10
IE-AFB Agreement Signature Date: |  | 2015-07-17 | [7 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-11-18 | [7 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2017-06-18 | As per Table H of the Disbursement Schedule, DPR pg No. 128.
| Terminal Evaluation Date: | 18/05/2018 (as per DPR). Proposed date for terminal evaluation may be considered as 18/10/2018 since the project started on 18/11/2015 and three years will be nearing completion on this date. | As per Table of the Project Calendar of the DPR pg No. 31.
|  | List documents/ reports/ brochures / articles that have been prepared about the project. |  | Cyprus
|  | 1. Inception Workshop report 2. Technical Advisory Group Meeting Report 3. District Steering Committee Report Dhar (Dec 2015) 4. District Steering Committee Report Jhabua (Jan 2016) 5. District Steering Committee Report Alirajpur (Jan 2016) 6. Report of the Meeting of the State Steering Committee 7. Panchayat Training Needs Assessment Report 8. Draft Training Material for Hatchery and Fisheries 9. Draft Training Material on Gender 10. Climate Change Pathways that Affect Fish Diversity: Study of Dhar and Jhabua 11. Process Documentation Report (2015-16) 12. Study on Sustainability and Scope of Development of Surface Water Pond Alirajpur, Jhabua district 13. Fish Market Study in Dhar, Alirajpur and Jhabua 14. Biodiversity Report of Pond Sites- Dhar, Jhabua and Alirajpur 15. Ground Truthing Reports 16. Preventive Measures for Vector Borne Diseases in Dhar, Jhabua and Alirajpur |  | Czech Republic
List the Website address (URL) of project. |  |  |  | Democratic People's Republic of Korea
|  | climate.taalindia.org |  | Democratic Republic of the Congo
Denmark
| Project contacts: |  |  | Djibouti
National Project Manager/Coordinator |  |  |  | Dominica
| Name: | AMOD KHANNA |  | Dominican Republic
| Email: | amod@taalindia.org |  | Ecuador
| Date: | 2018-05-21 |  | Egypt
| Government DA |  |  | El Salvador
| Name: | Ravi S. Prasad, IAS (Joint Secretary) Ministry of Environment, Forests & Climate Change, Govt. of India |  | Equatorial Guinea
| Email: | ravis.prasad@nic.in |  | Eritrea
| Date: | 2018-05-21 |  | Estonia
| Implementing Entity |  |  | Ethiopia
| Name: | Shankar A. Pande (CGM-FSPD) National Bank for Agriculture and Rural Development |  | Fiji
| Email: | shankar.pandey@nabard.org |  | Finland
| Date: | 2018-05-21 |  | France
| Executing Agency |  |  | Gambia
| Name: | Towards Action And Learning (TAAL) |  | Georgia
| Email: | chitra@taalindia.org |  | Germany
| Date: | 2018-05-21 |  | Ghana
| Executing Agency |  |  | Greece
| Name: | NA |  | Grenada
| Email: |  |  | Guatemala
| Date: |  |  | Guinea
| Executing Agency |  |  | Guinea Bissau
| Name: | NA |  | Guyana
| Email: |  |  | Haiti
| Date: |  |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial Information: Cumulative from project start (18 November 2015 to 31 October 2016)
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement in USD for 2 instalments as of [31 Oct 2016] | 304963 |  |  |  | In USD
| 18297810 |  |  |  | In Indian Rupees at the exchange rate of 1 USD = INR 60
Add any comments on AF Grant Funds. (word limit=200) | Unanticipated delays in project implementation have affected the project disbursement schedule and reasons for delay are mentioned in this report. Efforts are being made to bring project activities and the disbursement schedule in line with the project plan.
INVESTMENT INCOME | NABARD maintains one RBI account where all the funds are credited and pooled. In view of this, project wise investment income may not be ascertained.
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List output and corresponding amount spent for the current reporting period | S.No | Project Components | Expected Outputs | ITEM / ACTIVITY / ACTION | Planned (Upon Agreement Signing- 1st Instalment) in USD | AMOUNT Utilized (USD) | AMOUNT Utilized (INR ) | AMOUNT Utilized (INR Million) | Remarks
| 1 | Component 1: Adaptive measures to address rainfall variability |  | COMPONENT 1 | 202266 | 26257.8333 | 1575470 | 15.7547 | All utilization figures are till 31st Oct 2016
| 1.1 |  | 1.1 Ponds identified according to geo-hydrological protocol for fisheries | Hydro-geological assessment | 10000 | 8112.6667 | 486760 | 4.8676
| 1.2 |  | 1.2 Modified pond design developed and implemented on existing ponds | Modification of ponds (average size 4 ha per pond) | 190266 | 17167.5 | 1030050 | 10.3005
| 1.3 |  | 1.3 Small-scale fish famers linked to financial support systems to access resources for pond maintenance | Modification of Insurance product | 2000 | 977.6667 | 58660 | 0.5866
| 2 | Component 2: Building resilience through adaptation of climate resilient technology |  | COMPONENT 2 | 124834 | 20155 | 1209300 | 12.093
| 2.1 |  | 2.1 Catchment treatment plan for each pond prepared and implemented | Catchment Treatment (48 ha for average 4 ha of pond) | 111100 | 9101.6667 | 546100 | 5.461
| 2.2 |  | 2.2 Pond temperature regulating best management practices and greening the pond surrounds | Oxygenation (solar aerators and oxygen tablets- all ponds) | 0 | 0 | 0 | 0
| 2.3 |  | 2.3 Fish farmers trained in poly-culture, fish culture and making fish seed for composite fish culture available to small-scale aqua culturist | Water Quality Measurement & Maintenance | 3337 | 2663.3333 | 159800 | 1.598
| 2.3.1 |  |  | Poly culture Fingerling Support (Part support) | 0 | 0 | 0 | 0
| 2.3.2 |  |  | Feeding -Micro-nutrient etc. (Part support) | 0 | 0 | 0 | 0
| 2.3.3 |  |  | Construction of Hatchery units-CIFA technology | 8400 | 8390 | 503400 | 5.034
| 2.3.4 |  |  | Nursery Unit(0.1 ha) | 1500 | 0 | 0 | 0
| 2.3.5 |  |  | Seed Rearing Unit (0.1 ha) | 0 | 0 | 0 | 0
| 2.3.6 |  |  | Transportation of Fingerlings | 497 | 0 | 0 | 0
| 3 | Component 3: Building climate resilience through enhancement of adaptive capacity |  | COMPONENT 3 | 20200 | 17718.3333 | 1063100 | 10.631
| 3.1 |  | 3.1 Capacity building of Fish farmers on climate resilient fishing | Training and Capacity Building including exposure visits | 11000 | 10096.6667 | 605800 | 6.058
| 3.2.1 |  | 3.2 Fish farmers trained on market analysis of fish and prepare their business plans | Marketing and Infrastructure Support | 0 | 0 | 0 | 0
| 3.2.2 |  |  | Business Plan Prepared | 6500 | 6281.6667 | 376900 | 3.769
| 3.3 |  | 3.3.Panchayat representatives trained in climate change factors. | Training of Panchayat representatives | 2700 | 1340 | 80400 | 0.804
| 3.4.1 |  | 3.4 Fish farmers made aware on the weather based insurance product for fish culture | Linkages with Financial Services ( banking/ federation/ financial institutions) | 0 | 0 | 0 | 0
| 3.4.2 |  |  | Insurance Coverage ( premium for av.4 ha of pond part) | 0 | 0 | 0 | 0
| 4 | Component 4: Knowledge generation and management |  | COMPONENT 4 | 29658.5033 | 7681.6667 | 460900 | 4.609
| 4.1.1 |  | 4.1 Institutional Processes for multi-stakeholder learning are established and activated | Meetings of District Steering Committee | 1300 | 1265 | 75900 | 0.759
| 4.1.2 |  |  | Meeting of Technical Advisory Group | 4780 | 1326.6667 | 79600 | 0.796
| 4.1.3 |  |  | Meeting of State Steering Committee | 1593 | 5 | 300 | 0.003
| 4.1.4 |  |  | Meeting of Climate Change Observatory | 3385 | 320 | 19200 | 0.192
| 4.2.1 |  | 4.2 Evidence based learning documents prepared for dissemination | Action-Reflection Meetings | 1500 | 1455 | 87300 | 0.873
| 4.2.2 |  |  | Systematisation | 3108.3333 | 91.6667 | 5500 | 0.055
| 4.2.3 |  |  | Process Documentation | 2920 | 2856.6667 | 171400 | 1.714
| 4.2.4 |  |  | Development of Policy Briefs | 1890 | 0 | 0 | 0
| 4.3.1 |  | 4.3 Learning from Project Disseminated | Training of Civil Society Organisation | 0 | 0 | 0 | 0
| 4.3.2 |  |  | State Level Workshop | 0 | 0 | 0 | 0
| 4.3.3 |  |  | National Level Workshop | 500 | 73.3333 | 4400 | 0.044
| 4.4.1 |  | 4.4 Knowledge Products developed printed | Awareness (Leaflets/pamphlets) | 2282.57 | 70 | 4200 | 0.042
| 4.4.2 |  |  | Toolkit for Practitioners: Developing Adaptation Strategies in Natural Resource Management with Specific Reference to Fisheries | 0 | 0 | 0 | 0
| 4.4.3 |  |  | Training Manual for Fish Farmers on Climate Resilient Fish Rearing Practices | 1066.6 | 218.3333 | 13100 | 0.131
| 4.4.4 |  |  | Toolkit for Preparation of Business Plans for Small-Scale Fishery, Hatchery and Nursery | 5333 | 0 | 0 | 0
| 4.4.5 |  |  | Good Management Practices for Climate Resilient Small-Scale Fisheries | 0 | 0 | 0 | 0
| D |  |  | Total (1+2+3+4) | 376958.5033 | 71812.8333 | 4308770 | 43.0877
| E |  |  | Project / Programme Execution Cost | 35811.0578 | 35026.6667 | 2101600 | 21.016 | As per project sanction letter the Project Execution (PE) cost was envisaged to be 9.5%. At this stage, viz., 31st Oct 2016 PE is 48.77% (Salaries, Overheads etc.) as due to constraints of weather/season the works could not be carried out though expenses on Project Execution were undertaken.
|  |  | 9.5 | Grand Total (D+E) | 412769.5612 | 106839.5 | 6410370 | 64.1037
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | S.No | Project Component | Expected Concrete Outputs | ITEM / ACTIVITY / ACTION | Planned ( 02nd year ) in USD | Planned ( 02nd year ) in INR | Est. Completion Date
| 1 | Component 1: Adaptive measures to address rainfall variability |  | COMPONENT 1 | 185134 | 11108040
| 1.1 |  | 1.1 Ponds identified according to geo-hydrological protocol for fisheries | Hydro-geological assessment | 0 | 0 | 2017-10-01
| 1.2 |  | 1.2 Modified pond design developed and implemented on existing ponds | Modification of ponds (average size 4 ha per pond) | 185134 | 11108040 | 2017-10-01
| 1.3 |  | 1.3 Small-scale fish famers linked to financial support systems to access resources for pond maintenance | Modification of Insurance product | 0 | 0 | 2017-06-01
| 2 | Component 2: Building resilience through adaptation of climate resilient technology |  | COMPONENT 2 | 158335 | 9500100
| 2.1 |  | 2.1 Catchment treatment plan for each pond prepared and implemented | Catchment Treatment (48 ha for average 4 ha of pond) | 149735 | 8984100 | 2017-10-01
| 2.2 |  | 2.2 Pond temperature regulating best management practices and greening the pond surrounds | Oxygenation (solar aerators and oxygen tablets- all ponds) | 0 | 0 | 2017-06-01
| 2.3 |  | 2.3 Fish farmers trained in poly-culture fish culture and making fish seed for composite fish culture available to small-scale aqua culturist | Water Quality Measurement & Maintenance | 5000 | 300000 | 2017-04-01
| 2.3.1 |  |  | Poly culture Fingerling Support (Part support) | 0 | 0 | 2017-08-01
| 2.3.2 |  |  | Feeding -Micro-nutrient etc. (Part support) | 0 | 0 | 2017-10-01
| 2.3.3 |  |  | Construction of Hatchery units-CIFA technology | 2100 | 126000 | 2017-04-01
| 2.3.4 |  |  | Nursery Unit(0.1 ha) | 500 | 30000 | 2017-04-01
| 2.3.5 |  |  | Seed Rearing Unit (0.1 ha) | 500 | 30000 | 2017-04-01
| 2.3.6 |  |  | Transportation of Fingerlings | 500 | 30000 | 2017-08-01
| 3 | Component 3: Building climate resilience through enhancement of adaptive capacity |  | COMPONENT 3 | 6500 | 390000
| 3.1 |  | 3.1 Capacity building of Fish farmers on climate resilient fishing | Training and Capacity Building including exposure visits | 4000 | 240000 | 2017-10-01
| 3.2.1 |  | 3.2 Fish farmers trained on market analysis of fish and prepare their business plans | Marketing and Infrastructure Support | 0 | 0 | 2017-10-01
| 3.2.2 |  |  | Business Plan Prepared | 2500 | 150000 | 2017-07-01
| 3.3 |  | 3.3.Panchayat representatives trained in climate change factors. | Training of Panchayat representatives | 0 | 0 | 2017-10-01
| 3.4.1 |  | 3.4 Fish farmers made aware on the weather based insurance product for fish culture | Linkages with Financial Services ( banking/ federation/ financial institutions) | 0 | 0 | 2017-10-01
| 3.4.2 |  |  | Insurance Coverage ( premium for av.4 ha of pond part) | 0 | 0 | 2017-06-01
| 4 | Component 4: Knowledge generation and management |  | Component 4 | 26990 | 1619400
| 4.1.1 |  | 4.1 Institutional Processes for multi-stakeholder learning are established and activated | Meetings of District Steering Committee | 2800 | 168000 | 2017-10-01
| 4.1.2 |  |  | Meeting of Technical Advisory Group | 1000 | 60000 | 2017-07-01
| 4.1.3 |  |  | Meeting of State Steering Committee | 0 | 0 | 2017-10-01
| 4.1.4 |  |  | Meeting of Climate Change Observatory | 0 | 0 | 2017-09-01
| 4.2.1 |  | 4.2 Evidence based learning documents prepared for dissemination | Action-Reflection Meetings | 2165 | 129900 | 2017-09-01
| 4.2.2 |  |  | Systematisation | 3108.3333 | 186500 | 2017-10-01
| 4.2.3 |  |  | Process Documentation | 2916.6667 | 175000 | 2017-10-01
| 4.2.4 |  |  | Development of Policy Briefs | 0 | 0 | 2017-07-01
| 4.3.1 |  | 4.3 Learning from Project Disseminated | Training of Civil Society Organisation | 1000 | 60000 | 2017-06-01
| 4.3.2 |  |  | State Level Workshop | 1000 | 60000 | 0
| 4.3.3 |  |  | National Level Workshop | 2000 | 120000 | 0
| 4.4.1 |  | 4.4 Knowledge Products developed printed | Awareness (Leaflets/pamphlets) | 0 | 0 | 2017-08-01
| 4.4.2 |  |  | Toolkit for Practitioners: Developing Adaptation Strategies in Natural Resource Management with Specific Reference to Fisheries | 6000 | 360000 | 2017-09-01
| 4.4.3 |  |  | Training Manual for Fish Farmers on Climate Resilient Fish Rearing Practices | 2000 | 120000 | 2017-11-01
| 4.4.4 |  |  | Toolkit for Preparation of Business Plans for Small-Scale Fishery, Hatchery and Nursery | 0 | 0 | 2017-09-01
| 4.4.5 |  |  | Good Management Practices for Climate Resilient Small-Scale Fisheries | 3000 | 180000 | 2017-11-01
| D |  |  | Total | 376959 | 22617540
| E |  |  | Project / Programme Execution Cost | 35811.105 | 2148666.3
|  |  |  | Grand Total (D+E) | 412770.105 | 24766206.3
|  |  |  | 0 | 24766206.3 |  |  |  |  | 9.5
0
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | NA
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). | NA
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | NA

## Procurement (hidden)
PROCUREMENT DATA. For details related to all the bids submitted to TAAL and rationale for selection of the winner, please refer to the next sheet titled "New Procurement Table" created based on AFB's comments given in the Checklist of the 02 PPRs for the Year 1 of the project implementation
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | 9
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date (USD) | Remaining Balance (In USD)
Consultancy Contract | Central Institute of Freshwater Aquaculture (CIFA) | 13703.75 | 2016-07-15 | 6851.8667 | 6851.8833
Consultancy Contract | Deccan Consultants | 2893.7 | 2016-01-08 | 2384.0333 | 509.6667
Consultancy Contract | Astad Pastakia | 2500 | 2016-07-10 | 2000 | 500
Consultancy Contract | Ecociate | 9047 | 2016-07-22 | 4217 | 4830
Product contract | Punch line | 5083.3333 | 2016-08-08 | 5083.3333 | 0
General Services | RockMin Consultants | 6167 | 2016-09-02 | 3083 | 3084
| Total Amount (USD) | 39394.7833 |  | 20536.2333 | 15775.55
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Consultancy on Building Capacities of Small Inland Fishers for Climate Resilience and Livelihood Security Madhya Pradesh, Negotiated Terms of Reference | 1 | 13703.75 | 13703.75 | CIFA is a Government of India institution. It is a Centre of Excellence in research for developing sustainable and diversified freshwater aquaculture practices for enhanced productivity, quality, water use efficiency and farm income. It has the the mandate to provide training to fishers. Hence, no Bid was invited and negotiations were carried out with the institute directly.
Topographical Thematic Mapping of Project Area, Proposal and Negotiated Terms of Reference | 1 | 2893.7 | 2893.7 | Deccan Consultants was identified during the proposal development stage where the purchase methodology was followed. The maps on page 34-36 of the DPR have been made by Deccan Consultants and their name appears below the legend. Deccan Consultants had participated in DPR development workshop held in Indore that was attended by representatives from USAID, NABARD and TAAL. Deccan Consultants is represented in the project by Dr R M Singh, PhD with M Tech in Applied Geology and PG Diploma in Remote Sensing in GIS from IIRS. Dr R M Singh has provided services as Geologist and Remote Sensing expert to government departments and agencies that include Department of Electronics, Department of Forest, Rajive Gandhi Drinking Water Mission, MP Roads Development Authority, ONGC, and JICA among others. The expert services have also been provided to corporate sector that includes Tata Chemicals, De beers, Swadeshi Minerals, Persons Overseas private limited, Essar Power limited and HINDALCO. Among civil society projects his expertise has been used to provide inputs to DANIDA, Rajive Gandhi Watershed Mission, Bhoj Wetland Project among others.
Preparing Business Plan and Developing Orientation Plan for Pond Committee Members and Village Youth on Developing Plans for their respective Ponds, Proposal by Invitation | 2 | 9047 (Ecociate Consultants Private Limited) | 9047 | Ecociate was selected based on their earlier working experience in the project area and their thematic subject expertise. They also had a better qualified team that was nominated for the assignment.
14833 (Frametrics Consulting Private Limited)
Process Documentation, By Invitation | 1 | 2500 | 2500 | Astad Pastakia is a graduate in Agriculture Sciences and has done FPM and PGDM from IIM Ahmedabad with specialisation in Agriculture. He has authored book titled Locked Horns that deal with conflict resolution in CBNRM and has authored many books on Livelihood Augmentation in Rainfed Areas; and on Farmer Led Participatory Research Cases from Western India. Recipient on best paper award from the journal Organisation and Change for his paper on Grassroots Ecopreneurs change agents for sustainable society (1989) Astad Pastakia has taught courses on Livelihood Promotion; and New Product Development and Business Plan at EDI; CEPT University and Central University of Gujarat. Mr Astad Pastakia is the best fit because of his dual experience of working on NRM and Conflict Resolutions related to natural resources. TAAL has worked with Mr Pastakia earlier in three World Bank projects. His personal knowledge of the project area was an additional advantage that could contribute immensely towards implementation of the project.
Purchase of Solar Pump for drawing water for hatchery by invitation | 1 | Punchline Energy Limited (5083) | 5083 | Punchline is empanelled with Ministry of New and Renewable Energy, Government of India as a channel partner. They have earlier executed orders for Punjab Gramin Bank and Allahabad Bank for solar pumps which are working. Additionally, Punchline has executed project for TERI on Distribution Grid with Smart Metering System; and with Satpura Tiger Reserve in Madhya Pradesh. Secondly, the cost of Solar Pump contacted through internet search was 2500 USD per HP where as Punchline cost was 1694.44 USD per HP. Punchline Energy Limited agreed to supply the Solar Pump without battery, while the other supplier were providing the same with battery. Punchline was willing to provide training on maintenance of solar pump with no extra cost.
Development of Catchment Maps for each Pond selected by the project | 3 | Caresoft Inc. (8500 USD) | 6167 | RockMin Consultants agreed to develop catchment area map with each unit of land identified over the number of villages in the catchment of each pond. RockMin has the lowest quote and hence the bid was decided in favour of RockMin
Geo Resource Developers (17.25 USD per land unit, that is, 10320 USD for 100 land units per pond for 60 ponds)
RockMin Consultants (USD 6167)

## New Procurement Table
Details of all the bids received by TAAL for PPR- 01
Contract/Service Type | Procurement Method | Date of Open Call | Agency / Contracted party | Submitted Bids (Nos) | Contract Value/Amount (USD) | Type of Service for engagement | Justification for Selection of the Winner
Consultancy | Single source procurement | Not Applicable | Central Institute for Freshwater Aquaculture (CIFA) | 1 | 13704 | To carry out Capacity Building of Fish Farmers on Climate Resilience Fisheries | CIFA is the only institute of India which was known to have desired expertise and infrastructure to fulfill the requirements of the given contract.It is a Government of India institution and a Centre of Excellence in research for developing sustainable and diversified freshwater aquaculture practices for enhanced productivity, quality, water use efficiency and farm income. It has the the mandate to provide training to fishers for maintaining sustainable livelihoods. As the advantages of hiring CIFA was abundantly clear, no bid was invited and negotiations were carried out with the institute directly.
Consultancy | Single source procurement | Not Applicable | Deccan Consultants | 1 | 2894 | Preparation of Topographic and Thematic Maps of the Project Area | Deccan Consultants was identified during the proposal development stage where the purchase methodology was followed. The maps on page 34-36 of the DPR have been made by Deccan Consultants and their name appears below the legend. Deccan Consultants had participated in DPR development workshop held in Indore city, India that was attended by representatives from USAID, NABARD and TAAL. Deccan Consultants is represented in the project by Dr R M Singh, PhD with M Tech in Applied Geology and PG Diploma in Remote Sensing in GIS from IIRS. Hence, Deccan Consultants was chsoen for the continuation of work that cannot be reproduced by another supplier. Dr. R. M. Singh has provided services as Geologist and Remote Sensing expert to government departments and agencies that include Department of Electronics, Department of Forest, Rajive Gandhi Drinking Water Mission, MP Roads Development Authority, ONGC, and JICA among others. The expert services have also been provided to corporate sector that includes Tata Chemicals, De beers, Swadeshi Minerals, Persons Overseas private limited, Essar Power limited and HINDALCO. Among civil society projects his expertise has been used to provide inputs to DANIDA, Rajive Gandhi Watershed Mission, Bhoj Wetland Project among others.
Consultancy | Two Bid system | Not Applicable | Ecociate | 2 | 9047 | Preparation of Business Plan and Development of Orientation Plan for Pond Committee Members (PMCs). | Two Bids were received: 1. Ecociate Consultants Private Limited ($9047) 2. Frametrics Consulting Private Limited ($14833) Ecociate team member had academic background of rural marketing and had executed livehood assessments. Ecociate was selected based on their team members having earlier working experience in the project area and their thematic subject expertise. Frametrics had done social projects, but none of them was on livelihood.
Consultancy | Single source service/procurement | Not Applicable | Astad Pastakia | 1 | 2500 | Process Documentation for the Year 1 of project implementation. | Astad Pastakia is a graduate in Agriculture Sciences and has done FPM and PGDM from IIM Ahmedabad with specialisation in Agriculture. He has authored book titled "Locked Horns" that deal with conflict resolution in CBNRM and has authored many books on Livelihood Augmentation in Rainfed Areas; and on Farmer Led Participatory Research Cases from Western India. He is a recipient of best paper award from the journal Organisation and Change for his paper on Grassroots Ecopreneurs change agents for sustainable society (1989). Astad Pastakia has taught courses on Livelihood Promotion; and New Product Development and Business Plan at EDI; CEPT University and Central University of Gujarat. Mr Astad Pastakia is the best fit because of his dual experience of working on NRM and Conflict Resolutions related to natural resources. TAAL has worked with Mr Pastakia earlier in three World Bank projects. His personal knowledge of the project area was an additional advantage that could contribute immensely towards implementation of the project.
Product Contract | Single source procurement | Not Applicable | Punchline Energy Limited | 1 | 5083 | Installation of Solar Pumps and its maintenance. | Punchline is empanelled with Ministry of New and Renewable Energy, Government of India as a channel partner. They have earlier executed orders for Punjab Gramin Bank and Allahabad Bank for solar pumps which are functioning properly. Additionally, Punchline has executed project for TERI on Distribution Grid with Smart Metering System; and with Satpura Tiger Reserve in Madhya Pradesh. Secondly, the cost of Solar Pump contacted through internet search was 2500 USD per HP where as Punchline cost was 1694.44 USD per HP. Punchline Energy Limited agreed to supply the Solar Pump without battery, while the other supplier were providing the same with battery.
General Services | Three Bids/Limited Tender | Not Applicable | RockMin Consultants | 3 | 6167 | Development of Catchment Maps for each Pond selected under the project. | Local Service Providers were pro actively identified and they were asked to submit their bids. Three bids were received: 1. Caresoft Inc ($8500) 2. Geo Resource Developers ($10320) 3. RockMin Consultants ($6167) RockMin has the lowest quote and hence the bid was decided in favour of RockMin. Further, RockMin Consultants agreed to develop catchment area map with each unit of land identified over the number of villages in the catchment of each pond.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Water from pond drawn for irrigation that adversely affects the ability of the fisher to conduct fisheries in the pond | Low | (a) Involvement of Gram Sabha in selection of the pond for fisheries. Ponds that have moderate and high competition are not taken under the project. (b) Consultations of the farmers with fields near the pond; co-opting farmers as members of the Fish Farmer Group
Elite capture leasing rights of the pond and corner project benefits | Low | (a) For benami [(made, held, done, or transacted in the name of (another person)] membership we have suspended operations and have asked the community to resolve the issue. (b) It has been made clear to the fishermen groups that project support will be only for the fishermen who will actually undertake fishery activity. Sub letting and sub contracting ponds have either been dropped or have been asked to realign their activities with the project’s requirements.
Greater emphasis on development of fisheries than on development of adaptive capacities/ strategies by the fishers | Moderate | (a) Design of pond has been focused on water retention in all the ponds that have been covered in the first year. (b) Capacity building of the project implementation team to bring focus on climate adaptation activities.
Low adoption rate of adaptive strategies by target fishers | Low | (a) Exposure to fishermen for purchase of better seed and linked to fish seed supplier. Training and exposure to fish farmers.
Delays in approval and sanctioning of leasing rights | Low | (a) Launch workshop with other stakeholders at the State and District level (b) District Steering Committee has been constituted and meetings are held regularly for discussion.
Poaching of fish from pond by other members of the community | Low | (a) Consultation processes with community undertaken in all project villages (b) Resolution of the Gram Sabha for providing of leasing rights. Making households residing around the pond as members of the Fish Farmers Groups.
Non availability of fish seed on time by the fisher | Moderate | The permission for setting up a Hatchery in one district has been received though it is not yet installed or operationalized.
Extreme weather event- drought leading to lack of water for fisheries | Moderate | (a) Ponds selected under the project have some degree of perinniality and have low/no competition with agriculture. (b) Weather based insurance product developed and launched though not subscribed so far by the fisherman's.
Extreme weather event- excessive rains leading to outflow of fish seed | Moderate | (a) Weather based insurance for excessive rains developed and launched (b) Fish pass piloted in one of the pond
Conflict with farmers in the catchment area using chemical fertilizers that adversely affect the quality of water and hence productive capacity of the pond for fisheries | Low | (a) Water quality sample testing undertaken (b) Ponds with moderate and high competition with agriculture in catchment area is not undertaken under the project (c) Development and treatment of catchment undertaken by the project
Political interference in the selection of site and to provide political patronage to the selected fishers | Moderate | (a) Presentation of project to Gram Panchayat members before taking up the project for implementation (b) Training Needs Assessment (TNA) of Panchayat representatives undertaken and training module has being developed
Damage or loss of equipment given to the fisher e.g. mechanical aerators | Moderate | No activity has been undertaken so far
Duplication of booking expenses undertaken on ponds by the project and also by the Gram Panchayat as their expenditure | Low | (a) One Block Administration has been informed about the works undertaken in the project and process of informing other blocks is underway
High attrition rate amongst the staff that will delay the implementation of the project | Moderate | (a) Local persons have been drawn in as field workers (Cluster Associates) and local resource persons and experts empanelled to provide their expert inputs on a draw down basis. (b) Regular staff meetings and capacity building to ensure that all staff understand their role in the project.
Fisher not able to leverage funds for maintenance of pond that adversely affects the water retention capacity of the pond | Moderate | (a) Dialogue at one block has been initiated.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Two ponds shortlisted and approved by the District Steering Committee were later found to have area higher than 10 ha in the government records. Due to this, additional ponds had to be scoped, shortlisted and sought approval. | New ponds identified, were approved and taken up for work under the project | Project has collected data on area and ownership of all ponds in the block with lease records and incorporated in the selection process of ponds.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
YES. The risk of ponds not falling within the project criteria (less than 10 ha) even after approval has been mitigated by reinforcing the selection process.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Component 1: Adaptive measures to address rainfall variability
Project Manager/Coordinator: | Activity 1.1: Protocols for prioritizing rural ponds (less than 10 ha) for inland fisheries developed and implemented |  | a) Geo hydrological assessment completed b) 60 Pond sites finalized c) Completion of baseline |  | (a) Geo hydrological assessment of all the blocks under the project area completed (b) 60 Pond sites finalized (c) Completion of baseline of ponds finalised | S
| Activity 1.2: Modified Pond design specifically for fisheries developed and implemented on selected existing ponds |  | a) Finalisation of site specific maps b) Start of tank modification on 15% sites |  | (a) Maps of sites selected for first year has been finalized. (b) Work has started on 13.3% of the pond sites. | S
| Activity 1.3: Insurance Product has been developed that provides resources for making modifications to the technical design of the pond after the projected climate change has taken place |  | a) Farmer mobilization towards adoption of insurance as a risk transferring strategy |  | a) All 8 fishers groups selected for the first year have been informed about the insurance Products and how they can be use it for transferring risks | MS
Component 2:Building resilience through adaptation of climate resilient technology
| Activity 2.1: Catchment treatment of Ponds selected for intervention to provide climate resilience to small pond fisheries |  | a) Implementation of catchment treatment plans in 15% of the project sites |  | a) Catchment treatment plan in 13.3 % of the project sites has been implemented | S
| Activity 2.2: Pond Temperature regulating best management practices and greening of pond surrounds |  | a) Implementation in demonstration pond in one district |  | a) Greening of pond surrounding is undertaken as part of catchment treatment plan | S
| Activity 2.3: Best management practices to decrease likelihood of oxygen deficiency along with use of oxygen tablets and solar powered aerators |  | a) Implementation in demonstration pond in one district |  | a) Not yet undertaken as the project started late and this summer season the ponds were not intervened upon by the project | MS
| Activity 2.4: Composite fish culture practices with combination of intensive, semi intensive and extensive culture practices based on fish farmers capacity |  | a) Start of operation in 15% tanks |  | a) started in 15% of the ponds | HS
| Activity 2.5: 3 Seed hatcheries, 2 nurseries and 1 seed rearing unit per district established |  | a) Setting of one hatchery, one nursery and one seed rearing unit |  | a) one hatchery received and is in the process of installation and operationalization | S
Component 3:Building climate resilience through enhancement of adaptive capacity
| Activity 3.1: Productivity of Fish Farmer enhanced towards optimal level of production through training and capacity building on climate resilience fish farming |  | a) Training on Climate Resilient and Climate adaptive Fish Farming given to 15% of fishers |  | a) resource persons for training has been identified and training schedule developed- in the process of implementation | S
| Activity 3.2: Fish farmers supported through market infrastructure and value chain assessment done |  | a) Training and support provided to 15% fishers under the project |  | a) First batch of training of fishermen is underway | S
| Activity 3.3: Fish farmers prepare business plans based on local market and existing value chain |  | a) 15% of fishers are trained in preparation of Business plans for their ponds |  | a) Not yet undertaken as the project started late and this summer season the ponds were not intervened upon by the project | MS
| Activity 3.4: Institutional support intervention so as to enable local governance institutions and fish farmers to play the role envisaged in the legal framework of the State |  | a) Training of Panchayat representatives on climate change in three districts |  | a) Training Needs Analysis completed and the process of development of module is underway | S
| Activity 3.5: Insurance Coverage provided for risk minimisation of fish farmer project |  | a) Orientation on climate indexed insurance for fishers b) Support 15% fishers in opting for insurance coverage |  | a) Climate indexed insurance customised for small scale fishermen has been launched | S
Component 4: Knowledge generation and management
| Activity 4.1: District Steering Committee Meetings |  | a) 6 meeting per year per district |  | a) DSC constituted in all 3 districts and 2 meetings in each district held | S
| Activity 4.2: Technical Advisory Group Meetings |  | a) 2 meetings per year |  | a) 1 meeting of TAG held | S
| Activity 4.3: State Steering Committee Meetings |  | a) Completion of inception workshop b) 3 meetings per year |  | a) Inception workshop held b) 1 meeting held | S
| Activity 4.4: Climate Change Observatory |  | a) Establishment of CCO |  | a) CCO in 6 villages has been established | MS
| Activity 4.5: Action Reflection Meetings |  | a) Learning forum at the fishers level developed |  | a) 2 Action Learning meetings conducted | MS
| Activity 4.6: Systematisation |  | a) Baseline of fish culture practices undertaken |  | a) not yet undertaken | MS
| Activity 4.7: Process Documentation |  | a) Process document report prepared |  | a) Process documentation is underway | S
| Activity 4.8: Policy Briefs |  | a) One policy brief prepared and presented to SSC |  | a) Not yet undertaken | MS
| Activity 4.9: Training of Civil Society Organisation |  | a) Database of CSOs working in the three districts |  | a) Database developed | S
[5 empty] | Overall Rating | S | Satisfactory (S)
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Amod Khanna
| Email: | amod@taalindia.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project has started work on all the activities though they may be at different stages of completion. This is despite the fact that the field level activities started 3 months after the contract was signed. The project is well supported by the state and district level departments, the fishers group is responding to the project related activities, and expert agencies are supporting the project in developing and delivering capacity building inputs. Hence the overall progress of the project is rated as Satisfactory. Recommendation for the next step is to review the proposed budget in view of rates of inflation, increase in cost of remunerations and nature of execution of climate adaptation. measures. There is need to review the policy of putting a cap of 9.5% as Project Execution for the Executing Entity and no share in Management. Costs.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency (NABARD) | Component 1: Adaptive measures to address rainfall variability
| Activity 1.1: Protocols for prioritizing rural ponds (less than 10 ha) for inland fisheries developed and implemented |  | (a) Geo hydrological assessment completed (b) 60 Pond sites finalized (c) Completion of baseline |  | (a) Geo hydrological assessment of all the blocks under the project area completed (b) 60 Pond sites finalized (c) Completion of baseline of ponds finalised | S
| Activity 1.2: Modified Pond design specifically for fisheries developed and implemented on selected existing ponds |  | a) Finalisation of site specific maps b) Start of tank modification on 15% sites |  | (a) Maps of sites selected for first year has been finalized. (b) Work has started on 13.3% of the pond sites. | S
| Activity 1.3: Insurance Product has been developed that provides resources for making modifications to the technical design of the pond after the projected climate change has taken place |  | a) Farmer mobilization towards adoption of insurance as a risk transferring strategy |  | a) All 8 fishers groups selected for the first year informed of insurance Products and how they can be used for transferring risks | MS
Component 2:Building resilience through adaptation of climate resilient technology
| Activity 2.1: Catchment treatment of Ponds selected for intervention to provide climate resilience to small pond fisheries |  | a) Implementation of catchment treatment plans- 15% sites |  | a) Catchment treatment plan of 13.3 % sites is implemented | S
| Activity 2.2: Pond Temperature regulating best management practices and greening of pond surrounds |  | a) Implementation in demonstration pond in one district |  | a) Greening of pond surrounds undertaken as part of catchment treatment plan | S
| Activity 2.3: Best management practices to decrease likelihood of oxygen deficiency along with use of oxygen tablets and solar powered aerators |  | a) Implementation in demonstration pond in one district |  | a) Not yet undertaken as the project started late and this summer season the ponds were not intervened upon by the project | MS
| Activity 2.4: Composite fish culture practices with combination of intensive, semi intensive and extensive culture practices based on fish farmers capacity |  | a) Start of operation in 15% tanks |  | a) started in 15% of the ponds | HS
| Activity 2.5: 3 Seed hatcheries, 2 nurseries and 1 seed rearing unit per district established |  | a) Setting of one hatchery, one nursery and one seed rearing unit |  | a) one hatchery received and is in the process of installation and operationalization | S
Component 3:Building climate resilience through enhancement of adaptive capacity
| Activity 3.1: Productivity of Fish Farmer enhanced towards optimal level of production through training and capacity building on climate resilience fish farming |  | a) Training on Climate Resilient and Climate adaptive Fish Farming given to 15% of fishers |  | a) resource persons fir training identified and training schedule developed- in the process of implementation | S
| Activity 3.2: Fish farmers supported through market infrastructure and value chain assessment done |  | a) Training and support provided to 15% fishers under the project |  | a) First bath of training of fishers underway | S
| Activity 3.3: Fish farmers prepare business plans based on local market and existing value chain |  | a) 15% fishers trained in preparation of Business plans for their ponds |  | a) Not yet undertaken as the project started late and this summer season the ponds were not intervened upon by the project | MS
| Activity 3.4: Institutional support intervention so as to enable local governance institutions and fish farmers to play the role envisaged in the legal framework of the State |  | a) Training of Panchayat representatives on climate change in three districts |  | a) Training Needs Analysis completed and the process of development of module underway | S
| Activity 3.5: Insurance Coverage provided for risk minimisation of fish farmer project |  | a) Orientation on climate indexed insurance for fishers b) Support 15% fishers in opting for insurance coverage |  | a) Climate indexed insurance customised for small scale fishers launched | S
Component 4: Knowledge generation and management
| Activity 4.1: District Steering Committee Meetings |  | a) 6 meeting per year per district |  | a) DSC constituted in all 3 districts and 2 meetings in each district held | S
| Activity 4.2: Technical Advisory Group Meetings |  | a) 2 meetings per year |  | a) 1 meeting of TAG held | S
| Activity 4.3: State Steering Committee Meetings |  | a) Completion of inception workshop b) 3 meetings per year |  | a) Inception workshop held b) 1 meeting held | S
| Activity 4.4: Climate Change Observatory |  | a) Establishment of CCO |  | a) CCO in 6 villages established | MS
| Activity 4.5: Action Reflection Meetings |  | a) Learning forum at the fishers level developed |  | a) 2 Action Learning meetings conducted | MS
| Activity 4.6: Systematisation |  | a) Baseline of fish culture practices undertaken |  | a) not yet undertaken | MS
| Activity 4.7: Process Documentation |  | a) Process document report prepared |  | a) Process documentation underway | S
| Activity 4.8: Policy Briefs |  | a) One policy brief prepared and presented to SSC |  | a) Not yet undertaken | MS
| Activity 4.9: Training of Civil Society Organisation |  | a) Database of CSOs working in the three districts |  | a) Database developed | S
[5 empty] | Overall Rating | S | Satisfactory (S)
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | Sachin Kamble
| Email: | sachin.kamble@nabard.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other | NA
Overall Rating
Please Provide the Name and Contact information of person(s) responsible for completing the Rating section
| Name: | NA
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | The activities are implemented as per the planned schedule. The information about the project in the form of presentation is made in all gram sabhas. The brochure with contact number for grievance redressal is shared with the panchayats. The hatchery unit is received directly from Central Institute of Freshwater Aquaculture (CIFA) to the beneficiaries in the village. Community mobilisation, Increased awareness among communities about climate stress and alternative means of livelihoods, village level committees and increased participation from women are strong/ positive features of the project. Member Department of District Steering Committee in one district took time in approval of Ponds and new ponds had to be selected. Time was required to identify new ponds and conduct project processes at the newly selected pond. One monitoring visits were undertaken by NIE.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to achieve all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Component(s) | Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
| Objectives Climate Change Adaptation in the inland fishery sector for secured livelihoods for small and marginal farmers | % Fish Farmer (FF) adopting climate resilient fish rearing practices developed by the project | none at present | 10% Fish Farmer (FF) adopted climate resilient fish rearing practices | All FF covered by the project adopt climate resilient fish rearing practices
|  | % FF subscribing to weather based insurance products | One weather based insurance product negligible with subscription | 0% FF subscribed to weather based insurance product | All FF targeted by the project would subscribe to one of the insurance product
|  | % of income of small and marginal farmers and FF from fisheries | 20% of income of small and marginal farmers from fisheries | Will be assessed after fish harvesting is completed | 40% of income of small and marginal farmers will be from fisheries
|  | Selection protocol and design of ponds tested by the project and adopted by Government for small pond fisheries | Govt guidelines for pond design are not based on climate change parameters | Selection protocol and design of ponds tested by the project | Govt guidelines include climate change parameter for designing ponds for fisheries
|  | State Government resolves to formulate a separate policy for small FF that is based on climate adaptive strategies | State Policy for Fisheries have no separate provision for small-scale fisheries | Not presented to State Government | Recognition and specific provisions would be made for small-scale fisheries in the State Policy
Component 1: Adaptive Measures to address Rainfall Variability | Outcome 1 Increasing water retention capacity of the tanks as an adaptive measure to address rainfall variability by modifying technical specification | % ponds with water retention for more than 10 months | 50% of the ponds selected under the project can retain water more than 10 months | will be reported in PPR2 | 100% ponds with water retention for more than 10 months
|  | % ponds with depth of water at least 1.5 m during dry months | 30%of the ponds have water depth up to 1.5 m during dry months | will be reported in PPR2 | 80% ponds with water depth up to 1.5 m during dry months
|  | % ponds where silt load has been decreased | 0%. None of the ponds selected for the project has any work been done decreasing the silt load | 10% ponds | 80% ponds where silt load would be decreased
|  | % ponds where there has been no loss of fish because of flooding throughout the year | at present fish is introduced late in the Ponds | Fish loss due to flooding not reported in any of the 10% ponds in which work has been done in the first year | 100% ponds have protective features for flooding and insurance cover against loss of fish
|  | % ponds where Private/ Panchayat investment on maintenance of ponds to increase water retention capacity | No investment on ponds either on Panchayat/private land for maintenance | No Panchayat or Private investment till the end of first year | 100% ponds have resources for ensuring investment for maintenance of ponds for fisheries
| Outputs 1.1 Ponds Identified according to geo-hydrological protocol | % Ponds suitable for small-scale commercial fisheries | 25%of the ponds selected are suitable for small scale commercial fisheries | 75% ponds would require works for full suitability for small scale fisheries and 25% ponds will require improvements. Improvements were carried out in 7/60 ponds ( 11.66%) | 100% ponds would be used for small-scale commercial fisheries
To be determined during project implementation
| Outputs 1.2 Modified pond design developed and implemented on selected ponds | % Ponds suitable for small-scale commercial fisheries | 25%of the ponds selected are suitable for small scale commercial fisheries | 75% ponds would require works for full suitability for small scale fisheries and 25% ponds will require improvements. Improvements were carried out in 7/60 ponds ( 11.66%) | 100% ponds would be used for small-scale commercial fisheries
|  |  | To be determined during project implementation |  |  | 105.1333
| Output 1.3 Small scale fish farmers linked to financial support systems to access resources for pond maintenance | % small-scale FF have access to resources for pond maintenance | None of the ponds selected have access to resources for pond maintenance | Workshop was conducted with different insurance companies and ICICI Lombard developed the insurance product. Stakeholder workshop was conducted with fishers, department functionaries and the insurance company. The budget for premium contribution from project was 43.25$ but the total premium was 105.1333. The amount was high for contribution by fishers and we took up the matter with insurance company. Hence insurance was not done | 100% small-scale FF have access to resources for pond maintenance
To be determined during project implementation
Component 2:Building resilience through adaptation of climate resilient technology | Outcome 2 Diversification of fish species and temperature regulation of ponds as adaptive measures to warmer climatic regime | % ponds where water temperature is regulated and controlled during summer | None by design | Will be assessed and implemented in April 2017 | 100% ponds where water temperature would be regulated
|  | % FFs adopting poly culture fish farming | small-scale FFs practice 2 layered fisheries only | 12 % ponds implemented poly culture (3 layered) fish farming in first year | 100% small-scale FF adopt at least 3 layered fish culture
|  | % FF adopting recommended fish stocking rate | All small-scale FF resort to high density stocking | Fish Farmers in 12 % adopted recommended fish stocking rate | 100% small-scale FF adopt recommended fish stocking
|  | % hatcheries running successfully | No fish hatcheries among small-scale FFs | 1 hatchery installed and will be implemented in breeding season | 1 hatchery in each district running successfully
|  | % ponds with decrease in fish mortality due to decrease in BOD | Presently fish is harvested early to meet irrigation water needs. | will be reported in PPR2 | 100% ponds report decrease in fish mortality due to decrease in BOD
| Output 2.1 Catchment treatment plan for each pond prepared and implemented | % ponds catchment treatment plan prepared | Not prepared | 9 plans prepared and 5 have been implemented | 60 catchment treatment plans prepared and implemented
|  | % ponds silt load decrease | There are no works in catchment of the pond that will reduce the silt load of the pond | 10% ponds silt load has decreased | 80% ponds silt load has decreased
| Output 2.2 Pond temperature regulating best management practices and greening the pond surrounds | % FF adopt best management practices for regulating pond temperature | FF do not use any practice to control temperature of the pond | Will be assessed in summer of 2017 | 100% FF adopt best management practice for regulating pond temperature
|  | % FF adopting technology to decrease likelihood of oxygen deficiency | FF not using any technological input to decrease likelihood of oxygen deficiency | Technology not yet adopted | Two-third FF adopt technology to decrease likelihood of oxygen deficiency
| Output 2.3 Fish Farmers trained in poly-culture and making fish seed for composite fish culture available to small-scale aqua culturist | % FF trained in ploy culture fish rearing practices | No small-scale FF trained in poly culture and fish culture | 10% FF trained in poly culture and fish rearing practices | 100% FF trained in ploy culture and fish rearing practice
|  | % FF have access to different species of fish seed for their recommended fish culture | None of the Fish Farmers selected under the project have access to different species of fish seeds | 10% FF have access to composite fish seeds | 100% FF have access to composite fish seeds
Component 3: Building climate resilience through enhancement of adaptive capacity | Outcome 3 Making small pond fisheries climate adaptation resilient through productivity enhancement by capacity building and institutional linkages | % FFs adopting responsible fisheries practices | None of the Fish Farmers are adopting responsible fisheries practices | 10% FF have initiated responsible fisheries practices though it has yet to reach recommended benchmarks | 100% FF adopt responsible fisheries practices
|  | % Increase in productivity | 650-700 kg per ha | Indications of better growth, though productivity will be known after harvesting is completed | At least 25% increase in productivity
|  | % FF participated in the development of fisheries business plan | FF do not develop business plans | Data collection for model business plan completed and 10% FF recording data as part of roll out for the preparation of business plan | 100% FF have developed business plans
|  | % FF develop partnerships and linkages with other players in the market | FF do not have formal linkages | Linkages not yet taken place | 100% FF develop formal linkages with other players
|  | % FF members of formal groups formed | 10% of the ponds selected have existing Fisher's Group | 12% FF members of formal groups | 100% FF members of formal groups
|  | % FF pay for premium for insurance | FF do not have access to weather based insurance product | Weather indexed insurance product launched though FFs have yet to subscribe to it | 100% FF pay premium for weather based insurance product
|  | % GP formed plans to reflect climate change factors | No GP have prepared plans that reflect climate change factors | Training of GP not yet conducted | At least 50% of GPs attending training incorporate climate change factors in their plans
| Output 3.1 Capacity building of FFs on climate resilient fishing | % FF trained in climate resilient training | No FF trained in climate resilient fishing | 10% FF have been trained in climate resilient fisheries practices | 100% FF complete all modules of Climate Resilient Fishing
| Output 3.2 FF trained on market analysis of fish and prepare their business plans | % FF complete their training on market analysis and business plan | None of the Fish Farmers under the project have received training on market analysis and business plan | First Year, work was done in 9 ponds. Training not yet undertaken as the formal approval of remaining ponds from District steering committee had not been received. | 100% of FF would complete their training on market analysis and business plan
| Output 3.3 Panchayat representatives trained in climate change factors | % GP representatives trained in climate change factors | No training to GP representatives on Climate Change | Training not yet undertaken. The Training need Assessment was used to prepare training module and content. Training will be conducted in year 2 | 50% of GP representatives trained in Climate Change
| Output 3.4 FFs made aware on the weather based insurance product for fish culture | % FFs understanding the terms and conditions of insurance product | No FF has been trained in the terms and conditions of insurance product | 7% FFs made aware on the weather based insurance product | 100% FFs attend awareness and training on weather based insurance products
Component 4 Knowledge Generation and Management | Outcome 4 Preparing and disseminating evidence based resilient climate change adaptation strategies for inland fisheries for small pond | Institutional processes for stakeholder involvement identifying areas for learning and policy development | No processes exist at present | Steering Committee at the state and each of the three districts formed and they have held their meetings; Technical Advisory Group formed and its meeting held | Steering Committees and Technical Advisory Group active and recommend areas for generating evidence
|  | % stakeholders covered through training and dissemination events on adaptation strategies for climate change | None at present | This year 3 activity | 2 training and 2 workshops conducted
|  | Adaptive strategies for fisheries articulated and developed | Adaptive strategies does not exist | Adaptive strategies developed though not articulated in a documentation form | Adaptive strategy for small-scale fisheries articulated and presented to different stakeholders
| Output 4.1 Institutional Processes for multi-stakeholder learning are established and activated | Membership of Institutions | No institution | 3 District Steering Committees (DSC) formed | Key stakeholders represented in institutions
|  | No of meetings | No meetings | 6 meetings of DSC in 3 districts held | Meetings held as per schedule
|  | Presence of stakeholders at meetings | No meetings | All stakeholders present in the meetings | Two thirds of stakeholders present at all meetings
| Output 4.2 Evidence based learning documents prepared for dissemination | No of learning documents prepared | No learning document exist | 1 Process Report has been prepared | 3 Process Reports; 6 AR reports; 3 Systematisation reports and 3 Policy Briefs prepared
| Output 4.3 Learning from project disseminated | No of stakeholders covered for dissemination of project learning | No coverage | This is year 3 activity | At least 20 different types of key stakeholders covered
|  | No of dissemination events organised | No events | This is year 3 activity | 2 training of CSOs and 2 workshops conducted
| Output 4.4 Knowledge products developed and printed | No of document to facilitate training | No document exist |  | 1 Manual and 2 toolkits
|  | No of document to showcase good practices | No document exist | This is year 3 activity | 1 Good Practice document
|  | No of documents available in Hindi | No document exist | This is year 3 activity | All knowledge products in Hindi

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Positive Influence (a) Conduct of Project Launch Workshop at the State Level has informed different stakeholders about the project, its different processes and activities that will be instituted during its implementation. The state workshop was attended by district level officials that also brought them on board with project objectives and outputs. The presence of district level officials in the State Workshop led to conduct of similar workshops in each of the three districts so that stakeholders at the district level were also informed about the project and its implementation. These workshops created a facilitative environment for the project and led to development of rapport with the administrative machinery at all levels. (b) Validation of selection of ponds by the District level officials of the Fisheries department gave confidence to the project as well as to the government departments in the processes and methodologies adopted for the implementation of the project. This has positively impacted in the processing of documents at the department level for ponds and fishers group related to the project. (c) Constitution of District Steering Committee in each of the three districts has a positive influence on the project and in generating spin-off effect on other stakeholders. The GIS data of the districts presented in DSCs were found relevant by other departments who have picked it up to feed it for the development of their respective departmental plans. (d) Association of Central Institute of Freshwater Aquaculture with the project as member of Technical Advisory Group and as partner for providing Capacity Building inputs under the project. The association has brought credibility to the project that has facilitated associations from other stakeholders like Soil Research Institute, Central Institute of Agriculture Engineering, and National Fisheries Development Board.
Were there are any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The contract was signed on 31st July 2015 but the field implementation process was contingent on the conduct of Project Launch Workshop that could take place on 18th November 2015.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | (a) The diversity of fish species and the mechanism to promote it needs to be built in to the project that will be based on the results of the development of Business Plan. This will necessitate modifications in the project design and in revisiting of project outputs that are presently based on promotion of (at most) five species of table fish. (b) Rate of inflation and cost of living had increased to a level where it is not possible for the project to employ senior technical experts on a regular basis. Alternatively the project has empanelled senior technical experts whose services are taken on task basis for project related activities. (c) Revising the payment schedule for release of Programme Execution Cost to the EE is different from its current method of linking it with Programme Cost.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | (a) The meetings with the community, the conduct of PRA, and baseline of the fishers family were directed to include women as respondents and participants in discussion. (b) The new fishers committee facilitated by the project has proactively sought membership of women (at least one third or 33 %). (c) Two women members in the project implementation team have been purposively inducted so that project can relate to women and enable them to participate in project activities. (d) Training Needs Analysis with Panchayat representatives consciously sought responses from Women Panchayat members so that their views and needs are also reflected in the analysis and subsequently in the training. (e) Work Orders issued for contracting of equipment for transportation of soil/soil excavation had explicit clause related to behaviour of their staff with women working on site and the fact that act related to Sexual Harassment at Workplace will be applicable to them. The clauses were read to the contractor before their signature so that they can take informed decisions.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | Positive (a) Willingness of the stakeholders and beneficiary to institute adaptive measures depends on their conviction that the climatic change is leading to the observable changes in their production. This conviction arises when their hunches are backed by micro level and relevant climatic data which is communicated to them in a demystified and simplest way. This is as true for fishers as it is for government and other institutional stakeholders. Negative (a) Climate Change for government is a sub sector of the main work that they are engaged in. The project is viewed by government as a separate vertical at the district level and different from the other work that they are doing.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | Generating and building existing knowledge of fisheries amongst tribal especially related to the diversity of fish species and the suitability of the pond habitat for growth of local fish should be an integral part of development of climate resilient activity in similar projects.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Positive (a) Beneficiaries are willing to invest their own money if they are convinced that adaptive measure will lead to improved production as the fishers have done in purchase of fingerlings in place of spawns as they were doing earlier. Negative (a) Weather based insurance for fisheries as a single product (rain, temperature, disease and poaching) becomes costly for small fishers. The product needs to be re-packaged and customized for the needs of fisher groups to become popular and as adaptive measure for small fishers. (b) Insurance companies have not been able to identify weather based insurance for small fishers as a potential market for their products and services. This has led to limited products and smaller market for weather based insurance.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | (a) The project exclusively focused on existing ponds. The present experience indicates that climate adaptation measures demonstrated in existing ponds can be replicated in both other existing ponds and in construction of new ponds. (b) Geo hydrological protocols developed under the project have enabled prioritising smaller areas for fisheries in given geographies. Further, different strategies for regenerative practices can be developed based on temporal mapping of resources in each of the priorities so identified. (c) Fish habitat regeneration through catchment treatment and greening of pond surrounds reduce the silt load; impacts temperature at the pond level; and more importantly develops habitat that promotes increased migration of fish and diversity of fish stock in the pond. (d) Construction of fish pass on ponds give confidence to the fishers to go for reduced fish density at the time of introducing fish seed as it will reduce their potential fish loss at the time of flooding. This can be replicated at a larger scale as climate adaptive measure. (e) Fishers in the first year have moved from introducing spawn to introduction of fingerling in their ponds with their own money. This has been a critical adaptive measure as it enables the fishers to go for reduced stocking density; introduce multiple layered fishing; and aim for early harvesting.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | For target communities the works done under Pond Modification and Catchment treatment have been most successful so far. Target communities have assessed the quantum of silt that has been arrested in the catchment and pond strengthening that has taken place during pond modification works. Some of the ponds undertaken in the project were old and no investments were made on their maintenance.
What measures are/have been put in place to ensure sustainability of the project/program results? | (a) The target communities are regularly informed and consulted for all activities under taken in their village. This also includes linking them to suppliers of fish seed and other service providers. The target groups thus have their own information and data base that they can use after the project. (b) The records of meetings and activities at the village level are being kept in the village in the custody of group members so that the same can form the reference material for the target group beyond the project period. (c) Resource persons for training of fishers have been identified from and within the target community. These persons will be trained as Trainers so that they can provide direction and guidance to the fishers group within and outside the project on a continued basis.
What measures are being/could have been put in place to improve project/program results? | (a) Review of budget items at the end of the first year of implementation as it would bring in realistic estimation for the remaining project period. (b) Review of cap of 9.5% as the Programme Execution Cost for the Executing Entity as the only available money for implementation and management of the project.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Data on local fish diversity has been generated with the community. This information will be used to target increase in fish diversity in ponds.
If learning objectives have been established, have they been met? Please describe. | Not yet articulated
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | DPR of Ponds selected for the project are not available as most ponds are old and it is difficult for the agency to locate these DPRs. Working with the District Steering Committee to enable access to some of these DPRs.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Not applicable at this Stage

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | IND/NIE/Food/2013/1
Implementing Entity | NATIONAL BANK FOR AGRICULTURE AND RURAL DEVELOPMENT (NABARD)
Type of implementing entity | NIE
Country | INDIA
Region | ASIA-PACIFIC
Sector | Food Security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term (at the end of First Year) |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 5344 | 2004 | 3340 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 33% | 33% | 33% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 25% | 25% | 25% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis Threat and Hazard information are not part of the project | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Food security | Local | 1: No plans conducted or updated | 24 | Food security | Local | 3: Risk and vulnerability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems Threat and Hazard information are not part of the project | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Other | 2: Low capacity | Total | 12 | Other | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 20% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 300 | 50% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | NGO | Regional | Other | 1: No capacity | NGO | Local | Other | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and ownership of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 180 | 33% | 1: Aware of neither |  | 180 | 33% | 5: Fully aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Other | Local | 2: Partially responsive (Lacks most elements) |  | Other | Local | 5: Highly responsive (All defined elements )
| Core Indicator 4.2: Assets produced, developed, improved or strengthened Hatchery, Nursery, Pond Strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Food security | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Food security | 1: Health and Social Infrastructure (developed/improved) | 5: Fully improved
|  | Food security | 2: Physical asset (produced/improved/strengthened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strengthened) | 5: Fully improved
|  | Food security | 2: Physical asset (produced/improved/strengthened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strengthened) | 5: Fully improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change Hatchery, Nursery, Pond Strengthened | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | National |  | Other | 3 | National |  | Other
|  | 0 | Community |  | Other | 3 | Community |  | Other
|  | 0 | Community |  | Other | 60 | Community |  | Other
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated Catchment Area Treatment and Pond Modification | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 2880 | ha rehabilitated | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Other | 1 | ha protected | 2: Partially effective | Other | 240 | ha protected | 5: Very effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 100 | 0% | 2: Limited improvement |  | 960 | 0% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 100 |  | From 0 to 0.5% | Fishing | 960 | 40% | From 30% to 40% | Fishing
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Other | Livelihoods | 60 | Adaptation strategies | Other | Livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 2: Most not integrated |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 1 | Other | National | Public policy | 3 | Other | Regional | Public policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 1 | 2: Partially not enforced (Most elements not implemented) |  | 2: Partially effective | 3 | 3: Partially enforced (Some elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.