## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 4 March 2016 to 4 March 2017
| Project Title: | Programme Support for Climate Change Adaptation in the vulnerable regions of Mopti and Timbuktu
| Project Summary: | The main objective of the programme is to increase the resilience of vulnerable communities and their adaptive capacity to climate change in the Regions of Mopti and Timbuctu including the Faguibine system zone. The programme has three components with the following specific outcomes: Component 1: Enhanced water control measures in vulnerable water buffer zones. Outcome: Increased climate change resilience of local water systems in Mopti and Timbuctu Regions. Component 2: Resilience in subsistence livelihoods of vulnerable communities. Outcome: The production of local livelihood systems such as agriculture, fisheries, livestock, and forest enhanced under climate change Component 3: Capacity-building and knowledge generation for adaptation Outcome: Enhanced capacity of local institutions and of communities to better adapt to climate change.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme (UNDP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | UNDP as Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Mali | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Communes of Mopti Region : Bamba, Pelou, Kendé, Tédié, Koubewel koundia, Gandamia, Dangol Boré, Pondori and Togoro Kotia Communes of Timbuctu Region : Alafia, Hanzakoma, Haribomo, Goundam, Gargando, Bintagoungou, Essakane, Kondi, Arham, Tindirma, and Binga | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 30/03/2015
IE-AFB Agreement Signature Date: |  | 04 November 2015 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 04 March 2016 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | March 2018
| Terminal Evaluation Date: | March 2019
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Reports: • Report of the Launching workshop • Quarterly and annuel Reports to UNDP CO (Progress Report/Financial Reports/Quarterly Work Plan/Annual Work Plan) • Report of the Steering Committee • Background situation of the Programme. • Creation of the project Website | Czech Republic
| List the Website address (URL) of project. | www.pacvmt-mali.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Boubacar Sidiki DEMBELE | Dominican Republic
| Email: | boubacarsdembele@gmail.com | Ecuador
| Date: | March 2017 | Egypt
| Government DA |  | El Salvador
| Name: | Boureima CAMARA | Equatoral Guinea
| Email: | bouricamara@gmail.com, Tel: +22366805756 | Eritrea
| Date: | March 2017 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | United Nations Development Programme (UNDP) | Fiji
| Email: | Abdoulaye.Bayoko@undp.org | Finland
| Date: | March 2017 | France
| Executing Agency |  | Gambia
| Name: | Environment and Sustainable Development Agency (AEDD) | Georgia
| Email: | aedd@enironnement.gov.ml | Germany
| Date: | March 2017 | Ghana
| Executing Agency |  | Greece
| Name: | There is only one Executing Agency that is AEDD | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to 4 March 2017
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 4 March 2016 | 797763
Add any comments on AF Grant Funds. (word limit=200) | The disbursement to date (US$ 797,763,59 from March 2016 to March 2017) represents 10% of the total funding. The expenditure rate for the first year of implementation, which was budgeted at US$ 3,907,508 is 20,4%. The low disbursement can be explained by: (i) the slowness of the technical services involved in the processing of files, (ii) the difficulty of obtaining exemptions to enable companies to register themselves at the tax level, (iii) the organisation of the project launch and the realisation of baseline studies such as environmental socio economic and technical studies, which are time consuming but low-financial value activities, (iv) the security problems in the communes of Timbuctu region slowed down the implementation of most of the activities (v) The long national procurement procedure imposed on the programme's investments has slowed down the implementation of the activities in all communes of the programme.
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT SPENT | AMOUNT COMMITTED | BALANCE
| Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 20 km silted channels and obstructed ponds | 198143.03 | 532234 | 334090.97
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems | 399787.54 | 920766 | 520978.46
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities | 2677.64 | 524100 | 521422.36
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change | 35792.7 | 476454 | 440661.3
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities |  | 547446 | 547446
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) | 6665.13 | 109633 | 102967.87
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) | 13885.69 | 235771 | 221885.31
| Output 3.3 Local institutional capacity strengthened in 20 communities in establishing micro-credit schemes, cereal banks etc. and in managing |  | 222096 | 222096
| Project Management Costs | 140811.853 | 339008 | 198196.147
| TOTAL | 797763.583 | 3907508 | 3109744.417
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 20 km silted channels and obstructed ponds | 96263 | March 2018
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems | 2264694 | March 2018
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities | 120057 | March 2018
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change | 440623 | December 2017
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities | 0 | TBD
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) | 68799 | December 2017
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) | 11243 | March 2018
| Output 3.3 Local institutional capacity strengthened in 20 communities in establishing micro-credit schemes, cereal banks etc. and in managing | 0 | TBD
| Project Management Costs | 287917 | March 2018
March 2018
| TOTAL | 3289596
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | The total co-financing as stated in the project document and realized to date is estimated at US$ 217,519
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | Under the in kind co-financing of the Government of Mali, a building was made available for the project team. The Government also bears the cost of electricity, water and security services.This contribution to date is estimated at US$ 125,000. UNDP cash co-financing is estimated at US$ 92,519

## Procurement 1 (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | N/A
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signature Date | Payment to Date | Remaining Balance
Contract N° 000004 related to baseline studies in Mopti | Abdou BALLO: Independant Consultant | 24466.9312 | 2016-06-01 | 24466.9312 | 0
Contracts for the training of 20 producers on agroforestry practices adapted to Climate Change in the commune of Bamba in Mopti Region | Youssouf CAMARA Independant Consultant | 4120.3704 | 2016-06-03 | 4120.3704 | 0
Contracts for the training of 20 producers on agroforestry practices adapted to Climate Change in the commune of Kendé in Mopti Region | Moussa KAREMBE Independant Consultant | 4027.7778 | 2016-06-07 | 4027.7778 | 0
Contracts for the training of 20 producers on agroforestry practices adapted to Climate Change in the commune of Pelou in Mopti Region | Moussa KAREMBE ndependant Consultant | 4011.2434 | 2016-06-03 | 4011.2434 | 0
Consultancy service for the evaluation and design of a perimeter (gardening) for the women of Kandé, rural district of Pondori, circle of Djenné | KARA-CONSULT | 8664.0212 | 2016-04-23 | 8664.0212 | 0
Consultancy service for the evaluation and design of a perimeter (gardening) for the women of Gomitogo, rural district of Pondori, circle of Djenné | KARA-CONSULT | 8664.0212 | 2016-05-23 | 8664.0212 | 0
Consultancy service for the evaluation and design of a perimeter (gardening) for the women of DEGUERE, rural district of BAMBA, circle of KORO | KARA-CONSULT | 8664.0212 | 2016-06-23 | 8664.0212 | 0
Consultancy service for the evaluation and design of a perimeter (gardening) for the women of OBE, rural district of TEDIE, circle of DOUNETZA | KARA-CONSULT | 8664.0212 | 2016-07-23 | 8664.0212 | 0
Consultancy service for the evaluation and design of a perimeter (gardening)for the women of SAOURAKOM, rural district of TEDIE, circle of DOUENTZA | KARA-CONSULT | 8664.0212 | 2016-08-23 | 8664.0212 | 0
Consultancy service for the evaluation and design of a perimeter (gardening) for the women of ADIA, rural district of KOUBEWEL KOUNDIA, circle of DOUENTZA | KARA-CONSULT | 8664.0212 | 2016-08-23 | 8664.0212 | 0
Consulting service for the evaluation and design of the KOIRABERY crocodile pond, rural district of KOUBEWEL KOUNDIA, circle of DOUENTZA | Atelier Inter-Architectes (AIA) | 9734.4081 | 2016-08-25 | 9734.4081 | 0
Consultancy service for evaluation and design for the development of the fish pond of KOIRABERY, rural district of KOUBEWEL KOUNDIA, circle of DOUENTZA | Atelier Inter-Architectes (AIA) | 11907.8538 | 2016-08-25 | 11907.8538 | 0
Consulting service for the evaluation and design of the ADIA pond, rural district of KOUBEWEL KOUNDIA, circle of DOUENTZA | Atelier Inter-Architectes (AIA) | 11907.8538 | 2016-08-25 | 11907.8538 | 0
Consulting service for the evaluation and design of the PELOU pond, rural district of PELOU, circle of BANDIAGARA | Atelier Inter-Architectes (AIA) | 11873.9253 | 2016-08-25 | 11873.9253 | 0
Consulting service for the evaluation and design of the TABACO pond, rural district of KOUBEWEL KOUNDIA, circle of DOUENTZA | Atelier Inter-Architectes (AIA) | 11907.8538 | 2016-08-25 | 11907.8538 | 0
Consulting service for evaluation and design for the development of the feeding channel of the BORE pond, rural district of BORE, circle of DOUENTZA | Atelier Inter-Architectes (AIA) | 12023.6971 | 2016-08-25 | 12023.6971 | 0
Consultancy service for the evaluation and design for the digging of the Diabal Plain Feeding Area, rural district ofTogoro-Kotia , Circle of Tenenkou | Groupement BERICA-SARL | 8796.2963 | 2016-08-25 | 8796.2963 | 0
Consultancy service for the evaluation and design for the digging of the Dialamba Plain Feeding Area, rural district ofTogoro-Kotia , Circle of Tenenkou | Groupement BERICA-SARL | 8482.1429 | 2016-08-25 | 8482.1429 | 0
Consultancy service for the assessment and design for the construction of the Orobane dam, rural district of Bamba , circle of Koro | Groupement BERICA-SARL | 14169.9735 | 2016-08-23 | 14169.9735 | 0
Consultancy service for the evaluation and design of a perimeter for the women of Togoro-Kotia, rural district of Togor-Kotia, circle of Tenenkou | Groupement BERICA-SARL | 8895.5026 | 2016-08-23 | 8895.5026 | 0
Consulting service for the evaluation and design for the development of the Orobane pool, rural district of Bamba, circle of Koro | Groupement BERICA-SARL | 11954.3651 | 2016-08-23 | 11954.3651 | 0
Consultancy service for the evaluation and design of a perimeter for the women of Sossobé, rural district of Togor-Kotia, circle of Tenenkou | Bureau Ingenierie Conseil (TECHNISOL) | 8895.5026 | 2016-08-23 | 8895.5026 | 0
Consulting service for the evaluation and design for the development of the Engré pool, rural district of KENDE, circle of BANDIAGARA | Groupement BERICA-SARL | 14120.3704 | 2016-08-23 | 14120.3704 | 0
Consulting service for the evaluation and design of a water supply in Dembely, rural district of KOUBEWEL KOUNDIA, Circle of Douentza | Société Ingenierie etudes et contrôle (SINEC) | 11574.0741 | 2016-08-23 | 11574.0741 | 0
Consulting service for the evaluation and design of a water supply in FEDJI HOYE, rural district of GANDAMIA, Circle of Douentza | Bureau d'études hydraulique et assainissement (H & A) | 11078.0423 | 2016-08-23 | 11078.0423 | 0
Consulting service for the evaluation and design of a water supply in BIROL ADIODA, rural district of GANDAMIA, Circle of Douentza | Bureau d'études hydraulique et assainissement (H & A) | 11541.0053 | 2016-08-23 | 11541.0053 | 0
Consulting service for the evaluation and design of a water supply in BORE, rural district of DANGOL BORE, Circle of DOUENTZA | Société Ingenierie etudes et contrôle (SINEC) | 10631.6138 | 2016-08-23 | 10631.6138 | 0
Consulting service for the evaluation and design of a water supply in DJERA, rural district of PONDORI, Circle of DJENNE | Société Ingenierie etudes et contrôle (SINEC) | 10813.4921 | 2016-08-23 | 10813.4921 | 0
Consulting service for the evaluation and design of a water supply in ANDJI, rural district of TEDIE, Circle of DOUENTZA | Société Ingenierie etudes et contrôle (SINEC) | 10717.5926 | 2016-08-23 | 10717.5926 | 0
Consulting service for the evaluation and design of a water supply in WEDIE, rural district of PELOU, Circle of BANDIAGARA | Société Ingenierie etudes et contrôle (SINEC) | 10664.6825 | 2016-08-23 | 10664.6825 | 0
Consulting service for the evaluation and design of a water supply in KENDE, rural district of KENDE, Circle of BANDIAGARA | Société Ingenierie etudes et contrôle (SINEC) | 11078.0423 | 2016-08-23 | 11078.0423 | 0
Memorandum of Understanding (MoU) N° 000005 for data collection for baseline studies in 11 communes in Timbuctu | Office pour la Mise en Valeur du Système Faguibine (OMVF) | 23370.205 | 2016-08-01 | 23370.205 | 0
Contrat N° 0000032 for baseline studies in Timbuctu | Abdou BALLO: Independant Consultant | 12400.7937 | 2016-10-01 | 12400.7937 | 0
Consulting service for the evaluation and Dimensioning for the realization of asummary water supply for the gardening on behalf of women in the village of Bougouberi, rural district of Binga, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL) | 10955.6878 | 2016-12-15 | 10955.6878 | 0
Consulting service for the evaluation and Dimensioning for the realization of asummary water supply for the gardening on behalf of women in the village of Bangadria, rural district of Binga, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL) | 10955.6878 | 2016-12-15 | 10955.6878 | 0
Consulting service for the evaluation and dimensioning for the realization of a summary water supply for the gardening on behalf of women in the village of Bangadria, rural district of Binga, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL | 10955.6878 | 2016-12-15 | 10955.6878 | 0
Consulting service for the evaluation and dimensioningof the sand dunes in the villages of Bougouberi, Salakoira, Awali and Babaga-Kouye, rural district of Binga, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL | 3019.1799 | 2016-12-15 | 3019.1799 | 0
Consulting service for evaluation and dimensioningfor the realization of a fish pond in Tindirma, rural district ofTindirma, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL | 3845.8995 | 2016-12-15 | 3845.8995 | 0
Consulting service for the technical, socio-economic and environmental studies of the excavation of the Youmma channel in Tindirma, rural district of Arham, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL | 9302.2487 | 2016-12-15 | 9302.2487 | 0
Consulting service for the technical, socio-economic and environmental studies of the excavation of the Kondori channel with dike and crossing work in Feindoukaina, rural district of Kondi, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL | 9302.2487 | 2016-12-15 | 9302.2487 | 0
Consulting service for evaluation and dimensioning for the realization of a water-holding dam in Thitihaye with fish pond in Arham, rural district of Arham, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL | 10132.2751 | 2016-12-15 | 10132.2751 | 0
Consulting service for the technical, socio-economic and environmental studies of the excavation work of the M' Bagna channel on 400 m, rural district of Kondi, Timbuktu region | Bureau d'Etudes, d'Ingénieur, de Recherche, d'Assistance et de Formation (BEIRAF) | 9474.2063 | 2016-12-15 | 9474.2063 | 0
Consulting service for the rehabilitation of the water reservoir of Bagna on 300 m, rural district of Kondi, Timbuktu region | Bureau d'Etudes, d'Ingénieur, de Recherche, d'Assistance et de Formation (BEIRAF) | 7795.9656 | 2016-12-15 | 7795.9656 | 0
Consulting service for the evaluation and dimensioning for the realization of a summary water supply for the gardening in the village of Goungoume, rural distric of Tindirma, Timbuktu region | Bureau d'Etudes, d'Ingénieur, de Recherche, d'Assistance et de Formation (BEIRAF) | 11102.8439 | 2016-12-15 | 11102.8439 | 0
Consulting service for the evaluation and the dimensioning for the development of a 25 km dike with control work in Goundam in the urbandistrict of Goundam, Timbuktu region | Bureau d'Etudes, d'Ingénieur, de Recherche, d'Assistance et de Formation (BEIRAF) | 10300.9259 | 2016-12-15 | 10300.9259 | 0
Consulting service for the evaluation and dimensioning for the construction of a water restraint on the arm of Tassakane in the rural district of Alafia, Timbuktu region | Bureau d'Etudes, d'Ingénieur, de Recherche, d'Assistance et de Formation (BEIRAF) | 10251.3228 | 2016-12-15 | 10251.3228 | 0
Consulting service for evaluation and dimensioning for the construction of a store for the storage and processing of vegetable products in Goundam in the urban district of Goundam, Timbuktu region | Bureau d'Etudes, d'Ingénieur, de Recherche, d'Assistance et de Formation (BEIRAF) | 6886.5741 | 2016-12-15 | 6886.5741 | 0
Consulting service for the evaluation and dimensioning of the gardening perimeter of Goundam women in the urban district of Goundam, Timbuktu region | Bureau d'Etudes, d'Ingénieur, de Recherche, d'Assistance et de Formation (BEIRAF) | 10276 | 2016-12-15 | 10276 | 0
Consulting service for the evaluation and dimenssionnement of the development of two juxtaposed perimeters areas for the women of Toya in in the rural disrict of Alafia, Timbuktu region | Bureau d'Etudes, d'Ingénieur, de Recherche, d'Assistance et de Formation (BEIRAF) | 11102.8439 | 2016-12-15 | 11102.8439 | 0
Consulting service for the evaluation and dimenssionnement for the rehabilitation of the intercollectivity pond Fare-Fare in the rural disrict of Alafia, Timbuktu region | Bureau d'Etudes, d'Ingénieur, de Recherche, d'Assistance et de Formation (BEIRAF) | 11102.8439 | 2016-12-15 | 11102.8439 | 0
Consulting service for the technical, socio-economic and environmental studies of the excavation of "bras deFatty" on 7 km in Tindirma, rural districtf Tindirma, Timbuktu region. | Bureau d'Etudes, d'Ingénieur, de Recherche, d'Assistance et de Formation (BEIRAF) | 9862.7646 | 2016-12-15 | 9862.7646 | 0
MoU N° 01/2017for the training of 159 tree nurses in 8 communes in Mopti | Direction Régionale des Eaux et Forêts, Regional Headquarters in Mopti (Mopti Game and Wildlife Department Regional Headquarters) | 8266.584 | March 2017 | 8266.584 | 0 | e
Total |  | 532041.5291 |  | 532041.5291 | 0 | Tél : (00223) 76 42 37 99), dou BALLO (Géo-Environnementaliste ) le 6 juin 2016
Formulas:
Signature Date = [Signature Date, row above]

## Feuil1 (hidden)
PROCUREMENT DATA
Please provide information for all contracts over $2,500 USD
Please provide the number of contracts under $2,500, signed during this reporting period: |  |  |  | N/A
LIST OF CONTRACTS
List all contracts related to the project/program with signature dates
Contract Type | Agency / Contracted party | Contract Value/Amount (USD) | Signiture Date | Payment to Date (USD) | Remaining Balance (USD)
Contract N° 000004 related to baseline studies in Mopti | Abdou BALLO: Independant Consultant | 24466.9312 | 2016-06-01 | 24466.9312 | 0
Contracts for the training of 20 producers on agroforestry practices adapted to Climate Change in the commune of Bamba in Mopti Region | Youssouf CAMARA Independant Consultant | 4120.3704 | 2016-06-03 | 4120.3704 | 0
Contracts for the training of 20 producers on agroforestry practices adapted to Climate Change in the commune of Kendé in Mopti Region | Moussa KAREMBE Independant Consultant | 4027.7778 | 2016-06-07 | 4027.7778 | 0
Contracts for the training of 20 producers on agroforestry practices adapted to Climate Change in the commune of Pelou in Mopti Region | Moussa KAREMBE ndependant Consultant | 4011.2434 | 2016-06-03 | 4011.2434 | 0
Consultancy service for the evaluation and design of a perimeter (gardening) for the women of Kandé, rural district of Pondori, circle of Djenné | KARA-CONSULT | 8664.0212 | 2016-04-23 | 8664.0212 | 0
Consultancy service for the evaluation and design of a perimeter (gardening) for the women of Gomitogo, rural district of Pondori, circle of Djenné | KARA-CONSULT | 8664.0212 | 2016-05-23 | 8664.0212 | 0
Consultancy service for the evaluation and design of a perimeter (gardening) for the women of DEGUERE, rural district of BAMBA, circle of KORO | KARA-CONSULT | 8664.0212 | 2016-06-23 | 8664.0212 | 0
Consultancy service for the evaluation and design of a perimeter (gardening) for the women of OBE, rural district of TEDIE, circle of DOUNETZA | KARA-CONSULT | 8664.0212 | 2016-07-23 | 8664.0212 | 0
Consultancy service for the evaluation and design of a perimeter (gardening)for the women of SAOURAKOM, rural district of TEDIE, circle of DOUENTZA | KARA-CONSULT | 8664.0212 | 2016-08-23 | 8664.0212 | 0
Consultancy service for the evaluation and design of a perimeter (gardening) for the women of ADIA, rural district of KOUBEWEL KOUNDIA, circle of DOUENTZA | KARA-CONSULT |  | 2016-08-23 |  | 0
Consulting service for the evaluation and design of the KOIRABERY crocodile pond, rural district of KOUBEWEL KOUNDIA, circle of DOUENTZA | Atelier Inter-Architectes (AIA) | 9734.4081 | 2016-08-25 | 9734.4081 | 0
Consultancy service for evaluation and design for the development of the fish pond of KOIRABERY, rural district of KOUBEWEL KOUNDIA, circle of DOUENTZA | Atelier Inter-Architectes (AIA) | 11907.8538 | 2016-08-25 | 11907.8538 | 0
Consulting service for the evaluation and design of the ADIA pond, rural district of KOUBEWEL KOUNDIA, circle of DOUENTZA | Atelier Inter-Architectes (AIA) | 11907.8538 | 2016-08-25 | 11907.8538 | 0
Consulting service for the evaluation and design of the PELOU pond, rural district of PELOU, circle of BANDIAGARA | Atelier Inter-Architectes (AIA) | 11873.9253 | 2016-08-25 | 11873.9253 | 0
Consulting service for the evaluation and design of the TABACO pond, rural district of KOUBEWEL KOUNDIA, circle of DOUENTZA | Atelier Inter-Architectes (AIA) | 11907.8538 | 2016-08-25 | 11907.8538 | 0
Consulting service for evaluation and design for the development of the feeding channel of the BORE pond, rural district of BORE, circle of DOUENTZA | Atelier Inter-Architectes (AIA) | 12023.6971 | 2016-08-25 | 12023.6971 | 0
Consultancy service for the evaluation and design for the digging of the Diabal Plain Feeding Area, rural district ofTogoro-Kotia , Circle of Tenenkou | Groupement BERICA-SARL | 8796.2963 | 2016-08-25 | 8796.2963 | 0
Consultancy service for the evaluation and design for the digging of the Dialamba Plain Feeding Area, rural district ofTogoro-Kotia , Circle of Tenenkou | Groupement BERICA-SARL | 8482.1429 | 2016-08-25 | 8482.1429 | 0
Consultancy service for the assessment and design for the construction of the Orobane dam, rural district of Bamba , circle of Koro | Groupement BERICA-SARL | 14169.9735 | 2016-08-23 | 14169.9735 | 0
Consultancy service for the evaluation and design of a perimeter for the women of Togoro-Kotia, rural district of Togor-Kotia, circle of Tenenkou | Groupement BERICA-SARL | 8895.5026 | 2016-08-23 | 8895.5026 | 0
Consulting service for the evaluation and design for the development of the Orobane pool, rural district of Bamba, circle of Koro | Groupement BERICA-SARL | 11954.3651 | 2016-08-23 | 11954.3651 | 0
Consultancy service for the evaluation and design of a perimeter for the women of Sossobé, rural district of Togor-Kotia, circle of Tenenkou | Bureau Ingenierie Conseil (TECHNISOL) | 9598.2143 | 2016-08-23 | 9598.2143 | 0
Consulting service for the evaluation and design for the development of the Engré pool, rural district of KENDE, circle of BANDIAGARA | Groupement BERICA-SARL | 14120.3704 | 2016-08-23 | 14120.3704 | 0
Consulting service for the evaluation and design of a water supply in Dembely, rural district of KOUBEWEL KOUNDIA, Circle of Douentza | Société Ingenierie etudes et contrôle (SINEC) | 11574.0741 | 2016-08-23 | 11574.0741 | 0
Consulting service for the evaluation and design of a water supply in FEDJI HOYE, rural district of GANDAMIA, Circle of Douentza | Bureau d'études hydraulique et assainissement (H & A) | 11078.0423 | 2016-08-23 | 11078.0423 | 0
Consulting service for the evaluation and design of a water supply in BIROL ADIODA, rural district of GANDAMIA, Circle of Douentza | Bureau d'études hydraulique et assainissement (H & A) | 11541.0053 | 2016-08-23 | 11541.0053 | 0
Consulting service for the evaluation and design of a water supply in BORE, rural district of DANGOL BORE, Circle of DOUENTZA | Société Ingenierie etudes et contrôle (SINEC) | 10631.6138 | 2016-08-23 | 10631.6138 | 0
Consulting service for the evaluation and design of a water supply in DJERA, rural district of PONDORI, Circle of DJENNE | Société Ingenierie etudes et contrôle (SINEC) | 10813.4921 | 2016-08-23 | 10813.4921 | 0
Consulting service for the evaluation and design of a water supply in ANDJI, rural district of TEDIE, Circle of DOUENTZA | Société Ingenierie etudes et contrôle (SINEC) | 10717.5926 | 2016-08-23 | 10717.5926 | 0
Consulting service for the evaluation and design of a water supply in WEDIE, rural district of PELOU, Circle of BANDIAGARA | Société Ingenierie etudes et contrôle (SINEC) | 10664.6825 | 2016-08-23 | 10664.6825 | 0
Consulting service for the evaluation and design of a water supply in KENDE, rural district of KENDE, Circle of BANDIAGARA | Société Ingenierie etudes et contrôle (SINEC) | 11078.0423 | 2016-08-23 | 11078.0423 | 0
Memorandum of Understanding (MoU) N° 000005 for data collection for baseline studies in 11 communes in Timbuctu | Office pour la Mise en Valeur du Système Faguibine (OMVF) | 23370.205 | 2016-08-01 | 23370.205 | 0
Contrat N° 0000032 for baseline studies in Timbuctu | Abdou BALLO: Independant Consultant | 12400.7937 | 2016-10-01 | 12400.7937 | 0
Consulting service for the evaluation and Dimensioning for the realization of asummary water supply for the gardening on behalf of women in the village of Bougouberi, rural district of Binga, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL) | 10955.6878 | 2016-12-15 | 10955.6878 | 0
Consulting service for the evaluation and Dimensioning for the realization of asummary water supply for the gardening on behalf of women in the village of Bangadria, rural district of Binga, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL) | 10955.6878 | 2016-12-15 | 10955.6878 | 0
Consulting service for the evaluation and dimensioning for the realization of a summary water supply for the gardening on behalf of women in the village of Bangadria, rural district of Binga, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL | 10955.6878 | 2016-12-15 | 10955.6878 | 0
Consulting service for the evaluation and dimensioningof the sand dunes in the villages of Bougouberi, Salakoira, Awali and Babaga-Kouye, rural district of Binga, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL | 3845.8995 | 2016-12-15 | 3845.8995 | 0
Consulting service for evaluation and dimensioningfor the realization of a fish pond in Tindirma, rural district ofTindirma, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL | 3019.1799 | 2016-12-15 | 3019.1799 | 0
Consulting service for the technical, socio-economic and environmental studies of the excavation of the Youmma channel in Tindirma, rural district of Arham, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL | 9302.2487 | 2016-12-15 | 9302.2487 | 0
Consulting service for the technical, socio-economic and environmental studies of the excavation of the Kondori channel with dike and crossing work in Feindoukaina, rural district of Kondi, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL | 9302.2487 | 2016-12-15 | 9302.2487 | 0
Consulting service for evaluation and dimensioning for the realization of a water-holding dam in Thitihaye with fish pond in Arham, rural district of Arham, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL | 9302.2487 | 2016-12-15 | 9302.2487 | 0
Consulting service for the technical, socio-economic and environmental studies of the excavation work of the M' Bagna channel on 400 m, rural district of Kondi, Timbuktu region | Bureau d'Etudes, d'Ingénieur, de Recherche, d'Assistance et de Formation (BEIRAF) | 9474.2063 | 2016-12-15 | 9474.2063 | 0
Consulting service for the rehabilitation of the water reservoir of Bagna on 300 m, rural district of Kondi, Timbuktu region | Bureau d'Etudes, d'Ingénieur, de Recherche, d'Assistance et de Formation (BEIRAF) | 7795.9656 | 2016-12-15 | 7795.9656 | 0
Consulting service for the technical, socio-economic and environmental studies of the excavation of the Kondori channel with dike and crossing work in Feindoukaina, rural district of Kondi, Timbuktu region | Cabinet d'Etudes, d'Expertise pour le Développement des Initiatives Locales (CEEDIL | 9302.2487 | 2016-12-15 | 9302.2487 | 0
BIDS
List all bids for each contact signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Tender RFQ-TKM-006-2013 Procurement of water regulation device 16 pcs PO 7999 | Entrepreneur Iskander Sultanmuradov | 16210.53 | 16210.53 | Procurement was made for water regulation device 16 pcs with delivery to Sakarchaga District. Selection was based on lowest price with timely delivery.
| LLP “Altyn Taslama” | 24070.18
Tender RFQ-TKM-008-2013 Procurement of construction materials PO 8000 | 1. Entrepreneur S. Geldiev | 44441.02 | 29989.12 | Procurement was made for construction materials. Selection was based on lowest price with timely delivery.
| 2. Entrepreneur G. Gundogdiev | 31115.44
| 3. Entrepreneur I. Sultanmuradov | 29989.12
Tender Micropurchasing/ Canvassing Procurement of construction materials for Sakarchaga project office PO 8047 | PARLAK GURLUSYK HUSUSY KARHANASY | 4784.74 | 4784.74 | Construction materials were purchased for lowest price and timely delivery.
| GUNESHNUR Company | 5518.53
Tender Micropurchasing/ Canvassing Procurement of construction materials for Karakum project office PO 8048 | GUYCLI YYLDYRYM HUSUSY KARHANASY | 3781.23 | 3781.23 | The offered equipment meets requester’s requirements. The price is competitive and lowest; the vendor provides 1-year warranty on parts and services.
| TAYSYZ, Private Enterprise | 4500.386
Tender RFQ-TKM-004-2013 Procurement of Archa 627pcs for Nohur project region PO 8014 | AZAT ASHYRALIYEV | Unit Price $14.91 USD Total: 9,350.00 | 9350 | Selection was based on lowest price with timely delivery, good stand (color, plant health) and packing, no damages and good root system, plant height.
| Entrepreneur S. Huseynov | Unit Price $15.30 USD
Tender RFQ-TKM-004-2013 Procurement of Archa 623pcs for Nohur project region PO 8013 | RAHMAN ORAZMYRADOV | Unit Price $14.04 USD Total: $8,743.86 | 8743.86 | Selection was based on lowest price with timely delivery, good stand (color, plant health) and packing, no damages and good root system, plant height The reason for purchasing only 623 pcs was that available quantity was only 623 pcs. Total quantity needed as per RFQ-TKM-004-2013 was 1250 pcs, and remaining was bought from the Entrepreneur Mr. Azat Ashiraliyev as per PO#8014 for a bit higher unit price.
| Entrepreneur S. Huseynov | Unit Price $15.30 USD
Tender Micropurchasing/ Canvassing Procurement of winter tires and discs PO8037 (03.12.2013) | Enrepreneur Mr. YUSUP EMIRKULIYEV | 3415.78 | 3415.78 | Procurement of winter tires and discs for project vehicle
| Enrepreneur Mr. Begench Garriev | 3587.72
| Entrepreneur Mr. Hemra Emguliyev | 3589.47
Tender RFQ-TKM-006-2014 PO8153 (07.05.2014) | COMPANY GALKAN GALA | 23638.9263 | 23638.9263 | Procurement of Company Service for Construction of 5 dams with water reservoirs and Repairment of 2 dams with water reservoirs (RFQ-TKM-006-2014)
| Company “Yer Gazyjy “ | 26116.84
| Company “Keremli Gala” | 82100
Repair of the existing drip irrigation system in Nohur (RFQ-TKM-011-2014, PO-8165) | Mert Polat Company | 4978.95 | 4978.95 | Procurement of Company Service for Repair of the existing drip irrigation system by procurement of 33000pcs of drippers, Nohur
| Company AK Deutsche | 5775
| Entrepreneur Mr. Karajayev | 6892.98
| Company “OMR & SONS“ | 8900
| Entrepr. Mr. Nurgeldiyev | 11115.79
| Entrepr. Mr. Kerimov | 12421.05
| Entrepr. Mr. Suleymanov | 18526.32
| Entrepr. Mr. Ezimov | 22578.95
| Entrepr. Mr. Soltanyazov | 25473.68
| Entrepr. Ms. Mollayeva | 27720
| Company Mr. Guneshli Meydan | 31378.95
| Entrepr. Mr. Gaipniyazov | 32421.05
Grant Agreement for Adaptation Initiatives in Karakum | Farmers Union "Karakum" | 79744.43 | 79744.43 | Procurement of Services of Farmers Union for Construction of 7 new wells, Construction of 11 new sardobs, Repair the existing 6 wells, Repair the existing 5 Kaks, repair of 4 sardobs, Works on sand dune fixation, Karakum
Repair of the existing drip irrigation system in Nohur (RFQ-TKM-010-2014, PO-8188) | Arsh Gurlushyk | 23454.63 | 23454.63 | Procurement of Company Service for materials supply for a basin 400m3 and springs constructions in Nohur
| Entrepr Mr. Soltanyazov | 25976.67
| Entrepr Mr. Suleymanov | 25102.37
| Entrepr Mr. Hankurbanova | 34187.72
Materials supply for construction of 15 pits for vermicomposting in Nohur (RFQ-TKM-012-2014, PO-8186) | Entrepr Mr. Soltanyazov | 17684.21 | 19923.68 | Procurement of Company Service for materials supply for construction of 15 pits for vermicomposting (biohumus) in Nohur Project Region NOTE: The Vendor Mr. Soltanyazov provided a partial quote, by quoting only for the Lot-1
| Entrepr Mr. Suleymanov | 19923.68
Water regulating 5 devices installation in Sakarchage (RFQ-TKM-013-2014, PO-8177) | Company Galkan Gala | 16438.6 | 16438.6 | Procurement of Company Service for installation works of 5 water regulating devices (check-gates) in Sakarchaga Project Region
| Company Sarsmaz Gurlushyk | 18101.75
Construction materials supply for Grant Activities in Karakum (RFQ-TKM-018-2014, PO-8200) | Entrepr Mr. Gayipniyazov | 90762.11 | 90762.11 | Procurement of construction materials supply for wells and sardobs construction in Karakum Project Region
| Entrepr Mr. Shyhov | 122896.14
| Entrepr Mr. Suleymanov | 96835.58
Construction materials supply for sand dune fixation in Karakum (RFQ-TKM-019-2014, PO-8203) | Entrepr Mr. Gayipniyazov | 39312.28 | 39312.28 | Procurement of construction materials supply for sand dune fixation in Karakum Project Region
| Entrepr Mr. Shyhov | 45333.33
| Entrepr Mr. Suleymanov | 71549.12
| Entrepr Mrs. Hankurbanova | 170455.44
| Entrepr Mr. Chariyev | 406814.04
Buldozer Service for 3 Reservoirs in Nohur - by the Company Galkan Gala (RFQ-TKM-024-2014, PO-8219) | Company Galkan Gala | 7752.2982 | 7752.2982 | Direct Contracting modality was applied.
Installation of 7 water regulating devices in Sakarchaga - by the Company Galkan Gala (RFQ-TKM-027-2014, PO-8249) | Company Galkan Gala | 21898.2456 | 21898.2456 | Direct Contracting modality was applied.
Water regulating 3 devices Q = 0,8 м3/с installation in Sakarchage (RFQ-TKM-028-2014, PO-8251) | Company Dabaralanma | 14200 | 14200 | Procurement of Company Service for installation works of 3 water regulating devices (check-gates) Q = 0,8 м3/с in Sakarchaga Project Region
| Company Galkan Gala | 14900
Company service for 6 km drainage collector cleaning in Sakarchaga (RFQ-TKM-029-2014, PO-8274) | Company Altyn Dunya | 81600 | 15157.8947 | Company service for 6 km drainage collector cleaning in Sakarchaga Project Region
| Company Dabaralanma | 17017.5439
| Company Maryersuwhojalyk | 15157.8947
| Company Shukurli | 37894.7368
| Company Yer Gazyjy | 15700
20 ha land reclamation in Sakarchaga - by the Company Galkan Gala (RFQ-TKM-004-2015) | Company Galkan Gala | 19964.74 | 19964.74 | Direct Contracting modality was applied.
18.7 km drainage collector cleaning in Sakarchaga (RFQ-TKM-006-2015) | Company Galkan Gala | 17178.9474 | 17178.9474 | Direct Contracting modality was applied.
Printing of 10 booklets and one brochure in 3 languages (RFQ-TKM-016-2015) | BIDDER-1 Entrepreneur Cherkezov | 14071.43 |  | BIDDER-2 Entrepreneur Karmanovskaya was awarded the Contract for Printing of 10 booklets and one brochure in 3 languages
| BIDDER-2 Entrepreneur Karmanovskaya | 9102.17 | 9102.17
| BIDDER-3 Company Durmejik | 15862.86
| BIDDER-4 Company Gundogar Yildyzy | 8371.43 |  | Bidder-4 Company Gundogar Yildyzy didn't include the cost of State Registration in their quotation, which was required, and refused to provide it, and was disqualified.
Constr materials for grant activities (ITB-TKM-003-2015) | 1. Mr. Shyhov A. | 96265.56
| 2. Mr. Gayipniyazov S. | 91307.56
| 3. Guneshli Meydan | 85425
| 4. Watan Gurlushyk | 17985.68 |  | Partial offer
| 5. Mr. Gayipniyazov O. | 90620.41
| 6. Mr. A. Gochiyev | 73466.93 | 73466.93 | Mr. A. Gochiyev was awarded the contract on supply of construction materials for grant activities
Grant Agreement with Karakum Farmers Union signed on 08-Oct-15 | Direct payment | 33332.57 | 33332.57 | Grant Agreement with Karakum Farmers Union for payment of specialists labor cost involved in constructions
RFP-TKM-001-2016 - International Consulting Company Service to Develop a detailed Manual to assist Water User Groups to be established and carry out their work effectively. | Company MetaMeta Research was selected. There was IC announcement for the same TOR that can be used as a comparison for Meta Meta’s financial Offer. The following candidates were shortlisted: Mr. Merkley $59,442.00; Mr. Nurymgereyev $11,289.00; Mr. Vermillion $28,209.12 | 31660 | 31660 | International Consulting Company Service to Develop a detailed Manual to assist Water User Groups to be established and carry out their work effectively. MetaMeta Research's Contract was amended and additional $5300 was added for additional tasks assigned.
Pump and Power transformer supply and installation in Sakarchaga (RFQ-TKM-001-2016) | BIDDER-1 Barat Tokay | 85821.43 | 56171.43 | Company Galkan Gala was awarded the Contract for Pump and Power transformer supply and installation in Sakarchaga
| BIDDER-2 Galkan Gala | 56171.43
Supply of satellite geodesic receivers and software (RFQ-TKM-005-2016) | BIDDER-1 Leica-tm | 69367.5 | 14889.28 | BIDDER-2 Company Newcast East was awarded the Contract for supply of satellite geodesic receivers and software
| BIDDER-2 Newcast East | 14889.28
Procurement of Company service for abandoned land reclamation for Adaptation Fund Project. (RFQ-TKM-021-2015) | BIDDER-1 Company «Ussat Gurlushyk» | 29947.62 | 29514.29 | LLP «Галкан Гала» was awarded the contract for abandoned land reclamation
| BIDDER-2 Company «Ulag Bina» | 50240
| BIDDER-3 LLP «Галкан Гала» | 29514.29
Procurement of HDPE Geomembrane (RFQ-TKM-022-2015) | BIDDER-1 Entrepreneur Ms. Ogulsheker Mollayeva | 20460 | 20460 | Entrepreneur Ms. Ogulsheker Mollayeva was awarded the contract on procurement of HDPE Geomembrane as per RFQ-TKM-022-2015
| BIDDER-2 Entrepreneur Mr. Gochiev Ashir | 29000
Construction of 5 km drainage collector at Zahmet Farmers Union, Sakarchaga District, Mary Province (RFQ-TKM-008-2015) | BIDDER-1 Entrepreneur Ussat Gurlushyk | 80000 | 56000 | LLP «Галкан Гала» was awarded the contract for 5 km drainage collector construction.
| BIDDER-2 Entrepreneur Ulag-Bina | 171428.57
| BIDDER-3 LLP Galkan Gala | 56000

## Procurement 2 (hidden)
BIDS
List all bids for each contract signed with date of open call and winning bid
CONTRACT & Procurement Method | Submitted Bids | Technical qualified Bids | Open date | Bid Amount (USD) | Winning Bid Amount (USD) | Selection Justification for the Winner
Contract for baseline studies in Mopti Region | Mahamane.H.MAIGA | Mahamane.H.MAIGA | 6/06/ 2016 | 41474.041 | 24465.2778 | Cheapest Offer and Highest Experience in the development of projects baseline studies
| Abdou BALLO | Abdou BALLO |  | 24465.2778
| Tidiani SANOGO | Tidiani SANOGO |  | 45830.3571
| Mamadou BALLO | Mamadou BALLO |  | 36249.6743
Contract for the training of 20 producers on agroforestry practices adapted to Climate Change in the commune of Bamba in Mopti Region | Youssouf camara | Youssouf camara | 01/06/ 2016 | 4120.3704 | 4120.3704 | Cheapest Offer and most qualified in training and Agroforestry
| Moussa Karembé | Moussa Karembé |  | 4348.545
| Abdou Kader Touré | N/A |  | N/A
Contract for the training of 20 producers on agroforestry practices adapted to Climate Change in the commune of Kendé in Mopti Region | Youssouf camara | Youssouf camara | 01/06/ 2016 | 4216.2698 | 4027.7778 | Cheapest Offer and most qualified in training and Agroforestry
| Moussa Karembé | Moussa Karembé |  | 4027.7778
| Abdou Kader Touré | N/A |  | N/A
contract for the training of 20 producers in agroforestry practices adapted to Climate Change in the commune of PELOUin Mopti Region. | Youssouf camara | Youssouf camara | 01/06/ 2016 | 4174.9339 | 4011.2434 | Cheapest Offer and most qualified in training and Agroforestry
| Moussa Karembé | Moussa Karembé |  | 4011.2434
| Abdou Kader Touré | N/A |  | N/A
| KARA – CONSULT | KARA – CONSULT | 2016-08-06 | 8664.0212
Consultancy service for the evaluation and design of a perimeter (gardening) for the women of Kandé, rural district of Pondori, circle of Djenné | CONSULTING INTERNATIONAL AND SERVICE | N/A |  | N/A | 8664.02 | Cheapest offer of offices selected on the basis of their experience
| KENE-CONSULTING MANAGEMENT | KENE-CONSULTING MANAGEMENT |  | 10367.0635
| KARA – CONSULT | KARA – CONSULT | 2016-08-06 | 8664.0212
Consultancy service for the evaluation and design of a perimeter (gardening) for the women of Gomitogo, rural district of Pondori, circle of Djenné | KENE-CONSULTING MANAGEMENT | KENE-CONSULTING MANAGEMENT |  | 10367.0635 | 8664.02
| CONSULTING INTERNATIONAL AND SERVICE | N/A |  | N/A |  | Cheapest offer of offices selected on the basis of their experience
Consultancy service for the evaluation and design of a perimeter (gardening) for the women of DEGUERE, rural district of BAMBA, circle of KORO | KARA – CONSULT | KARA – CONSULT | 2016-08-06 | 8664.0212 | 8664.02 | Cheapest offer of offices selected on the basis of their experience
| CONSULTING INTERNATIONAL AND SERVICE | N/A |  | N/A
| KENE-CONSULTING MANAGEMENT | KENE-CONSULTING MANAGEMENT |  | 10367.0635
Consultancy service for the evaluation and design of a perimeter (gardening) for the women of OBE, rural district of TEDIE, circle of DOUNETZA | CONSULTING INTERNATIONAL AND SERVICE | N/A | 2016-08-06 | N/A | 8664.02 | Cheapest offer of offices selected on the basis of their experience
| KARA – CONSULT | KARA – CONSULT |  | 8664.0212
| KENE-CONSULTING MANAGEMENT | KENE-CONSULTING MANAGEMENT |  | 10367.0635
Consultancy service for the evaluation and design of a perimeter (gardening)for the women of SAOURAKOM, rural district of TEDIE, circle of DOUENTZA | KARA – CONSULT | KARA – CONSULT | 2016-08-06 | 8664.0212 | 8664.02 | Cheapest offer of offices selected on the basis of their experience
| CONSULTING INTERNATIONAL AND SERVICE | N/A |  | N/A
| KENE-CONSULTING MANAGEMENT | KENE-CONSULTING MANAGEMENT |  | 10367.0635
Consultancy service for the evaluation and design of a perimeter (gardening) for the women of ADIA, rural district of KOUBEWEL KOUNDIA, circle of DOUENTZA | KARA – CONSULT | KARA – CONSULT | 2016-08-06 | 8664.0212 | 8664.02 | Cheapest offer of offices selected on the basis of their experience
| CONSULTING INTERNATIONAL AND SERVICE | N/A |  | N/A
| KENE-CONSULTING MANAGEMENT | KENE-CONSULTING MANAGEMENT |  | 10367.0635
Consulting service for the evaluation and design of the KOIRABERY crocodile pond, rural district of KOUBEWEL KOUNDIA, circle of DOUENTZA | INGENIEUR CONSEIL EN CONSTRUCTIONS CIVILES ET RURAL (ICCCR) | INGENIEUR CONSEIL EN CONSTRUCTIONS CIVILES ET RURAL (ICCCR) | 2016-08-03 | 9734.4081 | 9734.4081 | Cheapest offer of offices selected on the basis of their experience
| ATELIER INTER-ARCHITECTES (AIA) | ATELIER INTER-ARCHITECTES (AIA) |  | 12101.5212
| CONSEIL EN INGENIERIE POUR LE DEVELOPPEMENT (CID) | CONSEIL EN INGENIERIE POUR LE DEVELOPPEMENT (CID) |  | 1202.877
Consultancy service for evaluation and design for the development of the fish pond of KOIRABERY, rural district of KOUBEWEL KOUNDIA, circle of DOUENTZA | INGENIEUR CONSEIL EN CONSTRUCTIONS CIVILES ET RURAL (ICCCR) | INGENIEUR CONSEIL EN CONSTRUCTIONS CIVILES ET RURAL (ICCCR) | 2016-08-03 | 11907.8538 | 11907.8538 | Cheapest offer of offices selected on the basis of their experience
| ATELIER INTER-ARCHITECTES (AIA) | ATELIER INTER-ARCHITECTES (AIA) |  | 12101.5212
| CONSEIL EN INGENIERIE POUR LE DEVELOPPEMENT (CID) | CONSEIL EN INGENIERIE POUR LE DEVELOPPEMENT (CID) |  | 12029.1005
Consulting service for the evaluation and design of the ADIA pond, rural district of KOUBEWEL KOUNDIA, circle of DOUENTZA | ATELIER INTER-ARCHITECTES (AIA) | ATELIER INTER-ARCHITECTES (AIA) | 2016-08-03 | 12101.5212 | 11907.8538 | Cheapest offer of offices selected on the basis of their experience
| INGENIEUR CONSEIL EN CONSTRUCTIONS CIVILES ET RURAL (ICCCR) | INGENIEUR CONSEIL EN CONSTRUCTIONS CIVILES ET RURAL (ICCCR) |  | 11907.8538
| CONSEIL EN INGENIERIE POUR LE DEVELOPPEMENT (CID) | CONSEIL EN INGENIERIE POUR LE DEVELOPPEMENT (CID) |  | 12103.1746
Consulting service for the evaluation and design of the PELOU pond, rural district of PELOU, circle of BANDIAGARA | INGENIEUR CONSEIL EN CONSTRUCTIONS CIVILES ET RURAL (ICCCR) | INGENIEUR CONSEIL EN CONSTRUCTIONS CIVILES ET RURAL (ICCCR) | 2016-08-03 | 11873.9253 | 11873.9253 | Cheapest offer of offices selected on the basis of their experience
| ATELIER INTER-ARCHITECTES (AIA) | ATELIER INTER-ARCHITECTES (AIA) |  | 12053.5714
| CONSEIL EN INGENIERIE POUR LE DEVELOPPEMENT (CID) | CONSEIL EN INGENIERIE POUR LE DEVELOPPEMENT (CID) |  | 11987.4339
Consulting service for the evaluation and design of the TABACO pond, rural district of KOUBEWEL KOUNDIA, circle of DOUENTZA | INGENIEUR CONSEIL EN CONSTRUCTIONS CIVILES ET RURAL (ICCCR) | INGENIEUR CONSEIL EN CONSTRUCTIONS CIVILES ET RURAL (ICCCR) | 2016-08-03 | 11907.8538 | 11907.8538 | Cheapest offer of offices selected on the basis of their experience
| ATELIER INTER-ARCHITECTES (AIA) | ATELIER INTER-ARCHITECTES (AIA) |  | 12101.5212
| CONSEIL EN INGENIERIE POUR LE DEVELOPPEMENT (CID) | CONSEIL EN INGENIERIE POUR LE DEVELOPPEMENT (CID) |  | 12029.1005
| SOCIETE D’INGENIERIES ET D’EXPERTISES CONSEILS (SIEXCO) | N/A |  | N/A
Consulting service for evaluation and design for the development of the feeding channel of the BORE pond, rural district of BORE, circle of DOUENTZA | ATELIER INTER-ARCHITECTES (AIA) | ATELIER INTER-ARCHITECTES (AIA) | 2016-08-03 | 12624.0079 | 12023.6971 | Cheapest offer of offices selected on the basis of their experience
| INGENIEUR CONSEIL EN CONSTRUCTIONS CIVILES ET RURAL (ICCCR) | INGENIEUR CONSEIL EN CONSTRUCTIONS CIVILES ET RURAL (ICCCR) |  | 12023.6971
| CONSEIL EN INGENIERIE POUR LE DEVELOPPEMENT (CID) | CONSEIL EN INGENIERIE POUR LE DEVELOPPEMENT (CID) |  | 12235.4497
Consultancy service for the evaluation and design for the digging of the Diabal Plain Feeding Area, rural district ofTogoro-Kotia , Circle of Tenenkou | ISSIAKA RUBIN KOURIBA, Ingénieur Conseil (BESIS) | N/A | 2016-08-04 | N/A | 8796.2963 | Cheapest offer of offices selected on the basis of their experience
| CIA -SARL Cabinet d’Ingénierie Appliquée | CIA -SARL Cabinet d’Ingénierie Appliquée |  | 8928.5714
| GROUPEMENT BERICA-SARL/ACG-SARL | GROUPEMENT BERICA-SARL/ACG-SARL |  | 8796.2963
Consultancy service for the evaluation and design for the digging of the Dialamba Plain Feeding Area, rural district ofTogoro-Kotia , Circle of Tenenkou | ISSIAKA RUBIN KOURIBA, Ingénieur Conseil (BESIS) | N/A | 2016-08-04 | N/A | 8796.2963 | Cheapest offer of offices selected on the basis of their experience
| CIA -SARL Cabinet d’Ingénierie Appliquée | CIA -SARL Cabinet d’Ingénierie Appliquée |  | 8928.5714
| GROUPEMENT BERICA-SARL/ACG-SARL | GROUPEMENT BERICA-SARL/ACG-SARL |  | 8796.2963
Consultancy service for the assessment and design for the construction of the Orobane dam, rural district of Bamba , circle of Koro | ISSIAKA RUBIN KOURIBA, Ingénieur Conseil (BESIS) | ISSIAKA RUBIN KOURIBA, Ingénieur Conseil (BESIS) | 2016-08-04 | 15211.6402 |  | Cheapest offer of offices selected on the basis of their experience
| CIA -SARL Cabinet d’Ingénierie Appliquée | CIA -SARL Cabinet d’Ingénierie Appliquée |  | 15707.672 | 14169.9735
| GROUPEMENT BERICA-SARL/ACG-SARL | GROUPEMENT BERICA-SARL/ACG-SARL |  | 14169.9735
Consultancy service for the evaluation and design of a perimeter for the women of Togoro-Sarré, rural district of Togor-Kotia, circle of Tenenkou | ISSIAKA RUBIN KOURIBA, Ingénieur Conseil (BESIS) | ISSIAKA RUBIN KOURIBA, Ingénieur Conseil (BESIS) | 2016-08-05 | 8597.8836
| Technisol Bureau d’Ingénieur-conseil | Technisol Bureau d’Ingénieur-conseil |  | 9098.8757 | 8895.5026 | Cheapest offer of offices selected on the basis of their experience
| GROUPEMENT BERICA-SARL/ACG-SARL | GROUPEMENT BERICA-SARL/ACG-SARL |  | 8895.5026
| ISSIAKA RUBIN KOURIBA, Ingénieur Conseil (BESIS) | ISSIAKA RUBIN KOURIBA, Ingénieur Conseil (BESIS) | 2016-08-05 | 15211.6402
Consulting service for the evaluation and design for the development of the Orobane pool, rural district of Bamba, circle of Koro | Technisol Bureau d’Ingénieur-conseil | N/A |  | N/A | 11954.3651 | Cheapest offer of offices selected on the basis of their experience
| GROUPEMENT BERICA-SARL/ACG-SARL | GROUPEMENT BERICA-SARL/ACG-SARL |  | 11954.3651
| ISSIAKA RUBIN KOURIBA, Ingénieur Conseil (BESIS) | ISSIAKA RUBIN KOURIBA, Ingénieur Conseil (BESIS) | 2016-08-05 | 9623.0159
Consultancy service for the evaluation and design of a perimeter for the women of Sossobé, rural district of Togor-Kotia, circle of Tenenkou | CIA -SARL Cabinet d’Ingénierie Appliquée | CIA -SARL Cabinet d’Ingénierie Appliquée |  | 9507.2751 | 8895.5026 | Cheapest offer of offices selected on the basis of their experience
| Technisol Bureau d’Ingénieur-conseil | Technisol Bureau d’Ingénieur-conseil |  | 8895.5026
Consulting service for the evaluation and design for the development of the Engré pool, rural district of KENDE, circle of BANDIAGARA | ISSIAKA RUBIN KOURIBA, Ingénieur Conseil (BESIS) | ISSIAKA RUBIN KOURIBA, Ingénieur Conseil (BESIS) | 2016-08-05 | 15707.672 | 14120.3704 | Cheapest offer of offices selected on the basis of their experience
| CIA -SARL Cabinet d’Ingénierie Appliquée | CIA -SARL Cabinet d’Ingénierie Appliquée |  | 17361.1111
| GROUPEMENT BERICA-SARL/ACG-SARL | GROUPEMENT BERICA-SARL/ACG-SARL |  | 14120.3704
Consulting service for the evaluation and design of a water supply in Dembely, rural district of KOUBEWEL KOUNDIA, Circle of Douentza | Bureau d’Etudes Hydraulique et Assainissement (H&A Consult sarl) | Bureau d’Etudes Hydraulique et Assainissement (H&A Consult sarl) | 2016-08-07 | 12400.7937 | 11574.0741 | Cheapest offer of offices selected on the basis of their experience
| Société d’Ingénierie, d’Etudes et de Contrôle (SINEC) | Société d’Ingénierie, d’Etudes et de Contrôle (SINEC) |  | 11574.0741
| Bureau d’études, de Recherche et d’Orientation pour la surveillance et le contrôle des Travaux (BURSOCLE-MALI) | N/A |  | N/A
Consulting service for the evaluation and design of a water supply in FEDJI HOYE, rural district of GANDAMIA, Circle of Douentza | Bureau d’Etudes Hydraulique et Assainissement (H&A Consult sarl) | Bureau d’Etudes Hydraulique et Assainissement (H&A Consult sarl) | 2016-08-07 | 11078.0423 | 11078.0423 | Cheapest offer of offices selected on the basis of their experience
| Bureau d’Etudes Techniques et de Gestion de Projets (BGET) | Bureau d’Etudes Techniques et de Gestion de Projets (BGET) |  | 11405.9772
| Bureau d’études, de Recherche et d’Orientation pour la surveillance et le contrôle des Travaux (BURSOCLE-MALI) | N/A |  | N/A
Consulting service for the evaluation and design of a water supply in BIROL ADIODA, rural district of GANDAMIA, Circle of Douentza | Bureau d’Etudes Hydraulique et Assainissement (H&A Consult sarl) | Bureau d’Etudes Hydraulique et Assainissement (H&A Consult sarl) | 2016-08-07 | 11541.0053 | 11541.0053 | Cheapest offer of offices selected on the basis of their experience
| Bureau d’Etudes Techniques et de Gestion de Projets (BGET) | Bureau d’Etudes Techniques et de Gestion de Projets (BGET) |  | 12827.9349
| Bureau d’études, de Recherche et d’Orientation pour la surveillance et le contrôle des Travaux (BURSOCLE-MALI) | N/A |  | N/A
Consulting service for the evaluation and design of a water supply in BORE, rural district of DANGOL BORE, Circle of DOUENTZA | Bureau d’Etudes Hydraulique et Assainissement (H&A Consult sarl) | Bureau d’Etudes Hydraulique et Assainissement (H&A Consult sarl) | 2016-08-07 | 11541.0053 | 10631.6138 | Cheapest offer of offices selected on the basis of their experience
| Bureau d’Etudes Techniques et de Gestion de Projets (BGET) | N/A |  | N/A
| Bureau d’études, de Recherche et d’Orientation pour la surveillance et le contrôle des Travaux (BURSOCLE-MALI) | N/A |  | N/A
| Société d’Ingénierie, d’Etudes et de Contrôle (SINEC) | Société d’Ingénierie, d’Etudes et de Contrôle (SINEC) |  | 10631.6138
| Bureau d’Etudes Hydraulique et Assainissement (H&A Consult sarl) | Bureau d’Etudes Hydraulique et Assainissement (H&A Consult sarl) | 2016-08-07 | 11904.7619
| Bureau d’Etudes Techniques et de Gestion de Projets (BGET) | N/A |  | N/A
Consulting service for the evaluation and design of a water supply in DJERA, rural district of PONDORI, Circle of DJENNE | Société d’Ingénierie, d’Etudes et de Contrôle (SINEC) | Société d’Ingénierie, d’Etudes et de Contrôle (SINEC) |  | 10813.4921 | 10813.4921 | Cheapest offer of offices selected on the basis of their experience
| Bureau d’Etudes Hydraulique et Assainissement (H&A Consult sarl) | Bureau d’Etudes Hydraulique et Assainissement (H&A Consult sarl) | 2016-08-07 | 11739.418
Consulting service for the evaluation and design of a water supply in ANDJI, rural district of TEDIE, Circle of DOUENTZA | Bureau d’études, de Recherche et d’Orientation pour la surveillance et le contrôle des Travaux (BURSOCLE-MALI) | N/A |  | N/A | 10717.5926 | Cheapest offer of offices selected on the basis of their experience
| Société d’Ingénierie, d’Etudes et de Contrôle (SINEC) | Société d’Ingénierie, d’Etudes et de Contrôle (SINEC) |  | 10717.5926
| Bureau d’Etudes Hydraulique et Assainissement (H&A Consult sarl) | Bureau d’Etudes Hydraulique et Assainissement (H&A Consult sarl) | 2016-08-07 | 11574.0741
| Bureau d’Etudes Techniques et de Gestion de Projets (BGET) | N/A |  | N/A
Consulting service for the evaluation and design of a water supply in WEDIE, rural district of PELOU, Circle of BANDIAGARA | Bureau d’études, de Recherche et d’Orientation pour la surveillance et le contrôle des Travaux (BURSOCLE-MALI) | N/A |  | N/A | 10664.6825 | Cheapest offer of offices selected on the basis of their experience
| Société d’Ingénierie, d’Etudes et de Contrôle (SINEC) | Société d’Ingénierie, d’Etudes et de Contrôle (SINEC) |  | 10664.6825
| Bureau d’Etudes Hydraulique et Assainissement (H&A Consult sarl) | Bureau d’Etudes Hydraulique et Assainissement (H&A Consult sarl) | 2016-08-07 | 11904.7619
Consulting service for the evaluation and design of a water supply in KENDE, rural district of KENDE, Circle of BANDIAGARA | Bureau d’études, de Recherche et d’Orientation pour la surveillance et le contrôle des Travaux (BURSOCLE-MALI) | N/A |  | N/A | 11078.0423 | Cheapest offer of offices selected on the basis of their experience
| Société d’Ingénierie, d’Etudes et de Contrôle (SINEC) | Société d’Ingénierie, d’Etudes et de Contrôle (SINEC) |  | 11078.0423
Memorandum of Understanding (MoU) N° 000005 for data collection for baseline studies in 11 communes in Timbuctu | OMVF (Office de la mise en valeur du système Faguibine) | OMVF (Office de la mise en valeur du système Faguibine) | 2016-07-27 | 23370.205 | 23370.205 | OMVF is a State structure operating within the Faguibine catchment Area. DespiteTimbuctu's landlocked location and security situation, this structure remains active in the area, making it a highly valuable partnership. In addition, they benefit from the security support from MINUSMA (Security Mission of the United Nations in Mali)
| Dr Djeneba Dembelé BA | N/A | 2016-10-25 | N/A
Contrat N° 0000032 for baseline studies in Timbuctu | Dr Abdou BALLO | Dr Abdou BALLO | 2016-10-25 | 12400.7937 | 12400.7937 | Cheapest Offer and highest expertise in the development of projects baseline studies
| Dr Souleymane sidi TRAORE | Dr Souleymane sidi TRAORE | 2016-10-25 | 13955.0265
| Cabinet d’Etude et d’Expertise pour le Développement des Initiatives locales (CEEDIL) | Cabinet d’Etude et d’Expertise pour le Développement des Initiatives locales (CEEDIL) | 01-04/11/2016 | 10955.6878
Consulting service for the evaluation and Dimensioning for the realization of asummary water supply for the gardening on behalf of women in the village of Bougouberi, rural district of Binga, Timbuktu region | Bureau d’Etude et de Conseil en Administration et Développement local(BECADL) | N/A | 01-04/11/2016 | N/A | 10955.6878 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Géomètrie-Cartographie-Aménagement et Topographie (GCAT) | N/A | 01-04/11/2016 | N/A
| Yoli Consult | Yoli Consult | 01-04/11/2016 | 11904.7619
| Cabinet d’Etude et d’Expertise pour le Développement des Initiatives locales (CEEDIL) | Cabinet d’Etude et d’Expertise pour le Développement des Initiatives locales (CEEDIL) | 01-04/11/2016 | 10955.6878
Consulting service for the evaluation and Dimensioning for the realization of asummary water supply for the gardening on behalf of women in the village of Bangadria, rural district of Binga, Timbuktu region | Bureau d’Etude et de Conseil en Administration et Développement local(BECADL) | N/A | 01-04/11/2016 | N/A | 10955.6878 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Géomètrie-Cartographie-Aménagement et Topographie (GCAT) | N/A | 01-04/11/2016 | N/A
| Yoli Consult | Yoli Consult | 01-04/11/2016 | 11904.7619
| Cabinet d’Etude et d’Expertise pour le Développement des Initiatives locales (CEEDIL) | Cabinet d’Etude et d’Expertise pour le Développement des Initiatives locales (CEEDIL) | 01-04/11/2016 | 10955.6878
Consulting service for the evaluation and Dimensioning for the realization of asummary water supply for the gardening on behalf of women in the village of Arham, rural district of Binga, Timbuktu region | Bureau d’Etude et de Conseil en Administration et Développement local(BECADL) | N/A | 01-04/11/2016 | N/A | 10955.6878 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Géomètrie-Cartographie-Aménagement et Topographie (GCAT) | N/A | 01-04/11/2016 | N/A
| Yoli Consult | Yoli Consult | 01-04/11/2016 | 11904.7619
| Cabinet d’Etude et d’Expertise pour le Développement des Initiatives locales (CEEDIL) | Cabinet d’Etude et d’Expertise pour le Développement des Initiatives locales (CEEDIL) | 01-04/11/2016 | 3019.1799
Consulting service for the evaluation and dimensioningof the sand dunes in the villages of Bougouberi, Salakoira, Awali and Babaga-Kouye, rural district of Binga, Timbuktu region | Bureau d’Etude et de Conseil en Administration et Développement local(BECADL) | N/A | 01-04/11/2016 | N/A | 3019.1799 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Géomètrie-Cartographie-Aménagement et Topographie (GCAT) | N/A | 01-04/11/2016 | N/A
| Yoli Consult | Yoli Consult | 01-04/11/2016 | 4133.5979
| Cabinet d’Etude et d’Expertise pour le Développement des Initiatives locales (CEEDIL) | Cabinet d’Etude et d’Expertise pour le Développement des Initiatives locales (CEEDIL) | 01-04/11/2016 | 3845.8995
Consulting service for evaluation and dimensioningfor the realization of a fish pond in Tindirma, rural district ofTindirma, Timbuktu region | Bureau d’Etude et de Conseil en Administration et Développement local(BECADL) | N/A |  | N/A | 3845.8995 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Géomètrie-Cartographie-Aménagement et Topographie (GCAT) | N/A |  | N/A
| Yoli Consult | Yoli Consult |  | 5753.9683
| Cabinet d’Etude et d’Expertise pour le Développement des Initiatives locales (CEEDIL) | Cabinet d’Etude et d’Expertise pour le Développement des Initiatives locales (CEEDIL) | 01-04/11/2016 | 9302.2487
Consulting service for the technical, socio-economic and environmental studies of the excavation of the Youmma channel in Tindirma, rural district of Arham, Timbuktu region | Bureau d’Etude et de Conseil en Administration et Développement local(BECADL) | N/A |  | N/A | 9302.2487 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Géomètrie-Cartographie-Aménagement et Topographie (GCAT) | N/A |  | N/A
| Yoli Consult | Yoli Consult |  | 9920.6349
| Cabinet d’Etude et d’Expertise pour le Développement des Initiatives locales (CEEDIL) | Cabinet d’Etude et d’Expertise pour le Développement des Initiatives locales (CEEDIL) | 01-04/11/2016 | 9302.2487
Consulting service for the technical, socio-economic and environmental studies of the excavation of the Kondori channel with dike and crossing work in Feindoukaina, rural district of Kondi, Timbuktu region | Bureau d’Etude et de Conseil en Administration et Développement local(BECADL) | N/A |  | N/A | 9302.2487 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Géomètrie-Cartographie-Aménagement et Topographie (GCAT) | N/A |  | N/A
| Yoli Consult | Yoli Consult |  | 9920.6349
| Cabinet d’Etude et d’Expertise pour le Développement des Initiatives locales (CEEDIL) | Cabinet d’Etude et d’Expertise pour le Développement des Initiatives locales (CEEDIL) | 01-04/11/2016 | 10132.2751
Consulting service for evaluation and dimensioning for the realization of a water-holding dam in Thitihaye with fish pond in Arham, rural district of Arham, Timbuktu region | Bureau d’Etude et de Conseil en Administration et Développement local(BECADL) | N/A |  | N/A | 10132.2751 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Géomètrie-Cartographie-Aménagement et Topographie (GCAT) | N/A |  | N/A
| Yoli Consult | Yoli Consult |  | 10132.2751
| Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | 01-04/11/2016 | 9474.2063
Consulting service for the technical, socio-economic and environmental studies of the excavation work of the M' Bagna channel on 400 m, rural district of Kondi, Timbuktu region | Conseils - Etudes - Recherches - Techniques - Engineering – Services (CERTES Sarl) | N/A |  | N/A | 9474.2063 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Aigle Structure Technique (ASTEC Sarl ) | Aigle Structure Technique (ASTEC Sarl ) |  | 11078.0423
| Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | 01-04/11/2016 | 7795.9656
Consulting service for the rehabilitation of the water reservoir of Bagna on 300 m, rural district of Kondi, Timbuktu region | Conseils - Etudes - Recherches - Techniques - Engineering – Services (CERTES Sarl) | N/A |  | N/A | 7795.9656 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Aigle Structure Technique (ASTEC Sarl ) | Aigle Structure Technique (ASTEC Sarl ) |  | 11078.0423
| Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | 01-04/11/2016 | 11102.8439
Consulting service for the evaluation and dimensioning for the realization of a summary water supply for the gardening in the village of Goungoume, rural distric of Tindirma, Timbuktu region | Conseils - Etudes - Recherches - Techniques - Engineering – Services (CERTES Sarl) | N/A |  | N/A | 11102.8439 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Aigle Structure Technique (ASTEC Sarl ) | Aigle Structure Technique (ASTEC Sarl ) |  | 11243.3862
| Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | 01-04/11/2016 | 10300.9259
Consulting service for the evaluation and the dimensioning for the development of a 25 km dike with control work in Goundam in the urbandistrict of Goundam, Timbuktu region | Conseils - Etudes - Recherches - Techniques - Engineering – Services (CERTES Sarl) | N/A |  | N/A | 10300.9259 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Aigle Structure Technique (ASTEC Sarl ) | Aigle Structure Technique (ASTEC Sarl ) |  | 11078.0423
| Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | 01-04/11/2016 | 10251.3228
Consulting service for the evaluation and dimensioning for the construction of a water restraint on the arm of Tassakane in the rural district of Alafia, Timbuktu region | Conseils - Etudes - Recherches - Techniques - Engineering – Services (CERTES Sarl) | N/A |  | N/A | 10251.3228 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Aigle Structure Technique (ASTEC Sarl ) | Aigle Structure Technique (ASTEC Sarl ) |  | 11078.0423
| Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | 01-04/11/2016 | 6886.5741
Consulting service for evaluation and dimensioning for the construction of a store for the storage and processing of vegetable products in Goundam in the urban district of Goundam, Timbuktu region | Conseils - Etudes - Recherches - Techniques - Engineering – Services (CERTES Sarl) | N/A |  | N/A | 6886.5741 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Aigle Structure Technique (ASTEC Sarl ) | Aigle Structure Technique (ASTEC Sarl ) |  | 11078.0423
| Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | 01-04/11/2016 | 10276.1243
Consulting service for the evaluation and dimensioning of the gardening perimeter of Goundam women in the urban district of Goundam, Timbuktu region | Conseils - Etudes - Recherches - Techniques - Engineering – Services (CERTES Sarl) | N/A |  | N/A | 10276 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Aigle Structure Technique (ASTEC Sarl ) | Aigle Structure Technique (ASTEC Sarl ) |  | 11078.0423
| Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | 01-04/11/2016 | 11102.8439
Consulting service for the evaluation and dimenssionnement of the development of two juxtaposed perimeters areas for the women of Toya in in the rural disrict of Alafia, Timbuktu region | Conseils - Etudes - Recherches - Techniques - Engineering – Services (CERTES Sarl) | N/A |  | N/A | 11102.8439 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Aigle Structure Technique (ASTEC Sarl ) | Aigle Structure Technique (ASTEC Sarl ) |  | 11243.3862
| Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | 01-04/11/2016 | 11102.8439
Consulting service for the evaluation and dimenssionnement for the rehabilitation of the intercollectivity pond Fare-Fare in the rural disrict of Alafia, Timbuktu region | Conseils - Etudes - Recherches - Techniques - Engineering – Services (CERTES Sarl) | N/A |  | N/A | 11102.8439 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Aigle Structure Technique (ASTEC Sarl ) | Aigle Structure Technique (ASTEC Sarl ) |  | 11243.3862
| Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | Bureau d’Etudes, d’Ingénierie, de Recherche, d’Assistance et de Formation (BEIRAF Sarl), | 01-04/11/2016 | 9862.7646
Consulting service for the technical, socio-economic and environmental studies of the excavation of "bras deFatty" on 7 km in Tindirma, rural districtf Tindirma, Timbuktu region. | Conseils - Etudes - Recherches - Techniques - Engineering – Services (CERTES Sarl) | N/A |  | N/A | 9862.7646 | Cheapest offer of offices selected on the basis of their experience. These offices are all in Timbuktu
| Aigle Structure Technique (ASTEC Sarl ) | Conseils - Etudes - Recherches - Techniques - Engineering – Services (CERTES Sarl) |  | 11078.0423
Memorandum of Understanding (MoU) for the training of 159 tree nurses in 8 communes in Mopti | DREF-Mopti | DREF-Mopti | 2017-02-27 | 8266.584 | 8266.584 | DREF-Mopti is a State structure specialized in Environment and represented in all the communes of the Mopti Region. It also hosts the project Focal Point in Environment for Mopti.
Formulas:
Open date = [Open date, row above]

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Armed conflict that has recently escalated and engulfed the Northern region of Mali | High | Macina area, in the Niger Central Delta, as well as the communes of Gargando, Bintagoungou, Essakane, Hanzakoma and Haribomo in Timbuctu region are always under the threat of bandits and rebels. Usually, meetings with commune representatives are held in regional or district headquarters and therefore do not require travels of the project team to risky areas such as in the Niger Central Delta, Mopti and Timbuctu communes. This strategy was suggested by the regional officials to ensure that the objective of the project can be reached in spite of the situation. Mali Armed Forces -MINUSMA mixed patrols are operating throughout the project area. The project has developed a partnership with OMVF for the realization of the backgroud situation. This partnership will continue for the installation of the investments, namely digging the canals and chenals in the Faguibine communes. This structure already has the necessary staff and material in the sites and can operate with support from MINUSMA which provide aerial transportation by Helicopter when needed. It should be noted that the Faguibine system is key to the agricultural sector in the region and is at the center of the objective of the project. Therefore in spite of the challenges to operate in the region it was decided that a change in the project sites would prevent the project from achieving its objective and alternative sustainable mitigative solutions were implemented as described above. Besides, the presence of OMVF in the region beyond the project lifetime will increase the sustainability of the activities by maintaining a presence and monitoring structure in the area. In particular as the objective of the project is largely aligned with the objectif of the OMVF.
Delays in project inception impacts the achievment of the outputs and outcomes and reduces the scope to deliver the project as outlined in proposal | Medium | This first year has been successfully used to start the project and conduct a large number of technical, socio-econimical and environmental studies for the investments to be realized in 2017. The initiation workshop of the project in March 2016 allowed the validation of the 2016 PTBA and the setting up of the national Steering Committee that is the decision making body, constituted of 11 State structures and the Region Governors.
A poor collaboration between programme partners | Low | Since the initiation workshop, national and regional level partners have been actively involved in the implementation of the activities. At the project launch, the roles and responsibilities have been clarified for each of the various actors involved in the implementation of the Programme activities. An AEDD -PACV-MT and Direction de la Coopération Multilatérale joint mission was organized in Mopti and Timbuctu Regions to meet the administrative and communal authorities and explain everybody's responsibility for the implementation of the project
A poor understanding of the objectives by the programme team | Low | The activities are planned and executed in time and within the budgets. The project Team is constituted of specialists that perfectly understand the project objectives
Low mobilization of the target group caused by a poor understanding of climate change issues | Low | Elected commune officials and target beneficiaries are fully committed to the implementation of the activities. Eligible investments for the project funds have been identified in each commune with the full implication of the elected officers, the communities and decentralized technical services.
Lack of sufficiently qualified partners | Medium | The understanding of climate change of the communal elected officers and producers still remains low. Within capacity building activities, 60 producers have been trained in agroforestry techniques.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The long national procurement procedure applied to investments delays the project implementation | High | Delays in signing MoUs by the Direction Générale des Marchés Publics are likely to delay the implementation of the investments. Therefore, a procurement unit has been created in the Ministry since Februay 2017 to reduce the delay in processing MoUs. The project Steering Committee has sought project support for the creation and the functioning of this unit in conformity with the 2015 Decree. This was supposed to reduce the delay in processing and raise the disbursement at rate.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The project catchment area has observed respite but sporadic armed bandit attaks still threaten some communes. However, the project team has developed collaborative stragtegies with different local partners (OMVF, MINUSMA, PAM, Local Authorities) to facilitate its operation in targeted communes. Throughout 2016, three meetings were held by PACV-MT and OMVF in view of a synergy of action in Timbuctu in the near future. During the first meeting the project document and studies undertaken by OMVF on canals in the Faguibine System were exchanged. During the second meeting an MoU was signed for the useful collection of data for the identification of the project indicators to prepare the baseline studies in the 11 communes. The third meeting was a joint mission of the two structures in Timbuctu to identify, with the Mayors and the the General Secretaries of the 11 communes, under the chairmanship of the Governor's Representative, the canals to be rehabilitated by OMVF. In that scope, the national Steering Committee meeting of November 2016 also recommended the organization of another meeting in Timbuctu to reach a concensus with all the stakeholders involved in the implementation of the project. That meeting is foreseen for April 2017. PACV-MT also sought a meeting with WFP in 2016 to discuss possible synergies. That meeting will be held on April 11th, 2017. Thanks to MINUSMA, the project Team is always informed about the evolution of the security situation in the targeted 20 communes to better secure travels. For each missions, the Governors inform the project Team on zones to avoid. Furthermore, the Coopération Multilatérale and Coordinators meeting strongly recommended the facilitation of disbursement procedures for UNDP sponsored projects under MEADD/AEDD. Relevant reports of those meetings are available.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones | Expected Progress | Progress to Date | Rating
Project Management Unit | Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 20 km silted channels and obstructed ponds | Conduct 33 studies and realize 11 investments in Timbuctu. | 18 studies have been carried for 6 communes in Timbuctu. Results have been delivered to the technical services. No investments. | Moderately Unsatisfactory
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems | Realize the project baseline studies in the 20 communes. Conduct 27 studies and realize 9 investments in Mopti. | The project baseline studies in 20 communes is realized. 27 studies are réalize. No investment. | Satisfactory
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities |  |  | -
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change | Train 180 producers on agroforestry practices adapted to Climate Changement. Installing and managing communal nurseries. | 60 producers trained on agroforestry practices adapted to climate change. Identification of 3.2 ha for tree nursery in 8 communes and 159 tree nurses ('pépiniérists') to be trained. | Moderately Unsatisfactory
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities |  |  | -
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) | Up date 20 economic, social and cultural development plans (ESCDP) | No plan realized | Highly Unsatisfactory
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) | Create a Website and provide informatin to feed it | Website realized and information provided. | Highly Unsatisfactory
| Output 3.3 Local institutional capacity strengthened in 20 communities in establishing micro-credit schemes, cereal banks etc. and in managing |  |  | -
| Project Management Costs | Hold the launching workshop.Organize and hold the first session of the national steering committee 2016. | The project was launched on March 04th, 2016. The steering committee met on Novembre 24th, 2016. | Highly Satisfactory
|  |  | Overall Rating | Unsatisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Boubacar Sidiki Dembélé
| Email: | boubacarsdembele@gmail.com
Despite the delay in starting the project and the persistant insecurity in the field, most of the planned activities have been realized satisfactorily (beyond 50%). Nevertheless, these activities have been achieved in only 15 communes (9 in Mopti and 6 in Timbuctu) over a total of 20 communes. Regarding the outcome 2, the project focused especially on the identification of technologies adapted to climate change, including adapted seeds and resilient species of livestock, poultry and fish, to be granted to farmers by May 2017 to prepare the next crop campaign for the agricultural year 2017 - 2018. Moreover, the sites for women's market gardening in 15 Communes have been identified and sized. Activities during the first year of the programme are prerequisites for the investment work in 2017, such as the rehabilitation and opening up of channels, the introduction of market gardens, the realization of basic water supply infrastructures and the deepening of ponds. Regarding the third outcome on capacity building and lessons learned capitalization, the programme was able to achieve the training of 60 producers on agroforestry practices adaptated to climate change. For the other 5 areas with high insecurity, the programme intends to develop synergies with local partners in the Timbuctu Region including the OMVF, WFP, NGOs and some engineering offices.
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Implementing Agency | Progress on Key Milestones | Expected Progress | Progress to Date | Rating
| Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 20 km silted channels and obstructed ponds | Conduct 33 studies and realize 11 investments in Timbuctu. | 18 studies have been carried for 6 communes in Timbuctu. Results have been delivered to the technical services. No investments. | Moderately Unsatisfactory
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems | Realize the project baseline studies in the 20 communes. Conduct 27 studies and realize 9 investments in Mopti. | The project baseline studies in 20 communes were realized. 27 studies are realized. No investment. | Satisfactory
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities |  |  | -
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change | Train 180 producers on agroforestry practices adapted to Climate Changement. Installing and managing communal nurseries. | 60 producers trained on agroforestry practices adapted to climate change. Identification of 3.2 ha for tree nursery in 8 communes and 159 tree nurses ('pépiniérists') to be trained. | Moderately Unsatisfactory
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities |  |  | -
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) | Up date 20 economic, social and cultural development plans (ESCDP) | No plan realized | Highly Unsatisfactory
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) | Create a Website and provide informatin to feed it | Website realized and information provided. | Highly Satisfactory
| Output 3.3 Local institutional capacity strengthened in 20 communities in establishing micro-credit schemes, cereal banks etc. and in managing |  |  | -
| Project Management Costs | Hold the launching workshop.Organize and hold the first session of the national steering committee 2016. | The project was launched on March 04th, 2016. The steering committee met on Novembre 24th, 2016. | Highly Satisfactory
|  |  | Overall Rating | Unsatisfactory
| Implementing Entity | United Nations Development Programme (UNDP)
| Name: | Abdoulaye BAYOKO
| Email: | abdoulaye.bayoko@undp.org
Executing Agency | Progress on Key Milestones | Expected Progress | Progress to Date | Rating
| Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 20 km silted channels and obstructed ponds | Conduct 33 studies and realize 11 investments in Timbuctu. | 18 studies have been carried for 6 communes in Timbuctu. Results have been delivered to the technical services. No investments. | Moderately Unsatisfactory
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems | Realize the project baseline studies in the 20 communes. Conduct 27 studies and realize 9 investments in Mopti. | The project baseline studies in 20 communes is realized. 27 studies are réalize. No investment. | Satisfactory
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities |  |  | -
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change | Train 180 producers on agroforestry practices adapted to Climate Changement. Installing and managing communal nurseries. | 60 producers trained on agroforestry practices adapted to climate change. Identification of 3.2 ha for tree nursery in 8 communes and 159 tree nurses ('pépiniérists') to be trained. | Moderately Unsatisfactory
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities |  |  | -
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) | Up date 20 economic, social and cultural development plans (ESCDP) | No plan realized | Highly Unsatisfactory
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) | Create a Website and provide informatin to feed it | Website realized and information provided. | Highly Satisfactory
| Output 3.3 Local institutional capacity strengthened in 20 communities in establishing micro-credit schemes, cereal banks etc. and in managing |  |  | -
| Project Management Costs | Hold the launching workshop.Organize and hold the first session of the national steering committee 2016. | The project was launched on March 04th, 2016. The steering committee met on Novembre 24th, 2016. | Highly Satisfactory
|  |  | Overall Rating | Unsatisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Executing Agency | Environment and Sustainable Development Agency (AEDD)
| Name: | Boureima CAMARA
| Email: | bouricamara@gmail.com, Tel: +22366805756
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words | For all the activities, progress has been observed in spite of the important security challenges faced in the regions of the project. The insecurity in some communes, especially Togoro-kotia in Mopti Region, Haribomo, Hanzakoma, Essakane, Bintagoungou and Gargando in Timbuctu Region did not enable the realization of the technical, socio-economical and environmental studies of the investments. For the monitoring, after the realization of the baseline studies in the 20 target communes, the project put the emphasis on checking the quality of the studies and its alignment with the Signing Agreement procedures. Various reports on activity achievements indicators and financial audit reports are available.
|  | Highly Satisfactory (HS) | Activities with a realization rate higher than 75%
|  | Satisfactory (S) | Actvities with a realization rate between 60% and 75%
|  | Marginally Satisfactory (MS) | Actvities with a realization rate between 50% and 60%
|  | Marginally Unsatisfactory (MU) | Actvities with a realization rate between 30% and 50%
|  | Unsatisfactory (U) | Actvities with a realization rate between 20% and 30%
|  | Highly Unsatisfactory (U) | Actvities with a realization rate under 20%
Note on E33: TELLY: No activity has been for seen for this reporting period

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Indicators towards Outcome 1 | % increase in functional waterways and channels in the targeted communes | Only about 15% of the waterways and channels are functional | 8 channels studied and one enterprise selected for the realization of 2 channels in Mopti Region | Functional waterways and channels increased by about 40 %
| Km increase of cleared water channel | Currently about 50 km of the water channels are cleared | 10.39 kms channel studied and field works to start by mid- April 2017 | 100 km increase of cleared water channel
Indicators towards Outcome 2 | Number of dry season market gardens managed by women, and community fish farms established | There are presently few market gardens and no community fish farms | 14 market gardens covering 28 ha have been studied and the installation of 16 ha will start by mid-April 2017. | At least 100 dry season gardening schemes for women, and 20 community fish farms established
| Number of tree nurseries of local tree species established in each local communities | Few communities benefit from community managed tree nurseries | 8 communal and central nursery sites have been identified to be prepared in May 2017 and 159 nurses were identified to benefit from the training by "Direction Régionale des Eaux et Forêts, Mopti". After the training, each nursery will benefit from a watering can and 200 pots to start the production of plants | At least 100 community nurseries (5 per community) established
Indicators towards Outcome 3 | Number of local official trained in institutional management of climate change | There are currently no local councilors trained to enhance their institutional capacity to adapt to climate change | In November 2016, communal elections resulted in the replacement of some communal councilors. The project is planning to train the new leader teams in May 2017 on the formulation of new PDESC. | 100 local councilors from 20 councils are trained in institutional management of climate change
| Number of PDESC revised in including climate change management | Just about 6 PDESC currently include climate change management | After the training of the elected officials, the project is planning to support PDESC revision and development as from third term 2017. | 20 local community plans will be developed to include climate change management

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Insecurity, characterized by high risk of agression, killing and kidnaping, limited or prevented the project team movements in some communes of Mopti and Timbuctu. The project has been assisted by MINUSMA in supplying useful information on security situation in the target communes for each mission in the field. In such a situation, local auhorities should provide assistance, especially the elected officials to secure the movements of various actors and to relay useful infomation for the planning and implementation of the activities.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | YES a delay has been noticed. The main causes identified are: (i) the delay in quaterly disbursements due to the UNDP processing procedures and the slow and cumbersome refunding requests treatment and cheques issuance with AEDD; (ii) the systematic delay in signing protocol agreement with "Direction Générale des Marchés Publics de l'Etat"; (iii) uncertain security situation in some communes in the Programme catchment area Corrective measues were undertaken: a) the meeting of the project coordinator with UNDP and MEADD; b) synergy with OMVF in Timbuctu for the overdigging of channels, c) collaboration with MINUSMA and Local Authorities for the travels of the project team in the field.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | For more clarity and accuracy, the project is seeking the reformulation of the target "Double the renewable water resources in the regions" to "Functional waterways and channels increased by about 40 %" and indicator 1 "Functional waterways and channels increased by about 40 %" replaced as "% increase in functional waterways and channels in the targeted communes". The same, for indicator 2, replaced by "Km increase of cleared water channel" to be in line with the target set in the project document.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Gender consideration started with the identification of activities that could be managed by women, especially market gardening, processing and storage of vegetables; Cultivar Seed and livestock spieces selection. The impacts will be visible from 2017, after the infrastructures and other investments have been made
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 81072 (PIMS 4789)
Implementing Entity | PNUD
Type of implementing entity | MIE
Country | Mali
Region | Africa
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion Performance de la cible à la fin |  |  |  | Performance at mid-term |  |  |  | Performance at completion Performance à la fin
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 |  | 0 | Total | 213758 | 23949 | 189809 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% |  | 0% | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% |  | 0% | % of Youth beneficiaries | 49% | 49% | 49% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
0
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 10% | Private |  | 400 | 10% | Private
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Disaster risk reduction | 2: Low capacity | Public | Local | Disaster risk reduction | 4: High capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  |  |  | 30%
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0% | 0% | 1: Aware of neither |  | 3000 | 50% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Water management | 40 | Community |  | Water management
|  | 0 | Community |  | Agriculture | 60 | Community |  | Agriculture
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Résultat | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 2: Limited improvement |  | 3000 | 50% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  |  | 2000
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agribusiness |  |  | 500
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Forestry |  |  | 300
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Fishing |  |  | 200
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.