## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | May 2018 to April 2019
| Project Title: | Increased Resilience to Climate Change in Northern Ghana through the management of water resources and diversification of livelihoods
| Project Summary: | The project aims at addressing climate change-induced decreases in the availability and increasing unpredictability of water resources, and the associated negative impacts of these trends on the livelihoods of rural communities. It is expected to enhance the resilience and adaptive capacity of rural livelihoods to climate impacts and risks on water resources in Northern Ghana. The objective of the project will be achieved through key results centered on the improvement of water access and increased institutional capacity as well as coordination for integrated water management to support other uses of water resources especially for the diversification of livelihoods by rural communities. This will be done by delivering the following three complementary outcomes: • Outcome 1: Improved planning and management of water resources taking into account climate change impacts on surface and groundwater sources • Outcome 2: Climate resilient management of water resources by communities in Northern Ghana • Outcome 3: Enhanced diversification of livelihoods of communities in northern Ghana
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Ghana | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | The programme targets the three regions in the northern part of Ghana, namely the Upper East, Upper West and Northern Regions (collectively referred to as the “northern regions”). Compared to other regions of the country, these three northern regions have a high degree of exposure to climate variability and change characterized by increasing temperatures and decreasing and erratic rainfall, which are classified by the government of Ghana as highly vulnerable to climate change and high priority regions for climate change adaptation when coupled with low socio-economic development. 10 Districts and 50 communities are benefiting from the Adaptation Fund Project in Ghana. Northern Region • Savelugu-Nanton District- The beneficiary communities are: Nagdigu-Tampion, Kukobila-Tamaligu, Libga-Zaazi-Nyoglo-Bihinaayili and Zieng communities; • Zabzugu District- The beneficiary communities are: Sabare No. 1, Sabare No. 2, Mognegu No.1, Mognegu No. 2 and Kolikolini Savannah Region • Bole District- The beneficiary communities are: Sonyor, Kiape, Chache-Bhemshi-Cheribawale-Ntreso, Jama & Kurupe-Zampe Upper East Region • Bongo District- The beneficiary communities are: Kunkua, Yidongo, Dua, Aliba & Adaboya • Builsa South District- The beneficiary communities are: Kanjarga Nyandem, Gbedema- Kunkual, Kasiesa, Weisi & Gbedembilisi • Bawku West District: The beneficiary communities are: Tilli Azupunpuga, Timonde, Farik, Dagunga & Laboya; • Bawku Municipal – The beneficiary communities are: Kpalwege, Jentiga 1&2, Kuka, Tempezua & Tambalgo Upper West Region: • Sissala East District- The beneficiary communities are: Tumu, Wallembelle, Bugubelle, Kong & Tarso/kulfuo; • Nadowli District- The beneficiary communities are: Zukpiiri, Goli, Takpo, Nanvilli & Jang communities; • Nandom District: The beneficiary communities are: Ko-Bukom, Nabugaugn, Zogpielle-Guri-Bechinteng-Ketuo, Dabagteng-Naapaal &Gengenkpe-Venne-Sonne | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date:
IE-AFB Agreement Signature Date: |  | 2015-03-31 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2016-05-01 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2018-10-01
| Terminal Evaluation Date: | 2020-01-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | 1. Inception Reports/Documents • ¬¬Project launch and Inception report • Social and Environmental Screening Report • Programme Implementation Manual • Monitoring and Evaluation Plan/Framework • Stakeholder Consultation and community entry reports 2. Technical Documents/Reports • Report on Trend/historical analysis of the impact of climate variability on the White, Black and Oti River basins • Report on climate change projections for the White and Black Volta and the Oti River basins • Report on Vulnerability analysis of communities along the White and Black Volta as well as the Oti River Basins • Report on management and investment plans for Black Volta and Oti River basins • Report on assessment of existing water resources and vulnerabilities in the project sites • Hydrological monitoring report for 100 Boreholes drilled under the project • Report on the formation of River Basin boards • Strategic Environmental Assessment workshop reports • Midterm Evaluation Report • Management Response to the Midterm Findings 3. Success stories and Media Publications • Project news article (http://www.ghananewsagency.org/science/northern-regions-urged-to-embrace-climate-adaptation-fund-project-11325) • articles:http://www.ghanaweb.com/GhanaHomePage/regional/Climate-change-adaptation-project-launched-441640 • http://www.gh.undp.org/content/ghana/en/home/presscenter/articles/2016/05/25/undp-supports-initiative-to-protect-water-bodies-in-northern-ghana/ • Increasing water supplies in rural Ghana http://www.gh.undp.org/content/ghana/en/home/presscenter/articles/2019/increasing-water-supplies-in-rural-ghana/ • Strengthening Resilience of Rural Women through Dry Season Farming in Ghana http://www.gh.undp.org/content/ghana/en/home/presscenter/articles/2019/strengthening-resilience-of-rural-women-through-dry-season-farmi.html • Trees for water protection http://www.gh.undp.org/content/ghana/en/home/presscenter/articles/2018/tampion_dam.html http://www.peacefmonline.com/pages/local/news/201811/368818.php • Stakeholders' engagement workshop to develop an Integrated Water Resource Management (IWRM) Plan • https://www.modernghana.com/news/872320/water-resource-commission-organises-workshop-on-oti-basin.html • Formation of sub-river basin committees | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://adaptationfundghana.org/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Mr. Peter Dery | Dominican Republic
| Email: | peterdery@yahoo.com | Ecuador
| Date: | 2019-05-01 | Egypt
| Government DA |  | El Salvador
| Name: | Levina Owusu | Equatoral Guinea
| Email: | info@mesti.gov.gh | Eritrea
| Date: | 2019-05-01 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | United Nations Development Programme | Fiji
| Email: | Assistant Country Director, louis.kuukpen@undp.org, Programme Analyst, stephen.kansuk@undp.org | Finland
| Date: | 2019-05-01 | France
| Executing Agency |  | Gambia
| Name: | MINISTRY OF ENVIRONMENT, SCIENCE, TECHNOLOGY AND INNOVATION OF GHANA | Georgia
| Email: |  | Germany
| Date: | 2017-05-01 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: Cumulative from Project start to [APRIL 2019]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [APRIL 2019] | 3134411.96
Add any comments on AF Grant Funds. (word limit=200) | It is acknowledge that the rate of disbursement of the AF funds is slower than expected. As noted in the risks log, at the time of submitting the PPR for the 3yr, the project experienced delays in the release of the second tranche of the project funds from Adaptation fund Secretariat. The delays affected the implementation of key activities. The UNDP Ghana CO initially pre-financed some activities to keep the project running, but only to a limited extent. This slowed down the implementation of activities, and thus the disbursement of AF grant resources. For example: Project consultants working on community water management and investment plans could not finalize their reports and embark on community consultations. Also, the drilling of the boreholes was delayed, and some other activities planned for that very year were postponed to the third year. Equally, tree planting activities in the target regions could only take place in June/July due to the delays in the release of funds. Cumulatively, this slowed down financial delivery. However, at the time of providing these comments the project delivery had increased to about 70%.
INVESTMENT INCOME | No investment income has been generated by the project.
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1: Climate change historical data and future projections generated for the White Volta, Black Volta and Oti basins | 0
| Output 1.2White Volta management and investment plans comprehensively reviewed to take into account climate change impacts | 11337
| Output 1.3: Climate smart water management plans designed for the Black Volta and the Oti River basins | 0
| Output 1.4 National, Regional, District and Community based Climate Change Adaptation Monitoring Committee established/adopted and strengthened (as envisioned by the National Climate Change Adaptation Strategy) in the three target regions | 11360.75
| Output 2.1 Climate responsive community water supply and management plans designed for 10 districts in northern Ghana | 10000
| Output 2.2 Climate smart community based water supply systems provided for multiple uses and users in 30 communities in northern Ghana | 447556.61
| Output 2.3Small scale irrigation systems installed in 30 communities and water users associations to manage irrigation systems established and/or strengthened to improve efficiency and effectiveness of water usage under conditions of climate-induced water pressures | 12013.14
| Output 2.4 Measures for water conservation under climate impacts implemented in 25 communities | 267988.63
| Output 2.5 Learning platforms on systems for integrating CC-related risks into community management of water resources and livelihood activities in northern Ghana institutionalized in 10 districts | 34919.3
| Output 3.1 Improved infrastructure for water distribution for CCA and agricultural use installed in 10 districts | 265109.97
| Output 3.2 Livelihoods diversification for improved adaptation to climate change in 50 communities. | 300000
| Output 3.3 Community tree nurseries and wood lots established for climate risk management in 40 communities. | 100000
| Output 3.4 Fish farms are established and supported in 20 communities | 96490.11
| Output 3.5 Best practices for adaptation and lessons learned from the implemented actions and related policy processes are recorded and disseminated to all 38 districts in northern Ghana through appropriate mechanisms | 61989.45
| Output 4.1 Programme Management Unit Established and Operational( Programme Execution cost) | 94541.66
| TOTAL | 1713306.62
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1: Climate change historical data and future projections generated for the White Volta, Black Volta and Oti basins | 0
| Output 1.2White Volta management and investment plans comprehensively reviewed to take into account climate change impacts | 0
| Output 1.3 Climate smart water management plans designed for the Black Volta and the Oti River basins | 75000 | Mar, 2020
| Output 1.4 National, Regional, District and Community based Climate Change Adaptation Monitoring Committee established/adopted and strengthened (as envisioned by the National Climate Change Adaptation Strategy) in the three target regions | 20000 | Dec, 2019
| Output 2.1 Climate responsive community water supply and management plans designed for 10 districts in northern Ghana | 342209.04 | Dec, 2019
| Output 2.2 Climate smart community based water supply systems provided for multiple uses and users in 30 communities in northern Ghana | 2310000 | Mar, 2020
| Output 2.3Small scale irrigation systems installed in 30 communities and water users associations to manage irrigation systems established and/or strengthened to improve efficiency and effectiveness of water usage under conditions of climate-induced water pressures | 500000 | May, 2020
| Output 2.4 Measures for water conservation under climate impacts implemented in 25 communities | 25000 | Mar, 2020
| Output 2.5 Learning platforms on systems for integrating CC-related risks into community management of water resources and livelihood activities in northern Ghana institutionalized in 10 districts | 200000 | Mar, 2020
| Output 3.1: Improved infrastructure for water distribution for CCA and agricultural use installed in 10 districts | 0
| Output 3.2 Livelihoods diversification for improved adaptation to climate change in 50 communities. | 620000 | May, 2020
| Output 3.3 Community tree nurseries and wood lots established for climate risk management in 40 communities. | 20000 | Mar, 2020
| Output 3.4 Fish farms are established and supported in 20 communities | 60000 | Mar, 2020
| Output 3.5 Best practices for adaptation and lessons learned from the implemented actions and related policy processes are recorded and disseminated to all 38 districts in northern Ghana through appropriate mechanisms | 60000 | Mar, 2020
| Output 4.1 Programme Management Unit Established and Operational( Programme Execution cost) | 277594 | Mar, 2020
| Total | 4509803.04
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | 250000 | The government as part of the co-financing support has absorbed the staff cost of the critical staff for the entire duration of the project. As at this reporting period, a total of USD 250,000 has been contributed by the government towards the payment of salaries of the project coordinator, Project Technical Advisor and Driver. The USD 250,000 is inclusive of USD 50,000 of office rent for the project staff for the entire duration of the project)
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESSMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Delays in programme inception impact on achieving outputs and outcomes and reduce scope to deliver programme as outlined in proposal | This is no longer a risk to the project. The measures and steps implemente over the last three years of the proejct have helped in addressing this risk (degree:Low) | Following the project inception workshop, a detailed inception work plan was developed and guided the inception phase. This allowed the project to reach out to key stakeholders and beneficiaries and get their buy-in, conduct community entry and get baseline data, as well as developing a Project Implementation Manual to define implementation details.
Insecurity in the area – terrorist attacks or regular banditry – may jeopardize the implementation and follow-up of the programme | Due to the measures and steps taken to mitigate this risk, the risk level has been reduced from Medium low as of the third year of the project ( Degree: Low) | The programme has taken this into account through various measures such as - strong cooperation with local communities and structures - a good cooperation with local organizations for the programme implementation - using UN security alert system distance follow-up and reporting tool
A poor understanding of the objectives by the programme team | The project beneficiaries and key stakeholders have a better understanding of the project as of date. This is no longer a risk to the project.(Degree: Low) | - The project has been mainstreamed into the activities of key national stakeholder - A strong involvement of leaders, particularly in implementing agencies and key stakeholders has been ensured - The project conducted training for the District Adaptation Committees to build the capacity and enhancing the work of members of the DAC in implementing their roles under the AF project. This allowed the project to: 1. Create public awareness and strengthen capacity of the DACs on the long-term National Climate Actions of Ghana; 2. Support the implementation of the Community Entry programme of the AF Project; 3. Obtain first-hand insight from DACs on the best approach to proceed with key AF project activities; and 4. Introduce the DACs members to new members of the AF project team
Low mobilization of the target group caused by a poor understanding of climate change issues | Due to the number of stakeholder engagement and advocacy works done over the last years, project targeted areas now have a better understanding of climate change issues and the impact that it has on water resources management. This is no longer a risk to the proejct ( Degree: low) | The project is relying on the District Adaptation Committees, and will continue to build their capacity, in order to ensure a better understanding of climate change at district and community level.
Lack of capacity to meet financial, and in particular resource commitments by partners in programme implementation | Medium |  A continuous dialogue before and after the signing of the programme document has been established among programme partners  Sufficient allocation within the detailed proposal and implementation arrangements made to developing teams with sufficient capacity (both in terms of size and technical abilities), which are sufficiently embedded into implementing agencies  Setting realistic targets for partner contributions
Lack of sufficiently qualified partners | This is no longer a risk to the project as competent and qualified personnels have been leading the implementation of the proejct activities>( Degree:Low) | - The Implementing Partner designated a Project Coordinator and a Technical Advisor, and additional staff were recruited to provide technical, M&E and administrative support. - National consultants have been recruited through a competitive process to undertake technical work and transfer their knowledge/expertise to project partners - The Implementing Partner is collaborating with other partners having specialized expertise (e.. Water Resources Commission for Component 1)
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Resistance by farmers whose farm area were selected to be used as buffer zones for rivers and dams | This is no longer a risk to the project. Regular field monitoring and engagement of key stakeholders including traditional leaders, high-level government officials at both the local and national levels was critically in addressing this risk. Initially, key stakeholders like the chiefs and landowners were not willing and ready to release their lands closer to the major water bodies for the creation of the buffer zones. However due to regular engagement with the key stakeholders including the traditional leaders this issue was resolved. This led to the creation of 15 Buffer around the water bodies. Indeed over 18, 000 tree seedlings have been planted in 15 communities (37.1 acres) as a result of the closer collaboration with the project key stakeholders at the local levels. It is expected that the trees planted will among others reduce siltation in the watershed. (Degree: Low) | Affected farmers were sensitised and ropped in the tree planiting activities in order to ensure ownership of trees by the farmers. Additionally, the agro forestry planting method is being adopted for the buffer zone. Under this arrangement, crops planted by farmers are inter-cropped with trees so that they have an immediate benefit from crops while benefits from trees come later.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The major risk encountered in year 3 was the possible delay in implementing planned activities due to the late release of the project resources by the Adaptation Fund Board. UNDP country office advanced some resources to the project to minimise this risk. Given this challenge, it is expected that implementation of all project activities especially the rehabilitation of the dams will most likelyNOT to be fully achieved by the end of the project in April 2020. In the circumstances, the project will most likely request for no cost extension until December 2020.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1] | At the time of project development and Board Decision, there were no ESP requirements identified or triggered. | n/a | n/a
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law
2 - Access and equity | [8 empty] | Not applicable
3 – Marginalized and vulnerable Groups | [8 empty] | Not applicable
4 – Human rights | [8 empty] | Not applicable
5 – Gender equality and women’s empowerment | [8 empty] | Not applicable
6 – Core labour rights | [8 empty] | Not applicable
7 – Indigenous peoples | [8 empty] | Not applicable
8 – Involuntary resettlement | [8 empty] | Not applicable
9 – Protection of natural habitats | [8 empty] | Not applicable
10 – Conservation of biological diversity | [8 empty] | Not applicable
11 – Climate change | [8 empty] | Not applicable
12 – Pollution prevention and resource efficiency | [8 empty] | Not applicable
13 – Public health | [8 empty] | Not applicable
14 – Physical and cultural heritage | [8 empty] | Not applicable
15 – Lands and soil conservation | [8 empty] | Not applicable
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Yes
Have unanticipated ESP risks been identified during the reporting period? |  | None
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | The Social and Environmental Screening report that was prepared for the project at the beginning continued to be used to guide implementation of the project activities.
Have the implementation arrangements been effective during the reporting period? |  | Yes
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | Project Implementation Manual, which was developed earlier in the project, and which mandated the Environmental Protection Agency of Ghana to provide guidance and undertake periodic field visits to ensure that all project activities are implemented in line with the Social and Environmental Screening report developed by the Implementing Entity at the inception of the project, continued to be used during the reporting period.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievancee were received during the reporting period
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | yes
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | yes
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Climate resilient management of water resources by 50 communities in northern Ghana | Climate smart community based water supply systems provided for multiple uses and users in 30 communities in northern Ghana | Number of operational boreholes, dugouts/dams and rainwater harvesting systems | Communities have limited infrastructure in place for supply and storage of water | 100 operational boreholes, benefitting at least 30,000 people (50% of whom should be women) Rainwater harvesting systems in place, providing water supplies to 50 community facilities | Good
Enhanced diversification of livelihoods by 50 communities in northern Ghana | Livelihoods diversification for improved adaptation to climate change in 50 communities. | Number of dry season gardening schemes for women established | Few communities benefit from effective dry season gardening | 50 dry season gardening schemes for women established, directly benefitting at least 1,000 women | Good
Enhanced diversification of livelihoods by 50 communities in northern Ghana | Livelihoods diversification for improved adaptation to climate change in 50 communities. | Number of women led agricultural product processing schemes established | Few communities benefit from agricultural product processing | 40 community level women led agricultural product (shea butter or honey) processing schemes established, directly benefitting at least 1,200 women | Good
Enhanced diversification of livelihoods by 50 communities in northern Ghana | Livelihoods diversification for improved adaptation to climate change in 50 communities. | Number of operational community scale irrigation systems installed | Very few communities have effective irrigation systems in place | 50 operational irrigation systems, benefitting at least 2,500 farmers | Good
Enhanced diversification of livelihoods by 50 communities in northern Ghana | Fish farms are established and supported in 20 communities | Number of operational community fish farms established | Few communities benefit from community fish farms | 20 community fish farms established, benefitting at least 10,000 people(50% of whom should be women) | Good
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
Selection of project beneficiaries: The Programme continuous to ensure that gender sensitive considerations are fully mainstreamed in the implementation of project activities especially those interventions relating to diversification of livelihoods. Recognizing that the dominance of men over women in the Programme locations, in terms of ownership of land, access to and control of resources, and in decision making, there was conscious and deliberate efforts to ensure that 60% of the entire project beneficiaries for each of the livelihoods activities such as bee keeping, agro processing schemes, dry season farming among others were women. For example, one of the project targets was to ensure that 40 community level women led agricultural product (shea butter or honey) processing schemes established, directly benefitting at least 1,200 women achieve. In meeting this target, the Programme engaged community-based NGOs to establish twenty-two (22) shea Butter processing schemes and thirty-five (35) honey production value-chain initiatives directly benefiting 1,260 and 1,348 people respectively. Over 60% of these direct beneficiaries are women. Due to the inclusion of women, there is wide spread upscale of the project activities in the Programme areas. The fast-track self- helped upscaling of project activities by the women using innovative practices demonstrate that women are not only those who are adversely impacted by climate change, but it also demonstrates the role of women as change agents in adapting to climate change impacts. The human-interest stories emanating from the Programme sites further buttress the role of women in addressing climate change impacts. For example, Madam Agabeni one of the project beneficiaries in the Bongo indicated that “In Yindongo, we have a 24-acre dry season garden and we are about 100 women benefiting from the initiative. Every 3 days is market day here, so we sell the vegetables and also consume some”. These small-scale activities provide a boost to business growth and development among the women population in the proejct and will potentially increase the household imcome of the project beneficiaries by 30% at the end of the project duration. |  |  |  | Good
Designing of interventions and stakeholder engagement The project sites remain dependent on food crop farming with very little opportunity for non-farm activities. The share of household income derived from non-farm activities remains significantly lower than the rest of the country. For seven to eight months in the year, the majority of the agricultural population in the project sites has no alternative or complementary means of securing their livelihoods, as infrastructure (small irrigation system, water reservoirs) to support off-season agricultural activities are underdeveloped or non-existent. To address this challenge, the project during the reporting period supported the rehabilitation of gender sensitive dams and other water supply systems. This is seen as a critical infrastructure to support the resilience of women who are mostly impacted adversely by climate change. With rehabilitation of the dams and dugouts, as part of the engagement process with contractors and vendors, an established criterion was developed to ensure that successful vendors took into consideration issues of gender and social inclusion in the construction and in the recruitment of local artisans in the construction of the water supply systems. During the reporting period, workshops and meetings were organized in a manner that fully captured issues that may increase the vulnerability of different groups in the communities such a gender and youths. The workshops brought together all key stakeholders, including organizations that particularly represent women and other vulnerable groups. As a result of these meetings and workshops, the integrated water resource and management plans developed by the Programme focused on strengthening and including climate change considerations and gender roles in terms of the differing roles of women and men in managing water resources. |  |  |  | Good
Increased water access to women In the Programme locations over 60% of households depend on wells compared to national average of 32.3% for water. Similarly, about 21% depend on natural water sources such as rivers, rainwater, ponds or reservoirs for their water use, compared to 9% at the national level. To address this challenge while taking into consideration gender dimensions, so far during this reporting period 50 boreholes (in all 100 boreholes) have been drilled in 50 climate risks communities, providing access to clean water to over 30 000 people, mainly women and children. This is impacting positively on the lives of the people in this Programme areas. For example, Fatima Mahama(woman), a resident of Kakease in Savannah Region of Ghana says “We used to suffer to get water especially during the dry season and had to travel far. With this borehole water close-by, we can only be grateful”. |  |  |  | Good
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | Development of reporting template to include gender considerations
Have the implementation arrangements at the IE been effective during the reporting period? |  | yes
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | The lead Executing Agency, Ministry of Environment, Science, Technology and Innovation (MESTI) together with the Environmental Protection Agency constituted Regional, District and Community level Climate Change Adaptation Monitoring Committees. The committee among other responsibilities was to ensure that gender is fully mainstreamed in the implementation of project activities. In addition, the Gender Working Group within the MESTI over the reporting period supported the review of project activity and annual reports to ensure that gender was fully mainstreamed not only in planning but in actual implementation of project activities.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | YES
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | The community based NGOs lacked the capacity to understand gender issues. Capacity building workshops were organsied for the participating NGOs.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No formal grievances were received
Note on E33: Muyeye Chambwera: Please explain how (briefly)
Note on E35: Muyeye Chambwera: Please complete
Note on E34: Muyeye Chambwera: Please complete

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1: Climate historical analysis generated for the White Volta, Black Volta and Oti River basins |  | Trend/historical analysis of the impact of climate variability on the White, Black and Oti River basins completed. Climate change projections for the White and Black Volta and the Oti River basins generated |  | This output has been achieved. Trend/historical analysis of the impact of climate variability on the White, Black and Oti River basins and climate change projections for the White and Black Volta and the Oti River basins available for water resource planning and management.Thanks to the studies undertaken by the project, the Water Resources Commission and other relevant stakeholders have now access to data and information about the historical climate trends and future climate change projections for the White Volta, Black Volta and Oti river basins. The findings from the studies led to the developmen of evidence-based and climate-resilient water management and investment plans for river basins. | Highly Satisfactory (HS)
| Output 1.3: Climate smart water management plans designed for the Black Volta and Oti River basins |  | Climate smart water management plans designed for the Black Volta and Oti River basins |  | Climate smart water management plans designed for the Black Volta and Oti River basins developed | satisfactory (S)
| Output 1.4: National, Regional, District and Community based Climate Change Adaptation Monitoring Committee established/adopted and strengthened (as envisioned by the National Climate Change Adaptation Strategy) in the three target regions |  | Organise disaster preparedness workshop for communities/stakeholders on disaster risk and disaster preparedness |  | Disaster preparedness training workships organised for over 100 participants | satisfactory (S)
| Output 2.1: Climate responsive community water supply and management plans developed for 10 districts to in northern Ghana. |  | Provide refreseher trainings for existing water management committees on management plans |  | Series of training workshops led by the Water Resources Commission have been conducted for over 100participants | satisfactory (S)
| Output 2.2: Water supply system implemented |  | 50 operational boreholes drilled for five adaptation fund district |  | All the 50 operational boreholes have been drilled benefiting over 15,000 people mainly women. The community have full-ownership of the boreholes and have started making monthly financial contributions towards the repairs and maintenance of the boreholes without relying on central government support. | Highly Satisfactory (HS)
| Output 2.3: Small-scale irrigation systems installed in 30 communities and water user associations to manage irrigation systems established and or strengthened to improve efficiency and effectiveness of water usage under conditions of climate induced water shortages. |  | 40 operational irrigation systems benefitting at least 1600 farmers |  | 40 communities with a total direct beneficiary of 1,590 have been supported with irrigations facilities. | Satisfactory (S)
| Output 2.4: Measures for water conservation under climate impacts implemented in 25 communities |  | 15 buffer zones with fence created |  | 15 Buffer zones have been created. Over 18, 000 tree seedlings have been planted in 15 communities (37.1 acres) designated for woodlots/ plantations in the third year of the project. These tree planting will among others reduce siltation in the watershed. | satisfactory (S)
| Output 2.5: Learning platforms and systems for integrating climate change-related risks into community management of water resources and livelihood activities in Northern Ghana |  | Lessons learnt documentation produced. |  | A 20-minutes video documentary, a photobook and a newsletter highlighting the progress the project from inception into mid-term of implementation have been developed. | Satisfactory (S)
| Output 3.2: Livelihoods diversification for improved adaptation to climate change in 50 communities |  | • Organise livelihood training workshops for workshops for all communities • Supply inputs for dry season gardening • Support community based bee keeping with hives and training/support for small ruminants production for women and youth groups • Build capacity and supply of input to women groups in shea butter/groundnut oil extraction • Build capacity on bushfire control • Build capacity on bee keeping and biodiversity business |  | As part of achieving outcome 3 of the project, which is to enhance diversification of livelihoods in at least 50 communities in northern Ghana, 46 local NGOs/CSOs have been contracted to partner with the project to support communities to undertake livelihood activities; • Agricultural processing schemes: 12 NGOs were recruited and are currently supporting 1,260 direct beneficiaries in the processing of shea, groundnut and baobab in 22 communities. • Fish Farming: 3 local organisations were recruited and are currently supporting 790 direct beneficiaries in 23 communities cage and pond fish farming activities. • Dry Season Gardening: 17 NGOs were recruited and are currently supporting 1, 590 direct beneficiaries in 40 communities to undertake the planting of pepper, okro, tomatoes among others during the dry season. • Bee-keeping activities: 9 local NGOs recruited are currently supporting 1,348 direct beneficiaries in 35 communities along the honey production value-chain. • Tree Seedling establishment: 5 local NGOs were recruited and are currently supporting 419 direct beneficiaries in tree seedling establishment and marketing. • Integrating Cultural values: Only one NGO applied and was recruited to undertake this community-wide intervention in 3 communities. This intervention sought to support community visioning and planning, Community institutions strengthening and resource mapping, water resource and dam basin protection among others. | Highly Satisfactory (HS)
[5 empty] | Overall Rating | Highly Satisfactory (HS)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Peter Dery
| Email: | peterjdery@yahoo.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Overall, the progress of the project towards the achievement of the project goals and objectives is highly satisfactory. All the project outputs under component of the project have been fully achieved at the end of the third year. For example, downscaled climate projections are available for the White Volta, Black Volta and Oti Basins, Black Volta and 5 sub-basin plans in the White Volta and the Oti Basins have been fully developed and validated for adoption at the inter-ministerial level. Regional Climate Change Adaptation Monitoring Committees are fully established and functional in the three target regions. Over 70% actions towards the full realization of the outcome two of the project that is ensuring Climate resilient management of water resources by 50 communities in northern Ghana have been completed. For example, the project has completed all the construction of 100 boreholes, benefitting at least 30,000 people (over 50% of whom are women). Prior to the interventions by the project, poor rural communities and local lacked incentives and preparedness to manage and provide better oversight to the management of natural resources, especially water resources; food and income vulnerabilities in the project intervention areas were accentuated by the limited investment in the development of agricultural infrastructure in the project locations. Incidentally, the limited investment in the construction of dams, dugouts and the judicious management of watersheds was not only negatively impacting on the ability of the project areas to produce food for home consumption and the market, it also created the situation where the poor management of water resources have contributed to increased risks and vulnerabilities due to weather-induced disasters. However, this situation is fast positively changing due to the investment made by the project through the provision of irrigations schemes and the livelihoods interventions. Indeed, as part of achieving outcome 3 of the project, which is to enhance diversification of livelihoods in at least 50 communities in northern Ghana, the project has engaged 46 community-based organizations in delivering the key outputs under outcome three of the project. For example, as of the end of the third year of the project the following has been achieved: 1,260 direct beneficiaries are engaged in the processing of shea, groundnut and baobab in 22 communities; 790 direct beneficiaries in 23 communities are engaged in cage and pond fish farming activities; 1, 590 direct beneficiaries in 40 communities are currently engaged in planting of pepper, okro, tomatoes among others during the dry season; 1,348 direct beneficiaries in 35 communities are engaged along the honey production value-chain and over 400 direct beneficiaries are engaged in tree seedling establishment and marketing. The programme also continuous to ensure that gender sensitive considerations are fully mainstreamed in the implementation of project activities especially those interventions relating to diversification of livelihoods. Recognizing that the dominance of men over women in the programme locations, in terms of ownership of land, access to and control of resources, and in decision making, there was conscious and deliberate efforts to ensure that 60% of the entire project beneficiaries for each of the livelihoods activities such as bee keeping, agro processing schemes, dry season farming among others were women. Despite these achievement over the reporting period, activities such as the mechanization of the boreholes and the finalization of the community water management plans have been very slow. However, steps including the development of procurement strategy have been put in place to address this challenge.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Output 1.1: Climate historical analysis generated for the White Volta, Black Volta and Oti River basins |  | Trend/historical analysis of the impact of climate variability on the White, Black and Oti River basins completed. Climate change projections for the White and Black Volta and the Oti River basins generated |  | The historical and trends analysis of the impact of climate change variability on the white, black and oti river basins have been completed. Through these studies undertaken by the project, the Water Resources Commission and other relevant stakeholders have now access to data and information about the historical climate trends and future climate change projections for the White Volta, Black Volta and Oti river basins. Knowledge about changes in temperature and rainfall is a very important asset for these organizations to develop evidence-based and climate-resilient water management and investment plans for river basins. | Satisfactory (S)
| Output 1.3: Climate smart water management plans designed for the Black Volta and Oti River basins |  | Climate smart water management plans designed for the Black Volta and Oti River basins |  | The water management and investment plans for the Black Volta and Oti river basins were finalized and validated. The implementation of these plans is expected to result in improved water resource management and long-term planning to effectively address the underlying drivers of water resource degradation and stimulate investments, while taking into account and trying to reduce the impact of climate change on surface and groundwater sources and livelihood As part of the development of these plans, key water resource management issues were subjected to thorough deliberations and ranking through the Strategic Environmental Assessment (SEA) tools. The development/review of community/district based water management plans to include tributaries has also been initiated. To ensure effective implementation of the management plans, there is the need for an effective institutional and governance structure at the sub-catchment level of the basins. In response to this, five sub-basins committees were established, namely, Noumbiel, Dapola, Bamboi, Bui and Vonkoro for the Black Volta basin. This is also part of efforts by the Water Resources Commission to decentralize the management of Water Resources in the basins. The sub-basin committees are composed of representatives of district assemblies, water users, civil society organizations in the water sector, women representatives, traditional authorities and other stakeholders who are key with regards to the implementation of water resources management strategies. | Highly Satisfactory (HS)
| Output 1.4: National, Regional, District and Community based Climate Change Adaptation Monitoring Committee established/adopted and strengthened (as envisioned by the National Climate Change Adaptation Strategy) in the three target regions |  | Organise disaster preparedness workshop for communities/stakeholders on disaster risk and disaster preparedness |  | Awareness raising, and advocacy workshops conducted to address water resource management challenges in the Black and Oti basins. In all, about 115 people made of traditional leaders, women and youth groups, civil society organizations and other community-based organizations were educated and sensitized on various water resource management activities and disaster risk and preparedness under climate change | Satisfactory (S)
| Output 2.1: Climate responsive community water supply and management plans developed for 10 districts to in northern Ghana. |  | Provide refreseher trainings for existing water management committees on management plans |  | In order to effectively implement the river basin management plans for the two basins, capacity building of stakeholders was undertaken. The Basin Boards and Sub-Catchment Committees received technical training in water resources management to enable them to perform their duties and responsibilities effectively. A total of 100 participants (65% male, 35% Female) were trained | Satisfactory (S)
| Output 2.2: Water supply system implemented |  | 50 operational boreholes drilled for five adaptation fund district |  | 50 operational boreholes have been drilled and fucntional and benefiting over 15,000 people, mainly women and children | Satisfactory (S)
| Output 2.3: Small-scale irrigation systems installed in 30 communities and water user associations to manage irrigation systems established and or strengthened to improve efficiency and effectiveness of water usage under conditions of climate induced water shortages. |  | 40 operational irrigation systems benefitting at least 1600 farmers |  | 40 communities with a total direct beneficiary of over 1,500 have been supported with irrigations facilities. | Satisfactory (S)
| Output 2.4: Measures for water conservation under climate impacts implemented in 25 communities |  | 15 buffer zones with fence created |  | 15 Buffer zones have been created. Over 18, 000 tree seedlings have been planted in 15 communities (37.1 acres) designated for woodlots/ plantations in the third year of the project. These tree planting will among others reduce siltation in the watershed. | Satisfactory (S)
| Output 2.5: Learning platforms and systems for integrating climate change-related risks into community management of water resources and livelihood activities in northern Ghana |  | Lessons learnt documentation produced. |  | A 20-minutes video documentary, a photobook and a newsletter highlighting the progress the project from inception into mid-term of implementation have been developed.
| Output 3.2: Livelihoods diversification for improved adaptation to climate change in 50 communities |  | • Organise livelihood training workshops for workshops for all communities • Supply inputs for dry season gardening • Support community based bee keeping with hives and training/support for small ruminants production for women and youth groups • Build capacity and supply of input to women groups in shea butter/groundnut oil extraction • Build capacity on bushfire control • Build capacity on bee keeping and biodiversity business |  | Various livelihoods interventions have been implemented. In all, the project is directly benefitting 5,407 people as well as 103, 834 in-direct beneficiaries from the livelihood activities value-chain as well as dependants of the direct beneficiaries. It is anticipated the interventions of these livelihoods activities will be a game changer to increase household incomes by at least 50% when a full scale individual assessment of their work is done by the close of the year 4. | Satisfactory (S)
[5 empty] | Overall ratings: To be considered as the overall project rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Stephen Sabunam Kansuk
Please justify your rating. Outline the positive and negative progress made by the project since it started. | Email: | stephen.kansuk@undp.org
Overall, the project has made significant progress in enhancing the resilience and adaptive capacity of rural livelihoods to climate impacts and risks on water resources in the northern region of Ghana. Under climate change impacts, ensuring that there is adequate water supply year-round for multiple uses and users is crucial but constituted a challenge prior to the project intervention. To address this challenge, the project in line with the project target as of the third year of the project has constructed 100 boreholes which is providing water access to over 300,000 direct beneficiaries especially women in all the intervention areas. Through the project a lot of activities that seek to mobilize community planning and implementation of practices that restore and preserve the natural character and functioning of the water system were done. For example, in order to effectively implement the river basin management plans for the Black and Oti basins, a number of capacity building training workshops were held. The Basin Boards and Sub-Catchment Committees received technical training in water resources management to enable them to perform their duties and responsibilities effectively. One of the key positive things that happened within this reporting period is the completion of some important studies. For example, the historical and trends analysis of the impact of climate change variability on the white, black and oti river basins were completed. Through these studies undertaken by the project, the Water Resources Commission and other relevant stakeholders have now access to data and information about the historical climate trends and future climate change projections for the White Volta, Black Volta and Oti river basins. Knowledge about changes in temperature and rainfall is a very important asset for these organizations to develop evidence-based and climate-resilient water management and investment plans for river basins. Indeed, these studies led to the finalization of the water management and investment plans for the Black Volta and Oti river basins. The implementation of these plans is expected to result in improved water resource management and long-term planning to effectively address the underlying drivers of water resource degradation and stimulate investments, while taking into account and trying to reduce the impact of climate change on surface and groundwater sources and livelihood. As a further step in implementing these plans, five sub-basins committees were established, namely, Noumbiel, Dapola, Bamboi, Bui and Vonkoro for the Black Volta basin. This is also part of efforts by the Water Resources Commission to decentralize the management of Water Resources in the basins. The sub-basin committees are composed of representatives of district assemblies, water users, civil society organizations in the water sector, women representatives, traditional authorities and other stakeholders who are key with regards to the implementation of water resources management strategies. A lot of communities in northern Ghana are dependent on rain-fed agriculture which is extremely vulnerable to the impacts of climate change. The project in recognizing this, has undertaken various livelihoods interventions. In all, the project as at the end of the third has directly supported over 5,000 people as well as 103, 834 in-direct beneficiaries from the livelihood activities value-chain. Noting that agricultural activities that maximize the economic benefits from increased capacity to drawdown water and increased capacity to use it productively, such as market gardening is crucial for diversification of livelihoods of rural communities; The project provided small-scale infrastructure support, such as watering cans, pumps and pipes, to facilitate dry seasoning gardening by women in 50 communities. Dry-season gardening, led by women, was strongly supported by communities during community consultation. This activity is linked to increased water supply and storage, particularly dugouts and small-scale dams. Dry-season gardening provided women not only with access to income sources during the dry-season but also importantly access to more and more diverse sources of food. It is anticipated the interventions of these livelihoods’ activities will be a game changer to increase household incomes by at least 50% when a full-scale individual assessment of their work is done within the fourth year of the project. One of the challenges encountered during the reporting period related to delays in procurement of contractors to undertake the construction of small dams and dugouts in the project intervention areas. However, some significant steps have been taken to ensure that this does not adversely impact on the overall objective of the project. In sum, all these achievemment will satisfactorily lead to the achievement of the project outputs and outcomes.
Other | Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Goal
Outcome 1 | Existence of historical and downscaled climate projections | No downscaled climate projections are in place | Historical and downscaled climate projecttions established. | Downscaled and historical climate projections available for the White Volta, Black Volta and Oti Basins
Outcome 1 | Revised White Volta management plan | Current plan does not address climate change impacts nor link clearly to community level | The White Volta Management and Investment Plans have been developed under Water Climate Programme and Development Programme (WACDEP) project which was implemented by the Water Resource Commission and funded by DANIDA. The project has obtained a copy of the report which will be used to inform other interventions | Revised White Volta Plan completed and adopted at inter-ministerial level
Outcome 1 | Three regional Climate Change Adaptation Monitoring Committees | There is no committee in place | The Regional, District and Community based Climate Change Adaptation Monitoring Committees have been established. Three regional training meetings, 10 districts level meetings and 50 community level engagement were completed. These trainings are expected to be done yearly. | Three regional Climate Change Adaptation Monitoring Committees
Outcome 1 | Management plans in the Black Volta and five sub-basins in the White Volta and the Oti basins at ministerial level | No plans are in place | The water management and investment plans for the Black Volta and Oti river basins have been finalized and validated. The implementation of these plans is expected to result in improved water resource management and long-term planning to effectively address the underlying drivers of water resource degradation and stimulate investments, while taking into account and trying to reduce the impact of climate change on surface and groundwater sources and livelihood | Black Volta and 5 sub-basin plans in the White Volta and the Oti Basins adopted at inter-ministerial level
Outcome 2 | Number of communities in which management plans have been developed and are being implemented | Management plans are not in place. Lack of coherent and planned water management activities in communities. | Draft community-catchment management plans developed for finalization in the next reporting. | 50 community water management plans implemented by community institutions with at least 50% representation by women in place by end of programme year 2.
Outcome 2 | Number of operational boreholes, dugouts/dams and rainwater harvesting systems | Communities have limited infrastructure in place for supply and storage of water | 50 operational boreholes have been drilled in the year under review bringing to total 100 boreholes drilled. These 50 boreholes are currently serving over 30, 000 people mainly women and children in 50 communities in 10 districts. | 100 operational boreholes, benefitting at least 30,000 people
Outcome 2 | Number of operational community scale irrigation systems installed | Very few communities have effective irrigation systems in place | 40 small irrigation systems, one each in 40 communities with a total direct beneficiary of 1,590 have been established. | 50 operational irrigation systems, benefitting at least 2,500 farmers
Outcome 3 | Number of operational community fish farms established | Few communities benefit from community fish farms | A total of 23 Fish ponds have been established in 23 Communities benefiting over 790 direct beneficiaries | 20 community fish farms established, benefitting at least 10,000 people
Outcome 3 | Number of tree nurseries/wood lots established | Few communities benefit from community managed tree nurseries and wood lots, nor from bee keeping activities | 25 tree nurseries established benefiting over 400 direct beneficiaries in tree seedling establishment and marketing | 40 community tree nurseries and wood lots, incorporating bee keeping, established
Outcome 3 | Number of dry season gardening schemes for women established | Few communities benefit from effective dry season gardening | 40 dry season gardening schemes for women have been established. These schemes are supporting over 1, 590 direct beneficiaries in 40 communities to undertake the planting of pepper, okro, tomatoes among others during the dry season. | 50 dry season gardening schemes for women established, directly benefitting at least 1,000 women
Outcome 3 | Number of women led agricultural product processing schemes established | Few communities benefit from agricultural product processing | 22 women led agricultural product processing schemes established benefiting over 1,260 direct beneficiaries in the processing of shea, groundnut and baobab in 22 communities. | 40 community level women led agricultural product (shea butter or honey) processing schemes established, directly benefitting at least 1,200 women
Outcome 3 | Household income | More than 50% of the households in the target communities have income levels below the poverty line | Independent studies using economic models to be conducted in the final year of the project to determine this indicator. | At least 50% of the households in the target communities increase their income by 30% by the end of the project

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Inadequate monitoring by the regional and district Environmental Protection Agency team on interventions being implemented at the community level. This does not give the Project Management Unit based in Accra timely feedback from consultants, communities and decentralized stakeholders on the progress, challenges and lesson learned to guide project management. To address this issue, the PMU intends to intensify its community outreaches, resource the regional/district EPA offices and conduct joint implementation monitoring as well as periodic post implementation monitoring to ensure that community level implementation is done timely, appropriately and yields the planned/intended outcomes.The late release of project funds and bureacratic procurement processess also impacted on the project implementation.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There was close to about five(5) months delays in implementation due to late release of funds from Adaptation Fund and the seasonal nature of the project interventions. For example, the contruction of boreholes and the rehabilitation of community dug outs and dams could not take place during the raining seasons.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | Regular field monitoring and engagement of key stakeholders including traditional leaders, high-level government officials at both the local and national levels improved project results. Initially, key stakeholders like the chiefs and landowners were not willing and ready to release their lands closer to the major water bodies for protection. However due to regular engagement with the key stakeholders including the traditional leaders this issue was resolved. This led to the creation of 15 Buffer around the water bodies. Indeed over 18, 000 tree seedlings have been planted in 15 communities (37.1 acres) as a result of the closer collaboration with the project key stakeholders at the local levels. It is expected that the trees planted will among others reduce siltation in the watershed.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | While ESP was not a requirement at the begining of the project, environmental and social safeguard measures guided the contruction and rehabilitation of the existing dams and the provision of other water supply systems such as the boreholes. Vendors and contractors obtained the necessary environmental permits and engaged effectively with the project beneficiaries taking into consideration social and gender issues.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Women generally face higher risks and greater burdens from the impacts of climate change due to their subordinate position in the project sites. Indeed, women face inequalities when it comes to control and access to land and decision-making power, due to the cultural norms existing in the project locations. As a result, there was a deliberate effort to ensure greater percentage (60%) of the project beneficiaries are women. Firstly, a simple gender analysis was conducted for each livelihood interventions in all the project sites. The project beneficiaries were then selected based on the findings of the gender analysis. One of key lessons learned is that women are active agents of climate change only if they are involved in decision making especially regarding the kind of livelihood interventions to be adopted in a given community considering their peculiar circumstances. One of the indicators of the project was to increase the number of dry season gardening schemes for women. As a result of the deliberate involvement of women, 40 dry season gardening schemes for women have been established. These schemes are supporting over 1, 590 direct beneficiaries in 40 communities to undertake the planting of pepper, okro, tomatoes among others during the dry season. The women are directly involved in the entire value chain of the dry season activities and other livelihood interventions like fish farming and Agro processing schemes. Th inclusion and involvement of women right from the conceptualization and implementation of the livelihood interventions have yielded positive results including increase in income levels of the women groups and enhanced community level ownership of the project interventions. In the Programme locations over 60% of households depend on wells compared to national average of 32.3% for water. Similarly, about 21% depend on natural water sources such as rivers, rainwater, ponds or reservoirs for their water use, compared to 9% at the national level. To address this challenge while taking into consideration gender dimensions, so far during this reporting period 50 boreholes (in all 100 boreholes) have been drilled in 50 climate risks communities, providing access to clean water to over 30 000 people, mainly women and children. This is impacting positively on the lives of the people in this programme areas. For example, Fatima Mahama(woman) , a resident of Kakease in Savannah Region of Ghana says “We used to suffer to get water especially during the dry season and had to travel far. With this borehole water close-by, we can only be grateful”.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The agro-forestry method of tree seedling planting minimizes the impact of the relocation of farmers from around water resources within the short to medium term period. The PMU has learned that inter-planting already existing crops on farm lands with the tree seedlings will foster ownership and nurturing of the trees especially for the first year of planting by the affected farmers since there may still be farm produce on the same lands designated for tree planting/buffer zones. In subsequent years’ however, these farmers within the enclaves of the planted trees and buffer zones will be moved completely away from these fenced sites with minimal impact on their household economy. For future programmes, there must be deliberate efforts in building partnerships with local NGOs/Community Based Organizations and the private sector in delivering community level adaptation interventions. It helps strengthen community level ownership of project interventions, it proves to be effective and efficient in delivery community services as well. For example, the Programme partnered with 46 local NGOs/CSOs to enhance diversification of livelihoods in at least 50 remote communities (reaching over 5,407 vulnerable people (60% women) and indirectly benefitting 103,834 people) who are in need of adaptation finance within a relatively shorter period and in a cost-effective manner. Partnership with local and community-based organizations reduces travel and monitoring cost. Again, in future adaptation projects, livelihoods interventions should be based on demand driven approaches through effective consultation and engagement with intended project beneficiaries.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The potential for replication and scaling up the climate resilience measures undertaken by the project is very high as government has indicated its willingness to mobilize additional resources within its national budget and with support from international climate finance to support water resource management and implementation of resilient adaptation measures through its flagship project of water for all, infrastructure for all and planting for food and jobs programmes. Other development partners have shown interest in upscaling of the project results.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | Engagement with people with respect, credible, authority, and getting the trust of the people as community core group will help support and ease implementation of concrete actions of the project. Thus identifying interest groups such as the traditional authority, land owners and farmers both within the community and off-farm migrants is key to the process of allocating areas required as buffer zones for protecting rivers and dams. Closely linked to the above is the need for the project to work with the local government authority to agree on and sign Memorandum of Agreement among the key stakeholders in the community, particularly with land owners and used to ensure full compliance. The key negative lesson learned is the political interference in the selection of project beneficiaries and concrete adaptation interventions. However, constant dialogue with political actors and the development of clear selection criteria agreed by all stakeholders are essential in addressing this challenge.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | The likelihood that the concrete adaptation interventions such as the rehabilitation of the community dams and the drilling of boreholes undertaken by the project will be replicated and scaled up both within and outside the project area is very high. Indeed, a private sector company, Guinness Ghana Limited as part of their water replenishment strategy have consulted UNDP for a potential partnership to provide additional funding to support the upscaling and replication of the rehabilitation of the dams undertaken by the project. The government through its flagship Programme of one village one dam policy is also considering supporting the upscaling of the dam rehabilitation. Again, key results and lessons of the current project especially lessons from the livelihoods interventions will be crucial in the implementation of the “Ghana Shea Landscape REDD+ Project” which has been submitted for consideration by the Green Climate Fund (GCF). This GCF project aims to significantly reduce emissions from deforestation and forest degradation in the Northern Savannah Zone (NSZ), whilst leveraging private sector investments in the shea value chain and supporting women’s empowerment through the development of sustainable and more profitable business opportunities for rural women. Ghana’s northern sector is fast losing its preponderance of forests, highly valuable and diverse savanna woodland species (including rosewood and shea trees), wildlife and ecosystem services.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | The provision of 100 boreholes, the community level project interventions like the dry season gardening and the rehabilitation of community dams and dugouts
What measures are/have been put in place to ensure sustainability of the project/program results? | The project interventions are archored on government priority projects such as one village one dam policy and water for all initiatives.
What measures are being/could have been put in place to improve project/program results? | One of the strategies that was adopted to improve the project results was the engagement of Community Based Organizations (CBOs) to support in the implementation of community level interventions. This strategy proves to effective and efficient in delivering multiple project results in a diverse project location. The project effectively leveraged on the existing institutional structures of government at national and sub-national levels as well as existing community structures. The formation of technical validation teams with representation from key line ministries and agencies also enhanced project results and has the potentials to ensure the sustainability of the project results. One of the measures that could have been effectively utilized to improve project results is frequent monitoring of project interventions at the community levels. The project has put measures to ensure that this is effectively addressed in the final year of the project.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | Through the studies undertaken by the project, the Water Resources Commission and other relevant stakeholders have now access to data and information about the historical climate trends and future climate change projections for the White Volta, Black Volta and Oti river basins. Knowledge about changes in temperature and rainfall is a very important asset for these organizations to develop evidence-based and climate-resilient water management and investment plans for river basins. These studies served as inputs to the finalization of the water management and investment plans for the Black Volta and Oti river basins .The implementation of these plans is expected to result in improved water resource management and long-term planning to effectively address the underlying drivers of water resource degradation and stimulate investments, while taking into account and trying to reduce the impact of climate change on surface and groundwater sources and livelihood
If learning objectives have been established, have they been met? Please describe. | All learning objectives have been achieved. The project beneficiaries have been trained on climate change impacts and livelihoods diversification to reduce the impacts of climate change.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | No difficulty was encountered.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | Yes. Through the trainings most of the project beneficiaries understood their individual roles in addressing climate change impacts, especially the women groups as key agents to addressing climate change impacts on water resources

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | UNDP
Type of implementing entity | MIE
Country | Ghana
Region | Africa
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 8060000 | 60000 | 8000000 | Total | 8060000 | 60000 | 8000000 | Total | 149277 | 46277 | 103000 | Total
|  | % of female beneficiaries | 40% | 40% | 40% | % of female beneficiaries | 40% | 40% | 40% | % of female beneficiaries | 60% | 60% | 60% | % of female beneficiaries
|  | % of Youth beneficiaries | 60% | 60% | 60% | % of Youth beneficiaries | 60% | 60% | 60% | % of Youth beneficiaries | 40% | 40% | 40% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 100 | Multi-sector | 2: Low capacity | Total | 150 | Multi-sector | 4: High capacity | Total | 150 | Multi-sector | 3: Medium capacity | Total
|  | % of female targeted | 20% |  |  | % of female targeted | 40% |  |  | % of female targeted | 40% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 100 | 20% | Public |  | 150 | 40% | Public |  | 150 | 40% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Regional | Multi-sector | 2: Low capacity | Public | Regional | Multi-sector | 4: High capacity | Public | Regional | Multi-sector | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 50% |  | Multi-sector |  | 100 |  | Multi-sector |  | 80
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 60000 | 30% | 3: Partially aware |  | 60000 | 60% | 5: Fully aware |  | 46277 | 40% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Multi-sector | Regional | 1: Non responsive (Lacks all elements ) |  | Multi-sector | Regional | 4: Mostly responsive (Most defined elements) |  | Multi-sector | Regional | 3: Moderately responsive (Some defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 21 | Community |  | Water management | 50 | Community |  | Water management | 50 | Community |  | Water management
|  | 25 | Community |  | Agriculture | 50 | Community |  | Agriculture | 40 | Community |  | Agriculture
|  | 8 | Community |  | Agriculture | 50 | Community |  | Agriculture | 50 | Community |  | Agriculture
|  | 43 | Community |  | Water management | 50 | Community |  | Water management | 50 | Community |  | Water management
|  | 11 | Community |  | Water management | 21 | Community |  | Water management | 11 | Community |  | Water management
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 2: Partially effective |  | Agriculture | land | 4: Effective |  | Water management | water areas | 3: Moderately effective |  | Water management
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 4 | ha protected | 3: Moderately effective | Cultivated land/Agricultural land | 20 | ha protected | 4: Effective | Cultivated land/Agricultural land | 19 | ha protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 30 | ha protected | 3: Moderately effective | Forests | 20 | ha protected | 4: Effective | Catchment area/Watershed/Aquifer | 18 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 10 | ha protected | 2: Partially effective | Catchment area/Watershed/Aquifer | 20 | ha protected | 4: Effective | Catchment area/Watershed/Aquifer | 18 | ha rehabilitated | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Protected areas/National parks | 10 | ha protected | 3: Moderately effective | Protected areas/National parks | 20 | ha protected | 4: Effective | Catchment area/Watershed/Aquifer | 10 | ha rehabilitated | 3: Moderately effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 5882 | 16.2% | 3: Moderate improvement |  | 5882 | 16.2% | 3: Moderate improvement |  | 5882 | 16.2%
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 5882 | 16.2% | From 1% to 5% | Livestock production | 5882 | 16.2% | From 10% to 20% | Livestock production | 5882 | 16.2% | From 5% to 10% | Livestock production
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 5882 | 16.2% | From 1% to 5% | Agricultural-related | 5882 | 16.2% | From 10% to 20% | Agricultural-related | 5882 | 16.2% | From 10% to 20% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 5882 | 16.2% | From 1% to 5% | Trading | 5882 | 16.2% | From 10% to 20% | Trading | 5882 | 16.2% | From 5% to 10% | Trading
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 5882 | 16.2% | From 1% to 5% | Agribusiness | 5882 | 16.2% | From 10% to 20% | Agribusiness | 5882 | 16.2% | From 5% to 10% | Agribusiness
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 2 | Financial capital | Food security | Microfinance | 4 | Financial capital | Food security | Livelihoods | 4 | water reservoirs | Agriculture | Strengthening infrastructure
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 5882 | Cultivation |  | 835 | 5882 | Cultivation |  | 1500 | 5882 | Cultivation |  | 1000
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 5882 | Agribusiness |  | 835 | 5882 | Agribusiness |  | 1200 | 5882 | Agribusiness |  | 1000
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 5882 | other |  | 835 | 5882 | other |  | 1200 | 5882 | other |  | 1000
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
3: Some
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 1 | Multi-sector | National | Domestic policy | 1 | Multi-sector | National | Domestic policy | 1 | Multi-sector | National
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 2 | 2: Partially not enforced (Most elements not implemented) |  | 2: Partially effective | 4 | 4: Enforced (Most elements implemented) |  | 4: Effective | 2 | 3: Partially enforced (Some elements implemented) |  | 3: Moderately effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on N103: Muyeye Chambwera:
Note on L25: Muyeye Chambwera:

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.