## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 4 March 2017 to 4 March 2018
| Project Title: | Programme Support for Climate Change Adaptation in the vulnerable regions of Mopti and Timbuktu
| Project Summary: | The main objective of the programme is to increase the resilience of vulnerable communities and their adaptive capacity to climate change in the Regions of Mopti and Timbuctu including the Faguibine system zone. The programme has three components with the following specific outcomes: Component 1: Enhanced water control measures in vulnerable water buffer zones. Outcome 1: Increased climate change resilience of local water systems in Mopti and Timbuctu Regions. Component 2: Resilience in subsistence livelihoods of vulnerable communities. Outcome 2: The production of local livelihood systems such as agriculture, fisheries, livestock, and forest enhanced under climate change Component 3: Capacity-building and knowledge generation for adaptation Outcome 3: Enhanced capacity of local institutions and of communities to better adapt to climate change.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PIMS No 4789 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations Development Programme (UNDP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | UNDP as Multilateral Implementing Entity | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Mali | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Communes of Mopti Region : Bamba, Pelou, Kendé, Tédié, Koubewel-koundia, Gandamia, Dangol-Boré, Pondori and Togoro-Kotia. Communes of Timbuctu Region : Alafia, Hanzakoma, Haribomo, Goundam, Gargando, Bintagoungou, Essakane, Kondi, Arham, Tindirma, and Binga; | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 30/03/2015
IE-AFB Agreement Signature Date: |  | 04 November 2015 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 04 March 2016 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | March 2018
| Terminal Evaluation Date: | March 2020
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Reports: • Program Launch Report • Report on the situation of references in Mopti and Timbuktu • PPR 2016 • 2016 and 2017 quarterly and annual reports to UNDP CO (Progress report/financial reports/quarterly work plan/annual work plan) • Report of the Steering Committee 2016 and 2017 • Creation of the project Website • Study report on the carbon sequestration rate of agroforestry parks in the project intervention zone. • Photos of construction sites and documentary films • Revision report on programme indicators and targets • Monitoring reports of natural assisted regeneration and training of peasants in agroforestry parks of the communities of Bamba, Kendé and Dangol-Boré • Farmer training report on improved seed cultivation techniques and improved seed monitoring • Farmer training report on agroforestry techniques adapted to climate change • Training report for Community counsellors and civil society on the institutional management of climate change • Report on the training of peasants and elected officials on climatic and meteorological applications • Communication Plan Document of the programme • Work Plan and annual Budget 2018 • Status of implementation of the recommendations of the first session of the Programme Steering Committee | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | www.pacvmt-mali.org | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Boubacar Sidiki DEMBELE | Dominican Republic
| Email: | boubacarsdembele@gmail.com | Ecuador
| Date: | March 2018 | Egypt
| Government DA |  | El Salvador
| Name: | Boureima CAMARA | Equatoral Guinea
| Email: | bouricamara@gmail.com, Tel: +22366805756 | Eritrea
| Date: | March 2018 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | United Nations Development Programme (UNDP) | Fiji
| Email: | oumar.tamboura@undp.org | Finland
| Date: | March 2018 | France
| Executing Agency |  | Gambia
| Name: | Environment and Sustainable Development Agency (AEDD) | Georgia
| Email: | aedd@enironnement.gov.ml | Germany
| Date: | March 2018 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Taux du jour
Financial information: cumulative from project start to 31st December 2017 |  |  |  |  | 556.89
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [31/12/2017] | 2823574
Add any comments on AF Grant Funds. (word limit=200) | To date, the project has a cumulative disbursement of US$ 2 823 574.00 (2 years of implementation), representing 36% of the total funding, and 72% of the first tranche of funding (US $ 3 907 508) received by UNDP. The slow disbursement by the programme can be explained by: (i) the security issues in the communes of Timbuktu region, which slowed down the implementation of most of the activities, (ii) the long national procurement procedures imposed on the programme's investments, slowing down the implementation of the activities in all communes of the programme.
INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT SPENT | AMOUNT COMMITTED | BALANCE
| Outcome 1: Increased climate change resilience of local water systems in Mopti and Timbuctu Regions. | 993979.5022 | 1802330.901 | 808351.3988
| Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 20 km silted channels and obstructed ponds | 298636.9516 | 304361.4915 | 5724.5399
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiple users including climate resilient water management systems | 695342.5505 | 1497969.4095 | 802626.859
| Outcome 2: The production of local livelihood systems such as agriculture, fisheries, livestock, and forest enhanced under climate change | 637515.4928 | 1040731.677 | 403216.1842
| Output 2.1: Climate-resilient fisheries and agro-pastoral practices and technologies (e.g. drought- and disease-resistant varieties) introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities | 159528.495 | 562744.6792 | 403216.1842
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change | 466970.4595 | 466970.4595 | 0
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities | 11016.5383 | 11016.5383 | 0
| Outcome 3: Enhanced capacity of local institutions and of communities to better adapt to climate change. | 105147.2779 | 105147.2779 | 0
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) | 70613.1329 | 70613.1329 | 0
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) | 34534.145 | 34534.145 | 0
| Output 3.3 Local institutional capacity strengthened in 20 communities in establishing micro-credit schemes, cereal banks etc. and in managing | 0 |  | 0
| Project Management Costs | 289168.2271 | 289168.2271 | 0
| TOTAL | 2025810.5 | 3237378.0831 | 1211567.583
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Outcome 1: Increased climate change resilience of local water systems in Mopti and Timbuctu Regions. | 1923000.9517
| Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 50 km silted channels and obstructed ponds | 481962.3265 | March 2019
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiple users including climate resilient water management systems | 1441038.6252 | March 2019
| Outcome 2: The production of local livelihood systems such as agriculture, fisheries, livestock, and forest enhanced under climate change | 1002242.2259
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities | 643046.797 | March 2019
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change | 319740.9377 | March 2019
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities | 39454.4912 | March 2019
| Outcome 3: Enhanced capacity of local institutions and of communities to better adapt to climate change. | 109572.5684
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) | 84253.385 | December 2019
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) | 25319.1833 | March 2019
| Output 3.3 Local institutional capacity strengthened in 20 communities in establishing micro-credit schemes, cereal banks etc. and in managing | 182869.6956 | March 2019
| Project Management Costs | 287274.7264
| TOTAL | 3322090.4724
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | The total co-financing as stated in the project document and realized during this reporting period is estimated at US$ 166,933. The cumulative realized co-financing since the start of the project is estimated at US$ 384,452
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | Under the in kind co-financing of the Government of Mali, a building was made available for the project team. The Government also finances the cost of electricity, water and security services. This contribution to date is estimated at US$ 125,000. UNDP cash co-financing is estimated at US$ 41,933. The co-financing of UNDP was carried out by TRAC payment.

## Risk Assessment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Armed conflict that has recently escalated and engulfed the Northern region of Mali | High | The security situation is increasingly degrading. Insecurity reached the center of Mali (Mopti and Ségou). In addition to existing security arrangements such as the G5 Sahel Force, the FAMAs and MINUSMA, the Government of Mali has taken a measure that prohibits the movement of two-wheeled and pickup vehicles in the 8 circles of Mopti and some circles of Segou. The project is in constant contact with the mayors in beneficiary sites for the supervision of activities including the completion of investment work by the various companies. As usual, the missions of the project staff are covered by security clearance and guided by MINUSMA on the conduct to be held. This year, the project will sign a memorandum of understanding with the OMVF, already operating in the targeted sites, to unlock about 20 km of channels in the Faguibine system in Timbuktu.
Delays in project inception impacts the achievment of outputs and outcomes and reduces the scope to deliver the project as outlined in proposal | Medium | The project was launched in March 2016, 5 months after its signature, and is in its second year of implementation. Despite insecurity issues, investments and studies are underway in each municipality, however, the project did not manage to catch up on the initially planned schedule, and observes important delays in the implementation. The mid-term evaluation to be conducted in 2018 will determine whether the delay in the start of activities - coupled with other drawbacks impacting the implementation - will require an extension of the project.
Poor collaboration between programme partners | Low | Currently, the collaboration efforts between the project and (i) the AEDD, the implementing entity, (ii) the DCM (iii) and UNDP are showing positive results on the project implementation. Besides, the 13-member Project Steering Committee held its second ordinary session and enabled the good understanding of the project between all the project partners. In addition, the project is constantly in contact with local authorities and beneficiaries in order to efficiently move activities forward and supervise their completion.
Poor understanding of objectives by the project team | Low | The project team has a full understanding of the results to be achieved as well as the issues, and has now a good ownership of the project activities. Detailed and comprehensive work plans and activity reports have been developed and validated with implementing and executing entities and the Steering Committee.
Low mobilization of the target group has led to little understanding of climate change issues | Low | The investment plan per municipality is available. These are investments that help increase the population's resilience to climate change. Currently, elected officials and civil society members - including women - have a good grasp of climate issues thanks to the training sessions organised by the project in 2017.
Lack of sufficiently qualified partners | Medium | In the project area, qualified and competent partners are available, with whom the project can establish partnership agreements to better implement the activities. These partners include: local NGOs, companies, technical services and consulting firms - some of whom were already contracted, as shown under the procurement tab. However, given the increasing insecurity issue, some partners identified during the project formulation are now reluctant to respond to bid requests to provide services in certain communities -namely Gargando, Essakane, Bintagoungou, Hanzakoma and Haribomo municipalities. However, new partnerships were identified and established to address issues such as movement restrictions in these areas.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The long national procurement procedure regarding investments has delayed project implementation | High | Despite the creation of the procurement unit in the Ministry of the Environment, the lengthy procurement process still persists and seriously hampers completion of investment works. This year, investments in Mopti started late in June 2017, the bids for all Timbuktu investments have been submitted to the AEDD since September 2017 but were only processed by the General Directorate for Public Procurement (DGMP) in December 2017. In addition, (i) the offer needs to be publicised in the newspapers for 1 month, (ii) the opening of the bids and offers takes at least 2 weeks, and (iii) the process for the signature of the contracts also lasts 1 to 2 months. Therefore, completing a procurement procedure through the DGMP can take up to 7 months. In order to reduce this lengthy procedure, the Steering Committee held on 30 November 2017 recommended the procurement to be supervised by communes for the activities under Component 1, in accordance with the program document Part III-A: "For component 1, local authorities (municipal and regional councils) of the Mopti and Timbuktu regions will be the contracting authorities for infrastructure, construction and other support investments aimed at strengthening the local water supply systems' resilience to climate change [...]". If this measure is accepted by all stakeholders (the Steering Committee, DGMP, and UNDP), this would make it possible to significantly shorten the procurement process
The communiqué of the army's Chief of Staff released on February 1st 2018 and which limits movement related to the project in the Mopti region | High | This communiqué prohibits the free movement of all motorcycles and pick-ups in all Mopti districts until further notice. These are the most popular means of transport used by the populations, companies, consulting firms and some partners working in the region. This may lead to delays in the execution and monitoring of investment works. For all trips, an authorization must be requested from the Army operating in the area. At present, such authorization is very difficult to obtain and the only means of transport are vehicles travelling to the weekly fairs, buses or trucks.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The project team will continue its collaboration with MINUSMA, the governors of the Mopti and Timbuktu Regions, the OMVF and elected municipal officials to facilitate the implementation of activities especially in areas where organized crime or terrorism still persist. The meeting with the 11 municipalities of Timbuktu and the Governor with the OMVF to discuss possible synergies helped to identify the 20 km of channels in the Faguibine system to be cleared, and a memorandum of understanding will be signed with the OMVF to this end. In addition, to enable the project to carry out all the planned activities in the 20 target communes, an extraordinary steering committee was conducted, and recommended an 18- month extension of the project. The consultants in charge of the mid-term evaluation will study this proposal and suggest a way forward.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 50 km silted channels and obstructed ponds |  | Identification of 20 km of silted channels in the Timbuktu region |  | 20 km of silted channels were identified around the Faguibine system zone located in 5 PACV-MT target municipalities. The aforementioned channels will be cleared by the OMVF as part of a cooperation initiative with the PACV-MT. | Highly Satisfactory (HS)
|  |  | Completion of 33 technical, socioeconomic, and environmental studies in the Timbuktu region. |  | Technical, socioeconomic and environmental feasibility studies were conducted for 18 investment works in the Timbuktu Region in the Alafia, Goundam, Kondi, Arham, Binga and Tindirma municipalities. Due to insecurity, studies could not be carried out yet in the Haribomo, Hanzakoma, Gargando, Essakane and Bintagoungou municipalities. | Satisfactory (S)
|  |  | Unlocking waterways and channels in the Mopti region |  | In the Togoro-Kotia municipality located in the Tenenkou district, two channels (Diabal and Dialamba), of 1.7 km in total, were dug to irrigate 50 ha of rice plains. In addition, 12 km of channels were cleared to feed a chain of ponds. | Highly Satisfactory (HS)
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems |  | Construction of two storage and rainwater collection facilities (micro-dams) in the Mopti region. |  | Two micro-dams in the Bamba and Kendé municipalities are under construction. | Unsatisfactory (U)
|  |  | Construction of 16 groundwater access facilities (wells and boreholes) |  | Two groundwater access facilities were constructed in the Timbuktu Region, and fourteen are under construction in the Mopti region. In terms of use, seven facilities will be used for fruit and vegetable production by women, and the nine others will provide drinking water to the population. Each installation comprises a water tower, a solar pumping system, and a supply network as needed. | Marginally Satisfactory (MS)
|  |  | Restoration of 6 backwaters and 5 ponds |  | A total of five fish ponds were restored in the Timbuktu region. As for the backwaters in the Mopti region, three are being restored, two were restored and one has not started yet. | Satisfactory (MS)
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practiced by 20 local communities |  | Training and equipment of small farmers and elected officials with appropriate adaptive technologies |  | 561 beneficiaries including 541 small farmers and 20 elected were trained in the use of weather applications. 45 small farmers were trained in the use of multifunctional seed drills and equipped with 45 seed drills. All villages within the project intervention area in Mopti and Timbuktu were equipped with rain gauges. | Highly Satisfactory (HS)
|  |  | Distribution of three improved seed varieties to agro-pastoralists |  | 6 seed varieties totalling 4,480 kg were distributed to 671 small farmers during the experimental phase.These varieties are as follow: Korobalen and Wulibalé (cowpea), Diakoumbé and Seguifa (Sorghum), Berico and apollon (corn). This year, the agricultural season was marked by the low and early rainfall that led to a poor harvest for traditional varieties. Contrarily, improved cowpea varieties showed good results and small farmers are planning to use the seeds for the next season. | Highly Satisfactory (HS)
|  |  | Introduction of 5 market gardening perimeters for women |  | In the Mopti region, 6 market gardening perimeters out of a total of eight are under development to enable women to grow fruits and vegetables. This work will be completed by the end of March 2018. In the Timbuktu region, one market gardening perimeter of 1.5 ha was built for 110 women from the village of Dialloubé. | Highly Satisfactory (HS)
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change |  | Training municipal tree-nurserymen in 8 communes |  | 176 tree-nurserymen were trained on seedling production and nursery management techniques in the 8 Mopti municialities. These tree-nurserymen were provided with plant pots and watering cans to practice in their respective villages. | Highly Satisfactory (HS)
|  |  | Introduction of 8 municipal tree-nurseries in the Mopti region |  | 8 tree-nurseries were introduced and the production of seedlings is expected to start for the May 2018 season. The project will sign a Memorandum of Understanding with the Mopti water and forestry department to supervise the tree-nurserymen trained in plant production and their maintenance. | Highly Satisfactory (HS)
|  |  | Training 250 small farmers on agroforestry practices adapted to climate change |  | 200 farmers are able to use resilient agroforestry techniques. | Highly Satisfactory (HS)
|  |  | Contribution of agroforestry parks in the project area to carbon sequestration |  | The average amount of carbon sequestered by agro-forestry parks totals 69.29 t / ha in the Kendé municipality, 23.92 t / ha in Bamba commune and 15.09 t / ha in the Dangol-Boré municipality. | Highly Satisfactory (HS)
| Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities |  |  |  | A total of 285 women were provided with small equipment and seedlings to grow 4 ha, including 175 women from the village of Gomitogo in the Mopti region and 110 women from the village of Dialloubé in the Timbuktu region. | Marginally Satisfactory (MS)
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) |  | Training for 100 elected officials in 20 municipalities on climate change management |  | A total of 267 municipal councillors - including 36 women from the 20 communal councils and 40 people from civil society, as well as 20 women from the Mopti and Timbuktu regions - have been trained on climate change management. | Highly Satisfactory (HS)
|  |  | PDESC updated |  | The recruitment process for consulting firms to conduct the revision of the PDESCs for the 9 municipalities in the Mopti region is underway. | Unsatisfactory (U)
|  |  | Support of local communication networks for the dissemination of climate and agro-meteorological data |  | Daily information were broadcasted in the Mopti and Timbuktu regions. MoUs were signed with the six (6) most popular local radios in the 20 municipalities of the program's area of intervention. | Highly Satisfactory (HS)
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) |  | Training of small farmers and elected officials on climate change and metereological variations |  | A contract for disseminating climate and agrometeorological information was signed with most popular local radio stations in 6 of the targeted districts. | Unsatisfactory (U)
|  |  | Sharing results achieved by the programme |  | All reports and photos of the investment works are available on the project website (www.pacvmt-mali.org). A video of the reception of the two water supply systems for the villages of Dialloubé and Feindoukaina was realized. This video was screened during the second session of the steering committee held on November 24, 2018; | Highly Satisfactory (HS)
| Output 3.3 Local institutional capacity strengthened in 20 communities in establishing micro-credit schemes, cereal banks etc. and in managing |  | Introduction of a micro-credit initiative |  | The recruitment process for an international micro-credit specialist to establish the reference situation for existing micro-credits (list of micro-credits per municipality, functioning and constraints) and devise a micro-credit model adapted to the requirements of climate change is under way. | Unsatisfactory (U)
| Project Management Costs |  | Updating project indicators and targets |  | The interim report is available | Highly Satisfactory (HS)
|  |  | Organisation of field monitoring missions |  | During 2017, the national unit carried out five field missions: • a mission to identify possible synergies with the OMVF for the clearing of channels in the Faguibine system area; • four missions to Mopti, including a mission to define the roles and responsibilities of the actors involved in the execution of the investment work and three investment monitoring missions. | Highly Satisfactory (HS)
|  |  | Organisation of the second session for the steering committee |  | The second session of the steering committee was held on November 30th, 2017 and recommendations were made as follows: 1- Restart the appointment process for members of the steering committee - particularly from the Ministry of Energy and Water; 2- Invite a representative of the Mayors for each region to the different sessions of the steering committee; 3- Organize an extraordinary steering committee meeting as soon as possible to review the Targets and Indicators Review Report, the Mid-Term Evaluation Report and the possible no-cost extension of the project to ensure the completion of the project activities; 4- Entrust project management to municipalities in accordance with the program document; 5- Organize field missions for the members of the steering committee and associate 3 members of the steering committee to site visits on a rotating basis. | Highly Satisfactory (HS)
|  |  | Conduct mid-term evaluation |  | A consultant team was selected by UNDP to conduct the mid-term review. Currently the consultants are in the field for data collection. The interim report will be available by the end of March 2018. | Satisfactory (S)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Boubacar Sidiki Dembélé
| Email: | Boubacarsdembele@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Apart from the delay in execution of investment works for diverse reasons, including:delay in the award of contracts due to lengthy national procedures, difficulties in registering some companies, the inaccessibility of some areas during the rainy season and the insecurity, the activities were carried out satisfactorily.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Output 1.1: Water infiltration, storage and flow in the Faguibine System improved through the rehabilitation and opening up to 50 km silted channels and obstructed ponds |  | In the Togoro-Kotia municipality in the Tenenkou district, 50 ha of rice plains are now irrigated thanks to the digging of two canals in Diabal and Dialamba.This is expected to greatly enhance agricultural production. In addition, 12 km of channels were cleared to supply water to a chain of ponds, including in the municipality of Dangol-Boré, and protect some villages against flooding. |  |  | Satisfactory (S)
| Output 1.2: Water access to 20 vulnerable communities enhanced by the rehabilitation of water canals and distribution plan for multiples users including climate resilient water management systems |  | Out of the 16 planned water supply systems, 2 were completed and 14 are in progress. These basic water supply systems will enable 6 715 women to grow fruits and vegetables for food diversification, generate increased income and enable about 6 403 inhabitants to benefit from drinking water; the completion of 5 ponds and 3 backwaters facilitates the development of fish farming and improves biodiversity, namely crocodiles and different species of fish. |  |  | Unsatisfactory (U)
| Output 2.1: Climate-resilient fisheries and agro- pastoral practices and technologies e.g. drought- and disease-resistant varieties introduced and, integrated crop-livestock production systems etc. practised by 20 local communities |  | Agricultural production was supported to address the risks posed by climate change and was improved thanks to the granting of 4 480 kg of improved seeds to 671 small farmers. In addition, small farmers and elected officials were trained on climate applications to take into account weather forecasts as part of agricultural planning. In addition, about 260 women were supported and now farm 6 ha of vegetables to increase their income and improve family nutrition. |  |  | Satisfactory (S)
| Output 2.2: Conservation and restoration practices e.g. conservation agriculture, agroforestry etc. introduced in 20 local communities for forest ecosystem resilience to climate change |  | Farmer capacity building in agroforestry practices adapted to climate change will improve agricultural production through the protection and conservation of land and trees. |  |  | Satisfactory (S)
Output 2.3: Dry-season gardening activities by women improved for food and income diversification in 20 local communities
| Output 3.1. The knowledge and capacity of community improved to integrate climate risk management in economic, social and cultural development plans (ESCDP) |  | A total of 267 communal councillors, including 36 women from the 20 municipal councils, and 40 people from civil society, including 20 women from the Mopti and Timbuktu regions, were trained in climate change management. This training improved the understanding of elected officials on the causes and consequences of climate change to improve communal planning and development. |  |  | Satisfactory (S)
| Output 3.2: 100 community actors trained to manage climate change hazards and in income-generating activities (IGA) |  | The creation of the website enabled good practices and lessons learned dissemination for further replication. |  |  | Satisfactory (S)
| Output 3.3 Local institutional capacity strengthened in 20 communities in establishing micro-credit schemes, cereal banks etc. and in managing |  | It is slow to get off the ground. Directions and gidance was given to the project team to speed up the process of setting up microcredits and cereal banks to benefit women and young people. |  |  | Highly Unsatisfactory (U)
| Project Management Costs |  | Follow-up missions took place as usual and helped improve the quality of the work through instructions and guidance given to companies and monitoring agencies. In addition, the ordinary steering committee provided five recommendations, most importantly regarding the extension of the project and the municipal project management initiative to accelerate investments in both regions. The consultant recruitment process is underway for the mid-term evaluation. |  |  | Satisfactory (S)
[5 empty] | Overall Rating | Marginally Satisfactory (MS)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | United Nations Development Programme (UNDP)
Oumar TAMBOURA
| Email: | oumar.tamboura@undp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Under output 1.1, the MoU with the OMVF is taking some time to be implemented in order to clear 20 km of channels in the Faguibine system. Most of the investments initiated to access water under output 1.2 were not completed. The design of market gardening perimeters is also underway for output 2.1 which determines women's capacity building under output 2.3. The capacity building of elected officials and small farmers was carried out in accordance with the established programme (output 2.2, 3.1 and 3.3). In addition, it should be noted that microcredit and cereal banks (output 3.3) have not yet benefited women and young people. Insecurity across the programme's intervention area - especially in the Timbuktu municipalities - coupled with the lengthy procurement process are limiting factors for the effective implementation of programme activities. What's more, the programme was launched in March 2016 - 5 months late - and the timely implementation, as planned in the project document, seems to be compromised. All these arguments prompted the program team to request a project extension that will be analysed during the extraordinary steering committee. All these considerations limit the achievements of the project and justify the "Marginally Satisfactory" rating.
National Executive Entity (AEDD)
[5 empty] | Overall Rating | Satisfactory (S)
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Environment and Sustainable Development Agency (AEDD)
Boureima CAMARA
| Email: | bouricamara@gmail.com, Tel: +22366805756
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Despite the security situation, the programme made progress in terms of investments and capacity building for the population and elected officials. Currently, about 40% of planned investments are completed. Better results could have been obtained if the arrival of the rainy season had not hindered the execution of some investment works, such as the construction of micro-dams in the Bamba and Kendé municipalities, and the introduction of market gardening perimeters in the Togoro-Kotia municipality. Landscaping of the market gardening perimeters and construction of basic water supply systems have also been delayed due to the rainy season. At the institutional level, the project is an experiment in terms of governance of environmental issues related to climate change.The Mali Government has put in place a montoring and evaluation framework through the Multilateral Cooperation Division for projects and programmes, and meetings are held on an annual basis. This will facilitate better monitoring of programmes and projects in the field. Low disbursement rate (33.17%): after two years of implementation, this is due mainly to the problem of insecurity and also the lengthy procurement process. The duration of the programme should therefore be extended by 18 months from November 28th, 2018 to May 28th, 2020. Nevertheless, considering the achievements of the project to date, the rating is "satisfactory".
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Indicators towards Outcome 1 | % increase in functional waterways and channels in the targeted communes | Only about 15% of the waterways and channels are functional i.e. 25 functional channels and waterways | 2 functional channels (Dialamba and Dialal) and 1 functional waterway (water supply for the Boré pond) | Functional waterways and channels increased by about 40 %
| Km increase of cleared water channel | Currently about 50 km of the water channels are cleared | 13.7 km of cleared water channels of which 1.7 km is used to irrigate 50 ha of rice plains in the Togoro-Kotia municipality, and 12 km will supply several ponds - particularly the Boré pond - and protect some neighbouring villages from flooding due to water runoff | 70 km of cleared water channel
Indicators towards Outcome 2 | Number of market gardening perimeters of at least 0.5 Ha each managed by women. | There are presently few market gardens and no community fish farms. | 6 market gardening perimeters out of the 8 planned for 2017 are being developed in the Mopti region. One market gardening perimeter is already functional in Timbuktu in the Dialloube village. | 20 market gardening perimeters of at least 10 ha.
| Number of community fish farms. | There are presently no community fish farms. | 5 community fish ponds are set up in Tindirma | 20 community fish farms established
| Number of municipal tree nurseries containing local functional species. | Few communities benefit from community managed tree nurseries | 8 municipal tree nurseries were established in the Mopti region and 176 people from community nurseries were trained in seedling production techniques and equipped with small equipment (plant pots and watering cans) to promote communty reforestation activities | At least fifteen community tree nurseries.
Indicators towards Outcome 3 | Number of local councilors trained in institutional management of climate change | No local councilors are trained in institutional management of climate change | 274 local councilors, including 38 women, and 40 civil society participants, including 20 women, were trained in climate change management. | Training of 100 local councilors and 40 civil society participants - including 40 women
| Number of PDESC revised to include climate change management | Just about 6 PDESC currently include climate change management | The recruitment of consulting firms to start PDESC revision is underway. | 20 local community plans will be developed to include climate change management

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Currently, insecurity constitutes the major threat to the project execution and, more broadly, to the development of municipalities in North and central Mali. Most actors involved in the area of development in Mali are faced with the problem of limited mobility for their teams. The government of Mali and partners such as MINUSMA, the G5 Sahel security force, and also the Barkhane security force, work hard each day to protect the various populations. MINUSMA always briefs its teams undertaking field missions, and ensures that team members are covered by security clearance. The project is also in constant contact with the mayors to coordinate the activities undertaken ant the local level. Synergies with specific partners - including with OMVF - are being established to implement specified activities.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Yes, there was a delay in project implementation for most of the activities. The main reasons are: (i) the lengthy process for company recruitment which in turn leads to a delayed start of contracts, (ii) agricultural works need to be paused during the rainy season, therefore, activities that are not finished by the end of the dry season will need to be continued after the rainy season, and the delays in restarting the activities once the dry season starts further delay the activities, (iii) the prevailing climate of insecurity prevented the realisation of technical studies on investment in the municipalities of Gargando, Essakane, Bintagoungou, Haribomo and Hanzakoma. Such insecurity also hinders field monitoring missions and business relocation. Some of the companies have been robbed or were victim of terrorist attacks. Measures taken to counteract such problems include (i) a simpler approach to procurement through use of communal circuits, i.e. getting the municipality to choose service providers and to sign the contracts which the AEDD then approves. This experiment has enabled the project to build 8 communal nurseries in three months - whereas since September 2017 some company procurement conducted via the DGMP circuit to oversee capital works in Timbuktu are still pending; (ii) a better planning of the field activities, to finish the activities before the end of the dry season. This will include a better coordination with UNDP to access ressources (iii) cooperation with the OMVF to clear 20 km of conduits belonging to the Faguibine system
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | (i) For outcome 2, the indicator "Number of dry season vegetable gardens managed by women, and community fish farms set up" is broken down into two reformulated indicators as follow: 1) "Number of market gardens measuring at least 0.5 ha each managed by women", with a target of 20 market gardens, and, 2) " number of fish farms organized and managed by the communities " with a target of 20 fish farms. (ii) For outcome 3, the following indicators and targets were revised: 1) "Number of local advisors trained in the management of institutional climate change" with a target of 100 local councillors and 40 civil society participants including 40 women; and, 2) "number of revised Social and cultural economic development Programmes (PDESC) to include climate change" with a target of 20 PDESC.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | At present, there are nine market gardening perimeters (1 in Timbuktu and 8 in Mopti) to be exclusively managed by women and which are almost completed. The programme has also built the capacitys of 58 women in institutional climate change management and provided 285 women with better quality seeds and small market gardening tools. In Timbuktu, the introduction of six market gardening perimeters will be effective by April 2018 as the company recruitment process is underway. Usually, women do not have land, but thanks to the programme, the men allocated land ranging from 0,5 to 2 ha depending on the village - or 11.25 ha.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | 81072 (PIMS 4789)
Implementing Entity | PNUD
Type of implementing entity | MIE
Country | Mali |  | 33.33% | 42751.6
Region | Africa | [7 empty] | 34.51%
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion Performance de la cible à l'achèvement |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 213758 |  |  | Total | 213758 | 140000 | 73758 | Total | 213758 | 109820 | 51755 | Total
|  | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries
|  | % of Youth beneficiaries | 49% | 49% | 49% | % of Youth beneficiaries | 49% | 49% | 49% | % of Youth beneficiaries | 49% | 49% | 49% | % of Youth beneficiaries
0
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats. Résultat 1: exposition réduite aux dangers et menaces liés au climat | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis. | Number of targeted stakeholders. Nombre d'intervenants ciblés |  | Hazards information generated and disseminated. Renseignements sur les dangers générés et disséminés | Overall effectiveness. Efficacité globale | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 6 | Drought | 4: Effective | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated. Rendement 1,1 évaluations des risques et des vulnérabilités réalisées et actualisées | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments. | No. of projects/programmes that conduct and update risk and vulnerability assessments. Nombre de projets/programmes qui mènent et actualisent les évaluations des risques et des vulnérabilités | Sector | Scale. Echelle | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Water management | National | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 1 | Food security | National | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 2 | Multi-sector | National | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 2 | Disaster risk reduction | National | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems. Extrants 1,2 groupes de population ciblés couverts par des systèmes de réduction des risques adéquats | Core Indicator 1.2: No. of Early Warning Systems. | No. of adopted Early Warning Systems. Nombre de systèmes d'alerte précoce adoptés | Category targeted | Hazard. Danger | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 2 | 3: Dissemination and communication | Geographical coverage | National |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 703 |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 2: Monitoring and warning service | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses. 2: renforcement de la capacité institutionnelle de réduire les risques associés aux pertes socioéconomiques et environnementales induites par le climat | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased. | Number of staff targeted. Nombre d'employés ciblés |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Multi-sector | 1: No capacity | Total | 100 | Disaster risk reduction |  | Total | 294 | Multi-sector | 3: Medium capacity | Total
|  | % of female targeted | 0% |  |  | % of female targeted | 10% |  |  | % of female targeted | 14% |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events. Rendement 2,1 renforcement des capacités des centres et réseaux nationaux et sous-nationaux pour répondre rapidement aux phénomènes météorologiques extrêmes | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events. | Total staff trained. Total du personnel formé | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 10% | Private |  | 400 | 5% | Private |  | 570 | 4% | Private
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks. | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Disaster risk reduction | 1: No capacity | Public | Local | Disaster risk reduction | 4: High capacity | Public | Local | Disaster risk reduction | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes. Résultat 3: renforcement de la sensibilisation et owernship des processus d'adaptation et de réduction des risques climatiques | Indicator 3.1: Increase in application of appropriate adaptation responses. | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Disaster risk reduction |  | 30% |  | Disaster risk reduction
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities. Résultats 3: groupes de population ciblés participant à des activités de sensibilisation à l'adaptation et à la réduction des risques | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate . | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0% | 0% | 1: Aware of neither |  | 3000 | 50% | 4: Mostly aware |  | 1132 | 2% | 4: Mostly aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets. Résultat 4: accroissement de la capacité d'adaptation au sein des services et des biens d'infrastructure pertinents du secteur du développement | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate. | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Multi-sector | Local | 2: Partially responsive (Lacks most elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened. | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability. Résultat 4: services du secteur du développement vulnérable et ressources d'infrastructure renforcées en réponse aux impacts du changement climatique, y compris la variabilité | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change. | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 25 | Community |  | Water management | 40 | Community |  | Water management
|  | 0 | Community |  | Agriculture | 60 | Community |  | Agriculture
|  | 0 | Community |  | Food security | 10 | Community |  | Food security
|  | 0 | Community |  | Multi-sector | 20 | Community |  | Multi-sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress. | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated. | Natural asset or Ecosystem (type). Patrimoine naturel ou écosystème (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas Résultat | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets. | No. of targeted households. Nombre de foyers ciblés | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 2: Limited improvement |  | 3000 | 50% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods . | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies. | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income. | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agriculture |  |  | 2000
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Agribusiness |  |  | 500
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Forestry |  |  | 300
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 0 | Fishing |  |  | 200
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy. | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
5: All (Fully integrated)
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks. | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced. | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
Note on E27: Microsoft: SAP, Mali-Météo, PAM
Note on D30: Microsoft: Omvf
Note on D32: Microsoft: Pam
Note on D34: Microsoft: Mali femmes et Asnac
Note on D36: Microsoft: Sap et PGRCI
Note on D40: Microsoft: Sap et Météo
Note on D43: Microsoft: PGRCI
Note on N54: Microsoft: Applications météorologiques et gestion des chnagements climatiques
Note on L57: Microsoft: Formation paysans sur les applications climatiques et formation de la société civile sur la gestion des changements climatiques
Note on L65: Microsoft: Formation en agroforesterie et semences améliorées et semoirs multifonctionnelles et production de plants en pépinières et foration surla gestion des changements climatiquesMicrosoft:
Note on D78: Microsoft: Debloquage de canaux, aménagement de mares, adduction d'eau sommaire
Note on D79: Microsoft: Périmètres maraichers, pisciculture, conservation des eaux et sols, production de pâturage, introduction de semences améliorées, agroforesterie adpatée au changements climatiques, Reboisement
Note on D80: Microsoft: Banque de céréales
Note on D81: Microsoft: Micro-crédits

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.