## Reliquats-au-31-déc (hidden)
9.6446
| Composantes |  | Intitule | Montant délégué (1) | Montant redéployé (1i) | TYPE | Montants engagés (2) |  | Reliquat (1)-(2) | Montant payé | % Paie. | Reste à payer
[7 empty] | Mnt marchés | int. moratoires | [6 empty] | 1466635.14 | 152067.887
| Fonds du projet | C1+C4 | Convention de partenariat ABH GZR | 9270000 |  | Convention | 9270000 |  | 0 | 9270000 | 100% | 0
270000 |  |  | Convention de partenariat ORMVAO | 2750000 |  | Convention | 2750000 |  | 0 | 2750000 | 100% | 0 | Marché 10/15 | STE AS2T INGENIERIE | 1452114 | 150562.2644
22290000 |  |  | Convention de partenariat ORMVAT |  | 2000000 | Convention | 2000000 |  | -2000000 | 2000000 | 100% | 0 |  | STE ECTA2E | 1494000 | 154905.2092
|  | C2 | Contribution aux projets de partenariat | 1700000 |  | 11 Conventions | 1500000 |  | 200000 | 1500000 | 100% | 0
|  | C5 | Formations | 1600000 |  | Marché 10/15 | 1452114 | 14521.14 | 133364.86 | 733116 | 50.49% | 733519.14 | Marché 11/15 | STE NEGOVERT | 394344 | 40887.5099
|  | C5 | Activité 5.1.1.2 (Particip. rencontres & forums) | 100000 |  |  | 0 |  | 100000 |  | - - | 0 |  | STE WINZIZ | 304800 | 31603.1511
| Assistance technique (ANDZOA) |  |  | 6000000 |  | Marché 05/16 | 4881600 | 48816 | 1069584 |  | 0% | 4930416
| Etude EIES/PGES |  |  | 1800000 |  | Marché 06/16 | 960000 | 9600 | 830400 |  | 0% | 969600 | Marché 05/15 | STE NOVEC | 9313920 | 965712.6681
[14 empty] | GPT CLINIQUE PLANTES & CADINOV | 4881600 | 506148.1053
| Frais d'exécution | Equipement | Acquisition de matériel de transport | 1040000 |  | Dérogation PG | 1040000 |  | 0 | 1040000 | 100% | 0 |  | STE H2S INGENIEURIE | 4982400 | 516599.5411
|  |  | Frais d’acquisition de matériel informatique | 200000 |  | BC N°22/15 | 143340 |  | 56660 | 143340 | 100% | 0
|  |  | Frais d’acquisition photocopieurs, multimédia et fourniture de bureau | 370000 |  | Marché 11/15 | 223752 |  | -22916.62 | 208089.32 | 93% | 15662.68
[6 empty] | BC N°19/15 | 97800 |  |  | 97800 | 100% | 0 | Marché 6/16 | STE YOURI CONSULTING | 840000 | 87095.2984
[6 empty] | BC N°20/15 | 22141.06 |  |  | 22141.06 | 100% | 0 |  | STE 3 ANGLES ETUDES | 1301520 | 134947.9437
[5 empty] | 22072.36 | BC N°12/16 | 22072.36 |  |  | 0 | 0% | 22072.36 |  | GPT ID GREEN LAND & ALPHA | 1380000 | 143085.133
[5 empty] | 27251.2 | BC N°13/16 | 27151.2 |  |  | 27151.2 | 100% | 0 |  | STE DMIC | 1164000 | 120689.1991
|  |  | Frais de publication et communication | 151500 |  | BC N°17/15 | 143088 |  | 8412 | 143088 | 100% | 0 |  | STE CAPITAL RH | 1197996 | 124214.0703
|  | Travel expenses | Frais de déplacements | 100000 |  |  | 87600 |  | 12400 | 87600 | 100% | 0 |  | STE NOVEC | 960000 | 99537.4838
|  |  | Frais de transport à l’intérieur du royaume | 100000 |  | CV 1729/15 | 100000 |  | 0 | 100000 | 100% | 0 |  | STE TEAM MAROC | 1149960 | 119233.4634
|  |  | Frais d’entretien et carburant | 100000 |  | CV 3905/15 | 100000 |  | 0 | 100000 | 100% | 0 |  | STE CID | 1198740 | 124291.2118
|  |  | Restauration, et hébergement | 150000 |  | CV 05/15 | 100100 |  | 158 | 100100 | 100% | 0 |  | GPT STE SELF & STE AREMO | 1152000 | 119444.9806
[5 empty] | 49742 | CV 04/16 | 49742 |  |  | 0 | 0% | 49742
| Total |  |  | 25431500 | 2099065.56 | -- | 24970500.62 | 72937.14 | 388062.24 | 18322425.58 | 73.38% | 6721012.18
25043437.76
[13 empty] | BC 13/15 | STE ETERCOS | 32767.2 | 3397.4632
[14 empty] | STE LIBRAIRIE IQRAE | 28230 | 2927.0241
[14 empty] | STE AMANOUN DAOUD | 50712 | 5258.0676
[14 empty] | STE NEGOVERT | 27151 | 2815.1481
[13 empty] | BC 12/15 | STE ETERCOS | 22072.36 | 2288.57
[14 empty] | STE ERRACHIDIA GRAPHIQUE | 24451.8 | 2535.2819
[14 empty] | STE OMEGA SUD | 23016.6 | 2386.4734
[13 empty] | BC 17/15 | STE ARCO PRINT | 144840 | 15017.7179
[14 empty] | STE IMPREMERIE ALJBOUN | 148680 | 15415.8678
[14 empty] | STE MEDAGRAPH PUB | 143088 | 14836.062
[13 empty] | BC 22/15 | STE ETERCOS | 265075.2 | 27484.29 | 169315.2 | 434390.4
[14 empty] | STE AXANET SERVICES | 219772.8 | 22787.1162 | 147028.8 | 366801.6
[14 empty] | STE NSIB | 143340 | 14862.1906 | 216780 | 360120
[14 empty] | STE RESO2DAY SERVICES | 280674 | 29101.6497 | 177024 | 457698
[13 empty] | BC 19/15 | STE AYOU ALI ELEC | 97800 | 10140.3812 | 222000 | 319800
[14 empty] | STE RESO2DAY SERVICES | 101460 | 10519.8678 | 223680 | 325140
[14 empty] | STE NEGOVERT | 106800 | 11073.5451 | 223800 | 330600
[13 empty] | BC 20/15 | STE ETERCOS | 22141.06 | 2295.6931
[14 empty] | STE WINZIZ | 23568 | 2443.6452
[14 empty] | STE OMEGA SUD | 22240.2 | 2305.9724
[14 empty] | STE TAFILALET BUREAU | 25843.2 | 2679.5491
[14 empty] | STE NEGOVERT | 38419.02 | 3983.4714
[14 empty] | STE DOUSDATE | 25926 | 2688.1342
[13 empty] | CV 05/15 | STE OISIS MIR | 100100 | 10378.8564
[14 empty] | STE WINZIZ | 114906 | 11914.0147
[14 empty] | STE OMEGA SUD | 123849 | 12841.2686
[13 empty] | CV 04/15 | STE OISIS MIR | 49742 | 5157.4933
[14 empty] | STE TRIOMUS | 52283 | 5420.9565
[14 empty] | STE ALAOUI NAJIB | 58674 | 6083.6066
[13 empty] | CV 1729/15 | SNTL | 100000 | 10368.4879
[13 empty] | CV 3905/15 | SNTL | 100000 | 10368.4879

## Reliquats-au-31-déc USD (hidden)
9.6446
Composantes |  | Intitule | Montant délégué (1) | Montant redéployé (1i) | TYPE | Montants engagés (2) |  | Reliquat (1)-(2) | Montant payé | % Paie. | Reste à payer
[6 empty] | Mnt marchés | int. moratoires
Fonds du projet | C1+C4 | Convention de partenariat ABH GZR | 961158.8282 |  | Convention | 961158.8282 |  | 0 | 961158.8282 | 100% | 0
|  | Convention de partenariat ORMVAO | 285133.4172 |  | Convention | 285133.4172 |  | 0 | 285133.4172 | 100% | 0
|  | Convention de partenariat ORMVAT | 0 | 207369.758 | Convention | 207369.758 |  | -207369.758 | 207369.758 | 100% | 0
| C2 | Contribution aux projets de partenariat | 176264.2943 |  | 11 Conventions | 155527.3185 |  | 20736.9758 | 155527.3185 | 100% | 0
| C5 | Training | 165895.8064 |  | Marché 10/15 | 150562.2644 | 1505.6226 | 13827.9194 | 76013.0437 | 50.49% | 76054.8433
| C5 | Activité 5.1.1.2 (Particip. rencontres & forums) | 10368.4879 |  |  | 0 |  | 10368.4879 |  | - - | 0
Technical Assitance for ANDZOA |  |  | 622109.2739 |  | Marché 05/16 | 506148.1053 | 5061.4811 | 110899.6876 |  | 0% | 511209.5863
EIES/PGES |  |  | 186632.7822 |  | Marché 06/16 | 99537.4838 | 995.3748 | 86099.9235 |  | 0% | 100532.8587
Frais d'exécution | Equipement | Acquisition of transport equipment (vehicles) | 107832.2741 |  | Dérogation PG | 93316.1537 |  | 14516.1205 | 93316 | 100% | 0.15365
|  | Acquisition of computer hardware | 20736.9758 |  | BC N°22/15 | 14862.1906 |  | 5874.7852 | 14862.1906 | 100% | 0
|  | Acquisition of photocopiers, multimedia and office supplies | 38363.4052 |  | Marché 11/15 | 23199.699 |  | -2376.107 | 21575.716 | 93% | 1623.9831
[5 empty] | BC N°19/15 | 10140.3812 |  |  | 10140.3812 | 100% | 0
[5 empty] | BC N°20/15 | 2295.6931 |  |  | 2295.6931 | 100% | 0
|  |  |  | 2288.57 | BC N°12/16 | 2288.57 |  |  | 0 | 0% | 2288.57
|  |  |  | 2825.5374 | BC N°13/16 | 2815.1689 |  |  | 2815.1689 | 100% | 0
|  | Publication and communication costs | 15708.2592 |  | BC N°17/15 | 14836.062 |  | 872.1972 | 14836.062 | 100% | 0
| Travel expenses | Travel expenses | 10368.4879 |  |  | 10368.4879 |  | 0 | 10368 | 100% | 0.4879
|  | Transportation within the Morocco | 10368.4879 |  | CV 1729/15 | 10368.4879 |  | 0 | 10368.4879 | 100% | 0
|  | Maintenance and fuel costs | 10368.4879 |  | CV 3905/15 | 10368.4879 |  | 0 | 10368.4879 | 100% | 0
|  | Catering and accommodation | 15552.7318 |  | CV 05/15 | 10378.8564 |  | 16.3822 | 10378.8564 | 100% | 0
|  |  |  | 5157.4933 | CV 04/16 | 5157.4933 |  |  | 0 | 0% | 5157.4933
Total |  |  | 2636862 | 217641.3586 | -- | 2575832.9071 | 7562.4785 | 53466.6144 | 1886527.4095 | 73.24% | 696867.9761

## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 2016
| Project Title: | Projet d’Adaptation au Changements Climatiques dans les Zones Oasiennes au Maroc PACCZO
| Project Summary: | PACCZO Project aims to help reduce the vulnerability of people and oasis agro ecosystems in Morocco to climate change by increasing the adaptive capacity of local actors, increasing the resilience of the target ecosystem and by disseminating knowledge management. Actions will include improved management of soil and water resources, as well as the use of resistant varieties of palm trees and training sessions for the stakeholders. The project objectives will be achieved through five components: - Component 1: Improving adaptive capacities of the water sector. - Component 2: Diversifying income sources and improving the living conditions of populations vulnerable to climate change. - Component 3: Improving the ecosystems’ resilience in response to climate change and variability. - Component 4: Improving stakeholder awareness though the management and exchange of knowledge. - Component 5: Strengthening the capacities of participants in the design and implementation of adaptation measures.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Agence pour Développement Agricole (ADA) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: |  | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Morocco | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Bassin Maider "area located downstream of a catchment where the availability of water resources must be protected to ensure the preservation of the drinking water supply" (Regions : Alnif, Hssia, Mssissi, Tazarine, Taghbalte, Ait Oualal, Ait Boudaoud, Nkob) Bassin Gheris "area located in the intermediary part of a catchment where water resources can still be mobilized for saving the palm groves with a potential for agricultural production" (Regions : Ferkla, Gheris, Tinjdad, Mellaab) | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2015-04-09
IE-AFB Agreement Signature Date: |  | 2015-05-14 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2015-12-14 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2018-06-30
| Terminal Evaluation Date: | 2020-12-14
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | AWPB (Annual Work Plan and Budget) 2016, Manual and the management procedures of the project, Project Brochure, Environmental and Social Management Plans, Training Reports (Strengthening capacities), First semi-annual report (Prepared by EE), Second half-yearly report (Prepared by EE), EE's Technical Assistance Reports, Project Monitoring Report n° 01 (Prepared by NIE), Project Monitoring Report n° 02 (Prepared by NIE), Audit report for the year 2015 (Prepared by NIE). | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://andzoa.ma/fr/2016/01/26/atelier-de-demarrage-du-pacczo/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: |  | Dominican Republic
| Email: |  | Ecuador
| Date: |  | Egypt
| Government DA |  | El Salvador
| Name: | Mr Mohammed NBOU | Equatoral Guinea
| Email: | nboudrm@yahoo.com / nbou@environnement.gov.ma | Eritrea
| Date: |  | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Mr Hamid FELLOUN | Fiji
| Email: | h.felloun@ada.gov.ma / hfelloun@gmail.com | Finland
| Date: |  | France
| Executing Agency |  | Gambia
| Name: | Mr Ali OUBHROU | Georgia
| Email: | oubrhou@gmail.com | Germany
| Date: |  | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [December-31-2016]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [Dec-31-2015] | 1695936
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 37479.2988
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | Compenent / Outcome | Outputs | Products | Activities | AMOUNT
| 1. Improving adaptive capacities of the water sector / Outcome 4 | Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | (1.1.1) Replenishment structures for groundwater are built | 1.1.1.1 Carry out complementary studies of groundwater recharge structures on the potential sites identified (Conv ABH). | 103684.879
|  |  |  | 1.1.1.2 Build infrastructure with the greatest potential (Conv ABH) | 463471.4091
|  |  |  | 1.1.1.3 Purchase of the follow-up equipment (piezometers). (Conv ABH) | 41473.9516
|  |  |  | 1.1.1.4 Ensure the follow-up evaluation in coordination with the HBA | --
|  |  |  | 1.1.1.5 Establish a maintenance agreement for the groundwater recharges structures. | --
|  |  | (1.1.2) Structures for perimeters protection are built | 1.1.2.1 : Carry out complete technical studies of protective infrastructure in the priority sites identified (Conv ORMVAO) | 31105.4637
|  |  |  | 1.1.2.2 : Build priority infrastructure. | 21773.8246
|  |  |  | 1.1.2.3 : Establish a maintenance agreement for perimeter protection structures | --
|  |  | (1.1.3) Feasibility studies on the exploitation of deep-water resources intended for the dried up palm groves of the Maïder basin are carried out. | 1.1.3.1 : Carry out an exploration/reconnaissance study through drilling for deepwater resources. (Conv ABH) | 207369.758
|  |  |  | 1.1.3.2 : Carry out feasibility studies to identify priority sites and their financing. (Conv ABH) | 82947.9032
|  |  | (1.2.1) Khettaras are restored | 1.2.1.1 Formalize the commitment of the beneficiaries in the restoration of the khettaras | --
|  |  |  | 1.2.1.2 Lead the works on the restoration of the khettaras (Conv ORMVAO) | 359786.5301
|  |  | (1.2.2) Seguias are restored | 1.2.2.1 Formalize the commitment of the beneficiaries in the restoration work | --
|  |  |  | 1.2.2.2 Carry out the restoration works on the irrigation water distribution networks: irrigation channels | 35252.8589
| Total of Component 1 |  |  |  | 1346866.5781
| 2. Diversifying income sources and improving the living conditions of populations vulnerable to climate change in the targeted areas / Oucome 6 | Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | (2.1.1) Conservation technics are circulated and adopted | 2.1.1.1 Carry out a study on the experiences already undertaken in the zone or in similar zones abroad. | 0
|  |  |  | 2.1.1.2 Train new farmers on the conservation techniques and promote their circulation | 0
|  |  | (2.1.2) Oasis agriculture products are developed and promoted | 2.1.2.1 Support the producers in the certification process for their products. | 0
|  |  |  | 2.1.2.2 Promotion of oasis agricultural products. | 0
|  |  |  | 2.1.2.3 Encourage research on endemic species and their uses. usages | 0
|  |  | (2.2.1) Sustainable and responsible tourism, which faces up to climate change is developed | 2.2.1.1: Support the Tourism stakeholders to make the sector more accountable | 0
|  |  |  | 2.2.1.2: Carry out a study on niche tourism products to develop. | 0
|  |  | (2.2.2) Other economic activities, particularly for youths and women, are supported and developed | 2.2.2.1: Support small-scale local economic projects | 155527.3185
|  |  |  | 2.2.2.2: Offer training adapted to the context and needs of the oasis | 0
| Total of Component 2 |  |  |  | 155527.3185
| 3. Improving the ecosystems’ resilience in response to climate change and variability / Oucome 5 | Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | 3.1.1 The fight against desertification is organized | 3.1.1.1 Carry out a study to identify the priority sites | --
|  |  |  | 3.1.1.2 Financial support for the Water and Forests Commission man-made and biological efforts | 0
|  |  |  | 3.1.1.3 Populations will be mobilized in the fight against desertification of housing and parcels of land. | --
|  |  | 3.1.2 Techniques for environmental cleanup are developed | 3.1.2.1 Study the impact of the oasis economic activities | 0
|  |  |  | 3.1.2.2: Train the stakeholders concerned on environmental cleanup techniques | 0
|  |  |  | 3.1.2.3: Support community services, which aim to protect natural resources | 0
|  |  | 3.2.1 Historic constructions are restored for new uses | 3.2.1.1: Carry out a study in order to identify the mud brick buildings to restore | --
|  |  |  | 3.2.1.2: Restore and fix up the buildings with a heritage interest | 0
|  |  | 3.2.2 Traditional techniques and materials are reused for new constructions | 3.2.2.1: Study, bearing in mind town planning, the most pertinent public building to be done in mud brick | --
|  |  |  | 3.2.2.2: Construct said building | 0
| Total of Component 3 |  |  |  | 0
| 4. Improving stakeholder awareness through the management and exchange of knowledge / Oucome 3 | Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | 4.1.1 An assessment of resources in the intermediary Gheris basin and Maider is carried out | 4.1.1.1: Implementation of a Documentation library | 0
|  |  |  | 4.1.1.2: Strengthening of the monitoring system for water resources in the project zones. (Conv ABH) | 41473.9516
|  |  | 4.1.2 local council for water dialogue is operational | 4.1.2.1: Writing of a draft Charter on water and climate change in the Oases | 0
|  |  |  | 4.1.2.2: Organization of conferences on the themes of water and climate change | 0
|  |  | 4.2.1 An awareness and communication strategy is developed | 4.2.1.1: Writing of a communication strategy | 0
|  |  |  | 4.2.1.2: « Mass » communication campaign | 0
|  |  |  | 4.2.1.3: Organization of a close out seminar | 0
|  |  | 4.2.2 A financing mechanism is implemented | 4.2.2.1 Establishing of a list of Partner-organizations for awareness actions | --
|  |  |  | 4.2.2.2 Management of call for projects on awareness. | 0
| Total of Component 4 |  |  |  | 41473.9516
| 5. Strengthening the capacities of participants in the design and implementation of adaptation measures / Oucome 2 | Output 2: Strengthened capacity of national and subnational centres and networks to respond rapidly to extreme weather events | 5.1.1 the managers of public service are informed on the issues of climate change and introduced to adaptability measures for the main sectors | 5.1.1.2: Participation in scientific meetings and forums | 0
|  |  |  | 5.1.1.1: Conduct climate change training modules (AO 14/2015) | 152067.887
|  |  | 5.1.2 Oasis beneficiaries are trained on innovative adaptability measures | 5.1.2.1: Conduct adaptation training modules (AO 14/2015) | 0
|  |  |  | 5.1.2.2: Organizing trips and internships | 0
|  |  | 5.2.1 The participants (operators and beneficiaries) are trained in the designing and financing of projects | 5.2.1.1: Conduct modules on the project cycle (AO 14/2015) | 0
|  |  |  | 5.2.1.2: Conduct training modules on project financing (AO 14/2015) | 0
|  |  | 5.2.2 : The participants (operators and beneficiaries) are trained on the implementation and joint management of projects. | 5.2.2.1: Conduct training modules on the participatory approach (AO 14/2015) | 0
|  |  |  | 5.2.2.2: Conduct training modules in conflict management and mediation (AO 14/2015) | 0
| Total of Component 5 |  |  |  | 152067.887
| TOTAL |  |  |  | 1695935.7352
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming (2017) reporting period | Compenent / Outcome | Outputs | Products | Activities | AMOUNT | Est. Completion Date
| 1. Improving adaptive capacities of the water sector / Outcome 4 | Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | (1.1.1) Replenishment structures for groundwater are built | 1.1.1.1 Carry out complementary studies of groundwater recharge structures on the potential sites identified | 0
|  |  |  | 1.1.1.2 Build infrastructure with the greatest potential | 528792.8828 | dec-2017
|  |  |  | 1.1.1.3 Purchase of the follow-up equipment (piezometers). | 7880.0508 | dec-2017
|  |  |  | 1.1.1.4 Ensure the follow-up evaluation in coordination with the HBA | 0
|  |  |  | 1.1.1.5 Establish a maintenance agreement for the groundwater recharges structures. | 0
|  |  | (1.1.2) Structures for perimeters protection are built | 1.1.2.1 : Carry out complete technical studies of protective infrastructure in the priority sites identified | 67395.1713 | dec-2017
|  |  |  | 1.1.2.2 : Build priority infrastructure. | 493540.024 | dec-2017
|  |  |  | 1.1.2.3 : Establish a maintenance agreement for perimeter protection structures | 0
|  |  | (1.1.3) Feasibility studies on the exploitation of deep-water resources intended for the dried up palm groves of the Maïder basin are carried out. | 1.1.3.1 : Carry out an exploration/reconnaissance study through drilling for deepwater resources. | 388818.2962 | dec-2017
|  |  |  | 1.1.3.2 : Carry out feasibility studies to identify priority sites and their financing. | 115090.2157 | dec-2017
|  |  | (1.2.1) Khettaras are restored | 1.2.1.1 Formalize the commitment of the beneficiaries in the restoration of the khettaras | 0
|  |  |  | 1.2.1.2 Lead the works on the restoration of the khettaras | 670841.1671 | dec-2017
|  |  | (1.2.2) Seguias are restored | 1.2.2.1 Formalize the commitment of the beneficiaries in the restoration work | 0
|  |  |  | 1.2.2.2 Carry out the restoration works on the irrigation water distribution networks: irrigation channels | 299649.3003 | dec-2017
| Total of Component 1 |  |  |  | 2572007.1082
| 2. Diversifying income sources and improving the living conditions of populations vulnerable to climate change in the targeted areas / Oucome 6 | Output 6: Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | (2.1.1) Conservation technics are circulated and adopted | 2.1.1.1 Carry out a study on the experiences already undertaken in the zone or in similar zones abroad. | 49768.7419 | 6 months
|  |  |  | 2.1.1.2 Train new farmers on the conservation techniques and promote their circulation | 72579.4153 | 6 months
|  |  | (2.1.2) Oasis agriculture products are developed and promoted | 2.1.2.1 Support the producers in the certification process for their products. | 103684.879 | dec-2017
|  |  |  | 2.1.2.2 Promotion of oasis agricultural products. | 46658.1955 | dec-2017
|  |  |  | 2.1.2.3 Encourage research on endemic species and their uses. usages | 99537.4838 | 5 months
|  |  | (2.2.1) Sustainable and responsible tourism, which faces up to climate change is developed | 2.2.1.1: Support the Tourism stakeholders to make the sector more accountable | 25921.2197
|  |  |  | 2.2.1.2: Carry out a study on niche tourism products to develop. | 99537.4838 | 6 months
|  |  | (2.2.2) Other economic activities, particularly for youths and women, are supported and developed | 2.2.2.1: Support small-scale local economic projects | 103684.879 | dec-2017
|  |  |  | 2.2.2.2: Offer training adapted to the context and needs of the oasis | 51842.4395 | dec-2017
| Total of Component 2 |  |  |  | 653214.7376
| 3. Improving the ecosystems’ resilience in response to climate change and variability / Oucome 5 | Output 5: Vulnerable ecosystem services and natural resource assets strengthened in response to climate change impacts, including variability | 3.1.1 The fight against desertification is organized | 3.1.1.1 Carry out a study to identify the priority sites | 0
|  |  |  | 3.1.1.2 Financial support for the Water and Forests Commission man-made and biological efforts | 51842.4395 | dec-2017
|  |  |  | 3.1.1.3 Populations will be mobilized in the fight against desertification of housing and parcels of land. | 0
|  |  | 3.1.2 Techniques for environmental cleanup are developed | 3.1.2.1 Study the impact of the oasis economic activities | 19700.127 | 6 months
|  |  |  | 3.1.2.2: Train the stakeholders concerned on environmental cleanup techniques | 103684.879 | dec-2017
|  |  |  | 3.1.2.3: Support community services, which aim to protect natural resources | 20736.9758 | dec-2017
|  |  | 3.2.1 Historic constructions are restored for new uses | 3.2.1.1: Carry out a study in order to identify the mud brick buildings to restore | 0
|  |  |  | 3.2.1.2: Restore and fix up the buildings with a heritage interest | 0
|  |  | 3.2.2 Traditional techniques and materials are reused for new constructions | 3.2.2.1: Study, bearing in mind town planning, the most pertinent public building to be done in mud brick | 0
|  |  |  | 3.2.2.2: Construct said building | 0
| Total of Component 3 |  |  |  | 195964.4213
| 4. Improving stakeholder awareness through the management and exchange of knowledge / Oucome 3 | Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | 4.1.1 An assessment of resources in the intermediary Gheris basin and Maider is carried out | 4.1.1.1: Implementation of a Documentation library | 29550.1905 | 6 months
|  |  |  | 4.1.1.2: Strengthening of the monitoring system for water resources in the project zones. | 0
|  |  | 4.1.2 local council for water dialogue is operational | 4.1.2.1: Writing of a draft Charter on water and climate change in the Oases | 29550.1905 | 5 months
|  |  |  | 4.1.2.2: Organization of conferences on the themes of water and climate change | 15552.7318 | dec-2017
|  |  | 4.2.1 An awareness and communication strategy is developed | 4.2.1.1: Writing of a communication strategy | 29550.1905 | 6 months
|  |  |  | 4.2.1.2: « Mass » communication campaign | 15552.7318 | 6 months
|  |  |  | 4.2.1.3: Organization of a close out seminar | 0
|  |  | 4.2.2 A financing mechanism is implemented | 4.2.2.1 Establishing of a list of Partner-organizations for awareness actions | 0
|  |  |  | 4.2.2.2 Management of call for projects on awareness. | 36289.7076 | dec-2017
| Total of Component 4 |  |  |  | 156045.7429
| 5. Strengthening the capacities of participants in the design and implementation of adaptation measures / Oucome 2 | Output 2: Strengthened capacity of national and subnational centres and networks to respond rapidly to extreme weather events | 5.1.1 the managers of public service are informed on the issues of climate change and introduced to adaptability measures for the main sectors | 5.1.1.2: Participation in scientific meetings and forums | 19700.127 | dec-2017
|  |  |  | 5.1.1.1: Conduct climate change training modules | 27994.9173 | dec-2017
|  |  | 5.1.2 Oasis beneficiaries are trained on innovative adaptability measures | 5.1.2.1: Conduct adaptation training modules | 26958.0685 | dec-2017
|  |  |  | 5.1.2.2: Organizing trips and internships | 57026.6834 | dec-2017
|  |  | 5.2.1 The participants (operators and beneficiaries) are trained in the designing and financing of projects | 5.2.1.1: Conduct modules on the project cycle | 20736.9758 | dec-2017
|  |  |  | 5.2.1.2: Conduct training modules on project financing | 20736.9758 | dec-2017
|  |  | 5.2.2 : The participants (operators and beneficiaries) are trained on the implementation and joint management of projects. | 5.2.2.1: Conduct training modules on the participatory approach | 27994.9173 | dec-2017
|  |  |  | 5.2.2.2: Conduct training modules in conflict management and mediation | 27994.9173 | dec-2017
| Total of Component 5 |  |  |  | 229143.5826
| TOTAL |  |  |  | 3806375.5926
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Institutionnal risk / The project is likely to suffer the consequences of inadequate staffing and a lack of qualified personnel, which affects some of the project stakeholders, particularly certain rural local authorities. | Levl: Moderate ; State : Controlled | State : Controlled Thanks to the great experience of ANDZOA in the management of semilar projects, this risk is well controlled. At present, the project is carried out in a good institutional conditions thanks to the externnal "Technical Assitance" and the EE personnel.
Institutionnal risk / The participatory approach promoted by the project runs the risk of being reduced or even diverted by local interest groups. | Levl: Moderate ; State : Controlled | State : Controlled The project is managed in a participatory approach which avoids any kind of intercations of interests or resistance to the actions of the project
Technical risk / In light of past experiences showing the difficulties faced by similar projects covering geographically remote and disadvantaged areas, risks relating to the sustainability of actions still remain | Levl: Moderate to substantial State : Controlled | State : Controlled The terms of reference of the projects clearly specify the difficulties associated with the work and the services requested. The Technical Assitance and the EE teams and staff conduct field visits to monitor achievements.
Technical risk / The groundwater refill structures could affect the access to resources in certain downstream sites | Levl: Moderate ; State : Controlled | State : Controlled The actions of the project are programmed according to the recommendations of the ESMP (Environmental and Social Management Plan)
Environomental risk / Adverse climate conditions could have a negative effect on the success of the project. | Levl: Moderate to substantial State : Controlled | State : Controlled The project area has experienced significant adaptations to climate change in the past. The project aims to improve resilience to climate change
Financial risk / The project activities risk being delayed by the circuits for transferring funds. | Levl: Moderate State : Controlled | State : Controlled Both NIE and EE intervened to the Paymaster to accelerate payments
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Project Objective: Help reduce the vulnerability of people and oasis agro ecosystems in Morocco to climate change by increasing the adaptive capacity of local actors, increasing the resilience of the target ecosystem and by disseminating knowledge management.
| Inception Phase of the Project completed |  | Inception Phase activities commenced on 14, December 2015. Within this phase, recruitment of the Technical Assistance for both NIE & EE, the inception workshop were held. The various activities of the project components have been started |  | Inception Phase commenced on 14 December 2015. Three partnerships were signed with a total amount of 1,453,662 USD (ABH, ORMVAO, ORMVAT). Technical assistance was recruited for both NIE & EE. The amount invested in the first year for all the components is 1.695.936 USD. (About 984 people received training on the subject related to the project (19% women). Works has begun) | S
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses
| Strengthening the capacities of participants in the design and implementation of adaptation measures |  | About 1744 of Officials and Oasis beneficiaries (whose ability to collectively manage climate change adaptation project) has been strengthened. |  | More than 984 people (oasis beneficiaries) plus officials (from different services) have benefited from trainings related to climate change adaptation, 35% of beneficiaries (cooperatives & agricultural water management associations). The managers of public service are informed on the issues of climate change and introduced to adaptability measures for the main sectors. Participants (operators and beneficiaries) are trained on innovative adaptability measures, are trained in the designing and financing of projects and are trained on the implementation and joint management of projects. | S
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes
| Improving stakeholder awareness though the management and exchange of knowledge |  | The population has awarned of climate change. |  | In accordance with the specific agreement signed between the NIE and the EE on the execution of the PACCZO project, the ADZOA has performed wide media coverage of the project through several means of communication. - A large media has been assured. - More than 9 press releases in adittion to workshops with admenistrations and population. - The PACCZO Project participation at the International Workshop on Integrated and Sustainable Management of oasis Territories held in Zagora on April 12-15, 2016. - The Implementing Entity (ADA) presented the PACZZO project is “Adaptation Fund Side Event – parallel activity to the Cop22”. | S
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure asset
| Improving adaptive capacities of the water sector |  | Development of water sectors' services responsive to evolving needs from changing and variable climate. |  | Both 1) works on "regulation of ground and surface water" and 2) "vulnirabel infrastrastructure allowing the improvement of water efficiency - Khettara & Saguia" has been started. It is too early to evaluate the results knowing the delays in starting the works. - Work in progress at 2 sites / 4 structures / 6 perimeters - Work in progress (Works not completed to measure efficiency) | S
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress
| Improving the ecosystems’ resilience in response to climate change and variability |  | Number of oases that have reduced the threats to their ecosystem and preserved their heritage |  | These activities have not been scheduled for the year 2016 | NA
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas
| Diversifying income sources and improving the living conditions of populations vulnerable to climate change in the targeted areas |  | Percentage of households with diversified income sources and sustained climate-resilient alternative livelihoods. |  | The EE launched a "call for projects" (or Call for Proposals) at the end of September 2015 to propose development projects to be funded by the project PACCZO. The “Call for Projects” concerned Organizations working in the Sustainable Development in municipalities of Errachidia, Zagora and Tinghir Provinces (within the action area of the ANDZOA). The “Call for projects” aims to diversify income sources and improve the living conditions of vulnerable people to climate change in the target areas. 31 candidates were received and 11 projects were selected (an amount of 155.527 USD). | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | ALI OUBARHOU
| Email: | oubrhou@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Even though there was a delay in large-value payment (at paymasters), the project follows the planned schedule. The population has awarned of climate change. About 1744 of Officials and Oasis beneficiaries (whose ability to collectively manage climate change adaptation project) has been strengthened and the population has awarned of climate change. Both 1) works on "regulation of ground and surface water" and 2) "vulnirabel infrastrastructure allowing the improvement of water efficiency - Khettara & Saguia" has been started. 11 projects were selected (of populations vulnarable to climate change) and funded in order to diversify income resources and living conditions of this population.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Project Objective: Improve the adaptability of the Oasis populations to the impacts of climate change
| Inception Phase of the Project completed |  | Inception Phase activities commenced in December 2015. Within this phase, recruitment of the Technical Assistance (for NIE & EIE), the inception workshop and partnership agreements were held. |  | The start-up workshop took place on 14 December 2015. Three partnerships were signed with a total amount of 1,453,662 USD (ABH, ORMVAO, ORMVAT). Technical assistance was recruited (for both NIE & EIE). The works in different components have been started. Approximately 984 people received training on the subject related to the project (19% women). The rehabilitation works has already begun. | S
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses
| Strengthening the capacities of participants in the design and implementation of adaptation measures |  | About 1744 of Officials and beneficiaries trained with reinforced capacities in adaptation project management. |  | The trainings have been an important success. More than 984 people have benefited from trainings related to climate change adaptation, 35% of beneficiaries (cooperatives & agricultural water management associations). 35% of public service officials. 30% of the population representatives. | S
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes
| Improving stakeholder awareness though the management and exchange of knowledge |  | The population has awarned of climate change. |  | More than 9 press releases in adittion to workshops with admenistrations and population. | S
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure asset
| Improving adaptive capacities of the water sector |  | Development of water sectors' services responsive to evolving needs from changing and variable climate. |  | - Work in progress at 2 sites / 4 structures / 6 perimeters - Work in progress (Works not completed to measure efficiency) (It is early to evaluate the results knowing the delays in starting the work) | S
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress
| Improving the ecosystems’ resilience in response to climate change and variability |  | Number of oases that have reduced the threats to their ecosystem and preserved their heritage |  | These activities have not been scheduled for the year 2016 | NA
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas
| Diversifying income sources and improving the living conditions of populations vulnerable to climate change in the targeted areas |  | Percentage of households with diversified income sources and sustained climate-resilient alternative livelihoods. |  | 11 production units (project holder) receives funding (a total of 155.527 USD). | S
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | HAMID FELLOUN
| Email: | h.felloun@ada.gov.ma / hfelloun@gmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
Project execution was carried out in accordance with 1) Annual Work Plan and 2) Budget and the Project Procurement Plan pre-established. Despite the delay in the start of the project, all the components of the project were started. The project partners are all aware of the problems of climate change and are actively involved in the success of the project. The amounts of the agreements signed with the partners (ABH, ORMVAO and ORMVATF) is 2.583.931 USD. Parteners participated with 44% (1.130.269 USD). The rate of participation in trainings was significant. Stakeholders are very aware of the project's objectives. The project is well publicized and field work has begun
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | All stakeholders (officials and oasis beneficiaries) have demonstrated their interest in the objectives of the project, which ensures outcome achivements.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Delay in large-value payment (agreement with partners) Measures : Intervention direcet at paymasters
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | No changes were made to project outputs
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | The women were present during all the training sessions. The women showed great interest toward project's objectives. Projects proposed for funding (to improve sources of income) all include women.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?

## Results Tracker-exemple (hidden)
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity
Type of implementing entity
Country | Morocco
Region
Sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Project Indicators
PROJECT Indicators
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator |  |  | Indicator | Baseline | Progress since inception | Target for Project End
Project Objective: Improve the adaptability of the Oasis populations to the impacts of climate change |  |  | Number of oases inhabitants vulnerable to the adverse effects of climate variability and change | There are no concrete adaptation measures currently being implemented in the project areas | 0 | By the end of the project, at least 4000 of the most vulnerable inhabitants in the project area will benefit from the proposed activities to cope with their vulnerability to climate change
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Output 4 : Vulnerable developement sector services and infrastructure assets strenthned in response to climate impacts, inculding variability | Ccomponent 1. Improving adaptive capacities of the water sector | Development of water sectors' services responsive to evolving needs from changing and variable climate. | There is evidence on the shortages by basin being updated | 0 | At least 10% of households secure their access to water for drinking and irrigation.
|  | (1.1) Improved joint regulation of ground and surface water through new sustainable hydraulic and protective structure management | Efficiency of mobilization | Available studies indicate the rate water mobilization by basin | 0 | Approximately 2 million m3
|  | (1.1.1) Replenishment structures for groundwater are built | Number of recharge structures | In the intervention sites, structures for exclusively recharging groundwater do not exist. | Work in progress in 4 | 4 structures
|  | (1.1.2) Structures for perimeters protection are built | Number of irrigated perimeters | Flooding reduces the rate of floodwater mobilization | 2 perimeters (location Tazarine) | 6 perimeters
|  | (1.1.3) Feasibility studies on the exploitation of deep-water resources intended for the dried up palm groves of the Maïder basin are carried out. | Feasibility studies by site | No deep borehole is used in the project zone to reduce the shortage of drinkable water | 2 Sites | 2 sites
|  | (1.2) Vulnerable infrastructure allowing the improvement of water distribution efficiency are restored | Agricultural irrigation efficiency (%) | Efficiency ratios of the traditional networks are below 50% according to APP (Agency for the Partnership for Progress) | 0 | 70% efficiency
|  | (1.2.1) Khettaras are restored | Area irrigated (hectares) | Khettaras to be restored are identified. According to the 2005 PDRT, the restoration will allow the khettaras to pass from 2 to 5 L/s. | Early to mesure irrigated Area / Work in progress | 200 Ha
|  | (1.2.2) Seguias are restored | Area irrigated (hectares) | SMH networks to be renovated are identified | Early to mesure irrigated Area / Work in progress | 200 Ha
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Output 6: targeted individual and community livelihood strategies strenthened in relation to climate change impacts, includin variability | Component 2. Diversifying income sources and improving the living conditions of populations vulnerable to climate change in the targeted areas | Percentage of households with diversified income sources and sustained climate-resilient alternative livelihoods. | The poverty rate in the zone remains especially high | 0 | At least 20% of families have diversified and improved their livelihoods through more resilient activities.
|  | (2.1) Improved livelihoods of families due to the development of more resilient small scale agriculture | VA/ha | 37000dh/ha (according to APP) | 0 | 20% increase for an objective of MAD 45000 per ha
|  | (2.1.1) Conservation technics are circulated and adopted | Number of trained farmers | The project’s target areas have not received significant training | 344 farmers (19% women) | 800 farmers. At least 400 women.
|  | (2.1.2) Oasis agriculture products are developed and promoted | Number of products that are certified and are represented in fairs/trade shows | Experiments near the project zones have successfully developed attractive local agricultural sectors (argan, saffron, cheese, olive oil, and cactus). | 0 | 4
|  | (2.2) Developed non-agricultural economic activities help increase the resilience of the Oasis population | Number and type of economic units (existing or new) that develop in a manner adapted to climate change. | Experiments near the project zones have successfully developed high value non-agricultural sectors | 11 units | At least 20 economic units
|  | (2.2.1) Sustainable and responsible tourism, which faces up to climate change is developed | Number of tourism units that develop in a manner adapted to climate change. | The potential of responsible tourism is under-valued in the project’s implementation zones (compared to the Dadès and Draa valleys). |  | At least 5 tourism units
|  | (2.2.2) Other economic activities, particularly for youths and women, are supported and developed | Projects financed Trainings exist | The existing VSE support programs do not particularly support innovative adaptation projects. | 11 projects (5 women projets) | 20 projects, at least 50% managed by women 2 trainings
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Output 5 : Vulnerable developement sector services and infrastructure assets strenthned in response to climate impacts, inculding variability | Component 3. Improving the ecosystems’ resilience in response to climate change and variability | Number of oases that have reduced the threats to their ecosystem and preserved their heritage | The MEA/FAO/UNESCO/PACO studies have sounded the alarm | Activities not yet started (activités prévue pour la deuxième année) | At least 4 oases
|  | (3.1) Threats reducing the value of Oasis ecosystems are taken into account by municipalities | Number of oases that have reduced the threats to their ecosystem. | Consultation workshops have stressed the importance of the degradation of ecosystems |  | At least 4 oases participate in a dynamic for protecting the ecosystems.
|  | 3.1.1 The fight against desertification is organized | Protected hectares | The fight against desertification is already well underway by the Water and Forests Commission, which has however reached a maximum given their current means. |  | 40 ha
|  | 3.1.2 Techniques for environmental cleanup are developed | Number of stakeholders trained | Techniques for cleanup are nearly inexistent in the oasis zones. |  | 400 trained individuals (at least 50% women) with a treatment device installed.
|  | (3.2) Preserved and Promoted Heritage | Number of solicitations for restoring post-project | Few landowners are currently interested in restoration or construction because they fear that their home will become a museum. |  | There are solicitations.
|  | 3.2.1 Historic constructions are restored for new uses | Restored and used buildings | Restored buildings have a low-valued museum function (empty kasbah) |  | 2 restored buildings used for a new purpose
|  | 3.2.2 Traditional techniques and materials are reused for new constructions | New buildings using traditional materials | Currently, only high-end tourism structures use these techniques for new constructions. |  | 2 new constructions
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Output 3 : Targeted population groups participating in adaptation and risk reduction awarness activities | Component 4. Improving stakeholder awareness though the management and exchange of knowledge | Part of the targeted municipal populations are educated on climate change issues | The population has heard of climate change but it remains an abstract concept that has yet to be connected to changes in the area. | 0 | 60% of households in the project zones
|  | (4.1) Organized public debate on water and climate change | The importance of communicating on the issue of climate change | Informal debates exist but there is a lack of data and areas for expression needed to reinforce the message. | 0 | Media coverage
|  | 4.1.1 An assessment of resources in the intermediary Gheris basin and Maider is carried out | Access to documentation | Several studies and documentation are unavailable | Work in progress / Establishment of a database on water ressources | The existence of a documentation library Study on accessible water resources
|  | 4.1.2 local council for water dialogue is operational | Number of thematic conferences organized by the Local Council on water | Debates on climate change issues remain national and centralized | 3 regional thematic conferences | 6 regional thematic conferences
|  | (4.2) Supported and developed local initiatives for communication | Population of targeted groups are educated on the overall issues relating to climate change | Communication/awareness campaigns are not targeted | 0 | Targeted content of communication/awareness campaigns
|  | 4.2.1 An awareness and communication strategy is developed | Number of mass communication campaigns | The project intervention zones have not had any mass communication activities | More than 9 press releases | 4 mass campaigns
|  | 4.2.2 A financing mechanism is implemented | Number of funded initiatives for raising the awareness of educated children, emigrants, and tourists | The project intervention zones have not had any targeted awareness activities | Activities not yet started | 50 funded awareness projects
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Output 2 : Strengthened of national and sub-national centers and networks to respond rapidly to extreme weater events | Component 5 Strengthening the capacities of participants in the design and implementation of adaptation measures | No. of Officials and beneficiaries trained with reinforced capacities in adaptation project management. | The project intervention zones have not had any capacity building activities | 984 people (640 framrs + 344 public services) | 240 officials 400 oasis beneficiaries, at least 50% women
|  | (5.1) Consolidated and developed adaptive capacities for climate change | Number of officials and beneficiaries whose adaptability to climate change has been strengthened. | There are major knowledge disparities between stakeholders | 344 | 240 public service officials 400 oasis beneficiaries, at least 50% women
|  | 5.1.1 the managers of public service are informed on the issues of climate change and introduced to adaptability measures for the main sectors | Number of training workshops and participants | Local and public officials have sectorial knowledge and are not well versed in the multi-sectoral effects of climate change. | 6 workshops | 12 training workshops (20 people/workshop) 50 participants for scientific conferences and beneficiary awareness forums
|  | 5.1.2 Oasis beneficiaries are trained on innovative adaptability measures | Number of training workshops and travel/internships | The oasis beneficiaries are up to date on adaptation techniques and experiments conducted in neighboring countries. | 6 workshops (640 people - 19% women) | 20 workshops, (20 people/workshop) 15 trips (at least 50% women)
|  | (5.2) Strengthened coordinated management capacities for climate change projects | Number of officials and beneficiaries whose ability to collectively manage climate change adaptation projects has been strengthened | The stakeholders are not familiar with the dialogue process in managing development projects | 344 | 240 public service officials 400 oasis beneficiaries (at least 50% women)
|  | 5.2.1 The participants (operators and beneficiaries) are trained in the designing and financing of projects | Number of training workshops being designed and funding of projects | The stakeholders are not aware of financing and monitoring-evaluation mechanisms for adaptation projects | 6 workshops (640 people - 19% women) | 12 workshops on the project cycle (20 people/workshop) 12 workshops on project financing (40 people/workshop) (at least 50% women)
|  | 5.2.2 : The participants (operators and beneficiaries) are trained on the implementation and joint management of projects. | Number of training workshops on the implementation and the coordinated management of projects and the number of participants | The stakeholders are not familiar with coordinated management mechanisms | 6 workshops (640 people - 19% women) | 12 workshops on the participatory approach (20 people/workshop) 12 workshops in conflict management and mediation (12 people/workshop) (at least 50% women)

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | ADA
Type of implementing entity | NIE
Country | Morocco
Region | Africa |  | * The reference situation (Baseline information) is underway. A bid is underway (launched by ANDZOA) whose objective is to determine "the baseline information"
Sector | Agriculture
|  | TBD |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total |  |  |  | Total | 40000 |  |  | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries | 50% |  |  | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | TBD |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total | 1794 | Multi-sector | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
[7 empty] | 50% | Private
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
[6 empty] | Public | Local | Multi-sector | 3: Medium capacity
|  | TBD |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
[6 empty] | 60% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage in targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
[6 empty] | 40000 | 50% | 4: Mostly aware
|  | TBD |  |  |  | Target performance at completion |  |  |  | Target performance at completion |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
[6 empty] | Water management | Local | 5: Highly responsive (All defined elements )
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
[6 empty] | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
[6 empty] | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
[7 empty] | Departmental |  | Agriculture
[7 empty] | Departmental |  | Water management
[7 empty] | Departmental |  | Food security
|  | TBD |  |  |  | Baseline information |  |  |  | Baseline information |  |  |  | Baseline information
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | TBD |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
[6 empty] | 1140 | 50%
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Tourism-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Handicrafts
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
other
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
[6 empty] | 3 | Adaptation strategies | Water management | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
Agricultural-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
Tourism-related
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
Handicrafts
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
other
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste