## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | May 1st, 2018 - April 30th, 2019
| Project Title: | ENHANCING RESILIENCE OF COMMUNITIES TO CLIMATE CHANGE THROUGH CATCHMENT BASED INTEGRATED MANAGEMENT OF WATER AND RELATED RESOURCES IN UGANDA
| Project Summary: | The “Enhancing Resilience of Communities to Climate Change through Catchment Based Integrated Management of Wate and Related Resources in Uganda” Project was designed to support the Uganda’ Government efforts to implement Integrated Water Resources Management (IWRM) through Catchment Management Planning and increase the resilience of communities to the risk of floods and landslides in Maziba, Aswa and Awoja Catchments. The project is implemented by the Sahara and Sahel Observatory (OSS) and executed by the Ministry of Water and Environment (Uganda) in close collaboration with the GWP Eastern Africa and the Uganda Country Water Partnership (CWP). The overall goal of the project is to increase the resilience of communities to the risk of floods and landslides of Awoja, Maziba and Aswa Catchments through promoting catchment based integrated, equitable and sustainable management of water and related resources. The Specific objectives of the project are to: • Increase the resilience of ecosystems by supporting the development and implementation of catchment based and community driven actions for sustainable management of natural systems including forests, wetlands, riverbanks and lakeshores in Awoja, Aswa and Maziba catchments • Increase the resilience of agricultural landscapes by supporting stakeholders and communities in the development and implementation of sustainable water harvesting, soil bio-physical and flood control structures. • Increase resilience of other livelihood systems by promoting new and off-farm activities through facilitating credit and market access • Build the capacity of extension services and institutions at local, catchment, water management zone and national level to better support local stakeholders. Higher level capacity building to integrate climate change adaptation in national and sector-wide development plans and strategies. The project is multi-sectoral and multi-disciplinary and is being implemented in a very participatory and integrated manner right from the national level to the catchment, district and the community levels.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | UGA/RIE/Water/2015/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | Sahara and Sahel Observatory (OSS) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Regional Implementing Entiy | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Republic of Uganda | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Awoja catchment located in Kyoga Basin in the Eastern Aswa catchment located in Aswa Basin in the Northern Maziba catchment located in Kagera Basin in the South Western | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | July 05, 2016
IE-AFB Agreement Signature Date: |  | November 20, 2016 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | May 05, 2017 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | 2019
| Terminal Evaluation Date: | 2021
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
|  | Inception workshop report, Supervision mission Aide-memoire, Press releases, Brochures, Poster, Links to some brochure and articles with refernce to the project: a) https://www.gwp.org/en/GWP-Eastern-Africa/WE-ACT/News/oss-and-the-government-of-uganda-sign-an-agreement-for-the-implementation-of-eureccca-project-in-uganda/ b) https://www.newvision.co.ug/digital_assets/84288dbb-1101-4bdc-b613-3e71113c3024/37-MIN-OF-WATER-_Victoria.pdf c) https://fr.scribd.com/document/379272083/Uganda-Climate-Finance-Policy-Brief-May-2018 | Czech Republic
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | http://www.oss-online.org/en/enhancing-resilience-communities-climate-change-through-catchment-based-integrated-management-water | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Dr Callist Tindimugaya | Dominican Republic
| Email: | Callist.tindimugaya@mwe.go.ug callist_tindimugaya@yahoo.co.uk | Ecuador
| Date: | March 09, 2017 | Egypt
| Government DA |  | El Salvador
| Name: | Mr Keith Muhakanizi | Equatoral Guinea
| Email: | keith.muhakanizi@finance.go.ug | Eritrea
| Date: | November 20, 2016 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | Sahara and Sahel Obervatory | Fiji
| Email: | boc@oss.org.tn | Finland
| Date: | November 20, 2016 | France
| Executing Agency |  | Gambia
| Name: | Ministry of Water and Environment (MWE) | Georgia
| Email: | mwe@mwe.go.ug | Germany
| Date: | November 20, 2016 | Ghana
| Executing Agency |  | Greece
| Name: |  | Grenada
| Email: |  | Guatemala
| Date: |  | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to [30th April 2019]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of [30th April 2019] | 663138
Add any comments on AF Grant Funds. (word limit=200) | The disbursement to date amounts US $ 663,138 from May 2017 to April 2019 and represents 9% of the total funding. The Payments to date have reached US $489,355.24. They represent around 6.8 % of the Grant total amount. The commitments at the end of May 2019 amounted to US$ 1 180,561.22 and US$ 228,037.17 has been paid up to end of April 2019. The low disbursement can be explained by: (i) the difficulty in developing and finalizing acceptable documents conditioning the first disbursement as stipulated by the Grant Agreement, that lasted 6 months (dated on October 2018), (ii) the long procurement process that in some cases requires specific clearances from Ministry of justice according to the national procurement regulations, (iii) the under-staffing of project management unit that has been addressed recently, (iv) the delay in developing a detailed and updated action plan for the catchment level for a better planning of the activities. Efforts are being made to bring project activities and the disbursement schedule in line with the project plan. In fact one of the major corrective measures undertaken was the development of a commun Action plan with OSS support during the second supervsison missionto detail all the required steps to implement the activities. This action plan take into account the procurement delays and the contraints related to communities seasonal availability.
INVESTMENT INCOME | 3577.78
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | 5806.4
| Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | 16776.86
| Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) | 59529.32
| Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | 7956
| Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | 0
| Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | 0
| Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | 0
| Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | 0
| Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | 0
| Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | 0
| Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported | 0
| Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | 24122.65
| Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established | 4980.18
Output 3.2.1 Good practices and lessons that influence policies and practices documented
| Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | 41942.61
| 4.1 Monitoring the Implementation of the Project | 4361.59
| 4. 2 Executing Entity Budget | 227330.37
| TOTAL | 392805.98
| Implementing Fees | 113538
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | 124693.6 | May 2020
| Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | 151223.14 | May 2020
| Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) | 80000 | May 2020
| Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | 0 | N/A
| Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | 663000 | October 2020
| Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | 208000 | October 2020
| Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | 976900 | January 2021
| Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | 602500 | January 2021
| Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | 928080 | January 2021
| Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | 489000 | October 2020
| Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported | 54250 | October 2020
| Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | 180877.35 | July 2020
| Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established | 647019.82 | December 2020
| Output 3.2.1 Good practices and lessons that influence policies and practices documented | 165000 | March 2021
| Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | 24104.03 | May 2020
| 4.1 Monitoring the Implementation of the Project | 10000 | May 2020
| 4. 2 Executing Entity Budget | 270413.39 | December 2020
| TOTAL | 5575061.33
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized? | Co-financing is non applicable to the project, but exists.
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) | The in-kind support and contribution that the MWE is offering to the project is as follows: 1. The MWE staff participate in project implementation but their salaries are paid by government and not by the project 2. 9 staff (3 Engineering Assistants, 3 Accountants and 3 drivers) have been specifically recruited to support EURECCCA Project and their salaries are paid by government 3. Due to recruitment of additional staff to support EURECCCA project, MWE had to procure additional office equipment and materials for these staff (computers, office furniture etc) 4. Taxes for the consultancy services are paid by government due to limited funds under those items in the project 5. Additional vehicles have been provided for use in implementation of project activities (the 3 vehicles procured under the project are not enough to carry out the various field activities in the different areas including supervision) 6. Additional project supervision costs are covered by MWE due to limited funds under the project to facilitate the supervision of the project by the various entities and individuals.

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Management risks
Competing interests between different stakeholders regarding access and use of water and other natural resources | Low | Multi-stakeholders’ forum has been established to agree and understand how the different areas complement each other. These fora are conducted by the local council (LC 3 and LC 5) authorities who are in charge of ensuring a continuous communication with communities
High expectations by communities and local government for quick investments on the ground | Medium | Awareness raising programs like stakeholder workshops, newspaper articles, IEC materials and Radio talk shows have been used to communicate the policy-practice and the deliverables of the project. Most of the consultancies have been finalised and yet to start implementation on ground.
Mismatch between the catchment and administrative boundaries | Low | Promote catchment-based management and development The project teams have continued to explain to the stakeholders that water does not follow administrative boundaries and that’s why the committees formed are for catchments not per district.
Sectoral bias by various stakeholders | Low | Multi sectoral meetings have been held to allow for full participation by all stakeholders for implementation. This has been achieved through the launch workshops, stakeholder forum meetings and steering committee meetings. Participatory approach is being adopted involving all the stakeholders for implementation, and strengthening country water partnership (several meetings with the Catchment Management committees has been conducted)
Inadequate baseline data/resource potential | Low | A baseline assessment was conducted in the 3 catchments. Field visits have been carried out to gather more information before project intervention starts concretly .
Low technology adoption rate by communities | Low | Sensitization sessions has been organized during the CMCs meeting to promote new technologies and their added value to the communities livelihoods. Demonstration centers and sites were indentified and selected to carry out trainings to improve capacity of communities to adopt to new technology.
Local communities with limited participation and willingness to promote project initiatives | Low | Sensitization meetings has promoted and improved communities willingness to contribute to project initiatives. The implication of CMCs in the project as a main stakeholder is important in prmomtoting particpation of communities in project activities at all levels.
Collaboration amongst the relevant technical institutions | Low | The relevant institutions have been involved and MoUs are being developed with the relevant technical institations as the Demonstartion centers (NARO) and GWPEA.
Project resource capture | Low | Catchment Management Structures (CMCs and SCMCs) have been established. These will ensure that a transparent and participatory process is followed in selecting beneficiaries according to agreed criteria : Nurseries, Women groups, concrete adaptation sites communities.
Elite capture of the project | Low | A strong project management structure which encourages transparency and stakeholders’ participation from project preparation to implementation, reporting/ communicating, monitoring and evaluation has been put in place. For example establishment of the Project Steering Committee, Catchment Management Committees and Sub Catchment Management Committees which are now functional. This has improved ownership and follow up of the project interventions. A close follow up of the project execution by the OSS that consists on ensuring the application of the national regulations and procedures for procurement, audit and accountability.
Project financial management | Medium | The project has ensured clear separation of roles and strengthened accountability and auditing. The project is also following the auditing system of the Ministry. Separate bank accounts have also been opened for the different catchments. The team has been reinforced by the recruitment of new accountants in the Head Office and the 3 CMZ this will help to improve the financial reporting and the application of the national procedures.
Delay in project implementation due to government bureaucracy, long and inefficient procurement processes. | Medium | This risk was considered during the project designing and measures were put in place to mitigate the impacts. However, in the implementation of these measures, new challenges appeared which affected the project: 1. Under-staffing of project management unit The project is mainstreamed in the Ministry of Water and Environment structure and so it had been assumed that execution of project activities would be undertaken only by the existing Ministry staff. It has to be noted that the Project Management Unit establishment was one of the entry into force conditions of the grant. The submitted composition of the team seemed to be correct, given that additional support from other Ministry staff had been proposed and expected. Therefore the recruitment of management support staff did not seem necessary, since several project activities were going to be carried out by external consultancy. However, due to the multi-disciplinary and demanding nature of the project, as well as the fact that the existing ministry staff have many other assignments, project execution became slower than expected 2. Time to get special treatment from the Procurement and Disposal Unit and the Contracts Committee of MWE: A lot of time was spent trying to get the Procurement and Disposal Unit and the Contracts Committee of MWE to understand the project, its philosophy and operational modalities so that it can be given special treatment during the procurement process. A lot of explanations and convincing therefore had to be done and this caused a lot of delays. However, after the Procurement and Disposal Unit and the Contracts Committee fully understood the project and its operational modalities they started giving special treatment to the project and the delays were hence reduced. 3. Negotiations with the MWE when offers are greater than the available budgets: During the procurement of some consultants, the submitted costs of doing the assignments were above what was available in the project budget. As such, the project team engaged the Procurement and Disposal Unit of MWE and OSS on the best way to handle the challenge. This took a long time with back and forth emails, letters and consultations. 4. Legal registration of community organizations: Some of the stakeholder groups that the project proposed to work with such as tree nursery operators, did not have the required legal documents to contractually be engaged on various assignments. The Ministry had to first help them with the registration processes which took some time. The following mitigation measures have been put in place to compensate for the lost time during procurements: 1. Recruitement of aditionnal support staff: 20 staff have been hired to work on the project; 11 paid using the project funds and 9 paid using the Government of Uganda funds. The following staff have been hired; 1. Accountant; 1 Monitoring and Evaluation Officer; 3 Capacity Development Officers; 3 Social Development Officers; 3 Technical Support Officers; 3 Engineering Assistants; 3 Accounts Assistants and 3 Drivers. The hired staff have helped in fast-tracking execution of the activities that were lagging behind. 2. Decentralization of procurement process: While initially all the procurements used to be handled together by the team at the centre and in the 3 Water Management Zones, currently procurements are handled concurrently at the centre and in the 3 Water Management Zones. Cross cutting procurements are handled at the centre while catchment specific procurements are handled in each Water Management Zone. This enables the teams at the center and in the 3 water management zones to follow up closely their assigned procurements and ensure that they are concluded in a timely manner. 3. Using of framework contracts: Framework contracts have been signed with various service providers and whenever inputs or supplies are needed a call off order is issued and services or supplies are provided as opposed to initiating a procurement each time services or supplies are needed. This approach saves time on procurement and enables the project team to only focus on implementation of activities on the ground.
Environmental and social risks
Delineation of degraded areas for rehabilitation may shift the pressure to non-degraded areas and some conservation measures (if not carefully selected) may aggravate degradation | Medium | -Areas for rehabilitation have been carefully selected and population is being involved in the rehabilitation activities -Alternative income generation activities for livelihood and diversification to reduce pressure on natural resources are being promoted and introduced. -Sensitization sessions on the risks of natural resources degradation and their impact on the revenues are organized.
Water harvesting, storage and irrigation facilities may aggravate some diseases such as malaria | Low | Some health officers have been involved in the stakeholder forums held so far and we expect to involve them in raising awareness on malaria and other water related diseases . Still Raising awareness through community based health workers on these issues. Environmental and Social assessment of the rehabilitation and restoration action plans are being conducted by consultancy firms.
Introduction of drought-tolerant crop varieties may contribute to loss of local varieties by farmers | Medium | Drought-tolerant crop varieties has been identified by the communities for the 3 catchments to ensure the ownership and the willingness to plant. The national forest and agriculture departments has been involved to select the final species to be planted and introduced based on the communities proposed species. This approach will ensure the conservation of local crop varieties. In addition sensitization meetings on complementarity of the selected varieties, the local and the introduced ones are being organized.
Upstream activities may have negative environmental impact downstream and cause social conflict with downstream users | Low | Coordination and conflict resolution mechanisms at catchment and sub catchment level as well as WMZ level have been strengthened and will continue to be strengthened through various stakeholder forums and formation of committees. Environmental and Social assessment of the rehabilitation and restoration action plans are being conducted by consultancy firms and meetings with the CMCs will be organised to sensitize them on the potential impacts and mitigation measures .
Promoting indigenous forest trees to replace plantation forests (e.g. Eucalyptus in Maziba) may cause conflict | Low | The Directorate of Environmental Affairs which is in charge of forestry activities is involved in the project activities and will provide guidance and reasons on using other species which are preferred to Eucalyptus trees. Proper consultations of all stakeholders in reforestation measures (forestry experts) to get good information about advantages of replacing Eucalyptus trees by indigenous ones.
Natural Resource Use related Conflicts | Low | All stakeholders have been included in consultation at local level and existing local conflict resolution mechanism strengthened. A conflict resolution mechanism was integrated in catchment-based management structures
Stabilization after long time of armed armed Conflict in Aswa Catchment | Low | The conflict in the area is perceived as a passed conflict that has been overcome. Many projects in the region work on the stabilization of the area, though recent development interventions are also there.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Communities not being able to appreciate the issue of adopting other tree species from the eucalyptus | Medium | The Communities have been sensitized about the importance of adopting other tree species other than eucalyptus. They have also been involved in the selection of the tree species for planting.
Some communities having to derive their livelihood from river buffer zones and wetlands | High | Awareness raising on the disadvantages and effects of farming in wetlands and river buffer zones is being done by the local council (LC 3 and LC 5) authorities who are in charge of ensuring a continuous communication with communities. Different stakeholder workshops have been held to emphasize the need to conserve the environment and the possibility of utilizing other alternative sources of income. These sensitization sessions are mainly done during CMCs and SCMCs meetings.
The continuous formation of new Town councils within the catchment and not included on the SCMC. | Medium | The leaders and technical staff of the subcatchments will be brought on board during trainings.
Centralization of the decision-making process and the execution of the activities | Medium | Given the distances and the difficulties in accessing the project sites for activities execution in addition to the centralization of the decision making process that is time consuming, it was agreed to establish an action plan per catchment and to empower the team leaders responsibility in the activities execution. The reinforcement of the reporting process between the HO and the catchment management zones will also be ensured for a better monitoring taking into account the field specificities.
Lack of trust attributed to failures from the previous projects in the catchment | Medium | The establishment of CMCs, which are working closely with the PCU will ensure community participation to embrace the project activities. Communities participation to the execution of the concrete adaptation action plans will ensure the ownership of the project outcomes and reinforce their trust in it.
Delay in developing a detailed and updated action plan for the catchment level for a better planning of the activities | Medium | At the beginning the project activities were mainly piloted from the central structure and a unique action plan was developed by the team at the center and then shared and communicated to the catchment teams. A coordination meeting every two weeks is organized with the team leaders of the WMZ for better coordination and planning of activities. However, the team is referring only to one global action plan which does not necessarily take into account the specificities of the catchment and sub catchment. The team leaders at the local level have accounts dedicated to the project which should make it easier for them to carry out certain activities at their own pace. Faced with this and given the particularities of each catchment and sub catchment there was a necessity to provide greater flexibility and decision making decentralization to ensure a promptly execution of some activities at the WMZ levels. During the second supervision mission it was recommended by OSS to draw up an activity plan for each catchment and decline it if necessary by sub- catchment in order to better take into account the particularities of each action and especially to integrate the concerns of each beneficiary and / or partner. This recommendation has been considered and corrective actions are being undertaken.
Underestimation of the required time for communty mobilization | Medium | Since the project approach is an innovation and is being implemented for the first time in Uganda, it took more time and effort to sensitize the communities and ensure their engagement. The Catchment Management Committees established under the project, were consulted and sensitized before starting any procurement action to avoid any conflict and ensure their commitment since they will be in charge of the execution of the concrete adaptation activities.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The Project risk category is unchanged and remains B/C. Since the execution of the concrete adaptation actions has not effectively started there are no additionnal environemental and social impacts, however sensitization and communication sessions are ongoing to inform about the project activities and discuss their potential risks and mitigation measures. Some risk mitigation measures were employed during the current reporting period, for example: - Implication of Catchment Management Structures (CMCs and SCMCs) to ensure that a transparent and participatory process is followed in selecting beneficiaries according to agreed criteria: Nurseries, Women groups, concrete adaptation sites communities. - Involvement of local authorities in the project implementation through their representation within the CMC's by the LC (Local Council), to ensure communication with the beneficiary community and to avoid conflicts in the resource use. - Sensitization sessions on the risks of natural resources degradation and their impact on the revenues are organized. - Involvement of the Directorate of Environmental Affairs which is in charge of forestry activities to provide guidance and reasons on using other species which are preferred to Eucalyptus trees - Environmental and Social assessment of the rehabilitation and restoration action plans are being conducted by consultancy to mitigate the potential impacts. - A close follow up of the project execution by the OSS that consists on ensuring the application of the national regulations and procedures for procurement, audit and accountability. - Decentralization of decision making to the CMZs for some activities and development of catchment specific action plans - Negotiations with Government to get a special support or treatment that can facilitate implementation is also being done. There is great effort to mitigate/reduce the risks that were identified during the project design and those identified during the baseline assessment and stakeholder workshops and all the suggested measures are being considered.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
ESP-RELATED CONDITIONS AND REQUIREMENTS ATTACHED TO PROJECT/PROGRAMME APPROVAL DECISION
| Condition or requirement | Current status | Planned actions, including a detailed time schedule
List all ESP-related conditions and requirements included in the Board decision that need to be met. For each condition and requirement, list the current status. (Add lines as needed) [1] | NA | NA | NA
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [2]
ESP principle [3] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [4] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [5] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [6] | List the monitoring indicator(s) for each impact identified. [7] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [8] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [8] | Describe remedial action for residual impacts that will be taken. [8]
1 - Compliance with the law
2 - Access and equity
3 – Marginalized and vulnerable Groups |  |  | 1- Affect the income resources of marginlazed groups that are farming in the project intervention areas such as the wetlands and river banks. 2- Upstream activities may have negative environmental impact downstream and cause social conflict with downstream users | 1- The delineation of buffer zones, the re-vegetation of river and stream banks and other conservation methods need to be monitored closely, particularly with regards to former resource users in those areas. 2- Strengthen coordination and conflict resolution mechanisms at catchment at WMZ level | Number of households trained | 0 | Consultations has been conducted with local communities during the CMC'S meetings
4 – Human rights
5 – Gender equality and women’s empowerment
6 – Core labour rights
7 – Indigenous peoples
8 – Involuntary resettlement |  |  | Community members that have encroached on natural resources such as riverbanks and wetlands will be asked to move out of the area. Such community members will lose their farm lands near river banks or in wetlands though such areas are public and supposed to be protected. | The project will closely monitor the targeting of the project beneficiaries, particularly to assure that those people who have encroached on protected natural resources have access to the revolving fund and are involved in income generating activities. | Number of households trained | 0 | Consultations has been conducted with local communities during the CMC'S meetings and during the site visits with the consultants in charge of the action plan development
9 – Protection of natural habitats |  |  | 1- Rehabilitation actions on the selected natural areas may shift the pressure to non-degraded areas and some conservation measures (if not carefully selected) may aggravate degradation. 2- Natural Resource Use related Conflicts | 1- During the implementation all the activities related to protection and management of wetlands, grasslands, forests shall be closely monitored to evaluate if the expected impact is achieved or if any unexpected negative side effects turn up. 2- Include all stakeholders in consultation at local level, strengthen existing local conflict resolution mechanism, integrate conflict resolution mechanism in catchment-based management structures | Rehabilitated area of wetland and river bank buffer zones | 0 | Consultations has been conducted with local communities during the CMC'S meetings and during the site visits with the consultants in charge of the action plan development
10 – Conservation of biological diversity |  |  | 1- Introduction of drought-tolerant crop varieties may contribute to loss of local varieties by farmers 2- Promoting indigenous forest trees to replace plantation forests (e.g. Eucalyptus in Maziba) may cause conflict | 1- Promote conservation of local crop varieties when introducing drought-tolerant crop varieties 2- Properly consult all stakeholders in reforestation measures and inform about advantages of replacing Eucalyptus trees by indigenous ones | Reforested areas with selected species | 0 | Consultations has been conducted with local communities during the CMC'S meetings and during the site visits with the consultants in charge of the action plan development
11 – Climate change
12 – Pollution prevention and resource efficiency
13 – Public health |  |  | Water harvesting, storage and irrigation facilities may aggravate some diseases such as malaria | Raise awareness through community based health workers on malaria and other water related diseases | Number of sensitization sessions | 0 | Consultations has been conducted with local communities during the CMC'S meetings and during the site visits with the consultants in charge of the action plan development
14 – Physical and cultural heritage
15 – Lands and soil conservation
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Ununanticipated ESP risks is being carried out by the M&E officer at the central and local level.
Have unanticipated ESP risks been identified during the reporting period? |  | Since concrete field actions hasn't start yet, no unanticipated ESP risks has been identified during this reporting period.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | NA
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | In order to implement the required ESP safeguard measures the IE as put in place the following arrangements: - Review of quarter reports on project progress - Review and NO of ToRs to ensure that the ESP safeguards are taken into consideration - Field visits to assess and monotir the project impacts according to the ESP
Have the implementation arrangements been effective during the reporting period? |  | YES, this arrangement has been effective during the reporting period through field visits at catchment levels to the project execution sites and review of 4 quarter reports as well as the annual report including M&E aspects
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | In order to implement the required ESP safeguard measures the EE as put in place the following arrangements: - Appointment of new staff (technical officer, social development officer and capacity development officer) - Involvement of technical direction in the selection of tree species |  |  |  | During the reporting period the IE has put in place the following arrangements to comply with the GP: - Review of quarter reports on project progress - Review and NO of ToRs to ensure that the ESP safeguards are taken into consideration - Field visits to assess and monotir the project impacts according to the ESP
Have the implementation arrangements at the EEs been effective during the reporting period? |  | YES, this arrangement has been effective during the reporting period through field visits at catchment levels to the project execution sites and the appointment of the recruited staff with ESP safeguards monitoring specified in the job decsription sheets
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs) [9]
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [10]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [11]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible [12] | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [13] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts of project/programme activities [14] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been received at this stage. The project is begining the execution of concrete adaptation activities and the Grievance Mechanisme is being presented to the benficiaries during awareness and training sessions. According to OSS process, grievances will be reported when they occur.
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, during the preparation of the project/programme's first submission as a full proposal an initial gender analysis was conducted (Annex VI of the full proposal)
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes, the results framework include gender-responsive indictors broken down at the output level
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [2] | Level [3] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa | Output | No. of gender balanced functional sub catchment and micro-catchment Committees, Fora and Secretariats established/ strengthened | 0 | All the Catchment committees, Fora and Secretariats established/strengthened in the three catchments and the 9 target sub-catchments and Micro-catchments within the sub-catchments | Good
Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | Output | Number of people/ households trained | 0 | At least 180 (72 Women and 98 Men) people trained | Poor
Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | Output | Number of Community women groups producing and marketing stoves Number of households trained Number of households using improved cook stoves | 0 | 18 groups are supported to produce 8000 stoves At least 3600 households trained in the installation and use of improved cooking stoves. At least 3600 households have acquired and are using improved cook stoves | Poor
Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | Output | Number of households trained | 0 | 1800 households trained of which 50% are women | Poor
Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | Output | Number of community members trained | 0 | At least 540 community members 50% of which are women trained | Poor
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [4]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [5]
Gender equality and women's empowerment issues [6] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | During the reporting period the IE as put in place the following arrangements to comply with the GP: - Review of quarter reports on project progress - Review and NO of ToRs to ensure that the GP are taken into consideration - Field visits to assess and monitor the implementation of GP actions
Have the implementation arrangements at the IE been effective during the reporting period? |  | YES, this arrangement has been effective during the reporting period through field visits at catchment levels to the project execution sites and review of 4 quarter reports as well as the annual report including M&E aspects
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [7] |  | During the reporting period the EE as put in place the following arrangements to comply with the GP: - Appointment of new staff (technical officer, social development officer and capacity development officer) - Ensuring women participation to the meetings and workshops
Have the implementation arrangements at the EE(s) been effective during the reporting period? [7] |  | YES, this arrangement has been effective during the reporting period through the appointment of the recruited staff with GP monitoring specified in the job decsription sheets
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | No, during the reporting period no capacity gaps affecting GP compliance has been identified
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [8]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [9] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No grievances have been received at this stage. According to OSS process, grievances will be reported when they occur.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | ESP-related conditions and requirements refers to all those that relate directly or indirectly to compliance with the ESP. These conditions are usually included in “Schedule II of the legal agreement” with the name of “requirements and conditions for disbursements and disbursement schedule.”
2 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
3 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
4 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
5 | Only complete for those ESP principles for which risks were identified
6 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
7 | See the monitoring plan in the ESMP
8 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
9 | This section needs only to be completed if the project/programme includes USPs
10 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
11 | Please submit the updated ESMP together with the PPR
12 | Add lines as appropriate, one line for each USP identified
13 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
14 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | To be completed at PPR1
2 | Add lines as appropriate, one line for each gender-responsive element
3 | Objective, outcome, output
4 | To be completed at final PPR
5 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
6 | Add lines as appropriate, one line for each issue
7 | Add lines as appropriate, one line for each executing entity
8 | To be completed at PPR1
9 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1.1 The existing Catchment Management Planning (CMP) guidelines revised to include aspects of climate change |  | • Revised CMP guidelines in place • 500 copies of revised guidelines • 8 workshops |  | Terms of Reference for the consultant have been prepared and approved by the Ministry’s contracts committee and OSS. Procurement is in the initial stages. | MU
| Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues |  | • 2 CMPs for Awoja and Maziba revised 700 copies of revised CMPs • 6 workshops held |  | Terms of Reference for the consultant have been prepared and approved by the Ministry’s contracts committee and OSS. Procurement is in the initial stages. | MU
| Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) |  | All the Catchment committees, Fora and Secretariats established/strengthened in the three catchments and the 9 target sub-catchments and Micro-catchments within the sub-catchments |  | All 3 Catchment Management Committees are established All 9 Sub Catchment Management Committees have been established | S
| Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed |  | • In each catchment an area of forest, wetland and riverbank defined as most vulnerable to intensive rainfall, risk of flooding and landslides. • A detailed baseline report |  | A detailed baseline assessment has been conducted 9 workshops were held in each of the sub catchments to confirm the most degraded areas that are vulnerable to intensive rainfall Field work to confirm them were carried out after the reporting period. | S
| Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation |  | • At least 9 tree nurseries supported to produce1,200,000 seedlings • At least 180 (72 Women and 98 Men) people trained • At least 10,000 households trained • 1000 ha restored No action required for year 1 |  | All the existing tree nurseries in the sub catchments were identified during the baseline survey and an assessment will be done to finalize the selection of the 9 tree nureseries to be supported The degraded areas that require restoration by planting trees were identified during the baseline survey The process to confirm the 1000ha to be restored is ongoing | MU
| Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation |  | • 18 groups are supported to produce 8000 stoves • At least 3600 households trained in the installation and use of improved cooking stoves. • At least 3600 households have acquired and are using improved cook stoves |  | The existing groups (and their capacity) that promote energy saving cook stoves were identified during the baseline survey. 1 school per sub catchment that uses a lot of firewood was identified and selected to pilot clean energy methods of cooking in order to reduce on the forest degradation | MU
| Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands |  | • 300 ha restored. • 1800 households trained of which 50% are women. • At least 12 individual wetland restoration action plans (4 per catchment) developed and implemented for 12 wetlands in the 3 catchments. |  | The existing degraded wetlands in the 9 sub catchments were identified as well as their level of degradation. Confirmation of the 12 wetlands to be restored is ongoing Terms of reference for consultancy services to spearhead the development and implementation of restoration action plans, working the communities, have been prepared and approved by OSS and MWE Contracts Committtee. Procurement is in the initial stages. | MU
| Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones |  | • 320ha stabilized and restored • 200 Km boundary put in place • At least 540 community members 50% of which are women trained |  | The existing degraded river banks in the 9 sub catchments were identified as well as their level of degradation. Confirmation of the riverbanks to be restored is ongoing Terms of reference for consultancy services to spearhead the restoration activities, working with the communities have been prepared and approved by OSS and MWE Contracts Committtee. Procurement is in the initial stages. | MU
| Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods |  | • At least 2,000 households trained • 1000 Km of biophysical structures in place At least 18 Community workshops and 36 training meetings • At least 6 radio talk shows to sensitize communities on biophysical structures held |  | Terms of reference for consultancy services to spearhead the design and implementation of water harvesting and flood control structures have been prepared and approved by OSS and MWE Contracts Committtee. Procurement is in the initial stages. | MU
| Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments |  | • At least 9 community groups (3 per catchment) trained 27community trainings • At least 3,000 HH are accessing the revolving fund • About 80% rates of return on investment |  | The existing revolving fund schemes in the catchments were identified during the baseline study in order to identify the opportunities and lessons learnt that will help the project to successfully implement the revolving fund schemes. | MU
| Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported |  | • At least 2,400 HH trained (20 trainings each of 30 participants per year with at least 2 trainings per sub-catchment) |  | The existing alternative sources of income were identified during the baseline survey. The project will build on what is existing and capacity building will be focused on enhancing what is already there but also other new IGAs | MU
| Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities |  | • At least- 14 TOT workshops conducted 90 micro-catchment level dissemination workshops in 3 years (10 community meetings per sub catchment) |  | Terms of reference have been prepared to procure Global Water Partnership to support capacity building and knowledge management activities in the project. The Tors have been approved by OSS and pending MWE Contracts Committtee approval. | MU
| Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established |  | • One Demonstration center set up in each of the 3 catchments • At least 5 trainings in key interventions conducted at each center • At least 4 plots established at each demonstration center |  | The potential demonstration centers were identified during the baseline survey. The selection of the final demonstration centers will be finalized in the next reporting period. | MU
| Output 3.2.1 Good practices and lessons that influence policies and practices documented |  | • At least 3 documents with lessons learned and best practices from the project documented (i.e. policy briefs, brochures, media articles etc) • At least 2 study tours per catchment organized |  | Terms of reference have been prepared to procure Global Water Partnership to support capacity building and knowledge management activities in the project. The Tors have been approved by OSS and MWE Contracts Committtee and procurement is ongoing. | MU
| Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans |  | • At least 150 Officials from Districts and Sub county levels trained on • At least 90% of Development plans at district, Sub county and National levels integrate climate change resilience and adaptation issues • A scaling up strategy developed and is being used to scale up project |  | Terms of reference have been prepared to procure Global Water Partnership to support capacity building and knowledge management activities in the project. The Tors have been approved by OSS and MWE Contracts Committtee before procurement can start. Baseline assessment for the 3 catchments completed | MS
| Project Management and M&E |  | • 4 Project launching workshops (1 national and 3 catchment levels) |  | 4 Project launching workshops (1 national and 3 catchment levels) were held | S
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Dr. Callist Tindimugaya
| Email: | Callist.tindimugaya@mwe.go.ug callist_tindimugaya@yahoo.co.uk
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
The project has gained stakeholder by in and has been well publicized so far through the stakeholder the launch workshops, stakeholder form meetings and the media. Although the EURECCCA Project formally started in May 2017, effective implementation of the project activities started in October 2017 after formal approval by OSS of the various project documents and the release of project funds. However, the project team has made great efforts to fast track implementation of the activities and recover the lost time. A lot of work has therefore been done that has set a stage for faster implementation of the activities through procurement of various consultancies to spearhead the implementation activities on ground and establishmen of the subcatchment management committtees to overlook and participate in the implementation activites. It is also hoped that provision of feedbacks and no objections by OSS will be faster to enable recovery of the already lost time.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Output 1.1.1 The existing Catchment Management Planning (CMP) guidelines revised to include aspects of climate change |  | • Revised CMP guidelines in place • 500 copies of revised guidelines • 8 workshops |  | Terms of Reference for the consultant have been prepared and approved by the Ministry’s contracts committee and OSS. Procurement is in the initial stages. | MU
| Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues |  | • 2 CMPs for Awoja and Maziba revised 700 copies of revised CMPs • 6 workshops held |  | Terms of Reference for the consultant have been prepared and approved by the Ministry’s contracts committee and OSS. Procurement is in the initial stages. | MU
| Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa) |  | All the Catchment committees, Fora and Secretariats established/strengthened in the three catchments and the 9 target sub-catchments and Micro-catchments within the sub-catchments |  | All 3 Catchment Management Committees are established All 9 Sub Catchment Management Committees have been established | S
| Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed |  | • In each catchment an area of forest, wetland and riverbank defined as most vulnerable to intensive rainfall, risk of flooding and landslides. • A detailed baseline report |  | A detailed baseline assessment has been conducted 9 workshops were held in each of the sub catchments to confirm the most degraded areas that are vulnerable to intensive rainfall Field work to confirm them were carried out after the reporting period. | S
| Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation |  | • At least 9 tree nurseries supported to produce1,200,000 seedlings • At least 180 (72 Women and 98 Men) people trained • At least 10,000 households trained • 1000 ha restored No action required for year 1 |  | All the existing tree nurseries in the sub catchments were identified during the baseline survey and an assessment will be done to finalize the selection of the 9 tree nureseries to be supported The degraded areas that require restoration by planting trees were identified during the baseline survey The process to confirm the 1000ha to be restored is ongoing | MU
| Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation |  | • 18 groups are supported to produce 8000 stoves • At least 3600 households trained in the installation and use of improved cooking stoves. • At least 3600 households have acquired and are using improved cook stoves |  | The existing groups (and their capacity) that promote energy saving cook stoves were identified during the baseline survey. 1 school per sub catchment that uses a lot of firewood was identified and selected to pilot clean energy methods of cooking in order to reduce on the forest degradation | MU
| Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands |  | • 300 ha restored. • 1800 households trained of which 50% are women. • At least 12 individual wetland restoration action plans (4 per catchment) developed and implemented for 12 wetlands in the 3 catchments. |  | The existing degraded wetlands in the 9 sub catchments were identified as well as their level of degradation. Confirmation of the 12 wetlands to be restored is ongoing Terms of reference for consultancy services to spearhead the development and implementation of restoration action plans, working the communities, have been prepared and approved by OSS and MWE Contracts Committtee. Procurement is in the initial stages. | MU
| Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones |  | • 320ha stabilized and restored • 200 Km boundary put in place • At least 540 community members 50% of which are women trained |  | The existing degraded river banks in the 9 sub catchments were identified as well as their level of degradation. Confirmation of the riverbanks to be restored is ongoing Terms of reference for consultancy services to spearhead the restoration activities, working with the communities have been prepared and approved by OSS and MWE Contracts Committtee. Procurement is in the initial stages. | MU
| Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods |  | • At least 2,000 households trained • 1000 Km of biophysical structures in place At least 18 Community workshops and 36 training meetings • At least 6 radio talk shows to sensitize communities on biophysical structures held |  | Terms of reference for consultancy services to spearhead the design and implementation of water harvesting and flood control structures have been prepared and approved by OSS and MWE Contracts Committtee. Procurement is in the initial stages. | MU
| Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments |  | • At least 9 community groups (3 per catchment) trained 27community trainings • At least 3,000 HH are accessing the revolving fund • About 80% rates of return on investment |  | The existing revolving fund schemes in the catchments were identified during the baseline study in order to identify the opportunities and lessons learnt that will help the project to successfully implement the revolving fund schemes. | MU
| Output 2.3.2 Alternative income generating activities-IGAs (Bee keeping, Eco-tourism, Zero grazing, Hand crafts etc.) supported |  | • At least 2,400 HH trained (20 trainings each of 30 participants per year with at least 2 trainings per sub-catchment) |  | The existing alternative sources of income were identified during the baseline survey. The project will build on what is existing and capacity building will be focused on enhancing what is already there but also other new IGAs | MU
| Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities |  | • At least- 14 TOT workshops conducted 90 micro-catchment level dissemination workshops in 3 years (10 community meetings per sub catchment) |  | Terms of reference have been prepared to procure Global Water Partnership to support capacity building and knowledge management activities in the project. The Tors have been approved by OSS and pending MWE Contracts Committtee approval. | MU
| Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, climate smart agriculture and alternative income generating activities established |  | • One Demonstration center set up in each of the 3 catchments • At least 5 trainings in key interventions conducted at each center • At least 4 plots established at each demonstration center |  | The potential demonstration centers were identified during the baseline survey. The selection of the final demonstration centers will be finalized in the next reporting period. | MU
| Output 3.2.1 Good practices and lessons that influence policies and practices documented |  | • At least 3 documents with lessons learned and best practices from the project documented (i.e. policy briefs, brochures, media articles etc) • At least 2 study tours per catchment organized |  | Terms of reference have been prepared to procure Global Water Partnership to support capacity building and knowledge management activities in the project. The Tors have been approved by OSS and MWE Contracts Committtee before procurement can start. | MU
| Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans |  | • At least 150 Officials from Districts and Sub county levels trained on • At least 90% of Development plans at district, Sub county and National levels integrate climate change resilience and adaptation issues • A scaling up strategy developed and is being used to scale up project |  | Terms of reference have been prepared to procure Global Water Partnership to support capacity building and knowledge management activities in the project. The Tors have been approved by OSS and MWE Contracts Committtee before procurement can start. Baseline assessment for the 3 catchments completed | MS
| Project Management and M&E |  | • 4 Project launching workshops (1 national and 3 catchment levels) |  | 4 Project launching workshops (1 national and 3 catchment levels) were held | S
[5 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Mrs Khaoula JAOUI
| Email: | khaoula.jaoui@oss.org.tn
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | In its first year, the project can be considered Marginally Satisfactory. Some highlights for this period are summarized below: Low expenditure level: The only expenditures OSS records on the PPR are the audited ones, so the reported values are related to the end of April 2019 and this explains part of the unspent budget. Also, it is important to notice that various activities planned for the first two year has been executed during the last period and their deliverables already finalized, however their payment is not yet done (e.g. Output 1.1.1, Output 1.1.2. and Output 3.1.1). This explain the expenditure rate to date. • The disbursement to date from the Adaptation fund to OSS amounts US $ 3 900 000 (US $ 3.600.000 for project execution and US $ 300 000 as implementing fees). • The disbursement to date from OSS to GoU amounts US $ 1 163 174.29 and represents 16% of the total funding. The undisbursed amount is US $ 2 436 825.71. • The Payments made by the GoU to date (end December 2019) are around US $ 1 000 000. They represent around 14 % of the Grant total amount. The expenditure balance is US $ 163 174.29. • The unspent balance from the previous years: (3.600 000 –1 000 000) = US $ 2 600 000 (includes undisbursed amount from OSS to the GoU and the expenditure balance in the project national account) ===> It has to be noted that the global commitment to date is around US $ 3 560 000.00 The first two years of the project were used to set the ground for implementation and hire the required service providers to facilitate the implementation. Stakeholder buy in has been achieved and most of the procurements have been completed and there is full scale implementation of the key activities. Progress of the project execution by Component The project kick-off workshop was held on May 5th, 2017, while the project effective execution has started on October 2017. This delay was mainly due to the difficulties encountered to develop and finalize acceptable documents required for the project entry into force stipulated by the Grant Agreement and the first disbursement. As planned by the project, in addition to the national kick-off workshop, other launching workshops were also held at the level of the three (3) catchment basins as follows: on 18 September 2017 in Soroti for the Awoja catchment basin, on 21 September 2017 in Gulu for the Aswa catchment basin and on 5 October 2017 in Kabale for the Maziba catchment basin. These workshops aimed to present the project to local beneficiary stakeholders, determine their roles and responsibilities and discuss the criteria used in the selection of the priority sub-basins. The Project Coordination Unit (PCU) developed 3 reports on the baseline studies of the three catchments conducted by the staff of the Directorate of Water Resources Management at the central level and in the three basins. This approach was adopted to allow the staff to better understand the basins conditions and to strengthen their capacities and the project ownership. A Memorandum of Understanding (MoU) was developed between the Nile Basin Initiative (NBI) /Global Water Partneship East Africa (GWPEA) and the Ministry of Water and Environment for the execution of a series of activities under component 3 of the project. This MoU aims to formalize the collaboration between the MWE and the NBI/GWPEA as mentioned in the project document. At the request of OSS, the MWE requested the agreement of the national competent institutions authorizing a direct procurement of GWPEA. The MOU was approved by the Ministry of Justice and Constitutional Affairs on 09/02/2018 and by the Ministry of Finance on 15/04/2018. In the framework of component 1, the MWE (PCU) executed the following activities: a) The Guidelines for the catchment-basins planning and management were updated in 2018 by the Ministry of Water and Environment in the framework of another project (World Bank). Hence, the PCU has developed ToRs for the review and professional editing of these guidelines, as well as for the production of popular versions for their dissemination. These ToRs received the no-objection of OSS on 14/05/2018 and the consultant selection is underway. b) The PCU developed documents for a call for proposals for the integration of the climate change dimension in the management plans of the three basins. The bidding documents were submitted to OSS who confirmed its no-objection on the ToR on 14/05/2018 and procurement is underway. c) The establishment of the nine (9) structures of the management committees started on 28 February and ended on 19 April 2018, during a series of consultation and engagement workshops. A participatory process was adopted and directed by the Chairpersons of the catchment management committees of the Aswa, Awoja and Maziba catchment basins for the selection of the (9) structures. These structures will be formalized by issuance of appointment letters as provided for in the Manual of Operations of the Catchment Management Organisations (CMOs). In the framework of Component 2, the MWE (PCU) implemented the following activities: a) The MWE proceeded to the confirmation of the most vulnerable and sensitive zones to intensive rainfall in the three basins over the period from 28 February to 19 April 2018. In total, 9 sub-basins were retained based on selection criteria developed by the Directorate of Water Resources Management. b) As a preparatory activity, the MWE endorsed a process for the recruitment of consultants for the development of action plans. Hence, the PCU elaborated the following ToR: (i) Study for the restoration of degraded river banks; (ii) Study for the construction of water harvesting and floods control structures; and (iii) study for the restoration of degraded wetlands. The three ToRs received the OSS No-objection on 18/05/2018 and the process for consultants recruitment is underway. It is important to mention that due to the nature of the activities planned under this component, it was necessary to launch these studies for the execution of the different restoration activities. In the framework of Component 3, the PCU developed and submitted to OSS Terms of Reference for a first part of the capacity building activities to be carried out by the GWPEA in the framework of the MOU. These ToRs received the No-Objection of OSS on 29/05/2018 and procurement is underway. As a general recommendation to clear the backlog it is agreed on the development of a reviwed Procurement Plan covering the whole next year. Project Coordination and Management PCU: The project coordinator submitted the list of the PCU members on 2 May 2017. The list includes the names of the technical staff at the local and national levels. Although specific staff have not yet been recruited for EURECCCA project the current staff supporting the project in various areas such as procurement, accounting, monitoring and evaluation etc should also be included on the list. As the project is executed by the Ministry of Water and Environment, the latter has mobilized its staff to handle the procurement and financial aspects of the project. Given the delay in the execution of the project activities, OSS recommends the recruitment of additional part-time or full-time staff for technical, administrative and financial support in order to make up for this delay. The composition of the new Project Team should be submitted in a formal manner to OSS for no objection.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Objective: To increase the resilience against the risk of flood and landslides of Awoja, Maziba and Aswa Catchments through promoting catchment based integrated, equitable and sustainable management of land and water resources | • Improved integrity of natural resources (land, water, forests, wetlands, and riverbanks) – Proportion of natural estate restored. • Proportion of households with improved resilience to cliame related hazards (floods and landslides | • From 1970 to date, 57, 93 and 48 landslides have occurred in Maziba, Awoja and Aswa catchments respectively. • From 1990 to-date, 35, 52 and 43 flood events have occurred in Maziba, Awoja and Aswa catchments respectively. • There is increased vulnerability to those risks due to degradation of riverbanks, wetlands and forests, less water infiltration and increased superficial runoff. | Terms of reference for various consultancy services to spearhead the restoration activities have been prepared and approved by both OSS and the Ministry’s contracts committee. Procurement of these consultants is ongoing. | • Integrity of targeted natural resources improved by at least 50% • 50% of targeted households develop climate resilience to climate change impacts by 2020 Natural resources restored by 10% in the project areas by 2020
Component 1: Establishing Frameworks for Climate Resilient Catchment Management in Awoja, Aswa and Maziba catchments
Outcome 1.1 Comprehensive catchment planning system that integrates issues of climate change established and tested in Awoja, Aswa and Maziba | Comprehensive catchment management plans for Awoja, Aswa and Maziba catchments developed and operational | • Catchment management structures exist in Maziba, Awoja and Northern part of Aswa catchments but are not fully functional • Awoja and Maziba have non-functional structures at catchment and sub-catchment and no structures at micro -catchment level exist | Three (3) fully functional Catchment management structures for the 3 target catchments are established Nine (9) sub catchment management structures for the 9 target micro catchments are established | Three (3) fully functional Catchment management structures for the 3 target catchments are in place.
Output 1.1.1 The existing catchment management planning guidelines revised to include aspects of climate change | Revised guidelines for Catchment Management Planning that integrate climate change issues in place | • Existing CMP guidelines do not have a component on integration of climate change issues in CMPs. | Procurement of the consultant was completed and the Final edited CMP guidelines report has been submitted. | • Revised CMP guidelines in place • 500 copies of revised guidelines • 8 workshops
Output 1.1.2 The Catchment Management Plans (CMPs) of Awoja, Maziba and Aswa revised to address climate change issues | Comprehensive catchment management plans for Awoja, Aswa and Maziba catchments that integrate climate change issues in place | • Climate change issues not incorporated in the existing CMPs of Awoja and Maziba catchments. | Procurement of the consultant was completed and CMP Guidelines Assessment Report has been submitted | • 2 CMPs for Awoja and Maziba revised 700 copies of revised CMPs • 6 workshops held
Outcome 1.2 Awoja Aswa and Maziba catchments managed by appropriate water and climate governance structures | Appropriate catchment management structures for Awoja, Aswa and Maziba catchments strengthened and functional | • Interim structures exist | 3 catchment management committees are fully functional | Fully functioning structures by end 2017
Output 1.2.1 Nine (9) sub-catchment level community management structures, established and supported, in the 3 catchments (3 for Awoja, 3 for Maziba & 3 for Aswa). | • No. of gender balanced functional sub catchment and micro-catchment Committees, Fora and Secretariats established/ strengthened | • No structures at catchment, sub-catchment and micro -catchment level in the targeted sites except for Aswa which has a sub-catchment structure; | All 3 Catchment Management Committees have been established All 9 Sub Catchment Management Committees have been established | All the Catchment committees, Fora and Secretariats established/strengthened in the three catchments and the 9 target sub-catchments and Micro-catchments within the sub-catchments
Component 2 Implementing concrete adaptation actions for resilient and sustained ecosystems, agriculture and other livelihood systems
Outcome 2.1 Resilience of ecosystems services of forests, wetlands and riverbanks to climate change impacts enhanced | • No. of natural systems with improved resilience/Area of degraded ecosystems (forests, wetlands, river banks) restored | • Ecological systems have low resilience. About 1,161,806 hectares of Communal and private forestlands in Uganda are degraded. • The total area of degraded wetlands in Maziba is 386.3 ha (58%), Awoja 7,000 ha and Aswa 5,800ha. i.e 13,186.3 ha in the entire project area. • Total area of degraded river banks (Statistics not available) | Degraded areas for restoration (Forests, wetlands and riverbanks) have all been identified during baseline study. Procurements for the consultancy services to spear head implementation of interventions is done | • At least two ecological systems improved their resilience by 2020
Output 2.1.1 The most degraded areas vulnerable to intensive rainfall confirmed | • Map of each catchment indicating the specific degraded areas vulnerable to intensive rainfall | • The size and specific location of degraded areas of forest, wetlands and riverbanks vulnerable to intensive rainfall in the 3 catchments are not mapped. | A detailed baseline assessment was conducted and a report was submitted. Field visits have been carried out to confirm areas most vulnerable to intensive rainfall. | • In each catchment, an area of forest, wetland and riverbank defined as most vulnerable to intensive rainfall, risk of flooding and landslides. • A detailed baseline report
Output 2.1.2 Communities in 3 catchments supported to restore deforested and degraded land through afforestation | • Survival rate of seedlings. • Number of people/ households trained • Area (ha) of forest restored. | • Tree nurseries exit but they are privately owned with low production and technical capacities. • Inadequate knowledge, skills and capacity for afforestation/restoration activities in the catchments • About 1,161,806 hectares of Communal and private forests in Uganda are degraded. | 9 tree nurseries to be supported have been identified and their procurement is in the final stages. The communities and households to be trained have been identified and the training module preparation is in its final stages. The degraded areas that require restoration by planting trees have been identified and verified for intervention. The species for planting have been agreed upon. | • At least 9 tree nurseries supported to produce1,200,000 seedlings • At least 180 (72 Women and 98 Men) people trained • At least 10,000 households trained • 1000 ha restored
Output 2.1.3 Improved cooking stoves promoted in the 3 catchments to reduce levels of forest degradation | • Number of Community women groups producing and marketing stoves • Number of households trained • Number of households using improved cook stoves | • A Limited number of households are using improved cooking stoves. • High rate of tree cutting for fuelwood leading to land degradation | Women groups and Community groups to be supported in cookstove production have been identified and their procurement is in final stages. | • 18 groups are supported to produce 8000 stoves • At least 3600 households trained in the installation and use of improved cooking stoves. • At least 3600 households have acquired and are using improved cook stoves
Output 2.1.4 Communities in 3 catchments supported to rehabilitate degraded wetlands | • Number of degraded wetlands restored. • Hectares of degraded wetlands restored (regenerated /Un disturbed) • Number of households trained | • Wetland degradation is rampant due to encroachment and overexploitation of wetland resources. • Limited expertise in wetland restoration activities. • No individual wetland restoration action plans for degraded wetlands | The degraded wetlands in the 9 sub catchments have been identified, verified and comfirmed for implementation. Procurement of consultancy services to spearhead the development and implementation of restoration action plans has been completed and inception reports have been submitted. | • 300 ha restored. • 1800 households trained of which 50% are women. • At least 12 individual wetland restoration action plans (4 per catchment) developed and implemented for 12 wetlands in the 3 catchments.
Output 2.1.5 Communities in 3 catchments supported to restore degraded river banks and protect buffer zones | • Number of hectares of restored un disturbed/not eroded • Number of Km of river bank boundary marked . • Number of community members trained | • The National Environment regulations on management of riverbanks and lakeshores 2000 are in existence but are not enforced in the catchments. | The existing degraded river banks in the 9 sub catchments have been identified, verified and comfirmed for project intervention. Procurement of consultancy services to spearhead the restoration of degraded river banks and protection of buffer zones has been completed and inception reports have been submitted. | • 320 ha stabilized and restored • 200 Km boundary put in place • At least 540 community members 50% of which are women trained
Outcome 2.2 Resilience of agricultural landscapes to climate change impacts enhanced | • Area of agricultural landscapes less susceptible to floods and landslides | • There is high degradation of agricultural landscapes, which increases their vulnerability to climate change impacts. | Procurement of consultancy services to spearhead the design and implementation of water harvesting and flood control structures is done and work has started. | • At least 400ha of land of agricultural land with biophysical and water harvesting structures in place.
Output 2.2.1 Communities in 3 catchments supported to harvest water and control floods | • Number of households trained in flood management • Number of flood control structures constructed • Number of trainings on water harvesting and flood management | • Households use traditional flood management techniques. • The flood control is done using ineffective and rudimentary methods | Procurement of consultancy services to spearhead the design and implementation of water harvesting and flood control structures has been completed and inception reports have been submitted. The affected communities have been identified in preparation for the trainings. | • At least 2,000 households trained • 1000 Km of biophysical structures in place At least 18 Community workshops and 36 training meetings • At least 6 radio talk shows to sensitize communities on biophysical structures held
Outcome 2.3 Resilience of livelihood systems to climate change impacts enhanced by providing alternative income generating opportunities | • Percentage of households with improved livelihoods and undertaking resilient alternative income generating activities • Percentage change in livelihoods of beneficiary households | • 19.7% of households are estimated to suffer from food insecurity • Communities have limited alternative income sources and are overexploiting natural resources. | During the baseline study, existing alternative livelihoods were identified | • The percentage of food insecure households is reduced to 10% • 2400 vulnerable households have improved livelihoods • At least incomes of 70% of participating farmers have improved
Output 2.3.1 Revolving fund schemes introduced to diversify sources of income in 3 catchments | • No. of sensitization meetings and workshops on revolving fund held • No. of community groups trained and prepared to access the revolving fund • No. of SACCOs branches formed and managing the revolving fund. • No. of community members benefiting from the revolving fund • Rates of return of the revolving fund | • The communities have limited access to and Knowledge on management of revolving fund schemes is inadequate. • There is no revolving fund solely focused on natural resources management (IWRM and CC adaptation). | The existing revolving fund schemes in the catchments were identified during the baseline study in order to identify the opportunities and lessons learnt that will help the project to successfully implement the revolving fund schemes. | • At least 9 community groups (3 per catchment) trained 27community trainings • At least 3,000 HH are accessing the revolving fund • About 80% rates of return on investment
Output 2.3.2 Alternative income generating activities-IGAs (bee keeping, tourism, Hand crafts etc.) supported | • Number of households trained in different IGAs | • Communities have limited knowledge and skills on business planning for various income generating activities | The project inteventions are focusing on strengthening and capacity building for the existing and other new IGAs. | • At least 2,400 HH trained (20 trainings each of 30 participants per year with at least 2 trainings per sub-catchment)
Component 3: Building climate change adaptive capacities of institutions and communities and knowledge management
Outcome 3.1 Adaptive capacity of communities and other stakeholders to climate change impacts strengthened | • Percentage of targeted communities undertaking climate change adaptation actions. | • Adaptive capacities of the Communities in the target areas are very low. | The Global Water Partnership has been procured to develop the TOT. The training sessions are planned for the next August in the selected demonstration centers. | Adaptive capacity of at least 60% target communities to climate change impacts have been strengthened.
Output 3.1.1 Capacities of extension services and institutions at catchment level are strengthened to support communities in Awoja, Aswa and Maziba to undertake climate change adaptation activities | • Number of Training of Trainers (TOT) workshops held • Number of trainers trained • Number of dissemination workshops organized | • The communities in the three catchments have inadequate capacity in climate change adaptation strategies | The Capacity Needs Assessment (CNA) and data collection have been been conducted in the 3 catchments. | At least- 14 TOT workshops conducted 90 microcatchment level dissemination workshops in 3 years (10 community meetings per sub catchment)
Output 3.1.2 Three (3) Demonstration centers to facilitate experience sharing activities regarding ecosystems conservation, control of floods and landslides and alternative income generating activities established | • Number of demonstration centers set up • Number of committee members trained in the management of interventions at the demo centers • Plots for key climate change adaptation interventions established and well maintained | • Demonstration centers are non-existent in the catchments. | Research Institutions in the 3 catchments were selected as demonstration sites in order to ensure sustainability of the implemented activities. Kachwekano Zonal Agricultural Research and Development Institute (KaZARDI) which is located in Kabale District in South Western Uganda was identified as a potential demonstration centre for the project in Maziba catchment. Ngetta Zonal Agricultural Research and Development Institute (ZARDI) was identified as the demonstration centre in Aswa Catchment. The National Semi Arid Resources Research Institute (NaSARRI) in Serere Town Council was identified as the demonstration centre for thr Awoja Catchment. Formal response has been received from NARO agreeing to the collaboration and requesting that the MWE teams and ZARDI teams work out the collaboration details including roles and responsbilities of either parties that will be formalized in a Memorandum of Understandings (MoUs) to be signed between MWE and NARO. The Project implementation team also conducted an assessment of the requirements for setting up the demonstration plots and renovating the infrastructure at the demonstration sites. | One Demonstration centre set up in each of the 3 catchments • At least 5 trainings in key interventions conducted at each center • At least 4 plots established at each demonstration centre
Outcome 3. 2 Demonstrating and developing mechanisms to integrate climate change adaptation and implementation | • Good practices and lessons from the project are documented and influence policy Number of development plans incorporating climate change resilience issues | • No documented experiences and practices to influence planning and policy on climate change mitigation. | Sensitization meetings has been organized with the key government officials at the local levels. | By the end of the project lessons and best practices are documented, shared and influence local and central government planning and policy
Output 3.2.1 Good practices and lessons that influence policies and practices documented | • Number of lessons learnt and best practice documents produced • Number of exchange visits between the catchments and the training centers organized | • No documentation of lessons learnt and best practices in climate change adaptation. | The consultant GWP has been procured and is expected to document the baseline situation of the 3 catchment to capture information on the status of the catchments before interventions are undertaken. He will document good practices of IWRM and climate change adaptation innovations implemented under other projects and this project for learning and scaling up. | • At least 3 documents with lessons learned and best practices from the project documented (i.e. policy briefs, brochures, media articles etc) • At least 2 study tours per catchment organized
Output 3.2.2 Key Government officials integrate IWRM and CC in national and sectoral development plans | • Number of trainings conducted • Number of Government staff trained • Number of National and Sectoral plans for integrating IWRM and CC adaptation issues • A scaling up strategy developed | • The capacity of Key Government Officials to integrate IWRM and CC into National and sectoral plans is inadequate. • The IWRM and CC issues are not integrated in existing National and sectoral development plans. | The consultant GWP has been procured and will develop a dissemination plan that will be targeted but comprehensive. The documentation will also include local languages to ensure that the targeted local communities understand the messages. | • At least 150 Officials from Districts and Sub county levels trained on • At least 90% of Development plans at district, Sub county and National levels integrate climate change resilience and adaptation issues • A scaling up strategy developed and is being used to scale up project
Project Management and M&E
| • Number of Project launching workshops held in the catchments. |  | 4 Project launching workshops (1 national and 3 catchment levels) | 4 Project launching workshops (1 national and 3 catchment levels)
| • Baseline • Mid-term evaluation • Final evaluation |  | MTE was conducted on October by an independent expert.

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Despite the global delay in the project execution, now it has entrered a more dynamic phase during which, the concrete field activities are starting. Accordingly there has been a necessity in providing additional assistance to the project team by recruiting new staff such as, Accountants (4); Engineering Assistant (3); Project Technical Officer (3); Social Development Officer (3); Capacity Development Officer (3) and M&E Officer (1). This staff has been appointed both at the central (2) and the local level (5) per Catchment level. In addition, it should be noted that the preparatory tasks for all project activities has been developed. This consists of i) the establishment of catchment committees which will be in charge of monitoring and follow up of all project activities; ii) the organization of concertation meetings with local partners; (iii) the involvement of the local government representatives in communities mobilization et consultation ensuring the project ownership; iv) the launching of all preparatory studies for action plans defining concrete activities to be carried out; v) the establishment of MoUs with all partners involved in the implementation of the project. While all these activities are time-consuming because of the procedures for formalizing the partnerships that are managed according to the national regulations, these preparatory activities have had a large positive impact on project communication aspects. The lesson learned is that a very detailed action plan of all these sub-activties must be developed in a consultative manner taking into account the bureaucracy and all the procedures.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Although the project was officially launched in May 2017 the effective start of activities was on October 2018 after formal approval by OSS of the various project documents and the disbursement of project funds. In spite of the foreseen risk, the exceptional experienced delays was mainly due to the project philosophy which is the community based approach. The delays could be explained by the following: 1. Necessity to discuss and agree, with the Catchment Management Committees established under the project, before starting any procurement action on the following aspects: i) Agree on the selection criteria of the project intervention areas among the most degraded ones, to avoid any conflict and ensure their commitment since they will be in charge of the execution of the concrete adaptation activities; ii) Agree on the list of the tree species that will be raised by the nurseries. This list has been proposed by the communities and then reviewed and validated by the Forestry department taking into account the environmental and social aspects and iii) Selection of the nurseries and the women groups for cook stoves production. It should also be noted that during the planning of the activities the required time for a good mobilization of the populations was underestimated. Indeed, since this approach is an innovation and is being implemented for the first time in Uganda, it took more time and effort to sensitize the communities and ensure their engagement. To date, all of these necessary preparatory actions have been completed and all the stakeholders have embarked on the process. 2. Time to get special treatment from the Procurement and Disposal Unit and the Contracts Committee of MWE: A lot of time was spent trying to get the Procurement and Disposal Unit and the Contracts Committee of MWE to understand the project, its philosophy and operational modalities so that it can be given special treatment during the procurement process. A lot of explanations and convincing therefore had to be done and this caused a lot of delays. However, after the Procurement and Disposal Unit and the Contracts Committee fully understood the project and its operational modalities they started giving special treatment to the project and the delays were hence reduced. 3. Negotiations with the MWE when offers are greater than the available budgets: During the procurement of some consultants, the submitted costs of doing the assignments were above what was available in the project budget. As such, the project team engaged the Procurement and Disposal Unit of MWE and OSS on the best way to handle the challenge. This took a long time with back and forth emails, letters and consultations. 4. Legal registration of community organizations: Some of the stakeholder groups that the project proposed to work with such as tree nursery operators, did not have the required legal documents to contractually be engaged on various assignments. The Ministry had to first help them with the registration processes which took some time. 5. Delay in developing a detailed and updated action plan for the catchment level for a better planning of the activities At the beginning the project activities were mainly piloted from the central structure and a unique action plan was developed by the team at the center and then shared and communicated to the catchment teams. A coordination meeting every two weeks is organized with the team leaders of the WMZ for better coordination and planning of activities. However, the team is referring only to one global action plan which does not necessarily take into account the specificities of the catchment and sub catchment. The team leaders at the local level have accounts dedicated to the project which should make it easier for them to carry out certain activities at their own pace. Faced with this and given the particularities of each catchment and sub catchment there was a necessity to provide greater flexibility and decision making decentralization to ensure a promptly execution of some activities at the WMZ levels. Mitigation measures: 1. Decentralization of procurement process: While initially all the procurements used to be handled together by the team at the center, currently procurements are handled concurrently at the center and in the 3 Water Management Zones. Cross cutting procurements are handled at the center while catchment specific procurements are handled in each Water Management Zone. This enables the teams at the center and in the 3 water management zones to follow up closely their assigned procurements and ensure that they are concluded in a timely manner. 2. Using of framework contracts: these kind of contracts have been signed with various service providers and whenever inputs or supplies are needed a call off order is issued and services or supplies are provided as opposed to initiating a procurement each time services or supplies are needed. This approach saves time on procurement and enables the project team to only focus on implementation of activities on the ground. 3. Recruitment of staff: 17 technical staff (5 per catchment and 2 at the central level) to assist in project implementation have fully settled in and have been assigned roles of spearheading implementation of various project activities. 4. Setting up of the Contract management teams involving staff from local governments and other related departments in the MWE and other Ministries. These teams are closely following up implementation of the activities and ensuring timely delivery of good quality products 5. Development of an activity plan for each catchment and decline it if necessary by sub- catchment in order to better take into account the particularities of each action and especially to integrate the concerns of each beneficiary and / or partner.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | The Guidelines for the catchment-basins planning and management were updated in 2018 by the Ministry of Water and Environment in the framework of another project (World Bank). Hence, the updated Catchment Management Planning guidelines (including aspects of climate change) will be professionally reviewed, edited and popular versions produced.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Environmental and social safeguard measures has been implemented to mitigate the first unwanted impacts of the project, such as: - Implication of Catchment Management Structures (CMCs and SCMCs) to ensure that a transparent and participatory process is followed in selecting beneficiaries according to agreed criteria: Nurseries, Women groups, concrete adaptation sites communities. - Sensitization sessions on the risks of natural resources degradation and their impact on the revenues are organized. - Promotion of local and indigenous species though sensitization of women groups. - Involvement of the Directorate of Environmental Affairs which is in charge of forestry activities to provide guidance and reasons on using other species which are preferred to Eucalyptus trees - Environmental and Social assessment of the rehabilitation and restoration action plans are being conducted by consultancy to mitigate the potential impacts.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | Delibarate efforts have been made to involve women, youth and elderly in the activities carried out so far. Gender consideration has been maintreamed at different levels during this reporting period: - The supporting staff recuited includes young professional and women at 30%. - The SCMCs established have a good representation of women, elderly and youth. women represent 40 % of the members in all the sub-catchments. - The participation of women youth and elderly to all the consultative meetings and workshops. - The Cook Stoves promotion activities are mainly executed by women groups for the benefit of women.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | The establishment of the Catchment Management Committees and their involvement in the selection of the most vulnerable sites to CC and related hazards is one of the positive lessons learned. This approach has ensured the mobilization and willingness of the communities in the execution of sensitive actions in particular the afforestation and the restoration of wetlands and riverbanks.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | This section will be filled in the next PPR.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | To date only awareness raising actions related to Climate Change impacts has been implemented. Communities are involved and sensitized toward the adapation measures planned by the project. More details will be provided in the next PPR.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | To date only awareness raising actions related to Climate Change impacts has been implemented. Communities are involved and sensitized toward the adapation measures planned by the project. More details will be provided in the next PPR.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | To date only the Catchment Management Communities has been established and can be considred as the most successful aspect for the target communities. More details will be provided in the next PPR.
What measures are/have been put in place to ensure sustainability of the project/program results? | Same
What measures are being/could have been put in place to improve project/program results? | Same
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | The output 1.1.1 and 1.1.2 has been using the exiting information from the Catchment Management Guidelines developed under a World Bank Project ended in 2018. The output 1.1.1 will use the data for development of popular versions of these guidelines and their dissemination, while output 1.1.2 will improve them by including the CC dimension in the catchment management plans.
If learning objectives have been established, have they been met? Please describe. | This section will be filled in the next PPR.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | This section will be filled in the next PPR.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | This section will be filled in the next PPR.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | UGA/RIE/Water/2015/1
Implementing Entity | Sahara and Sahel Observatory (OSS)
Type of implementing entity | Regional Implementing Entiy
Country | Uganda
Region | Africa
Sector | Water management
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 928355 | 132620 | 795735 | Total | 173490 | 24780 | 148710 | Total | 43370 | 6196 | 37174 | Total
|  | % of female beneficiaries | 53% | 53% | 53% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries | 37% | 37% | 37% | % of female beneficiaries
|  | % of Youth beneficiaries | 34.8% | 34.8% | 34.8% | % of Youth beneficiaries | 12% | 12% | 12% | % of Youth beneficiaries | 8.1% | 8.1% | 8.1% | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 | 0% | Public |  | 955 | 31% | Public |  | 500 | 36% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Water management | 1: No capacity | Public | Local | Water management | 3: Medium capacity | Public | Local | Water management | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Agriculture | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
|  | Water management | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Water management | 2: Physical asset (produced/improved/strenghtened) | 2: Somewhat improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | National |  | Water management | 4 | National |  | Water management | 1 | National |  | Water management
|  | 0 | Community |  | Water management | 9 | Community |  | Water management | 0 | Community |  | Water management
|  | 0 | Community |  | Disaster risk reduction | 9 | Community |  | Disaster risk reduction | 0 | Community |  | Disaster risk reduction
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 1000 | ha rehabilitated | 2: Partially effective | Forests | 1000 | ha rehabilitated | 4: Effective | Forests | 1 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 300 | ha rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 300 | ha rehabilitated | 4: Effective | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 200 | km rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 200 | km protected | 4: Effective | Catchment area/Watershed/Aquifer | 1 | km protected | 2: Partially effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer | 320 | ha rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 320 | ha rehabilitated | 4: Effective | Catchment area/Watershed/Aquifer | 1 | ha rehabilitated | 2: Partially effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 | 0% | 1: No improvement |  | 2400 |  | 4: High improvement |  | 0 | 0% | 1: No improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% | From 0.5 to 1% | Services | 3000 |  | From 1% to 5% | Services | 0 | 0% | From 0 to 0.5% | Services
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Water management | National | Water policy | 1 | Water management | National | Water policy | 0 | Water management | National | Water policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste