## Overview
Project Performance Report (PPR)*
* Refers to both projects and programs
| Period of Report (Dates) | October 15th 2018 - October 15th 2019
| Project Title: | AYNINACUY: Strengthening the livelihoods for vulnerable highland communities in the provinces of Arequipa, Caylloma, Condesuyos, Castilla and La Union in the Region of Arequipa, Peru
| Project Summary: | The project objective is to reduce vulnerability and increase adaptive capacity to respond to the impacts of climate change of the highland Andean peasant communities in the provinces of Arequipa, Caylloma, Castilla, La Union, and Condesuyos. In view of the fact that these communities depend almost exclusively on the production of alpaca fiber, the Project seeks to reduce their exposure to the threats of climate risk, through the strengthening of their livelihood through the development of adaptation processes and reduction of climate change risks which grant resilience to this way of life and through the strengthening of capacities of the communities for reducing the risks associated with the economic losses resulting from the effects of climate change. The project promotes the breeding of alpaca and improves fiber production, as well as providing access to safe water and housing in producing communities in extreme poverty. The project includes the installation of SAT early warning modules, improvement of levees, improvement of rustic channels to optimize water management to expand wetlands in Andean highland areas, reconstruction of outhouses to improve sanitary conditions and prevent mortality of pregnant female alpacas and newly born offspring, as well as the placement of protection fences and cultivation of pastures for forage.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | PER / RIE / Rural / 2015/1 | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | CAF - Development Bank of Latin America | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Regional Implementing Entity (RIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Peru | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Peasant communities in the provinces of Arequipa, Caylloma, Condesuyos, Castilla y La Union: San Juan de Tarucani, Huayllacucho, Sarpani, Misahuanca, San Antonio, Rio Blanco, Tolconi I, Huaracopalca, Chapacoco, CuspaMaghuanca, Pampamarca, Tecca-Rumiwasi, Huayqui, Huarcaya, Ancaro, Visca, Cristal Puquio, Chojanilayoc,Arirahua, Huamanmarca, Huchumiri I, Huchumiri II, Capilla, Maucallacta, Pusa Pusa, Santa Rosa, Ran Ran, Chungara,Tres estancias,Condorcuyo, Hanansaya I, Hanansaya II, San Antonio de Chuca and Vincocaya. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | March 17, 2017
IE-AFB Agreement Signature Date: |  | September 8, 2017 / Addendum date: August 21, 2018 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | October 15, 2018 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable):
| Original Completion Date: | April 15, 2021
Revised Completion Date after approval of
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://www.copasa.gob.pe/proyectos/proyecto-ayninakuy/ | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National/Regional Project Manager/Coordinator |  |  | Dominica
| Name: | Maria Angelica Salinas Valencia | Dominican Republic
| Email: | mariangelicasv@hotmail.com | Ecuador
| Date: | 15/10/2018 | Egypt
Government(s) DA [if regional project/program add rows as necessary]
El Salvador
| Name: | Sra. Rosa Mabel Morales S. - General Director of the General Directorate for Climate Change and Desertification - Ministry of Environment of Peru | Equatoral Guinea
| Email: | rmorales@minam.gob.pe | Eritrea
| Date: | 15/10/2018 | Estonia
| Implementing Entity |  | Ethiopia
| Name: | María Carolina Torres / Carolina Cortés - Development Bank of Latin America - CAF | Fiji
| Email: | mctorres@caf.com / acortes@caf.com | Finland
| Date: | 15/10/2018 | France
| Executing Agency |  | Gambia
| Name: | Elva Cueto de Mariscal - Executive Director - Cooperation for Sustainable Development in Arequipa -COPASA-Arequipa's Regional Government | Georgia
| Email: | ecuetom@copasa.gob.pe | Germany
| Date: | 15/10/2018 | Ghana
| Executing Agency |  | Greece
| Name: | Maria Argüello (Executive Director of the Consortium for the Sustainable Development of the Andean Eco region - CONDESAN) | Grenada
| Email: | maria.arguello@condesan.org | Guatemala
| Date: | 15/10/2018 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: |  | Guyana
| Email: |  | Haiti
| Date: |  | Honduras
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to October 15, 2019 |  |  |  | Financial information PPR 2: cumulative from project start to [insert date] |  |  |  | Financial information PPR 3: cumulative from project start to [insert date] |  |  |  | Financial information PPR 4: cumulative from project start to [insert date] |  |  |  | Financial information PPR 5: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS |  |  |  | DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date? |  |  |  | How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of of October 15, 2019 | 723956 |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date] |  |  |  | Estimated cumulative total disbursement as of [enter Date]
Add any comments on AF Grant Funds. (word limit=200) | This is the amount that CAF has transferred to the Administrative Executing Entity- CONDESAN. However, AF has transferred a total of USD 923, 255 to the Implementing Entity, CAF. The transfer made by CAF to CONDESAN is based on clause 13 of the Agreement signed between CAF-CONDESAN-COPASA, which states: "CAF will contribute the Funds for the Project, which will be disbursed to the Administrative Executing party, once CAF submits the corresponding disbursement request, which accredits compliance with the Agreement, to CAF's satisfaction The amount of payments to be transferred by CAF to the Administrative Executing party will be transferred up front, on a semi-annual basis, according to the updated semi-annual Acquisition Plan, and according to the level of budget execution (for amounts agreed between the Administrative Executing party and CAF)." |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200) |  |  |  | Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | USD 562 |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME |  |  |  | INVESTMENT INCOME
Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant |  |  |  | Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA |  |  |  | EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT |  | List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| COMPONENT 1: APPLICATION OF MEASURES AIMED AT STRENGTHENING MEANS OF SUBSISTENCE AND SOURCES OF INCOME FOR VULNERABLE COMMUNITIES | 285855.04
| ANIMAL NOURISHMENT AND PROTECTION AXIS | 267049.99
| Products 1.1.1: shelters built for animal protection (in particular alpaca dams and offspring) | 115829.58
| Products 1.1.2: Protective fences, with livestock netting, installed. | 30761.75
| Products 1.1.3: Seeding and cultivation of high altitude forage cereals. | 111544.97
| Products 1.1.4: Seeding and cultivation of improved grasses. | 764.58
| Products 1.1.5: Installation of clover in wetlands for improving forage cover | 1185.91
| Products 1.1.6: Animal health campaigns in selected rural communities | 6963.2
| WATER RESOURCE MANAGEMENT AXIS | 18805.05
| Products 1.2.1: Pressurized irrigation modules installed in selected communities. | 7135.86
| Product 1.2.2.: Vulnerable physical, natural, and social assets strengthened in response to climate change impacts, including variability. | 734.52
| Products 1.2.4: Construction of reservoirs for storage of rainfall, runs or natural sources (springs). | 10934.67
| COMPONENT 2: IMPLEMENTATION OF MEASURES AIMED AT STRENGTHENING INSTITUTIONAL AND COMMUNITY CAPACITIES TO REDUCE RISKS OF LOSSES OCCASIONED BY CLIMATE CHANGE. | 18538
| KNOWLEDGE MANAGEMENT AXIS | 18538
| Products 2.3.3: Elaboration of technical guides | 18270.32
| Products 2.3.4: Training sessions about: | 267.68
| TOTAL DIRECT COSTS = (COSTS SUB COMPONENTS 1 +2 OF THE PROJECT), USD | 304393.04
| PROJECT EXECUTION COST / ADMINISTRATIVE EXPENSES | 71173.89
| A.- PROFESSIONAL SERVICES | 65949.78
| B.- TICKETS AND PER DIEMS | 457.53
| C.- VISIBILIZATION /DISSEMINATION | 230.07
| F.- ENVIRONMENTAL MANAGEMENT MONITORING AND EVALUATION | 4536.51
| TOTAL DIRECT + INDIRECT COSTS, USD | 375566.93
| PROJECT IMPLEMENTATION COSTS, USD | 0
| TOTAL | 375566.93
| TOTAL | 375566.93 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0 |  |  | TOTAL | 0
PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE |  |  |  | PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST al segundo año | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date | List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| COMPONENT 1: APPLICATION OF MEASURES AIMED AT STRENGTHENING MEANS OF SUBSISTENCE AND SOURCES OF INCOME FOR VULNERABLE COMMUNITIES | 1140218.92
| ANIMAL NOURISHMENT AND PROTECTION AXIS | 644159.74 | 2020-10-15
| WATER RESOURCE MANAGEMENT AXIS | 244170.16 | 2020-10-15
| ATTENTION TO HUMAN HEALTH AXIS | 251889.02 | 2020-10-15
| COMPONENT 2: IMPLEMENTATION OF MEASURES AIMED AT STRENGTHENING INSTITUTIONAL AND COMMUNITY CAPACITIES TO REDUCE RISKS OF LOSSES OCCASIONED BY CLIMATE CHANGE. | 141130.63
| GOVERNANCE AXIS | 1791.41 | 2020-10-15
| RISK AND CLIMATE CHANGE MANAGEMENT AXIS | 28455.88 | 2020-10-15
| KNOWLEDGE MANAGEMENT AXIS | 110883.34 | 2020-10-15
| PROJECT EXECUTION COST / ADMINISTRATIVE EXPENSES | 75072
| A.- PROFESSIONAL SERVICES | 64392 | 2020-09-30
B.- TICKETS AND PER DIEMS
C.- VISIBILIZATION /DISSEMINATION
E.- TRANSPORT AND MOVES
| F.- ENVIRONMENTAL MANAGEMENT MONITORING AND EVALUATION | 10680
| TOTAL | 1356421.55
[8 empty] | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.) |  |  |  | ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
[8 empty] | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized? |  |  |  | How much of the total co-financing as committed in the Project Document has actually been realized?
[8 empty] | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  |  |  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
[8 empty] | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  |  |  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The exchange rate for the PEN/USD is not holding above 3.43 | Low; it remained in this condition throughout the first year of implementation. | The Central Reserve Bank of Peru's exchange rate projections were reviewed on a quarterly basis, and an annual variation of 3.35 was identified. This issue is not considered unfavorable for the first year of project execution. Additionally, the Administrative Executing Entity receives the amounts in dollars, and the staff has the option of receiving their salary in Soles or in Dollars. Similarly, consulting contracts can be prepared in Dollars or in Soles. http://www.bcrp.gob.pe/estadisticas/cuadros-de-la-nota-semanal.html https://estadisticas.bcrp.gob.pe/estadisticas/series/mensuales/resultados/PN01206PM/html/2018-10/2019-10/
The restrictions foreseen for water resources are increased meaningfully by unforeseeable effects of climate change and of its variability. | Low; there have been no considerable changes in climate scenarios. Variations fall within the project's anticipated effects. | - For monitoring purposes, and in order to receive monitoring information, activities have been coordinated with the Local Water Authority (ALA) and the National Meteorology and Hydrology Service of Peru (SENMAHI). - The reports of the National Water Resources Information System of the National Water Authority and SENAMHI are consulted every six months. https://snirh.ana.gob.pe/consultassnirh/oHerramientasSnirh.aspx https://www.senamhi.gob.pe/?&p=monitoreo-hidrologico - During 2019, climate projections did not affect water availability in the communities.
Resistance to change in vulnerable communities | Low; this risk remains low given the communities' strong support for the implementation of the project. | - Agreements were signed with local and communal authorities to guarantee cooperation and mutual support in the 36 communities. - Technical guides on climate change adaptation and environmental management were used. These guides were developed to provide information on the benefits of the project. - Training in climate risk management for students enrolled in district schools is planned for the second year, thereby ensuring the adaptation of best practices. - Field Technical Specialists -Yachachiq's native language is Quechua, and this facilitates the identification of the beneficiaries and members of the communities and enables building a strong connection with them. These beneficiaries and community members are key stakeholders in the implementation and sustainability of the activities that are being implemented.
The project’s dissemination, communication and motivation strategies are not effective for achieving a broad and active participation on the part of women. | Low; it remains low given women's participation in training processes and in the implementation of activities. | - Mechanisms were developed to invite women to apply to the Field Technical Specialist positions - Yachachiqs, in each community: home visits were carried out for each beneficiary, the Lieutenant Governors of the Districts and the leaders of the community pledged their support to reinforce the calls. As a result, women's participation amounted to 31% and this percentage is expected to increase for the second year. - Family and personal development matters, as well as equality issues in couples' decision making (taking into account women's opinions) are addressed throughout the training sessions, along with technical issues such as improving the sheds, installing protection fences for grasslands, and improving pastures. - Women have been prioritized as beneficiaries of 50% of project activities
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Climate change manifests itself differently and with greater intensity than projected by analyzes and studies. This could affect the success of particular adaptation measures that will be tested throughout the project’s life. | Medium: - During the December 2018-March 2019 rainy season, the effects on the communities were as foreseen by the project. - 60% of the selected districts with DS Nº 023-2019-PCM (February 12) were declared in emergency. This prevented the implementation of activities on the scheduled dates -The same happened during the June-August period, due to low temperatures with an intensity that was not foreseen by the project. This affected 84% of the districts, which were declared in a state of emergency by means of DS N° 158-2019-PCM | -The executing agency COPASA coordinated actions with the Emergency Operations Center (COER) to obtain information on the restoration of the affected roads and highways. In some cases there were alternative routes, which were deemed safe to be used by the communities and for delivering materials, complying with the planned and supervisory activities. - Coordination is maintained with the National Meteorology and Hydrology Service of Peru (SENMAHI) to obtain meteorological information regarding climatic events in the project areas and to better schedule the activities during the rainy and cold season.
Change of the Regional Government and local authorities, who will have to commit themselves to a project they are unfamiliar with. A few months will be required for them to comprehend the advantages of the climate change adaptation project. | Low: - There was a change of Regional Government and local authorities in January 2019, and this implied minimal changes in the beneficiary targeting process. | During the first quarter of 2019, individual meetings were held with the new authorities to inform them about the Ayninacuy Project, the signed agreements and commitments assumed by their predecessors. The new authorities ratified their support to the agreements. No changes are expected for the second and third years of execution.
Salaries for the Field Technical Specialists – Yachachiqs, and the Field Supervisor are below the market value. | Medium: - Better salaries are offered in other similar projects, and this could attract the attention of team members, thus affecting the continuity of the Project’s activities | - Budget adjustments have been discussed with the Project’s Advisory Steering Committee, in order to better adjust salaries to market values, making sure that this doesn’t affect the total budget amount.
In the proposal design, only one (1) Field Supervisor was considered: | Medium - The current Field Supervisor must cover a territorial extension of more than 1500 km, which corresponds to making a round trip of the project. This means that the field supervisor needs 45 field days to implement his activities, which makes the supervision activity inefficient and ineffective. | -Budget adjustments have been discussed with the Project’s Advisory Steering Committee, in order to hire a Second Field Supervisor, which will allow providing support to the most remote provinces and recovering time lost and delays in reaching these communities. Each of the two supervisors can distribute the workload between 22 days, and this will allow for greater efficiency.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | • Physical and cultural heritage. • Protection of protected natural areas and natural resources. | 1. At the beginning of the Project, the Project Director verifies with the environmental authority, whether the requirement to submit the Project’s Environmental and Social Management Report (ESMR) is applicable. 2. The Project Director follows up every two weeks to the environmental authority’s response to the consultation regarding the applicability of the requirement to submit the Environmental and Social Management Report (ESMR). 3. In the event that the response to the consultation to the environmental authority (regarding the applicability of the requirement to submit the Project Environmental and Social Management Report (ESMR) implies the need for the Project to assume commitments with regard to the Ministry of Environment, the Project Director will provide a timely response to the required commitments. 4. The Project’s Field Supervisor is executing the plan on a timely basis, in order to respond to commitments in the ESMR. 5. The Field Supervisor verifies the current regulations in environmental matters and physical and cultural heritage before scheduling a field activity, following the planned procedures and, if applicable, informs the competent activity. | (1) Coordination meetings with environmental authorities (2) Document attended (Environmental Management Report) (3) (4) Technical report (5) Field activities carried out to date have not breached any environmental regulations. | Coordination Meeting with the Environmental Authority - SERNANP Semiannual Environmental and Social Management Report, from the Project Director Monthly report of the Field Supervisor on the activities carried out, addressed to the Project Director | (1) (2) Technical meetings were coordinated with the Directors of the Salinas and Aguada Blanca Reserve and the Cotahuasi Sub-Basin Landscape Reserve. During these meetings, it was confirmed that the activities carried out will not generate a greater impact in the targeted areas superimposed on the reserve’s buffer area, because these activities only contribute to the improvement of the dwellings and productive units of the settled population. (2) The Technical Opinion Compatibility Report 954-2018-SERNANP-DGANP was issued by SERNANP (4) The field supervisor reported the measures implemented in the field pertaining to products 1.1.1 Improvement of sheds and 1.1.2 Fences of livestock mesh. | There were no impacts.
2 - Access and equity |  |  | •Effectiveness of the calls •Lack of trust from the community, due to similar projects that were not successful | Regarding the risk in the effectiveness of the calls (in their contacts and motivation), at the following levels: 1.i. COPASA towards local authorities; 1.1. For each cycle of calls, the Project Field Supervisor prepares a synthesized proposal for the call. 1.2 The previous call proposal is reviewed, commented and authorized by the Project Director, who copies the final proposal to the COPASA’s Executive Director and to CAF- Implementing Entity. 1.3. The Project Field Supervisor initiates or implements the call proposal authorized by the Project Director. 1.5. The Environmental Specialist submits an evaluation report to the Project Director, who attaches it to the project’s periodic monitoring and evaluation reports. 1.6. It is the responsibility of the Project Director to verify that each authorized call proposal includes the relevant lessons learned that the Project may have generated. 2. At level ii. The local authorities (district mayors) towards the communities’ representatives, through other figures of the district authorities (vice governors, sub-prefects, commissioners, others) and through community leaders. 2.1. At the beginning of the Project, the Field Supervisor will prepare a list of critical contacts for each District (including contacts for each community, responsibilities, names and, if possible, phone numbers). 2.2. As of the first meeting, the Field Supervisor will be responsible for reaching agreements between the leaders and representatives of each community, organizing a network of key contacts (for each critical contact, two alternative means to deliver information). 2.3. The Field Supervisor initiates and implements the call proposal, authorized by the Project Director. 2.4 In case there are errors made by the Field Technical Specialists that could lead to shortfalls in the calls, these will put in writing by the Field Supervisor. 2.5 The Field Supervisor verifies: - Compliance of the agreements for the selection of direct beneficiaries -The effective call made to community members during the training and instruction sessions. -Compliance with the quarterly schedule of training activities and field days. The role of the activities is shared with the district mayors. 3. Regarding the risk in the coherence of the preparation of the agreements: the agreements must be practical and socially viable. 3.1. An agreement will be drawn up for each of the 18 selected districts and 36 communities targeted by the Project, in order to decide the mechanism to select the direct beneficiaries of the following activities: a. Sheds for camelids, fences, cattle mesh, rustic water canals, rustic reservoirs, pressure irrigation modules. b. Improved housing c. Seeds for the cultivation of forage cereals at altitude, seeds for improved pastures at altitude, seeds to install clovers in wetland buffer areas. d. Tools to improve rustic canals, to optimize water management. e. Supplies for animal health campaigns. f. Training workshops 3.2. As a direct beneficiary of the activities described in items a. and b., the following will be designated: -The head of each productive family unit -Or the representative from a group of two or more families from productive units (in the latter case, members sign a commitment clause where they agree to share these spaces). 3.3. To aspire to become a direct beneficiary of the activities described between a. and e. above, the candidate must have participated in one or more of the corresponding training workshops. 3.4. To aspire to become a direct beneficiary of the activities described between a. and d. above, the candidate must commit to comply with the number of work hours or days set per activity, which must be defined in an agreement signed by the beneficiary. 3.5. Before signing each agreement, the Project Field Supervisor is responsible for distributing a list of the resources available for each activity. 4. Regarding the follow-up to the agreements in decision making processes. 4.1. In all meetings where at least one decision is made related to the selection of direct beneficiaries, the meeting minutes will include written evidence of this decision and all interested parties participating in the meeting will sign the minutes. 4.2. To make such a decision, a complete written copy of the minutes of each meeting must be available, and these minutes must include the agreements for the selection of direct beneficiaries. 4.3. The procedures followed to select the beneficiaries are explained to the community, and a clause acknowledging the selection process will be included in the minutes. In agreements made prior to the Project’s activities or its outputs. 5. Before the beginning of an activity cycle or developing a Project output, the Project Field Supervisor is responsible for: 5.1. Verifying that a workplan is prepared for the development of the activities or products. 5.2. Verifying that the workplan for the implementation of the activities or products is shared with the corresponding beneficiaries and participants. 5.3. Verifying that the contributions, opinions and requests of the beneficiaries and participants regarding the workplan for the implementation of the activities or products and its implications, are included in its dissemination. 5.4. If the beneficiaries request any modifications to the workplan, these will be submitted to the consideration of the communal Assembly . 5.5. Verifying that during the dissemination of the workplan, community members’ comments, opinions, requests or complaints and concerns related to other aspects of the project, are compiled in writing to the project Director and that the response is communicated in a timely manner to the community. | (1.1) (1.2) Plan implemented (1.3) Technical report (2.1) Directory implemented (2.2) Signed Agreements and/or Minutes (2.3) Planning the call (2.4) (2.5) Monthly Technical Report. Monthly oversight report (2.5) Attendance lists Signed agreements and/or Minutes (3.1) (3.2) Signed agreements (3.3) Attendance list (3.4) Commitment minutes Report Delivered (4.1)(4.2)(4.3)(4.4)Meeting Minutes Signed minutes (5.5) Monthly report | Training Development Plan and coaching sessions. Field Technical Experts' monthly progress report Field Supervisor’s monthly project progress report. Project Director’s Quarterly Project Progress Report 2,1 Directory of Stakeholders (2.2) 4 agreements with Provincial Governments, 18 agreements with district governments and 36 minutes signed and ratified (2.3) Call plan proposal submitted to the Project Director (2.4) Monthly activities report from Field Technical Experts (2.4) (2.5) Field Supervisor’s quarterly project progress report (3.1) (3.2) District and Communal Agreements signed (3.1) (3.2) Minutes signed by the beneficiaries (3.3) Attendance list of training sessions (3.4) Minutes signed by the beneficiaries Field supervisor Monthly Report (4.1)(4.2)(4.3)(4.4) Minutes of community meetings 1 workplan 36 agreement minutes per meeting Field Supervisor’s monthly report on Plan compliance Project Director’s Quarterly Report | (1.1) (1.2) The Training Plan was prepared, and it includes the activities to carry out the calls: Objectives, call activities, contents of the calls, a list of the leaders/representatives or contacts to be convened and support strategy or strategies. (1.3) The Field Supervisor made the call before the field work, as follows: - initiated the call, in January 2019, with local authorities, to sign the agreements to initiate Project activities (outputs 2.1.1 and 2.2.2, 2.3.1) - In April 2019, the call for activities 1.1.1 Improvement of sheds and 1.1.2 Fences of livestock mesh and 2.3.4 Training sessions for the improvement of sheds and installation of fences began. (2.1) The directory was prepared in accordance with the map of stakeholders and development of a directory with key stakeholders: - Governmental: Mayors, Municipality’s Agricultural Technician, President and vice president of the community. - At the educational level, the director of the Local Educational Management Unit (UGEL) was identified. - Head of the Natural Reserve - Head of the Landscape Reserve - Head of Agrarian Agency of the 5 provinces. - Director of SENAMHI -Arequipa. - Head of the Regional Office of Civil Defense (2.2) There are signed agreements from 5 provinces: Arequipa, Caylloma, Castilla, Condesuyos and La Unión. 18 districts: S.J. Tarucani, Orcopampa, Pampacolca, Chachas, Chilcaymarca, Puyca, Pampamarca, Huaynacotas, Toro, Chuquibamba, Andaray, Yanaquihua, Salamanca, Caylloma, Tuti, Sibayo, Callalli, San Antonio de Chuca 36 communities: S.J.Tarucani, Huayllacucho, Sarpani, Misahuanca, San Antonio, Rio Blanco, Toconi I, Huaracopalca Chapacoco, Huilluco, Cuspa, Maghuanca, Pampamarca, Tecca-Rumihausi, Huayqui, Huarcaya,Ancaro, Visca, Cristal puquio, Chojanilayoc, Arirahua, Huamanmarca/Ochuro/Tumpullo, Huchumiri I, Huchumiri II, Capilla / Pucuncho I, Maucallacta , Pucuncho II, Pusa Pusa, Caylloma/ Santa Rosa, Ran Ran, Tuti / Chungara, Tres Estancias, Condorcuyo, Hanansaya I, Hanansaya II, San Antonio de Chuca, Vincocaya / Imata. (2.3) The Field Supervisor implemented the call proposal, coordinating on a monthly basis with the Field Technical Specialists. Invitations to the activities were carried out effectively: presenting and increasing awareness of the project at the local and community level, presenting the Activity Plan, the training program, selecting the beneficiaries, and implementing training sessions to improve sheds and fences. (2.4) (2.5) The Field Supervisor verified the selection agreements with local and communal authorities, and identified the following: -In 95% of the districts the initial communal assembly commitments were met. - The Mayor of the Anduaga district is not willing to be part of the project due to political discrepancies with his predecessor. Given this situation, the Mayor of Pampacolca’s request for the project to benefit the communities in her district was approved. - There is still limited participation of women, in 3 communities (10%) because their communities are in very dispersed areas. These communities are Rio Blanco, Cristal Puquio, Huilluco. To improve the call, work will be carried out in advance in order to engage the participation of more women. There are 71 attendance lists for training events, prior to the implementation of activities to improve the sheds and install the fences. There are 18 District agreements and 36 communal agreements. There are 42 minutes signed by the beneficiaries (16 men, 10 women) Certification from the Household Targeting System (SISFOH). There are 33 attendance lists to training workshops for the improvement of sheds and the installation of livestock mesh fences. There are 42 minutes signed by the beneficiaries. In the monthly reports, the Field Supervisor has provided information on the agreements and commitments signed by the beneficiaries: Proper material storage and use, compliance with the technical specifications for the improvement of sheds and installation and livestock mesh, adequate use of the improved spaces. (4.1) (4.2) (4.3) (4.4) There are minutes that have been signed by the communities, containing clauses that define the mechanisms for the selection of beneficiaries and the annulment procedure. (5.1) (5.2) (5.3) Operational Plan presented to 36 communities, shared during the first training meetings for the improvement of sheds and the installation of fences. (5.4) 42 training sessions were held in which the beneficiaries were informed about the scope of each activity carried out: the improvement of sheds and the installation of fences. The Field Supervisor’s activity report includes the following suggestions made by beneficiaries regarding the training sessions: - Training events should not be schedules on the same dates as local holidays. - The official Agricultural and alpaca management calendar should be taken into account. - The opinion of the community leaders should be taken into account when making decisions regarding the beneficiaries. - It is important to coordinate with other institutions that are working in the area, to avoid scheduling activities on the same date. These suggestions were collected and taken into account when selecting beneficiaries and when programming project activities. | There were no impacts.
3 – Marginalized and vulnerable Groups
4 – Human rights
5 – Gender equality and women’s empowerment |  |  | • Participation of women. • Women's access to the benefits of the project. | 1. Before each cycle of calls, the Project Director is responsible for preparing a call strategy. 2. The Project Director will be responsible for evaluating and reinforcing the communication proposals of the Field Supervisor regarding the clarity of the contents, promoting improvements (including the objectives of the project and the participation of women in connection with the activity) and the consistency with the call strategy. 3. The Project Field Supervisor will be responsible for training and strengthening the proposals and communication skills of the Field Technical Specialists (Yachachis), as described in the previous paragraph. 4. At the beginning of each cycle of activities, the project’s Field Supervisor will make a positive motivational acknowledgement and will reinforce the call and the results obtained regarding the overall participation and the participation of women. 5. At the end of each call cycle, the Project Director is responsible for evaluating the call strategy resulting from the implementation and for including the relevant lessons learned in the evaluation report. 6. During the implementation of the project activities, the Field Supervisor will be responsible for reminding the parties responsible for the activity, to verify the following recommendations during the implementation of the follow-up activities: • In all Project activities involving collective or group participation, establish criteria for women’s participation: women should be treated equally when they speak and then they vote on decisions. The location of men and women in workshops should be arranged equitably. • Encourage gender equity in all training and coaching sessions. | Training Plan (including the call strategy) Monthly Progress Report | Training plan approved by the Project Director Monthly Report of the Field Technical Specialist (Yachachiq) Monthly report of the Field Supervisor. Quarterly Report of the Project Director | The Training Plan foresees that the Training Module will be developed by taking into account women’s equality and participation. Five guides highlighting the participation of women were prepared: 1) improvement of sheds, 2) adaptation to climate change, 3) planting forage cereals, 4) installation of irrigation pilot 5) operation of the early warning system. | There were no impacts.
6 – Core labour rights
7 – Indigenous peoples |  |  | There weren't any risks identified, as the project involves only rural Andean (non-indigenous) communities. However, the presence of a Yachachiq Field Technical Specialist, who acts as a Quechua and Spanish translator/interpreter, guarantees that participants in all meetings and workshops are able to understand. | 1. At the beginning of each activity in the communities, the Project Field Supervisor is responsible for verifying in which language the training will be carried out (Spanish or Quechua). 2. At the end of each meeting, the group will consult on the need to maintain the interpreter / translation mechanism during the following Project meetings or activities with the same community. 3. The decision to continue with the interpreter/translator for the following Project meetings or activities with the same community, shall be recorded in the minutes of the meeting. 4. In case there is consensus on the decision not to perform a translation, the decision will be recorded in the meeting minutes. | Translator / Interpreter identified and meeting minutes | 5 Field Technical Specialists - Yachachiqs with bilingual Quechua / Spanish skills | - 5 Field Technical Specialists - Yachachiqs were hired with native language skills: Quechua / Spanish. - A leader was identified for each community (a native), to support the Yachachiq during the trainings. - During the first training sessions for the improvement of sheds and installation of fences with livestock mesh, a decision was made regarding the language to be used for the training, | There were no impacts.
8 – Involuntary resettlement
9 – Protection of natural habitats |  |  | Protection of protected natural areas and natural resources | In the event that the selection of the project’s direct beneficiaries (in line with the relevant procedures) includes areas within the limits of the Reserve, to be intervened by the project: 1. The Project Director provides notification to the environmental authority- SERNANP of the situation, while also including a summary of the project’s objectives, activities and progress. 2. The Project Director monitors the response of SERNANP. 3. In the event that the response from SERNANP applies environmental and/or social requirements to the project, the Project Director will include the measures to comply with the requirements in this component of the Environmental and Social Management Plan. 4. The Field Supervisor sends the requirements to the Field Technical Specialists and verifies and documents compliance with the requirements made by SERNANP. | Requirement made by the Environmental Authority Field Supervisor’s technical report | By means of the Technical Executing Entity, the Project Director, sends the request to the Environmental Authority for the Opinion on Technical Compatibility. Quarterly Report of the Project Director Monthly Report of the Field Supervisor | SERNANP was informed of the implementation of the project and it issued the Compatibility Report and gave a favorable opinion regarding the Environmental and Social Management Plan. (954-2018-SERNANP-DGANP), since the project will not carry out activities within the reserve. Before the beginning of each activity, the Field Supervisor reviews the conditions outlined in the Compatibility Report and reports on any contingencies identified. | There were no impacts.
10 – Conservation of biological diversity |  |  | • No risks were identified; preventive measures were established, nonetheless. | 1. It is up to the Project Director to consult with the relevant environmental authority, regarding the ecological adoption of species such as Ryegrass and Dactylis Glomerata (grasses) and other non-native cultivated grasses as forage alternatives. 2. In the event that the authority’s eventual response implies decisions that affect the programming of project activities with regard to the cultivated pastures, the Project Director and CAF-Implementing Entity will agree on an alternative plan for the activities that could be affected. 3. If an alternative plan has been defined for the project activities in relation to cultivated pastures, the Project Director implements the plan accordingly. | Technical report | Field Supervisor Report on crops approved by the environmental authority-SERNAP | Safeguard measures have not been implemented, because activities 1.1.3 Seeding and cultivation of highland forage cereals and 1.1.4 Installation of clover in wetlands for improving forage cover, have not yet been implemented. | There were no impacts
11 – Climate change |  |  | • Conversion of peat deposits • Greenhouse gas emissions from vehicles | 1. Before taking part in the activities, a photographic record will be produced on the state of the wetlands. 2. The processes defined for the improvement of the existing rustic channels will be authorized by the Project Field Supervisor, before implementation. 3. The areas used for planting the resistant native species proposed by the Project, will be authorized by the Project Field Supervisor, in accordance with the following principles: 3.1. The parts of the wetland that are wet, will remain wet and will not be intervened. 3.2. As far as possible, dehumidification will be attempted in the parts of the wetland that can be drained. 3.3. For parts of the wetland that are unlikely to be re-humidified, some of the following management measures will be implemented if possible, given the terrain conditions: cleaning the wetland; implementing measures to prevent overgrazing; irrigating buffer zones and sowing clover seeds. 3.4. The use of native resistant species (red and white clovers) for the recovery/expansion of the wetland, will only be implemented in the re-humidified areas of the wetland or in the expanded irrigation areas obtained by managing rustic canals. 4. Prior to the implementation of the activities for the recovery and expansion of the wetland, the Project Director will order that at least two soil samples are taken from two large wetlands that can be located in several areas (a sample from each wetland), and which can be included in the wetlands to be recovered. Control greenhouse gas emissions-GHG from the project’s vehicles. 5. The Field Supervisor is responsible for maintaining an updated registry of each vehicle used for Project activities. 6 The Field Supervisor is responsible for maintaining an updated copy of the Official Gas Certificate for each vehicle. This copy shall be kept in the registry of vehicles used for Project activities. | (1) Photographic record of the state of the wetlands (2) (3) Approved technical report (5) Registry for each vehicle (6) Official Gas Certificate for each vehicle (4) Soil study (5) Contracts and agreements (6) (7) Semiannual report | Photographic record per wetland (72 hectares) Technical Intervention report from the Environmental Specialist Monthly Field Supervisor Report Quarterly Report from the Project Director (5) Contractual clauses (6) (7) Semiannual Supervisor’s Report Quarterly report from the Administrator | Safeguard measures have not been implemented, because activity 1.1.5 for the recovery of wetlands has not been implemented yet. The following means are used to transport personnel and materials. They all have the circulation and smoke control permits required by law: - 1 COPASA 4x4 truck - 5 trucks from Local Governments (one per province) - 5 motorcycles | There were no impacts
12 – Pollution prevention and resource efficiency |  |  | • Solid waste | 1. Before performing the following activities: i. events related to skills development and ii. activities to improve or build sheds for animal protection, the party responsible for the activity will prepare the elements to contain solid waste, considering the following classification: organic waste, recyclable inorganic waste and other waste. Containment elements will include plastic bags and/or plastic containers. 2. At the beginning of the activities, participants will be instructed on the classified collection of solid waste. 3. At the end of the event, it will be verified that the classified waste is brought to the local solid waste management system. If the activity is carried out in a rural area, the party responsible for the activity will verify that the classified waste is properly disposed of or that it is transported to an urban area to be incorporated into the local solid waste management system. 4. The party responsible for the activity will document the activities described in this section, including by means of a photographic record. | Implemented Plan Photographic record Activity Report | Solid Waste Management Plan Project Monthly Field Supervisor Report Quarterly Report of the Administrative Assistant (purchases are also linked to the waste issue) | For the implementation of these measures, a Solid Waste Management Plan was developed for the Project activities, carried out so far: a. Training Sessions b. Coaching sessions c. Workshops | There were no impacts
13 – Public health
14 – Physical and cultural heritage |  |  | • Archaeological remains | 1. If the activity (improving or building the shed or implementing the water reservoir) is carried out on previously intervened land, the Certificate of Non-Existence of Archaeological Remains (CIRA) process is not applied. 2. The Field Supervisor verifies that the assigned location is technically adequate; and also confirms that, given its location, the work will not interfere with a body of water or with a wetland. 3. A photographic record will be made, and a label will be placed in the area defined for the activity. 4. The Field Supervisor collects information for the request made by CIRA [Certificate of non-existence of archaeological remains], in accordance with Circular 1998-2016-DDC-ARE / MC of the Decentralized Directorate of Culture of Arequipa. | Photographic record Activity report | Photographic record Quarterly Field Supervisor Report Project Director’s Annual report | The activities to improve sheds, carried out in 30 communities, took place in previously intervened areas, so it was not necessary to request the Certificate of Non-existence of Archaeological remains - CIRA. | There were no impacts
15 – Lands and soil conservation |  |  | • Soil conservation | 1. 1. Avoid compaction of the original soil layer in the area surrounding the work, to the extent possible. 2. Remove the layer of soil when it is dry, or the moisture content is less than 75%. 3. Keep the topsoil separated from the inorganic excavated subsoil; locate both separate piles where there is no chance of cascading and there are adequate drainage conditions. Protect them with a plastic cover to avoid erosion losses. 4. In the case of a reservoir, where storing the topsoil is not feasible, to the extent possible, relocate it nearby so that it can be recovered in case the reservoir is subsequently closed. 5. At the end of the activity, leave the workplace surroundings in better or similar conditions to those found before work. 6. Gather, classify and dispose of solid waste resulting from the activity, in accordance with the best practices in the area. If a disposal place is not found, take the waste to an appropriate disposal site, within the same district. 7. Document the management measures implemented, including the photographic archive. | Procedure Implemented Field Supervisor Report Photographic Registry | Procedure implemented by the Field Technical Specialist -Yachachiq Monthly Report by the Field Supervisor | No safeguard measures have been implemented because the activities have not yet been implemented: 1.2.3 Improvement of channels to improve water resources in wetlands, 1.2.4 Construction of rustic reservoirs for water storage rains, streams and natural springs. | There were no impacts
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | Risk monitoring is performed according to the ESMP, and the risks are within the levels identified by the project.
Have unanticipated ESP risks been identified during the reporting period? |  | No unexpected risks have been identified during the implementation of activities throughout the first year of the project.
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | No risks have been identified.
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization.
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | - CAF has ensured the Project Director’s commitment in the implementation of the Environmental and Social Management Plan, as established in the agreement issued by its Legal Consultancy, and signed between the two Executing Entities and the Implementing Entity. - CAF has initiated the process of hiring an Environmental and Social Specialist with its own resources - Continuous evaluation and monitoring meetings are held
Have the implementation arrangements been effective during the reporting period? |  | Yes, they have been effective in fulfilling the established contractual commitments and thereby the measures for each of the environmental and social principles
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | 1. Coordination with authorities from the Ministry of Agriculture - AGRORURAL; Directorate of Livestock; Ministry of Culture; Environmental Authority - National Service of Natural Protected Areas - SERNANP, in order to learn about the protocols to follow in natural reserves and places with heritage protection. 2. Coordination with local governments to ensure strong compliance with project activities and women’s engagement in training sessions.
Have the implementation arrangements at the EEs been effective during the reporting period? |  | Yes they have been effective, since the commitments assumed by the mayors and community chiefs, have enabled stronger acceptance of the project and the conditions for its intervention, with regards to the implementation of the gender policy. As for measures to mitigate social and environmental risks, they are well accepted by the community because they are part of their traditional environmental care practices.
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs.
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details.
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9]
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts?
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | Yes, the gender evaluation was carried out and consultations were held with the participation of women in the communities. As a result, the following gender-sensitive activities and indicators were included: 1. The project will guide its actions with the following criteria that promote equal participation and the empowerment of women in decision-making: i) In information and dissemination activities and in calls and invitations; ii) In meetings and decision-making processes in the communities; iii) In the logistics of the different events; iv) The commitment to ensure women’s participation is achieved during coordination activities with authorities and community leaders; v) The Project Director takes advantage of opportunities to motivate women's participation, during follow-up and monitoring activities, in identifying gaps and problems. The results of the call strategies and the participation of women are continuously monitored. 2. A parameter awarding priority to female heads of household was included for the selection of beneficiaries. 3. A goal specifying the minimum participation of women is considered for training activities throughout the entire project. Specifically for the housing improvement component, this percentage is increased. 4. At the organizational level, at least one woman is included in the civil defense platforms at the district and community level. 5. Preparing a guide on women’s development, personal growth and family strengthening.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes it is included, as shown below: OUTCOME 1.3: Improvement in the conditions of housing quality to withstand extreme climate conditions. - Indicator 1.3.2 Women heads of households prioritized in beneficiary selection criteria. OUTCOME 2.1: Greater awareness and ownership concerning the local processes of management and self-management for adaptation to and reduction of climate risk. - Indicator 2.1.2 % of target population aware of local processes of management and self- management for adaptation to and reduction of climate risk. OUTCOME 2.2: Greater awareness and ownership of local processes of adaptation to and reduction of climate risk. Indicator 2.2.4.3: Include at least one woman to the District's Civil Defense Platform and per Platform of Community Civil Defense. - OUTPUT 2.2: Awareness activities about adaptation and risk reduction with group participation of the target population: see specific products under indicator 2.2.4.3 Number of women included in the formation of each platform at district level. Indicator 2.2.4.6 Number of women included in the formation of each community level platform. OUTCOME 2.3: improvement in awareness and climate risk management and adaptive techniques skills. - OUTPUT 2.3.4: Training sessions. Indicator % of women participants (25% for all activities, 30% housing improvements) - Products 2.3.3: Elaboration of technical guides : 1,000 guides about personal and family development and strengthening aimed primarily at women.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Prioritization of female heads of household as beneficiaries. | outcome 1.3 Improvement in the conditions of housing quality to withstand extreme climate conditions Sec. 1.3.2: | N° Women heads of households prioritized in the criteria of beneficiary selection | 0 women heads of households | 1 woman per community (it is expected that 36 women will benefit) | Poor. This activity has been rescheduled for the second year of execution, because home improvements in the communities are made after May, when the rainy period has passed. During 2019, it could not be executed because heavy rains affected the communities' economy, forcing the population to look for work alternatives to alleviate the losses, delaying the improvement of their homes. - The decision was made with the communities to prioritize and focus community work efforts on animal protection and pasture improvement activities. - An agreement was reached with the communal authorities to select at least one female head of household per community and this benefit was additionally included in the improvement of sheds. There are 7 female beneficiaries of executed sheds.
Equal participation and empowerment of women in decision making regarding project activities. | outcome 2.1 Greater awareness and ownership concerning the local processes of management and self-management for adaptation to and reduction of climate risk. Sec 2.1.2 | % of target population aware of local processes of management and self-management for adaptation to and reduction of climate risk is made up of women. | No uniform and reliable baseline information was identified. | 25% set as the project goal. (31% of women's participation was achieved) | Satisfactory. 62 training workshops were held on shed improvement, improved pasture planting and livestock fence installation. Female participation amounted to 31% (440 participations)
Include women at the organizational level in climate risk management | output 2.2.4 Advisories for the formation and strengthening of district and community level civil defense platforms (reconnoitering, startup). Sec 2.2.4.3 | N° of women included in the formation of each platform at district level. | Without precedents. The project will promote the formation of the first platforms. | 1 woman per district platform | Poor. Activity rescheduled for the second year, due to the change of authorities at the regional level, with whom it was agreed to include the activities of the Government Axis (OUTCOME 2.1) as of January 2020. During coordination efforts with the Mayors, it was agreed to promote the inclusion of at least one woman in each civil defense platform
Include women at the organizational level in disaster risk management. | output 2.2.4 Advisories for the formation and strengthening of district and community level civil defense platforms (reconnoitering, startup). Sec 2.2.4.3 | 2.2.4.6 N° of women included in the formation of each community level platform. | Without precedents. The project will promote the formation of the first platforms. | 1 woman per communal platform | Poor. Activity rescheduled for the second year, since it is carried out in coordination with the local government. Peasant communities’ authorities committed to ensuring the participation of at least one woman in the Civil Defense Platform.
Personal and family development | output 2.3.3 Elaboration of technical guides. - about personal and family development and strengthening aimed primarily at women. | N° developed guides and delivered | Baseline value not applicable | 1000 guides delivered | Poor. The design of the guide for Family Development and Welfare is scheduled for the second year of the project. However, the design of the five guides delivered, consider women as protagonists of project’s planed activities. The following guides were distributed equally to women: 1) Shed Improvement. 2) Climate change adaptation. 3) Planting of forage cereals. 4) Installation of irrigation pilot, and 5) Operation of the early warning system
Equal participation and empowerment of women in decision making regarding project activities.. | output 2.3.4 Training sessions. Sec 2.3.4.4 | % of women participants | Baseline value not applicable | 25% for all the activities except for household improvement activities | Satisfactory. Women’s participation in training sessions amounted to 31%.
Equal participation and empowerment of women in decision making regarding project activities.. | output 2.3.4 Training sessions. Sec 2.3.4.4 | % of women participants | Baseline value not applicable | 30% for housing improvement activities. | Poor. It was postponed for the second year, due to delays that hindered activities in the field. These delays correspond to procedures with the Environmental Authority, and climatic events such as snowfall, heavy rains and low temperatures, which affected the population’s livelihoods. The implementation of activities was prioritized with the communities: 1.-Improvement of sheds and installation of livestock mesh fences, for the first stage, and sowing and water management (installation of technical or sprinkler irrigation systems); during the last quarter of the first year.
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity – CAF Legal Advisor’s Office, issued a tripartite Agreement which was signed by CAF, by the Technical Executing Entity - COPASA and the Administrative Executing Entity - CONDESAN. This agreement sets the parties’ roles and responsibilities, in accordance with the provisions of the approved Ayninacuy project proposal and the actions specified therein to comply with a gender approach.
Have the implementation arrangements at the IE been effective during the reporting period? |  | The effectiveness of the agreements is evidenced in compliance with the Environmental and Social Management Plan, specifically policy # 5, gender equality and women’s empowerment. The effective management of calls is evidenced in women’s strong participation in training workshops, which has promoted empowerment in decision making. Likewise, commitments to prioritize female heads of household in the beneficiary group were met.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | 18 agreements (covenants) were formulated at the district level and 36 agreements at the community level, to ensure women’s involvement and strong participation. Point five in each document states "(...) this signed agreement will allow the consolidation of the capacities of women and men in the beneficiary peasant communities (...)”. Committed local authorities include 2 mayors, contributing to raise the level of women's empowerment in the community.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | They have been effective; the population has accepted and acknowledged the participation of women in different project activities. This has been reflected in women’s participation in training workshops (improvement of sheds, fences and crops) and in the development of capacities and technical skills in family productivity.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | It was identified that the communities of Río Blanco, Huilluco and Cuspa, women’s participation is low, in contrast to the rest of the communities where women’s participation exceeds 22%, even reaching 55% in some cases (Pamapamarca, Hanansaya I, San Antonio de Chuca). Therefore, the Yachachiqs are making home visits, which they have been carrying out since July in these communities: 30 families in Rio Blanco, 21 families in Huilluco, 24 families in Cuspa, thereby reinforcing awareness and motivation initiatives with women and their families
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1]
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
For the second year, a chapter will be made available in the Yachachiq field notebook to enable collecting or writing down women's complaints and suggestions, if any.
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| All project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Implementing Entity: | All Project components/outcomes |  | Outcome 3 | Outcome 6 | Outcome 5 | -Agreement signed between the executing entities prior to the beginning of the execution of the Project |  | The Legal Advisor’s Office of the Implementing Entity - CAF, issued a tripartite Agreement which was signed by CAF, by the Technical Executing Entity - COPASA and the Administrative Executing Entity - CONDESAN. This agreement establishes the roles and responsibilities of the parties, in accordance with the provisions of the approved proposal of the Ayninacuy project. | S
| All Project components/outcomes |  | Outcome 3 | Outcome 6 | Outcome 5 | -The different CAF areas carry out the fiduciary and financial supervision of the execution of the funds, as well as the monitoring of the technical advances of the Project |  | CAF’s third-party’s resources area validates that the Administrative Executing Entity - CONDESAN complies with fiduciary standards regarding i) Integrity and financial management; ii) Institutional capacity and iii) Transparency and powers of self-investigation. It manages funds disbursements for project execution according to revised and authorized purchasing plans. The Directorate of Sustainability, Inclusion and Climate Change, with support from other specialized areas, monitors the technical progress of the Project and the fulfillment of the commitments | S
| All Project components/outcomes |  | Outcome 3 | Outcome 6 | Outcome 5 | -The project's original budget is adjusted to the reality of the market |  | The budget was adjusted with support from COPASA and CONDESAN. The items were restructured without exceeding the total amount, and complying with the principles of the AF. For this, the following activities were coordinated: • An exhaustive exercise was carried out to update material costs, requesting quotes from potential suppliers and selecting those that met best price and quality criteria, in accordance with CAF purchasing regulations. • Salaries were adjusted so that members of the Project Team are able to receive fair remuneration. It should be taken into account that the initial salaries were calculated 3 or 4 years ago, without considering social benefits. For this activity, CONDESAN developed a market study and considered the mandatory social benefits for the staff. • A second Field Supervisor will be hired, thereby enabling to 5 provinces to be covered efficiently, especially La Unión and Condesuyos, which are the most remote and most strongly affected by extreme weather. • Field labor (corresponding to 5 Field Technical Specialists or Yachachiqs and 2 Field Supervisors), as well as the costs of Transporting Materials, were distributed in Direct Costs, in accordance with accounting principles regarding costs. The amount of the total budget remains unaltered: USD 2,941,446. The products and activities were not modified and there were no variations equal to or greater than 10% in any of the Outputs. This adjusted budget was presented to the Advisory Steering Committee, where the Designated National Authority – the Ministry of Environment was present. | S
| All Project components/outcomes |  | Outcome 3 | Outcome 6 | Outcome 5 | -The Regional Government of Arequipa, the Environmental Regional Authority and the Ministry of Environment are aware of the progress of the Project and participate in meetings and Committees |  | The Authorities are informed about the progress of the Project -The Regional Government of Arequipa and the Ministry of Environment are aware of the progress of the Project and participate in meetings and Committees The Regional Government of Arequipa and the Ministry of Environment are part of the Advisory Steering Committee, and they are kept informed about the progress of the Project in technical, fiduciary and administrative matters. Information and local, district and provincial authorities’ engagement with the project have been promoted through the Technical Executing Entity - COPASA. | S
[7 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | María Carolina Torres -Directorate for Sustainability, Inclusion and Cimate Change Executive, CAF
| Email: | mctorres@caf.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Management of project implementation has been based on technical, administrative and financial oversight to ensure that the Project meets the objectives set. Once the project began, we worked jointly with the Technical Executing Entity-COPASA and with the Administrative Executing Entity-CONDESAN. In a joint and ongoing effort with the Directorates of Accounting, Operations Control, and Development Cooperation Funds, we have ensured that CONDESAN applies the international principles of fiduciary management appropriately, engages in proper accounting practices and controls the resources. At the beginning, COPASA had a hard time adjusting to CAF purchasing and contracting rules and regulations, but the team is already familiar with the standards to be met, and the processes are already more efficient. Institutional relations with organizations linked to the project have also been strengthened: The Ministry of Environment, the Regional Government, the Regional Environmental Authority, as well as Provincial and District Governments. Field visits have been made, holding meetings not only with the authorities, but visiting project beneficiaries and community members, assessing progress and conditions of vulnerability that will be addressed. In the first months, the project budget was evaluated once more, since it was prepared between 2015 and 2016, so costs were already outdated in terms of current market costs. As for staff salaries, when the project was designed, salaries with social benefits had not been considered, but rather consultancy salaries were considered, and only one (1) Field Supervisor was designated for the five provinces, which are very far apart from each other. The budget amount remains unaltered, but some items were adjusted. Surpluses and remnants that originated in the adjustment process were compensated, so even though there is no variation with the original budget, the project is based on an estimate that is better adjusted to reality. Recommendations or next steps are based on continuing to strengthen institutional support; finding a way to insert the project’s activities in the Regional Government Agenda; strengthening measures to comply with and maintain the agreements signed with local governments and communities; hiring a Second Field Supervisor; generating synergies with other activities planned in the communities, which could supplement the Project’s efforts.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Executing Entity/Project Coordinator: | OUTCOMES 1.1, 1.2 and 1.3 |  | Outcome 6 | Outcome 5 | 1- Awareness of the Project’s benefits at the national, sub-national and community level. 2- Initiation of administrative activities for activity programming. 3- Project beneficiaries have been identified. |  | Within the expected scheduled time: 1.1. Initial workshop to launch the project with authorities and community representatives. (October 15th, 2018) 2.1. The project’s administrative staff (Director and Assistant) has been hired and is installed at the headquarters of the Cooperation for the Sustainable Self-Development Process of Arequipa-COPASA of the Arequipa Regional Government (October 2018). 2.2. The following programming activities were carried out: Operational Activities Plan; Preparing and signing Agreements with the Authorities; Procedures for obtaining permits from environmental authorities; Calls, interviews and selection process for the Field Supervisor and 5 Field Technical Specialists. 3.1. The beneficiaries were identified by the communities’ steering committee. 3.2. Information from the Household Targeting System - SISFOH (http://www.sisfoh.gob.pe/ ) was used for the socio-economic selection of beneficiaries. This is an official instrument used by the State's social programs, and is critical to respond to the needs of social information that the Peruvian state uses for the implementation of its public policies, linked to poverty reduction. (http://www.sisfoh.gob.pe/ ) | S
| All Project components/outcomes |  | Outcome 6 | Outcome 5 | 1- Office installed with equipment for follow up and project monitoring. 2- Field personnel is trained and is operating |  | 1. A donation was received from local companies with the following equipment: Two (2) desktop computers; Two (2) laptops; One (1) camera; One (1) Multimedia Projector and Three (3) motorcycles, which facilitated the start of activities and the operation of the office. 2. There were delays in hiring the Field Technical Specialists - Yachachiqs, due to: • The beginning of field activities were planned for April 2019, because the planting activities, as of October 2018, had already been concluded according to the alpaca calendar. • Shed improvements must be carried out between March and November (period of drought in the high Andean areas), so it was not possible to start in October 2018. • It is not easy to find bilingual trained technical personnel (Quechua/Spanish), to facilitate communication with community members. • In order to comply with the environmental and social safeguards which would allow entering the field, exhaustive actions were carried out to obtain a response from the environmental authority to OFFICIAL COMMUNICATION 122-2018 GRA / COPASA / DE, regarding the "compatibility opinion and report" of the communities settled in the scope of the Natural Reserve of Salinas and Aguada Blanca and Cotahuasi Sub-basin Landscape Reserve. In January 2019, the TECHNICAL OPINION 954-2018-SERNANP-DGANP document was received from the environmental authority, which declares the compatibility of the project activities. Similarly, the OFFICIAL COMMUNICATION 102-2017 GRA / COPASA / DE, which requests the MINAM to identify the competent authority and/or determine the enforceability of the project’s environmental certification. Finally, with OFFICIAL COMMUNICATION 921-2018-MINAM / VMGA / DGPIGA of December 31, 2018, it was resolved that the project does not require an Environmental Certification. • In order to carry out the activities in the field, it was necessary to ratify commitments (agreements) with the new authorities (2019-2022), which was carried out during the months of January-March 2019. | MS
| All Project components/outcomes |  | Outcome 6 | Outcome 5 | 1- Technical personnel is installed in the 5 provinces. 2- The supervisor attends to the needs of 5 provinces |  | 1- Since May 2019, there are 5 Field Technical Specialists (natural Yachachiqs from each area) installed in the prioritized districts of each province and they coordinate their work directly with the communities. 2- It is necessary to hire a Second Field Supervisor to support and recover the time and make up for the delays in reaching the most remote provinces. The current Supervisor must cover a territorial extension of more than 1500 km, which corresponds to making a round trip of the project. This means that the field supervisor needs 45 field days to implement his activities. For two supervisors, they can distribute the workload between 22 days. | MS
| OUTCOMES 1.1, 1.2 and 1.3 |  | Outcome 5 | Outcome 6 | 1- Implementation of mechanisms for purchases and inventory development in the first quarter of implementation. |  | 1.1. During the first semester of project implementation, there was a sufficient and favorable learning curve for the recognition of acquisition mechanisms set by the Administrative Executing Entity (CONDESAN). 1.2. Limitations for the identification of suppliers that could cover the purchase demands for the most remote communities. This condition has already been overcome. 1.3. Upon issuance of this report, purchases have been made in accordance with the request for acquisition plans to execute pending activities for the first year. | MU
| OUTCOME 2.1: Greater awareness and ownership concerning the local processes of management and self- management for adaptation to and reduction of climate risk. |  | Outcome 5 | Outcome 6 | 1- Commitment and agreements signed with authorities and beneficiaries in the first quarter of implementation |  | 1. From January to May 2019, coordination with the new elected authorities continued and culminated in the ratification of the agreements. Therefore, the project obtained the new elected authorities’ support for the deposits, surveillance and for transporting materials to beneficiary communities in their territorial areas. Currently there is a strong commitment from local and communal governments with regard to the execution of project activities. | S
[7 empty] | Overall Rating | MS
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Maria Angelica Salinas Valencia
| Email: | mariangelicasv@hotmail.com
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Although the start of the Project (2018) was well received by the Regional Government as well as Local, Community Governments and beneficiaries; there were delays in the first semester of execution, due to issues beyond those projected in the proposal, such as: 1. New electoral period of regional and local authorities, in January 2019. Therefore, it was necessary to inform and sensitize new officials about the benefits of the project and the commitments assumed by the previous government, with the following results: - Written communications were sent and visits were made to the new authorities during the months of January and February, informing them about the implementation of the project and the recognition of the commitments assumed by the previous authorities (deposits, inventories, surveillance and transfer of materials to the beneficiary communities in their territorial areas). - During the months of March, April and May, 5 provincial agreements, 17 district agreements and 34 communal agreements were ratified. Only the Local Government of Andagua refused, due to political problems with its predecessor. Therefore, an evaluation was carried out to find a replacement and the Pampacolca district was selected since it met the conditions and the mayor was a woman. - The activities of the Government Axis (OUTCOME 2.1) had to be rescheduled for the second year in order to be articulated to the Municipal Programs. - The beginning of the project in October (2018) was close to the period of heavy rains, so the activities of the Animal Protection and Health Axis (Component 1) were scheduled for the month of May 2019, so that it coincided with the sowing and alpaca communities’ management calendar (official agricultural and alpaca calendar). - The January-March period of heavy rains affected 60% of the selected districts declared in a state of emergency through Supreme Decree No. 023-2019-PCM (February 12, https://www.indeci.gob.pe/ rehabilitation / declarations-state-of-emergency / year-2019 / February-2019 /). The communities were affected again by the effects of low temperatures (-20 ° C), at an intensity not foreseen in the project, during June-August 2019, and 84% of the districts were declared in a state of emergency through Supreme Decree N ° 158-2019-PCM (https://www.indeci.gob.pe/rehabilitacion/declaratoria-estado-de-emergencia/ano-2019/setiembre/). As a result of this situation the community decided that activities related to the recovery of their livelihoods (improvement of sheds, pastures and water resources management: installation of irrigation systems) should be prioritized. - There was a delay in hiring agricultural technical personnel (Yachachiqs), due to the reasons explained above. - From October 2018 to January 2019, the programming of the field activities was also conditioned to compliance with the environmental safeguards: 1) the approval of the SERNANP Compatibility report (OP 954-2018 SERNANP -DGNAP, delivered in January 2019 ), a requirement to carry out the work in the communities located nearby or in buffer areas of the natural and landscape reserves; 2) MINAM response on the project’s Environmental Certification requirement, which was resolved through Report N ° 1161-2018-MINAM / VMGA / DGPIGA of December 31, 2018, indicating that no certification was required.
| Project components/outcomes |  | Alignment with AF outcome(s) |  | Expected Progress |  | Progress to Date | Rating
Other (If there is more than one executing entity a rating should be provided from each EE for the outputs/outcomes of the project for which the entity is responsible; the Designated Authority can also provide a rating)
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words
| AF Outcomes |  |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
OUTCOME 1.1: Improvements in the conditions and means of providing animal nourishment and health, through strengthening the life strategies in relation to the impacts of climate change. | Products 1.1.1 N° of shelters built. | 0 | 33 sheds executed in 30 communities, 51 sheds in the process of completion during the first quarter of the second year, in 36 communities. | First year: 84 end of project: 270
| Products 1.1.2 N° of fences installed | 0 | 9 livestock fences installed; material delivered to 24 communities for the installation of 24 fences during the first quarter of the second year. | First year: 33 End of project 72
| Products 1.1.3 Ha of high altitude forage cereals planted | 0 | 0 ha of crops installed, • The selection of suitable lands for the installation of crops has begun. • The beginning of the project on October 2018 project did not allow the execution of this activity due to the sowing schedule according to the alpaca calendar. The sowing period is carried out from October to November, after having prepared the land and at the beginning of the rainy season. • According to the alpaca calendar (October 2019) certified seeds of forage cereals were delivered to 36 communities for the installation of 281 hectares. | First year 281 Ha. End of the project 900 Ha
| Products 1.1.4 Ha of improved grasses seeded | 0 | 0 ha of crops • Progress was made with land preparation for sowing 5 Ha of grass seeds: land selection, preparation and fertilization. The crops will be installed as of November 2019. • The communities’ planting period from October to December was taken into account, according to the official agricultural calendar. | First year: 5 End of project 72
| Products 1.1.5 Ha of wetlands improve with clover | 0 | 0 improved wetlands • Progress was made with the selection of wetlands in processes involving drying, cleaning and maintenance of channels. In the months of November and December 2019, the recovery process will begin by resowing 27 Ha (the wetlands’ water cycle begins in October, with the beginning of the rainy season in the Andean areas) in buffer zones | First year: 27 End of project 72
| Products 1.1.6 N° of dosed animals executed. | 0 | 0 animals received doses • 3,125 doses of medication were acquired in the month of October 2019: restorative medications and antibiotics, for the beginning of animal health campaigns, in the month of November 2019 (in coordination with the campaigns programmed by the National Agricultural Health Service - SENASA and the Local Governments for the months of October and November) There were limitations in identifying suppliers within the region | First year: 3,125 End of the project 10,000
OUTCOME 1.2: Improvements in the availability of water and irrigation conditions allow for providing greater volumes of vegetal production and of greater areas consolidated for animal feed | Products 1.2.1 N° of modules irrigation installed. Ha of improved grasses | 0 | 0 modules installed • Progress has been made with the selection and preparation work for the installation of 05 irrigation systems • The water cycle of the Andean areas takes place between October and March, so the collection works must start on May. | First year: 5 End of project 72
| Products 1.2.2 N° of wetlands with improved irrigation via rustic canals. | 0 | 0 wetlands irrigated • Improvement of canals has been rescheduled for the first quarter of the second year. The water cycle of the Andean areas takes place between October and March, so the collection works must start on May. | First year: 13 End of project 36
| Products 1.2.3 N° meters of improved canals | 0 | 0 meters of improved canals • The activity has been rescheduled for the second year. The water cycle of the Andean areas takes place between October and March, so the collection works must start on May. | First year: 0 End of project 10,000 ml
| Products 1.2.4 N° of reservoirs (ponds) built. | 0 | 0 reservoirs improved • The activity has been rescheduled for the second year. (The water cycle of the Andean micro-watersheds takes place between October and March, so the collection works must start on May | First year: 11 End of project 36
OUTCOME 1.3 Reduction in cases indexes of ARIS and ADDS in communities and beneficiary households | Products 1.3.1.1 N° of safe water purification systems installed | 0 | 0 Water Purification Systems • The activity has been rescheduled for the second year. This decision was made by the communities during communal assemblies, sessions on agreements regarding scheduling of trainings and training meetings where approximately 30 to 40 community members participated and prevention activities for the recovery of their livestock capital were prioritized. | First year: 2 End of project: 5
| Products 1.3.2.2 N° of Composting Latrines Built | 0 | 0 Hygienic Services with Biodigesters • The activity has been rescheduled for the second year, for the reasons already explained in Product 1.3.1.1 0 | First year: 24 End of project 72
| Products 1.3.2.3 N° of improved stoves built | 0 | 0 Improved Kitchens • the activity has been rescheduled for the second year, for the reasons already explained in Product 1.3.1.1 | First year: 24 End of project 72
| Products 1.3.2.3 N° of photovoltaic panels installed | 0 | 0 photovoltaic panels installed • The activity has been rescheduled for the second year, for the reasons already explained in Product 1.3.1.1 | First year: 24 End of project 72
| Products 1.3.2.4 N° of solar walls | 0 | 0 solar walls • The activity has been rescheduled for the second year, for the reasons already explained in Product 1.3.1.1 | First year: 24 End of project 72
OUTCOME 2.1: Greater awareness and ownership concerning the local processes of management and self- management for adaptation to and reduction of climate risk. | Products 2.1.1.1 N° of agreements (covenants) Provincial | 0 | 5 agreements signed with the provinces of Arequipa, Caylloma, La Unión, Castilla and Condesuyos | First year: 4 End of project 4
| Products 2.1.1.1 N° of agreements (covenants) District | 0 | 18 agreements signed with the districts of S.J. Tarucani, Pampamarca, Huaynacotas, Puyca,Toro, Chuquibamba, Andaray, Yanaquihua, Salamanca, Callalli, Tuti, S.A. Chuca, Caylloma, Sibayo, Chachas, Chilcaymarca, Orcopampa y Pampacolca | First year: 18 End of project 18
| Products 2.1.2.1 N° of dissemination and motivation visits (Community) | 0 | 36 agreements signed with the communities | First year: 36 End of project 36
OUTCOME 2.2: Greater awareness and ownership of local processes of adaptation to and reduction of climate risk | Products 2.2.2 N° de events for implementation and dissemination module | 0 | 0, the activity has been rescheduled for the second year, due to the fact that the new regional educational authorities decided that support to the risk management and climate change axis should be start on the second year of government: 2020. The Manager of the Regional Education Directorate has been changed three times. | First year: 21 End of project 36
| Products 2.2.3 N° of accompaniment processes to project execution. | 0 | 0, the activity has been rescheduled for the second year, for the reasons already explained in Product 2.2.2 | First year: 1 End of project 5
| Products 2.2.4 N° of processes initiated and culminated. | 0 | 0, the activity has been rescheduled for the second year, for the reasons already explained in Product 2.2.2 | First year: 6 End of project 18
OUTCOME 2.3: improvement in awareness and climate risk management and adaptive techniques skills. | Products 2.3.3.1 N° developed guides | 0 | 5 guides developed, addressing the following topics: 1) improvement of sheds, 2) adaptation to climate change, 3) planting of forage cereals, 4) installation of irrigation pilot 5) operation of the early warning system. 16,380 guides were printed, 5000 on Adaptation were delivered and another 2400 (480 guides per topic) were delivered to beneficiaries and local and communal authorities. | First year: 5 printed guides End of project 13
| Products 2.3.3.2 N° of printed copies | 0 | 16,380 printed guides are being delivered in each of the trainings in all project areas. | First year: 12,286 End of project 43,000
| Products 2.3.4.1 N° of participants per workshop (5 per community) for the installation of early warning EWS teams | 0 | 0, activities are planned for the second year of execution. Jointly the new authorities, its implementation was scheduled for the year 2020 | First year: 21 End of project 180
| Products 2.3.4.2 N° of participants per workshop in the upgrading of the community civil defense platforms | 0 | 0, activities are planned for the second year of execution. Jointly the new authorities, its implementation was scheduled for the year 2020 | First year: 68 End of the project 540
| Products 2.3.4.3 N° students per workshop | 0 | 0, activities are planned for the second year of execution. Jointly the new authorities, its implementation was scheduled for the year 2020 | First year: 125 End of the project 1,000 trained students
| Products 2.3.4.4 N° of participants per workshop held in 05 provincial municipalities for EDAN teams | 0 | 0, activities are planned for the second year of execution. Jointly the new authorities, its implementation was scheduled for the year 2020 | First year: 13 End of project 64
| Products 2.3.4.4 % of women participants (25% for all activities, 30% housing improvements) | 0 | 31% of female participants in project workshops for the improvement of sheds, installation of livestock fence and management and conservation of forage cereals. | 25% during the entire execution
| Products 2.3.4.5 N° of beneficiary households participate in the process of elaboration of prevention plans through training programs. | 0 | 0, activities are planned for the second year of execution. Jointly the new authorities, its implementation was scheduled for the year 2020 | First year: 108 End of project 540
| Products 2.3.4.6 N° of participants per workshop, municipal official and community representatives are trained in prevention workshops, | 0 | 0, activities are planned for the second year of execution. Jointly the new authorities, its implementation was scheduled for the year 2020 | First year: 36 End of project 142
| Products 2.3.4.7 N° of participants per workshop, Training sessions for the transfer of techniques for improvement of rural Andean highland housing: Trombe solar walls. | 0 | 0, activities planned for the second year of execution. These training sessions are linked to OUTCOME 1.3 for home improvement and their activities were rescheduled | First year: 28 End of project 140
| Products 2.3.4.8 N° of participants per workshop, Construction of composting latrines | 0 | 0, activities planned for the second year of execution. These training sessions are linked to OUTCOME 1.3 for home improvement and their activities were rescheduled | First year: 28 End of project 141
| Products 2.3.4.9 N° of participants per workshop, Construction of improved stoves | 0 | 0, activities planned for the second year of execution. These training sessions are linked to OUTCOME 1.3 for home improvement and their activities were rescheduled | First year: 28 End of project 142
| Products 2.3.4.10 N° of participants per workshop, Installation of photovoltaic panels | 0 | 0, activities planned for the second year of execution. These training sessions are linked to OUTCOME 1.3 for home improvement and their activities were rescheduled | First year: 28 End of project 143
| Products 2.3.4.11 N° of participants per workshops (144 workshops) | 0 | 469 people trained in adaptive technologies for the management and conservation of forage cereals and the installation of livestock mesh fences. These activities are programed to be completed in the second year of the project, since training sessions for the improvement of sheds, pastures, water resource management and housing improvements are carried out in advance of activities with the communities. Furthermore, training activities for communities and authorities to strengthening risk management and adaptation to climate change are scheduled for the year 2020 | First year: 1,172 End of project 3,750 beneficiaries

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | 1. Institutional arrangements were carried out during the start of the Project (October 2018) and institutional support was obtained for the deposits, surveillance and for transporting materials to beneficiary communities from their territorial areas. 2. Changes in local and regional authorities in the first quarter of 2019 generated delays in the programming of the activities of the government axis and risk management and climate change (OUTCOME 2.1, OUTCOME 2.2), because the commitment of the new authorities and the ratification of previously signed agreements were required. 3. There were unexpected climatic problems such as heavy rains during January - March and snow-low temperatures during June-July 2019. These limited the execution of activities to improve the alpaca sheds and it was necessary to postpone the reconstruction of rustic ponds, reprogram sowing and the transportation of materials to the work area. 4. Development of synergies with public and private institutions such as: Regional Council from the Regional Government of Arequipa, Agro-Rural Program (Agricultural-Rural Productive Development Program) of the Ministry of Agriculture, National Meteorology and Hydrology Service of Peru (SENAMHI-MINAM), National Service of Natural Protected Areas- SERNAMP- (MINAM), Regional Agricultural Directorate of Arequipa, Arequipa Chamber of Commerce (considering its rural support program for high Andean areas), National Livestock Directorate of the Ministry of Agriculture and Irrigation (MINAGRI), National Service of Health and Quality Agri-Food -SENASA, Head of Community Development of Cerro Verde Mining Company, Head of Community Relations of Bateas Mining Company, Autonomous Authority of Majes - AUTODEMA. 5. It should be borne in mind that the activities foreseen in the project for sowing, animal health and water collection must be carried out within the Andean basin hydrological cycle and the alpaca calendar, established by the communities (beginning of sowing cycle in November, improvement of facilities as of March, animal health campaigns are carried out in October / November, improvement of wetlands begins in September, improvement of rustic ponds are carried out in September). Therefore, these activities began in May. 6. Poor condition of the roads due to landslides and snowfall, limited the assistance provided to very scattered and remote communities. (Orcopampa-Caylloma, San Juan de Tarucani road, Cotahuasi – Pampamarca road, Pampacolca - Chuquibamba road was out of service; access to Cotahuasi was affected by the activation of a geological fault). This has limited the delivery of materials for the improvement of sheds and fences in the most remote communities, located in the provinces of La Unión and Condesuyos. 7. Good coordination with local authorities and the permanent residence of the Field Technical Specialists -Yachachiqs in the prioritized districts, as well as the scheduled monitoring of the Field Supervisor, the Administrative Assistant and the Project Director, enabled starting and continuing with field activities during the second semester of execution. 8. The coordination process between the Technical Executing Entity - COPASA and the Administrative Executing Entity - CONDESAN, for the purchase processes was longer than expected, generating delays in the first semester. This situation has already been overcome.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | The delays were detailed in the previous point. The following measures were carried out in response: 1. Permanent coordination of the technical team with local and communal authorities through motivational and awareness visits, to explain the project’s components, areas of influence, selection of beneficiaries, explanation of the importance of taking into account the risks and the timely prevention of harmful events linked to climate change in the high Andean zone. 2. Given that the beginning of the project was close to the rainy season in the high Andean areas, and this was not compatible with the communities’ agricultural calendar (from April to November), field activities were rescheduled to begin on the second semester of the project. 3. The procedures were completed before the National Service of Natural Protected Areas-SERNANP, with authorization from the Compatibility Report that was necessary to intervene in the areas of natural and landscape reserve. This guaranteed the beginning of field activities in April 2019, allowing local communities and authorities to learn about the Ayninacuy project and familiarize themselves with the team and the work methodology, in order to transfer the techniques and knowledge. 4. Problems regarding accessibility to work areas, due to the period of heavy rains, were overcome in many cases by identifying some alternate routes, and in other cases we had to wait to be able to pass through (in cases of cave-ins or landslides). 5. Joint decisions stipulated in the agreements with the local authorities, facilitated transporting materials despite the damage to the roads, because the authorities themselves were responsible for transporting and delivering the materials to the communities. However, field supervision work was affected. 6. A portfolio of suppliers was put together, improving cohesion between the Technical Executing Entity - COPASA and the Administrative Executing Entity - CONDESAN. Tasks have been rescheduled to achieve significant progress during the second year.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | 1. The activities of the Human Health Care Axis have been rescheduled to be fully implemented during the second year of execution and to ensure that results are not affected by climatic events, since housing improvements must begin once the April rainy season has ended. 2. A budget modification has been proposed in order to execute a higher percentage of Component 1 activities during the second year of the Project. 3. It may be necessary to extend the Project’s execution period, to compensate for the delay during the first year. 4. It was suggested to the Steering Committee that a second Field Supervisor should be hired, in order to improve assistance to the provinces of La Unión and Condesuyos, which are the most remote and most strongly affected by extreme weather. The current Supervisor must cover a territorial extension of more than 1500 km, which corresponds to making a round trip to the project. This means that the field supervisor needs 45 field days to implement his activities. For two supervisors, they can distribute the workload between 22 days. These changes will optimize project implementation for years two and three. 5. It was suggested to the Steering Committee that it should adjust the salaries of team members to market value, since this will reduce the risk of dropouts thereby affecting the continuity of activities.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | Yes because: • They have enabled carrying out an early evaluation of the project’s area of probable influence; the identification of communities and groups that may be affected by the project, and initial estimates regarding the potential social risks and benefits related to the project. • They have allowed us to transmit and assume the importance of proper solid waste management before, during and after trainings, meetings and / or community assemblies. • It is planned to carry out preventive and permanent maintenance of vehicles working on the project (van and motorcycles), ensuring that they have their respective technical reviews from the Ministry of Transportation and Communications (MTC). • Permanent coordination with the National Service of Protected Natural Areas (SERNANP). • There are reports on the activities carried out. • There are Quechua-speaking technicians in the work team. • In all collective activities, women’s equal participation has been taken into account. This means that they are able to vote on decisions and locate themselves wherever they decide.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | 1. For the call, home visits were made to 100% of women, who accepted the project, and this has guaranteed their participation in training sessions, exceeding 25% of planned participation in most of the communities. 2. Compliance with gender sensitive indicators, such as the selection of female heads of household in the community to be benefited, is well accepted by the communities. It is also approved by local authorities and replicable in their decision making processes. 3. The participation of 2 mayors in charge of the municipalities of Pampacolca and Chachas in the project, raises the level of empowerment and participation of women in their communities. 4. Agreements with the new authorities ratify the appointment of a woman to be part of the civil defense platforms. 5. Women have also benefited from the selection of beneficiaries to improve sheds and fences, in recognition to their participation which amounts to 30%.
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change?
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes?
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change?
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions?
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area?
Community/National Impact
What would you consider to be the most successful aspects for the target communities?
What measures are/have been put in place to ensure sustainability of the project/program results?
What measures are being/could have been put in place to improve project/program results?
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used?
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used?
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.)
If learning objectives have been established, have they been met? Please describe.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed?
Innovation
Describe any innovative practices or technologies that figured prominently in this project.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization.
Yes
No

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID | PER / RIE / Rural / 2015/1
Implementing Entity | Development Bank of Latin America (CAF)
Type of implementing entity | RIE
Country | Peru
Region | Latin America and Caribbean
Sector | Multi-sector
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 240467 | 68848 | 171619 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 47% | 49% | 48% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total |  |  |  | Total |  |  |  | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 9.632%
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0 | 0% | 2: Partially not aware |  | 469 | 31% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | Baseline information |  |  |  | Baseline information |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 | 0% |  |  | 42 | 28% | From 5% to 10% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Multi-sector | Livelihoods | 33 | Financial capital | Other | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
Note on H65: TORRES, MARIA CAROLINA: 7.16% of 68,000= 48,688