## Overview
Project Performance Report (PPR)
| Period of Report (Dates) | 3rd May 2018- 3rd May 2019
| Project Title: | Building adaptive capacity to climate change through food security and nutrition actions in vulnerable Afro and indigenous communities in the Colombia-Ecuador border.
| Project Summary: | The binational project proposes to strengthen food security and nutrition through climate change adaptation measures in two watershed on the Colombia-Ecuador border area in accordance with the binational working groups’, and Awa and Afro community´s priorities. Project actions will contribute to reversing the marginalization that Afro and Awá communities have faced from the social and environmental damage from the conflict and contribute to peace and reconciliation through adaptation to climate change. This initiative will generate local climate change adaptation responses with a focus on both community-based adaptation (CbA) and ecosystem-based adaptation (EbA) approaches to promote food security and nutrition. The strengthening of Awá and Afro institutional and community capacities in a culturally and conflict-sensitive manner, with a focus on gender, are other important expected results of the project. Also, this project presents an important opportunity to integrate climate change adaptation in Afro and indigenous development plans (Life Plans and Local Governance Plans) and binational watershed management plans, contributing to local economic development in historically marginalized areas.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: |  | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | United Nations World Food Programme (WFP) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral implementing entity (MIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Colombia and Ecuador | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Mira-Mataje and Guaitara-Carchi watersheds; Colombia: municipalities of Tumaco, Barbacoas and Ricaurte (department of Nariño) and municipalities of Valle del Guamez, San Miguel and Puerto Asís (department of Putumayo). Ecuador: provincies of Esmeraldas, Carchi, Imbabura and Sucumbíos. | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | July 2017
IE-AFB Agreement Signature Date: |  | 2017-11-27 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2018-05-03 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Mid-term Review Date (if planned): |  | January 2020
| Terminal Evaluation Date: | 2022-05-01
|  | List documents/ reports/ brochures / articles that have been prepared about the project. | Cyprus
1. Press clipping on the inception workshop; 2. Binational Annual operational Plan; 3. Executing Entities capacity strengthening strategy. 4. The climate risk methodology was elaborated and designed for the project baseline. In alignment with IPCC AR5 framework, food security, nutrition and gender were included in the climate risk formula as key variable to measure climate sensitivity.
List the Website address (URL) of project. |  |  | Democratic People's Republic of Korea
|  | N/A | Democratic Republic of the Congo
Denmark
| Project contacts: |  | Djibouti
National Project Manager/Coordinator |  |  | Dominica
| Name: | Javier León | Dominican Republic
| Email: | javier.leon@wfp.org | Ecuador
| Date: | 2019-05-23 | Egypt
| Government DA |  | El Salvador
| Name: | Ricardo Lozano | Equatoral Guinea
| Email: | RLozano@minambiente.gov.co | Eritrea
| Date: | 2019-05-23 | Estonia
Government DA
| Name: | Marcelo Mata Guerrero
| Email: | marcelo.mata@ambiente.gob.ec
| Date: | 2019-05-23
| Implementing Entity |  | Ethiopia
| Name: | Carlo Scaramella | Fiji
| Email: | carlo.scaramella@wfp.org | Finland
| Date: | 2019-05-23 | France
Implementing Entity
| Name: | Mario Touchette
| Email: | mario.touchette@wfp.org
| Date: | 2019-05-23
| Executing Agency |  | Gambia
| Name: | Juan Carlos Ángulo Vasquez | Georgia
| Email: | crecompas18.tumaco@gmail.com | Germany
| Date: | 2019-05-23 | Ghana
| Executing Agency |  | Greece
| Name: | Gregorio Rodriguez García | Grenada
| Email: | inkalawa2015@gmail.com | Guatemala
| Date: | 2019-05-23 | Guinea
| Executing Agency |  | Guinea Bissau
| Name: | Rider Pay Nastacuaz | Guyana
| Email: | rpnastacuas@gmail.com | Haiti
| Date: | 2019-05-23 | Honduras
Executing Agency
| Name: | Florencio Canticuz
| Email: | fcae.ibarra@gmail.com
| Date: | 2019-05-23
Executing Agency
| Name: | Inés Morales Lastra
| Email: | fedoca2001@yahoo.com
| Date: | 2019-05-23
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## FinancialData
Financial information: cumulative from project start to May 3rd, 2019
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement as of 3rd May 2019 | 533902
Add any comments on AF Grant Funds. (word limit=200)
INVESTMENT INCOME | 0
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period | ITEM / ACTIVITY / ACTION | AMOUNT
| Output 1.1.1. One study per watershed produced on traditional and local practices, promoting resilience to climate change and variability in the targeted binational watersheds, with community participation and particular attention to ancestral and native plant and tree species that can improve dietary diversity and are resilient to climate change | 10251.39
| Output 1.1.2. Feasibility study conducted with communities to assess the potential for marketing native species for medicinal, artisanal, food and fodder related uses at regional and departmental levels | 0
| Output 1.1.3. Workshops, dialogues and cultural events (including fairs) organized to disseminate study results to 120 Afro and Awá communities, leaders and decision makers, in local languages. Equitable participation of men and women will be promoted | 53374.61
| Output 1.2.1. In 120 communities, leaders, community members and women groups trained on climate change threats with culturally and gender sensitive methods. Equitable participation of men and women will be promoted | 18355
| Output 1.2.2. Dialogues, fairs and exchanges involving 120 communities, leaders and community members on food security, nutrition and healthy living habits, considering climate threats, with special focus on diversifying diets and increasing incomes from the production and sale of native species and products. Equitable participation and opportunities of men and women will be promoted. | 0
| Output 1.2.3. One binational web-based adaptation learning platform in use | 0
| Output 1.2.4. Compilations and sharing of best practices on risk reduction and risk management actions at binational watershed level, considering ecosystem type and emphasizing traditional and local knowledge. | 0
| Output 2.1.1. Studies at the binational watershed level produced on: 1) water provision considering climate threats; 2) ecosystem vulnerability in the face of climate change and variability and extreme events; and 3) food security and nutrition in vulnerable communities and 4) a gender assessment | 289541.36
| Output 2.2.1 Binational Early Warning Systems introduced, specifically tailored to inform the Afro and Awá communities about extreme events. Additionally, climate services will be introduced to include agro-meteorological data; vulnerability mapping, with a focus on crop yields and cycles; and climate risks in mangrove and high-mountain ecosystems | 0
| Output 2.2.2. Approximately 120 leaders and community members trained in Emergency Preparedness and Response and understanding and planning for climate threats with a focus on gender | 0
| Output 3.1.1. Participatory approaches developed, interfacing scientific and traditional knowledge | 0
| Output 3.1.2. Effective adaptation measures designed and implemented incorporating participatory approaches, traditional and local knowledge and tested techniques, and promoting equal opportunities for access to resources for women and men to recover of degraded ecosystems in 120 communities | 0
| Output 3.1.3. Community water harvesting, storage and management measures introduced | 0
| Output 3.1.4. Cost-benefit analysis of proposed adaptation measures at micro-watershed level | 0
| Output 3.1.5. Native species reintroduced to diversify production and consumption and for commercialization, including introduction of organic and agro-ecological crop production practices and ocean species | 0
| Output 3.2.1. Soil management activities implemented, including agro-forestry and native nitrogen-fixing species | 0
| Output 3.2.2. Conservation and recovery of 3,000 ha of forest ecosystems and 2,000 ha of mangroves threatened by climate change through tree planting and forest management actions, at the micro-watershed level, with species that are native and resistant to climate variability, in line with national plans | 0
| Project Execution costs | 162379.6
| TOTAL | 533901.96
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period | ITEM / ACTIVITY / ACTION | PROJECTED COST | Est. Completion Date
| Output 1.1.1. One study per watershed produced on traditional and local practices, promoting resilience to climate change and variability in the targeted binational watersheds, with community participation and particular attention to ancestral and native plant and tree species that can improve dietary diversity and are | 158948.61 | 20/10/2019
| Output 1.1.2. Feasibility study conducted with communities to assess the potential for marketing native species for medicinal, artisanal, food and fodder related uses at regional and departmental levels | 56400 | 20/10/2019
| Output 1.1.3. Workshops, dialogues and cultural events (including fairs) organized to disseminate study results to 120 Afro and Awá communities, leaders and decision makers, in local languages. Equitable participation of men and women will be promoted | 376825.39 | 2020-02-29
| Output 1.2.1. In 120 communities, leaders, community members and women groups trained on climate change threats with culturally and gender sensitive methods. Equitable participation of men and women will be promoted | 94445 | 2020-03-31
| Output 1.2.2. Dialogues, fairs and exchanges involving 120 communities, leaders and community members on food security, nutrition and healthy living habits, considering climate threats, with special focus on diversifying diets and increasing incomes from the production and sale of native species and products. Equitable participation and opportunities of men and women will be promoted | 72700 | 2020-03-31
| Output 1.2.3. One binational web-based adaptation learning platform in use | 30000 | 2020-04-30
| Output 1.2.4. Compilations and sharing of best practices on risk reduction and risk management actions at binational watershed level, considering ecosystem type and emphasizing traditional and local knowledge | 156400 | 2020-04-30
| Output 2.1.1. Studies at the binational watershed level produced on: 1) water provision considering climate threats; 2) ecosystem vulnerability in the face of climate change and variability and extreme events; and 3) food security and nutrition in vulnerable communities and 4) a gender assessment | 471758.64 | 20/10/2019
| Output 2.2.1 Binational Early Warning Systems introduced, specifically tailored to inform the Afro and Awá communities about extreme events. Additionally, climate services will be introduced to include agro-meteorological data; vulnerability mapping, with a focus on crop yields and cycles; and climate risks in mangrove and high-mountain ecosystems | 467000 | 2020-05-03
| Output 3.1.1. Participatory approaches developed, interfacing scientific and traditional knowledge | 40000 | 2020-04-30
| Output 3.1.2. Effective adaptation measures designed and implemented incorporating participatory approaches, traditional and local knowledge and tested techniques, and promoting equal opportunities for access to resources for women and men to recover of degraded ecosystems in 120 communities | 904000 | 2020-05-03
| Output 3.1.4. Cost-benefit analysis of proposed adaptation measures at micro-watershed level | 73400 | 2020-05-03
| Project Execution costs | 235920.4 | 2020-05-03
| TOTAL | 3137798.04 | 2020-05-03
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
How much of the total co-financing as committed in the Project Document has actually been realized?
Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE).
Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200)

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Revaluation of the Colombian Peso | Low | The project will make transactions in dollars when possible to avoid currency fluctuations. Colombian Peso is devaluating, with a positive impact on the budget. In addition, financial and expenditure monitoring is carried out on a monthly basis.
Lack of coordination between different entities (regional, territorial and national governments) | Low to medium | By establishing a binational cross-sectorial project implementation team, communication between different stakeholders has been facilitated and streamlined. This risk is minimized through project coordination among stakeholders at national (MADS, MAE), departmental and local levels (Grand Family Awá, RECOMPAS and CANE). Also, by establishing a binational cross-sectorial project implementation team, communication between different stakeholders has been facilitated and streamlined.
Lack of territorial capacity to implement technical activities | Low | In both countries, technical organizations and institutions (Corponariño, CIAT, CIIFEN, IDEAM) will actively participate in the technical advisory committees, in order to provide specialized assistance and technical capacity as required.
Scientific and technical information on climate change in the border region is incomplete | Low | Climate risk assessment and studies on water provision in the binational watershed will generate updated information to complement the already existing secondary data recollected in collaboration with IDEAM (Institute of Hydrology, Meteorology and Environmental Studies in Colombia) and IEE (Ecuatorian Spatial Institute).
Disruptions to TransAndino Pipeline affects FSN | Low | Ecopetrol has security measures in place. Peace agreement will reduce disruptions. Environment ministry studies of hydrocarbon concentrations in sediments and fish will be used for monitoring. Those will be tracked and reported on annually.
Change of government or other key stakeholders in Ecuador or Colombia which impacts project implementation schedule | Low | In Colombia and Ecuador, new governments provided political support to the project. WFP and the project coordinator liaised with government officials to explain the project and anticipated outcomes. In addition, project coordination among stakeholders at national (Ministries of Environment and Agriculture), departmental and local levels (local governments, local environmental corporations, Afro and Awá organizations) have been carried out.
Once areas are under an adaptation measure, communities can decide to grow non-project supported crops. | Low | The project will undertake extensive consultations with communities. In addition, communities will be trained on value added and marketing of the production from adaptation measures.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Change in Awá leadership in Colombia leads to interests not aligned with project objectives, thus delaying its implementation. | Medium | 1. Regular coordination meetings have been held with Awá organizations in Colombia and Ecuador to share and ensure understanding of project procedures, governance mechanisms, timeline and outputs. 2. Promote capacity strenghtening actions to support Awa organizations in the management (financial and organisational) of the project as executing entities in both countries. A capacity strenghtening strategy was developed and is being implemented. 3. Standard Operating Procedures (SOPs) shared and explained to the Awa and Afro organisations at various coordination meetings to ensure understanding and compliance. 4. In Ecuador, the FCAE (Awá organization) is willing to participate as executing entity in the project implementation. 5. In Colombia, two out of three Awá organizations are willing to participate as executing entities in the project implementation.
Re-emergence of violence in the ​​project implementation area. | Medium/High | 1. Carry out security monitoring on a monthly basis, in coordination with UNDSS; 2. Implement UNDSS MOSS standards of operations; 3. Close coordination and escort service with communities leaders in the implementation of project activities. 4. Coordination with local authorities to ensure all actors are informed about the objectives of the project.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
As multilateral implementing entity (MIE), WFP has provided technical assistance and political support in finding innovative solutions to the implementation challenges that arised.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions please see bottom of page.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Project Manager/Coordinator: | Output 1.1.1. One study per watershed produced on traditional and local practices, promoting resilience to climate change and variability in the targeted binational watersheds, with community participation and particular attention to ancestral and native plant and tree species that can improve dietary diversity and are resilient to climate change |  | Studies in the binational watersheds carried out and results shared with communities and key stakeholders at binational, national and local level |  | Studies on traditional and local practices, promoting resilience to climate change, in the two binational watershed are in progress. Results will be shared with all key stakeholders at binational, national and local level. In addition, in colaboration with IDEAM (Institute of Hydrology, Meteorology and Environmental Studies) secondary information on ecosystem services and vegetation has been collected. These data have been updated with the analysis of free satelite images provided by the European spatial agency and the IEE (Ecuatorian spatial institute). | MS
| Output 1.1.2. Feasibility study conducted with communities to assess the potential for marketing native species for medicinal, artisanal, food and fodder related uses at regional and departmental levels |  | Study carried out and results shared with communities and key stakeholders at binational, national and local level |  | Feasibility studies to assess the potential for marketing native species at regional and departamental level are in progress in both countries to assess the potential for marketing native species. To generate comprehensive knowledge and complement the recollection of primary data, studies under outputs 1.1.1 and 1.1.2 will be carried out through a unique watershed study on traditional practices promoting resilience to climate change, with a special emphasis on native species and plants and their potential for marketing. | MS
| Output 1.1.3. Workshops, dialogues and cultural events (including fairs) organized to disseminate study results to 120 Afro and Awá communities, leaders and decision makers, in local languages. Equitable participation of men and women will be promoted |  | Workshops, dialogues and meetings to share project's outputs and procedures |  | Training workshops for the project baseline and meetings to share project's timeline, outputs, procedures and key documents (Annual operational operational plan, standards of operation and climate risk assessment methodology) have been carried out in both countries. To date, 17 workshops and meetings have been carried out. Equitable participation of men and women have been promoted (155 community leaders and members participated in the events, out of which 72 women). | HS
| Output 1.2.1. In 120 communities, leaders, community members and women groups trained on climate change threats with culturally and gender sensitive methods. Equitable participation of men and women will be promoted |  | 45 leaders and community members trained |  | A binational capacity streghtening strategy for Awá and Afro communities has been elaborated. In collaboration with key stakeholders at national and local level (Ministries of Environment, local governments and universities), a diploma course on climate change, disaster risk management, food security and nutrition and gender has been carried out and it will also be implemented in the community education centres. To date, 42 leaders and community members have been trained. Equitable participation of men and women has been promoted (21 women trained). | HS
| Output 1.2.2. Dialogues, fairs and exchanges involving 120 communities, leaders and community members on food security, nutrition and healthy living habits, considering climate threats, with special focus on diversifying diets and increasing incomes from the production and sale of native species and products. Equitable participation of men and women will be promoted |  |  |  | This activity will be implemented in the last quarter of this year. | N/A
| Output 1.2.3. One binational web-based adaptation learning platform in use |  | Edufami platform implemented for the binational project |  | On the basis of the Nutrifami platform (WFP e-learning platform on nutrition and healthy lifestyle), new platforms on climate change (Climafami) and on gender (Equifami) have been developed with correlated contents. Although these two platforms are not available for public users yet, contents have been validated with 23 Afro leaders and community members. Climate change and gender contents have been complemented with training materials elaborated in the FORECCSA project. | HS
| Output 1.2.4. Compilations and sharing of best practices on risk reduction and risk management actions at binational watershed level, considering ecosystem type and emphasizing traditional and local knowledge |  |  |  | This activity will be implemented in the last quarter of this year, once the studies results are available, they will be published. | N/A
| Output 2.1.1. Studies at the binational watershed level produced on: 1) water provision considering climate threats; 2) ecosystem vulnerability in the face of climate change and variability and extreme events; and 3) food security and nutrition in vulnerable communities |  | Baseline of Awá and Afro populations in the border region. Climate risk assessment, studies on water provision considering climate threats and ecosystem vulnerability in the face of climate change and extreme events in the Mira-Mataje and Guaitara-Carchi watersheds |  | At binational level, baseline survey has been conducted with 1615 Awá and Afro households. Primary data on household general characteristics, socio-economic condition and income, food security and nutrition, housing access and conditions, climate change, gender and family violence was collected. In alignment with IPCC framework, studies will generate knowledge on climate risks and water provision in the Mira-Mataje and Guaitara-Carchi watersheds. | S
| Output 2.2.1 Binational Early Warning Systems introduced, specifically tailored to inform the Afro and Awá communities about extreme events. Additionally, climate services will be introduced to include agro-meteorological data; vulnerability mapping, with a focus on crop yields and cycles; and climate risks in mangrove and high-mountain ecosystems |  |  |  | This activity will be implemented in year 2. | N/A
| Output 2.2.2. Approximately 120 leaders and community members trained in Emergency Preparedness and Response and understanding and planning for climate threats |  |  |  | This activity will be implemented in year 2. | N/A
| Output 3.1.1. Participatory approaches developed, interfacing scientific and traditional knowledge |  |  |  | This activity will be implemented in year 2. | N/A
| Output 3.1.2. Effective adaptation measures designed and implemented incorporating participatory approaches, traditional and local knowledge and tested techniques to recover of degraded ecosystems in 120 communities |  |  |  | This activity will be implemented from year 2. | N/A
| Output 3.1.3. Community water harvesting, storage and management measures introduced |  |  |  | This activity will be implemented from year 3. | N/A
| Output 3.1.4. Cost-benefit analysis of proposed adaptation measures at micro-watershed level |  |  |  | This activity will be implemented in year 2 and 3. | N/A
| Output 3.1.5. Native species reintroduced to diversify production and consumption and for commercialization, including introduction of organic and agro-ecological crop production practices and ocean species |  |  |  | This activity will be implemented in year 2 and 3. | N/A
| Output 3.2.1. Soil management activities implemented, including agro-forestry and native nitrogen-fixing species |  |  |  | This activity will be implemented from year 3. | N/A
| Output 3.2.2. Conservation and recovery of 3,000 ha of forest ecosystems and 2,000 ha of mangroves threatened by climate change through tree planting and forest management actions, at the micro-watershed level, with species that are native and resistant to climate variability, in line with national plans |  |  |  | This activity will be implemented from year 3. | N/A
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Javier León
| Email: | javier.leon@wfp.org
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. . (word limit=500)
In the first year, project implementation made significant progress. For coordination activities, binational and national governance committees have been set up and the binational annual operational plan was approved. In relation to project activities, significant progress has been made in baseline primary data collection on climate change, food security and nutrition and gender at community level, as well as on collection of secondary information for baseline technical studies. In addition, a capacity strenghetening strategy for the executing entities has been elaborated. This strategy comprises technical, organizational, planning and resource management issues. First training workshops have been carried out. Although, the project presents some difficulties, mainly due to coordination problems with some Awá organizations in Colombia that belong to the binational Gran Familia Awá, one of the executing entities. In particular, change in Awá leadership in Colombia led to interests not aligned with project objectives, thus delaying its implementation. Fortunately, the project team identified this issue on time and implemented transparent and efficient mitigation measures, in alignment with its principles and mandate. As next steps, it is crucial to provide assistance to executing entities in the capacity strengthening process, as well as speed up with the implementation of the remaining activities of year 1, to reduce delays and to ensure a timely and successful project implementation.
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Implementing Agency | Output 1.1.1. One study per watershed produced on traditional and local practices, promoting resilience to climate change and variability in the targeted binational watersheds, with community participation and particular attention to ancestral and native plant and tree species that can improve dietary diversity and are resilient to climate change |  | Studies in the binational watersheds carried out and results shared with communities and key stakeholders at binational, national and local level |  | Studies on traditional and local practices, promoting resilience to climate change, in the two binational watershed are in progress. Results will be shared with all key stakeholders at binational, national and local level. In addition, in colaboration with IDEAM (Institute of Hydrology, Meteorology and Environmental Studies) secondary information on ecosystem services and vegetation has been collected. These data have been updated with the analysis of free satelite images provided by the European spatial agency and the IEE (Ecuatorian spatial institute). | MS
| Output 1.1.2. Feasibility study conducted with communities to assess the potential for marketing native species for medicinal, artisanal, food and fodder related uses at regional and departmental levels |  | Study carried out and results shared with communities and key stakeholders at binational, national and local level |  | Feasibility studies to assess the potential for marketing native species at regional and departamental level are in progress in both countries. To generate comprehensive knowledge and complement the recollection of primary data, studies under outputs 1.1.1 and 1.1.2 will be carried out through a unique watershed study on traditional practices promoting resilience to climate change, with a special emphasis on native species and plants and their potential for marketing. | MS
| Output 1.1.3. Workshops, dialogues and cultural events (including fairs) organized to disseminate study results to 120 Afro and Awá communities, leaders and decision makers, in local languages. Equitable participation of men and women will be promoted |  | Workshops, dialogues and meetings to share project's outputs and procedures |  | Training workshops for the project baseline and meetings to share project's timeline, outputs, procedures and key documents (Annual operational operational plan, standards of operation and climate risk assessment methodology) have been carried out in both countries. At the date, 17 workshops and meetings have been carried out. Equitable participation fo men and women have been promoted (155 community leaders and members participated in the events, out of which 72 women). | HS
| Output 1.2.1. In 120 communities, leaders, community members and women groups trained on climate change threats with culturally and gender sensitive methods. Equitable participation of men and women will be promoted |  | 45 leaders and community members trained |  | A binational capacity streghtening strategy for Awá and Afro communities have been elaborated. In collaboration with key stakeholders at national and local level (Ministries of Environment, local governmrnts and universities), a diploma course on climate change, disaster risk management, food security and nutrition and gender has been carried out and it will also be implemented in the community education centres. At the date, 42 leaders and community members have been trained. Equitable participation fo men and women have been promoted (21 women trained). | HS
| Output 1.2.2. Dialogues, fairs and exchanges involving 120 communities, leaders and community members on food security, nutrition and healthy living habits, considering climate threats, with special focus on diversifying diets and increasing incomes from the production and sale of native species and products. Equitable participation of men and women will be promoted |  |  |  | This year will be implemented in the last quarter of this year. | N/A
| Output 1.2.3. One binational web-based adaptation learning platform in use |  | Edufami platform implemented for the binational project |  | On the basis of the Nutrifami platform (WFP e-learning platform on nutrition and healthy lifestyle), new platforms on climate change (Climafami) and on gender (Equifami) have been developed with correlated contents. Although these two platforms are not available for public users yet, contents have been validated with 23 Afro leaders and community members. Climate change and gender contents have been complemented with training materials elaborated in the FORECCSA project. | HS
| Output 1.2.4. Compilations and sharing of best practices on risk reduction and risk management actions at binational watershed level, considering ecosystem type and emphasizing traditional and local knowledge |  |  |  | This activity will be implemented in the last quarter of this year, once the studies results will be published. | N/A
| Output 2.1.1. Studies at the binational watershed level produced on: 1) water provision considering climate threats; 2) ecosystem vulnerability in the face of climate change and variability and extreme events; and 3) food security and nutrition in vulnerable communities |  | Baseline of Awá and Afro populations in the border region. Climate risk assessment, studies on water provision considering climate threats and ecosystem vulnerability in the face of climate change and extreme events in the Mira-Mataje and Guaitara-Carchi watersheds |  | At binational level, baseline survey has been conducted with 1615 Awá and Afro households. Primary data on household general characteristics, socio-economic condition and income, food security and nutrition, housing access and conditions, climate change, gender and family violence was collected. In alignment with IPCC framework, studies will generate knowledge on climate risks and water provision in the Mira-Mataje and Guaitara-Carchi watersheds. | S
| Output 2.2.1 Binational Early Warning Systems introduced, specifically tailored to inform the Afro and Awá communities about extreme events. Additionally, climate services will be introduced to include agro-meteorological data; vulnerability mapping, with a focus on crop yields and cycles; and climate risks in mangrove and high-mountain ecosystems |  |  |  | This activity will be implemented in year 2. | N/A
| Output 2.2.2. Approximately 120 leaders and community members trained in Emergency Preparedness and Response and understanding and planning for climate threats |  |  |  | This activity will be implemented in year 2. | N/A
| Output 3.1.1. Participatory approaches developed, interfacing scientific and traditional knowledge |  |  |  | This activity will be implemented in year 2. | N/A
| Output 3.1.2. Effective adaptation measures designed and implemented incorporating participatory approaches, traditional and local knowledge and tested techniques to recover of degraded ecosystems in 120 communities |  |  |  | This activity will be implemented from year 2. | N/A
| Output 3.1.3. Community water harvesting, storage and management measures introduced |  |  |  | This activity will be implemented from year 3. | N/A
| Output 3.1.4. Cost-benefit analysis of proposed adaptation measures at micro-watershed level |  |  |  | This activity will be implemented in year 2 and 3. | N/A
| Output 3.1.5. Native species reintroduced to diversify production and consumption and for commercialization, including introduction of organic and agro-ecological crop production practices and ocean species |  |  |  | This activity will be implemented in year 2 and 3. | N/A
| Output 3.2.1. Soil management activities implemented, including agro-forestry and native nitrogen-fixing species |  |  |  | This activity will be implemented from year 3. | N/A
| Output 3.2.2. Conservation and recovery of 3,000 ha of forest ecosystems and 2,000 ha of mangroves threatened by climate change through tree planting and forest management actions, at the micro-watershed level, with species that are native and resistant to climate variability, in line with national plans |  |  |  | This activity will be implemented from year 3. | N/A
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Carmen Galarza/ Chiara Trozzo
| Email: | carmen.galarza@wfp.org/ chiara.trozzo@wfp.org
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Executing Entities | Output 1.1.1. One study per watershed produced on traditional and local practices, promoting resilience to climate change and variability in the targeted binational watersheds, with community participation and particular attention to ancestral and native plant and tree species that can improve dietary diversity and are resilient to climate change |  | Studies in the binational watersheds carried out and results shared with communities and key stakeholders at binational, national and local level |  | Studies on traditional and local practices, promoting resilience to climate change, in the two binational watershed are in progress. Participatory planning and constant coordination were key factor for ensuring progress in the activity implementation, thus enhancing trust relationships within the territory. This process also contributes to raise awareness on the effects of climate change and the importance of climate actions among the targeted communities. | S
| Output 1.1.2. Feasibility study conducted with communities to assess the potential for marketing native species for medicinal, artisanal, food and fodder related uses at regional and departmental levels |  | Study carried out and results shared with communities and key stakeholders at binational, national and local level |  | Feasibility studies to assess the potential for marketing native species at regional and departamental level are in progress in both countries.The implementation of this activity is in progress, the main challenge was the creation of a common understanding of the scope and purpose of the study among the targeted communities. Therefore, coordination and collaboration with community leaders were essential to translate scientific methodologies into local language in an easily understandable way. Intellectual property rights of Afro and indigenous organizations have been guaranteed from the first stage of the elaboration of the feasibility study. | S
| Output 1.1.3. Workshops, dialogues and cultural events (including fairs) organized to disseminate study results to 120 Afro and Awá communities, leaders and decision makers, in local languages. Equitable participation of men and women will be promoted |  | Workshops, dialogues and meetings to share project's outputs and procedures |  | Training workshops for the project baseline and meetings to share project's timeline, outputs, procedures and key documents have been carried out in both countries. Participatory planning was a key factor to ensure equal participation of men and women in the events and meetings. These periodic coordination and planning meetings enhanced trust relations among targeted communities. Training sessions contributed to capacity strenghtening on technical issues. | S
| Output 1.2.1. In 120 communities, leaders, community members and women groups trained on climate change threats with culturally and gender sensitive methods. Equitable participation of men and women will be promoted |  | 45 leaders and community members trained |  | In collaboration with key stakeholders at national and local level (Ministries of Environment, local governmrnts and universities), a diploma course on climate change, disaster risk management, food security and nutrition and gender has been carried out. Training methodology and contents were tailored to the context and communities'needs, thus linking scientific information with traditional knowledge and practices. Participatory planning and the implementation of these sessions even in remote areas fostered the equal participation of men and women. All these factors contributed to awareness raising on the importance of climate adaptation action with food security and gender approaches and to strengthen sustainable governance mechanisms of the territory. | HS
| Output 1.2.2. Dialogues, fairs and exchanges involving 120 communities, leaders and community members on food security, nutrition and healthy living habits, considering climate threats, with special focus on diversifying diets and increasing incomes from the production and sale of native species and products. Equitable participation of men and women will be promoted |  |  |  | This year will be implemented in the last quarter of this year. | N/A
| Output 1.2.3. One binational web-based adaptation learning platform in use |  | Edufami platform implemented for the binational project |  | Based on the Nutrifami platform (WFP e-learning platform on nutrition and healthy lifestyle), new platforms on climate change (Climafami) and on gender (Equifami) have been developed with correlated contents. The web-based platform is considered an useful tool to disseminate information in an accessible and timely manner. Contents on climate messages, food security and nutrition and the linkage with gender fostered awareness on these issues among targeted communities. Community leaders and members are evaluating the feasibility to disseminate this information and replicate this training methodology in key places, such as schools. | S
| Output 1.2.4. Compilations and sharing of best practices on risk reduction and risk management actions at binational watershed level, considering ecosystem type and emphasizing traditional and local knowledge |  |  |  | This activity will be implemented in the last quarter of this year, once the studies results will be published. | N/A
| Output 2.1.1. Studies at the binational watershed level produced on: 1) water provision considering climate threats; 2) ecosystem vulnerability in the face of climate change and variability and extreme events; and 3) food security and nutrition in vulnerable communities |  | Baseline of Awá and Afro populations in the border region. Climate risk assessment, studies on water provision considering climate threats and ecosystem vulnerability in the face of climate change and extreme events in the Mira-Mataje and Guaitara-Carchi watersheds |  | At binational level, baseline survey has been conducted with 1615 Awá and Afro households. Participatory methodology ensured the successfull implementation of the activity. Baseline survey tools were designed and validated with targeted communities. Community members were trained and hired as enumerators. This process enhanced trusty relationships within the territory and ensured the good quality of the collected primary information. Gender baseline contributed to awareness raising on the negative effects of family and gender-based violence at grassroot level. | S
| Output 2.2.1 Binational Early Warning Systems introduced, specifically tailored to inform the Afro and Awá communities about extreme events. Additionally, climate services will be introduced to include agro-meteorological data; vulnerability mapping, with a focus on crop yields and cycles; and climate risks in mangrove and high-mountain ecosystems |  |  |  | This activity will be implemented in year 2. | N/A
| Output 2.2.2. Approximately 120 leaders and community members trained in Emergency Preparedness and Response and understanding and planning for climate threats |  |  |  | This activity will be implemented in year 2. | N/A
| Output 3.1.1. Participatory approaches developed, interfacing scientific and traditional knowledge |  |  |  | This activity will be implemented in year 2. | N/A
| Output 3.1.2. Effective adaptation measures designed and implemented incorporating participatory approaches, traditional and local knowledge and tested techniques to recover of degraded ecosystems in 120 communities |  |  |  | This activity will be implemented from year 2. | N/A
| Output 3.1.3. Community water harvesting, storage and management measures introduced |  |  |  | This activity will be implemented from year 3. | N/A
| Output 3.1.4. Cost-benefit analysis of proposed adaptation measures at micro-watershed level |  |  |  | This activity will be implemented in year 2 and 3. | N/A
| Output 3.1.5. Native species reintroduced to diversify production and consumption and for commercialization, including introduction of organic and agro-ecological crop production practices and ocean species |  |  |  | This activity will be implemented in year 2 and 3. | N/A
| Output 3.2.1. Soil management activities implemented, including agro-forestry and native nitrogen-fixing species |  |  |  | This activity will be implemented from year 3. | N/A
| Output 3.2.2. Conservation and recovery of 3,000 ha of forest ecosystems and 2,000 ha of mangroves threatened by climate change through tree planting and forest management actions, at the micro-watershed level, with species that are native and resistant to climate variability, in line with national plans |  |  |  | This activity will be implemented from year 3. | N/A
[5 empty] | Overall Rating | S
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Alvaro Guanga - Resguardo Nulpe Medio Alto Río San Juan (CAMAWARI) / Inginio Castillo - Fedarpon/CANE
| Email: | alvaromg15@gmail.com / castilloinginio@hotmail.com
| Progress on Key Milestones |  | Expected Progress |  | Progress to Date | Rating
Other
Overall Rating
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
Name:
Email:
| Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  | Led by WFP, the inception workshop was held in may 2018. During this first year, significant progress has been made in the elaboration of project standard operating procedures (SOP) and coordination mechanisms with key stakeholders at binational, national and local level. Governance committees have been set up: the binational steering committe in October 2018 (with the participation of Ministries of Environment) and the national steering committees in both countries in 2019. In addition, significant progress has been made in the baseline primary data recollection with a household survey on socio-economic conditions and income, production, food security and nutrition, climate change and gender. A capacity strengthening strategy for Awá and Afro organizations has been elaborated, incorporating technical, organizational, planning and resource managament issues, covered during the first training workshops. Although coordination problems have been registered with some Awá organizations in Colombia, WFP efficiently solved this issue, implementing mitigation measures in alignment with its principles and mandate. In particular, various coordination meeting were carried out to share project Standard Operating procedures (SoPs), thus ensuring understanding and compliance. A capacity assessment of Awá organizations as executing entities has also been carrying out to identify gaps and implement concrete actions to support these organizations in the project management. Great emphasis was also made on WFP active role in adaptation to climate change to promote resilience of the most vulnerable communities and improve their food security and nutrition.Finally, this year baseline information will be complemented with climate risk assessment and studies on water provision, traditional practices and native species, promoting resilience to climate change and feasiblity study on marketing in the two binational watersheds. These activities will carried out in close collaboration with Awá and Afro communities to enhance participatory approaches in the implementation of the activities. The executing agencies highlighted the participatory planning and constant coordination with community leaders and members as the key factor for the progress in the activities implementation, thus contributing to strengthen their technical and management capacities. Activities methodologies and contents were tailored to the context and communities needs, enhancing trsuting relationships and sustainable governance mechanisms among targeted communities.
Rating Definitions
|  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
|  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
|  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
|  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
|  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
|  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
| Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Impact
|  | Afro and Awá communties’ vulnerability reduced, with increased capacities to confront climate variability | Communities vulnerability is rated high (in alignment with new IPCC framework, the project will measure climate risk instead of climate vulnerability) | To be measured at mid-term review | Community vulnerability is low to medium by the end of the project (in alignment with new IPCC framework, the project will measure climate risk instead of climate vulnerability)
|  | Dietary diversity score | Four items in household diet | To be measured at mid-term review | Increased dietary diversity to seven items in household diet
|  | Binational capacity strengthening score | Climate risks related to FSN are not articulated in local plans | To be measured at mid-term review | Institutions strengthened to incorporate adaptation and risk reduction measures in plans
|  | Percentage of women with physical, political and economic empowerment | Women with limited role in decision-making, participation and opportunities for income generation | To be measured at mid-term review | Increased the women’s physical, political and economic empowerment
Outcomes & Ouputs
Objective 1: Recover with full participation of Afro and Awá communities traditional knowledge and capacities to manage climate change risks and food security and nutrition in targeted binational watersheds.
|  | Outcome 1.1 Ancestral knowledge and practices recovered in support of adaptation and food security | Ancestral knowledge is being lost and not used in adaptation or development planning or implementation | Due to progress in outputs 1.1.1, 1.1.2 and 1.1.3, the estimated progress for the outcome is 25%. | By project end, ancestral knowledge and practices will be included in the design of adaptation measures and local planning
|  | Output 1.1.1 Number of studies on traditional and native species | Number of studies on traditional and native species | The Terms of Reference of these studies have been jointly elaborated with Ministries of Environments, Awá and Afro organizations. In both countries, teams of experts have been set up. Articulation and coordination will be promoted between the two teams, in alignment with the binational methodological framework elaborated by project staff. The estimated progress is 20%. | Two watershed-level studies produced on 1) tree and plant species resilient to climate change and variability in the binational watersheds; and 2) ancestral and native species that can improve dietary diversity and are resilient to climate change and variability
|  | Output 1.1.2 Number of studies on marketing traditional and native species | Limited knowledge on market opportunities for native species | The Terms of Reference of these studies have been jointly elaborated with Ministries of Environments, Awá and Afro organizations. In both countries, teams of experts have been set up. Articulation and coordination will be promoted between the two teams, in alignment with the binational methodological framework elaborated by project staff. The estimated progress is 20%. | Three feasibility analyses of potential marketing of native species with community participation
|  | Output 1.1.3 Number of events to disseminate information | No previous events to raise awareness and no existing use of traditional knowledge for adaptation and food security in the border region | At the date, 17 events were carried out to raise awareness on the nexus between climate change and food security and nutrition, as well as to share project's standards of operations and annual operationla plan. The estimated progress is 30%. | At least 10 workshops and cultural events organized to share and disseminate study results with 120 Afro and indigenous communities, leaders and decision makers, in local languages. There is an equitable participation of men and women
|  | Outcome 1.2 Traditional knowledge on climate change and adaptation generated, disseminated and integrated into adaptation and development territorial planning processes | Traditional knowledge not used in adaptation or food security planning or activity implementation | Due to progress in outputs 1.2.1 and 1.2.3, the expected progress for the outcome is 20%. | By project end, ethnic communities receive support in integrating climate-related ancestral knowledge into Life Plans and Safeguard Plans
|  | Output 1.2.1 Number of communities and leaders trained | Limited awareness of climate change threats and impacts on gender | In collaboration with local governments and universities, a diploma course on climate change, food security and nutrition and gender has been carried out. This course will be replicated in the community education centres. To date, 42 Afro leaders and community members have been trained. | By project end, leaders and community members in 120 communities trained in climate change threats, using culturally and gender-sensitive methods. There is an equitable participation of men and women
|  | Output 1.2.1 Number of women trained |  | In collaboration with local governments and universities, a diploma course on climate change, food security and nutrition and gender has been carried out. This course will be replicated in the community education centres. To date, 21 Afro women have been trained.
|  | Output 1.2.2 Number of communities and leaders trained | Limited awareness of food security, dietary diversity and diversifying livelihoods | No Progress | By project end, 120 communities trained. There is an equitable participation of men and women
|  | Output 1.2.2 Number of women trained |  | No Progress
|  | Output 1.2.3 Number of learning platforms | Lack of information and learning sharing in binational watersheds | On the basis of the Nutrifami platform (WFP e-learning platform on nutrition and healthy lifestyle), new platforms on climate change (Climafami) and on gender (Equifami) have been developed with correlated contents. The estimated progress is 30% | By project end, one binational learning platform in place and used by communities and local authorities
|  | Output 1.2.4 Number climate risk reduction and management best practices | Lack of information on best practices in risk reduction and management in border region | No Progress | By project end, twelve best practices compiled from each binational watershed on risk reduction and management
|  | Output 1.2.4 Number climate risk reduction and management best practice sharing events | Lack of spaces to share knowledge on risks | No Progress | By project end, one knowledge sharing event per watershed on risk reduction and management
Objective 2: Strengthen knowledge generation to effectively plan, design and implement adaptation responses in highly food insecure communities, considering emergency preparedness and response actions.
|  | Outcome 2.1 Scientific studies tailored to binational contexts, considering traditional knowledge and community priorities | Limited scientific climate information accessible for Afro and Awá communities and decision-makers | Due to progress in output 2.1.1, the estimated progress for the outcome is 20%. | By project end, 120 communities will have access to scientific climate risk information at the micro-watershed level
|  | Output 2.1.1 Number of scientific studies | No knowledge of water provision and ecosystem threats due to climate change | In alignment with the new IPCC framework, a binational climate risk assessment methodology has been developed, with a great emphasis on the nexus between climate change and food security and nutrition. As the adverse effects of climate change are contributing to Awá and Afro food insecurity and malnutrition, FSN pillars have been included in the vulnerability and adaptive capacity formulas. The estimated progress is 20% | By project end, at least one study on each of the following: 1) water provision and climate risks in two binational watersheds; and 2) ecosystem vulnerability due to climate change and variability and extreme events
|  | Outcome 2.2 Disaster preparedness score | Limited disaster preparedness and response mechanisms | No Progress | Disaster preparedness score equal to or greater than 7, indicating local government capacity in disaster preparedness ad food security information with WFP support
|  | Ouput 2.2.1 Number of early warning systems | No Afro or Awá directed early warning systems or climate services for agro and hydro-climatic data | No Progress | By project end, at least one EWS in place covering all targeted communities with at least 20 nodes at community level, and territorial organizations able to take appropriate response actions following protocols
|  | Ouput 2.2.1 Number of climate information products/services provided for decision making |  | No Progress
|  | Output 2.2.2 Number of EPR training | Limited Afro and Awá capacity to prepare or respond to emergencies | No Progress | By project end, at least five training conducted targeting 120 leaders. Training of community members include equitable percentage of men and women
Objective 3: Strengthen adaptive capacity of highly food insecure communities to reduce climate risks and food insecurity and improve community resilience in targeted populations through concrete adaptation measures.
|  | Outcome 3.1 Percentage of households and communities having more secure access to livelihood assets | Limited adaptive capacity in Afro and Awá binational watershed communities | No Progress | By project end, 100 percent of targeted communities in the binational watersheds have created assets which reduce risk to climate change
|  | Output 3.1.1. No of methodologies developed to integrate scientific and traditional knowledge | No methodology established | No Progress | By project end, participatory approaches enables communities to incorporate both scientific both scientific and traditional knowledge to reduce climate risks
|  | Ouput 3.1.2 No. of natural resource assets created, maintained or improved to withstand conditions resulting from climate variability | Adaptation measures not customized to local context | No Progress | By the end of the project, created assets support the sustainable recovery of degraded ecosystems. Target to be developed with baseline information
|  | Output 3.1.2 Time saved due to adaptation measures for women and men | Men and Women spend excessive time gathering water, fuelwood, etc. | No Progress | 120 community-based adaptation plans
|  | Ouput 3.1.2 Number of community based adaptation plans | Communities in the area of intervention do not have adaptation plans | No Progress
|  | Output 3.1.3 Number of communities with improved access to water for agriculture and consumption | Limited community access to water resources | No Progress | By the end of the project, up to 120 communities adopt water management measures according to community plans
|  | Output 3.1.3 Number of people with improved access to drinking water | Water is not purified and especially children’s nutrition is affected by unclean water | No Progress | Up to 120 communities, clean drinking water is made available
|  | Output 3.1.4 Number of cost-benefit analyses | Little research completed on the cost or benefits of proposed adaptive measures | No Progress | By the end of the project, cost-benefit analyses implemented for each adaptation measure, on a watershed level
|  | Output 3.1.5 Number of communities that reintroduced climate resilient native species | Low levels of utilization and protection for native species | No Progress | By the end of the project, 120 communities increased land area dedicated to the cultivation of native crops
|  | Output 3.1.5 Type of income sources for households generated under climate change scenario | Communities do not market native species | No Progress | Targeted households develop one alternate income source
|  | Output 3.1.5 Porcentaje de aumento en los ingresos de los hogares por los servicios ecosistemicos y los sistemas agrícolas |  | No Progress | At least 10 percent increase in household monetary incomes through introduced adaptation measures
|  | Outcome 3.2 Number of natural assets implemented | Limited number of natural assets in place to withstand or adapt to climate change events | No Progress | Activities implemented according to community plans
|  | Output 3.2.1 Number of ha | Limited soil management activities | No Progress | At least 3,000 ha degraded land recovered using agro-forestry and nitrogen fixing species
|  | Output 3.2.2 Number of ha | Lack of effective protection of native forests and mangrove populations | No Progress | At least 3,000 ha of forest and 2,000 ha of mangroves protected and recovered

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | Participatory approaches enhanced coordination and synergies among government ministries, local governments, Awá and Afro communities and enriched project process and outputs, respecting their cosmovision and cultural context. This process implied broad and extensive consultations with Afro and Awá leaders and community members, thus causing some delays in the project roadmap.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | Conflict of interests within the Gran Familia Awá in Colombia affected the transparent and trusty dialogue between Awá and Afro populations and the project team, vital to the successful project implementation in the border territories. As the Gran Familia Awá has no legal personality neither in Colombia nor in Ecuador, conflict of interests was solved through a frank dialogue and negotiation process with Awá organizations that legally represent communities. Negotiations generated unplanned delays which are not expected to affect the final outcomes.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design) | A constant dialogue and sharing processes and activities with Afro and Awá populations were key factors for a joint project plannig at binational and national level. Participatory approaches and regular coordination meetings contributed to successfully implement the project and solve the above mentioned challenges. No major changes were undertaken.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? | Enhancing dialogues and workshops with the participation of women and men, where women actively participated in the decision-making process, has been enabling a gender-sensitive project execution, thus contributing to the implementation of gender-sensitive adaptative and food security measures in the following years.
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | n/a
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | n/a
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | n/a
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | n/a
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | n/a
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | n/a
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | n/a
What measures are/have been put in place to ensure sustainability of the project/program results? | n/a
What measures are being/could have been put in place to improve project/program results? | n/a
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | n/a
If learning objectives have been established, have they been met? Please describe. | n/a
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | n/a
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | n/a

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
Link: http://www.adaptation-fund.org/sites/default/files/Results%20Framework%20and%20Baseline%20Guidance%20final.pdf
Adaptation Fund Strategic Results Framework
Project ID | LAC/MIE/Food/2015/1
Implementing Entity | WFP
Type of implementing entity | MIE
Country
Region | Latin America and Caribbean
Sector | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 92567 | 19867 | 72700 | Total |  |  |  | Total
|  | % of female beneficiaries |  |  |  | % of female beneficiaries | 51% | 51% | 51% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries | 30% | 30% | 30% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 0 | Drought | 1: Ineffective | Total | 19867 | Drought | 4: Effective | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted | 51% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 0 | Food security | National | 1: No plans conducted or updated | 2 | Food security | National | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Regional | 2 | 1: Risk knowledge | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 10 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Wind | No. of adopted Early Warning Systems | Category targeted | Hazard | Wind | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 3: Dissemination and communication | Geographical coverage | Regional | 2 | 3: Dissemination and communication | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 10 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Coastal flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 0 | 1: Risk knowledge | Geographical coverage | Regional | 2 | 1: Risk knowledge | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 0 |  |  | Number of municipalities | 2 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 0 | Food security | 1: No capacity | Total | 50 | Food security | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted |  |  |  | % of female targeted | 51% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 0 |  | Public |  | 50 | 51% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | Local | Food security | 1: No capacity | Public | Regional | Food security | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 0% |  | Multi-sector |  | 80% |  | Multi-sector
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 0% |  | 1: Aware of neither |  | 19867 | 51% | 5: Fully aware
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Food security | Local | 1: Non responsive (Lacks all elements ) |  | Food security | Local | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 1: Not improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 0 | Community |  | Food security | 1 | Community |  | Food security
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 1: Ineffective |  | Food security | land | 4: Effective |  | Food security | land
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Catchment area/Watershed/Aquifer |  | km rehabilitated | 2: Partially effective | Catchment area/Watershed/Aquifer | 10 | km rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests |  | ha rehabilitated | 2: Partially effective | Forests | 3000 | ha rehabilitated | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves |  | ha protected | 1: Ineffective | Mangroves | 2000 | ha protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 0 |  | 1: No improvement |  | 4967 | 51% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 0 |  |  | Agriculture | 4967 | 51% | From 5% to 10% | Agriculture
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Physical capital | Food security | Community-based adaptation | 120 | Physical capital | Food security | Community-based adaptation
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 4967 | Agriculture |  | 150 | 4967 | Agriculture |  | 165
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 1: None |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 0 | Food security | National | Environmental policy | 2 | Food security | National | Environmental policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 0 | 1: Not enforced (No elements implemented) |  | 1: Ineffective | 2 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste

## Units for Indicators
Fund Outcome Indicator Units
1. Generation of relevant data, Stakeholders, and Timeliness 2.1. Include both qualitative and quantitative measures of capacity level within targeted institutions 2.2. Number (men and women and other vulnerable groups) 3.1. Use scale from 1 to 5: 5: Fully aware 4: Mostly aware 3: Partially aware 2: Partially not aware 1: Aware of neither predicted adverse impacts of climate change nor of appropriate responses 3.2. Use scale from 1 to 5: 5: All 4: Almost all 3: Half 2: Some 1: None 4.1. Summarize in an overall scale (1-5): 5: Highly responsive (All defined elements ) 4: Mostly responsive (Most defined elements) 3: Moderately responsive (Some defined elements) 2: Partially responsive (Lacks most elements) 1: Non responsive (Lacks all elements ) 4.2. Summarize in an overall scale (1-5): 5: Fully improved 4: Mostly Improved 3: Moderately improved 2: Somewhat improved 1: Not improved 5. Depends on the targeted natural asset: Biological (species): measure through changes in population numbers (dynamics, structure, etc.) Land: measure changes in hectares. Baseline data will be necessary to estimate the change. Supporting indicators baseline and target (as well as contextual information) are needed such as the following: Farmers adopting recommended technologies, Ha. of land improved, Average deforestation rate Etc. Use scale from 1 to 5. 5: Very effective (All elements are present) 4: Effective (Most elements are present) 3: Moderately effective (Some elements are present) 2: Partially effective (Most elements are not present) 1: Ineffective (No elements are present) 6.1. Summarize in an overall scale (1-5): 5: Very high improvement 4: High improvement 3: Moderate improvement 2: Limited improvement 1: No improvement 6.2. Household income by source of livelihood in project area (USD) prior and post project intervention 7. Summarize in an overall scale (1-5). 5: All (Fully integrated) 4: Most 3: Some 2: Most not integrated 1: None
Fund Output Indicator Units
1.1. Number, sector(s) and level(s) of projects or interventions in separate fields of monitoring plan 1.2. Number 2.1.1. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target 2.1.2. Number of staff (male/female) of targeted institutions: a. Obtain baseline information: total number of staff from targeted institutions b. Define target: needs to be defined by project proponents 2.2.1. Quantitative: Percentage (includes women – and other vulnerable groups – and men). Qualitative: Adequacy: include direct analysis of major areas; adequacy/effectiveness of systems or analysis of perceptions of populations and institutions. 2.2.2. Number (broken down by gender and, if possible, by vulnerable groups defined in the area of intervention) of people 3.1. Number and type (in separate columns) at local level. 3.2. Number 4.1. Number and type 4. 2. Number and type (entered in separate columns) 5. Number of interventions by type of natural asset and intervention 6.1. Number and type (in separate columns of monitoring plan) 6.2. Income sources per household; description of income source and number of households. 7.1. Number/Sector 7.2. Number; Effectiveness (see previous indicator) through enforcement level.