## Overview
Project Performance Report (PPR)-I
* Refers to both projects and programs
| Period of Report (Dates) | 26 June 2019-25 June 2020
| Project Title: | Integrating Flood and Drought management and Early warning for climate change adaptation in the Volta Basin (VFDM)
| Project Summary: | The VFDM project will provide the first large scale and transboundary implementation of Integrated Flood and Drought Management by empowering the National Meteorological and Hydrological Services (NMHS) and other competent authorities of the six riparian countries (Benin, Burkina Faso, Côte d’Ivoire, Ghana, Mali, and Togo) with robust and innovative solutions for disaster risk reduction and climate change adaptation, including ecosystem-based solutions and gender-sensitive participatory approaches. An early warning system (EWS) will be designed to reach the civil security services and other private and public stakeholders. The three specific objectives of the project are to: 1)Develop capacity and established frameworks at the local, national and regional levels to ensure risk-informed decision-making; 2) Develop concrete adaptation and environmentally friendly actions with an integrated approach; 3) Strengthening policy and institutional capacity for integrated flood and drought management at the local, national, and transboundary levels.
|  |  | Countries | Project Type: |  | GEF Focal Area: | GEF 4 Focal Areas | GEF 2 / 3 Operational Programme: | Overall Rating of the project in the evaluation by the project evaluator: | GEF-4 Focal Area Strategic Program: | GEF-3 Focal Area Strategic Program:
| Database Number: | Not available at the project page at the Adaptation Fund website https://www.adaptation-fund.org/project/integrating-flood-drought-management-early-warning-climate-change-adaptation-volta-basin-benin-burkina-faso-cote-divoire-ghana-mali-togo/ | Afghanistan | FP | Yes | Biodiversity | 1 | 1 | U | BD-SP1-PA Financing | 1: Arid & semi-arid ecosystems
Implementing Entity (IE) [name]: |  | World Meteorological Organization(WMO) | Albania | MSP | No | Climate Change Adaptation | 2 | 2 | S | BD-SP2-Marine PA | 2: Coastal, marine & freshwater ecosystems
| Type of IE: | Multilateral Implementing Entity (MIE) | Algeria | EA |  | Climate Change Mitigation | 3 | 3 | MU | BD-SP3-PA Networks | 3: Forest ecosystems
| Country(ies): | Benin, Burkina Faso, Côte d’Ivoire, Ghana, Mali, and Togo | Angola |  |  | International Waters | 5 | 5 | Good | BD-SP5-Markets | 13: Conservation and Sustainable Use of Biological Diversity Important to Agriculture
Relevant Geographic Points (i.e. cities, villages, bodies of water): |  | Volta River Basin covering an area of about 400,000 km2 with a population of 29 Million (2016) and extending from semi-arid to sub-humid areas | Argentina |  |  | Multiple Focal Area |  |  |  | BD-SP7-Invasive Alien Species(IAS) | 6: Promoting the adoption of renewable energy by removing barriers and reducing implementation costs
[8 empty] | CC-SP2- Industrial EE | 8: Waterbody based operational program
| Project Milestones | [6 empty] | CC-SP3-RE,CC-SP4-Biomass | 9: Integrated Land and Water multiple focal area
| Milestone |  | Bahamas | [6 empty] | CC-SP5-Transport | 10: Contaminants based operational program
AFB Approval Date: |  | 2018-10-12
IE-AFB Agreement Signature Date: |  | 2019-02-19 | [6 empty] | CC-SP6-LULUCF | 12: Integrated Ecosystem Management
Start of Project/Programme: |  | 2019-06-25 | [6 empty] | Cross cutting capacity building | 14: Persistent Organic Pollutants
Actual Mid-term Review Date (if applicable): |  | TBD - Since overall duration of the project is 4 years
| Original Completion Date: | 2023-06-25
Revised Completion Date after approval of |  | N/A
extension request (if applic)
List each approval condition, if any, and report on the status of meeting them (duplicate table as nec)
Category of condition
Condition or Requirement
Current Status
Planned actions, including a detailed time schedule
|  | List (only) inception report/ extension request(s)/ MTR that have been prepared for the project and provide date(s) of submission for each | Cyprus
|  | No approval condition or clause was listed during the approval of the VFDM project | Czech Republic
List the Website address (URL) of project |  |  | Democratic People's Republic of Korea
|  | https://www.floodmanagement.info/floodmanagement/volta-basin/ | Democratic Republic of the Congo
https://www.adaptation-fund.org/project/integrating-flood-drought-management-early-warning-climate-change-adaptation-volta-basin-benin-burkina-faso-cote-divoire-ghana-mali-togo/
Denmark
List documents/ reports/ brochures / articles that have been prepared about the project. |  |  | Denmark
https://public.wmo.int/en/media/news/wmo-leads-new-flood-and-drought-management-project-volta-basin
https://public.wmo.int/en/resources/bulletin/integrated-approach-flood-and-drought-management-volta-basin
https://wmoomm.sharepoint.com/:b:/s/Services/ET-6ZVR9Lg1MhA8leqfnnesBJm9B2miya5mEy-XiZ5Bthg?e=uk1wNI
https://www.gwp.org/en/GWP-West-Africa/WE-ACT/News--Events/a-new-project-to-support-transboundary-climate-change-resilience-in-the-volta-basin/
https://www.gwp.org/fr/GWP-Afrique-Ouest/GWP-in-Action/News--Activities/un-nouveau-projet-pour-soutenir-la-resilience-au-changement-climatique-dans-le-bassin-de-la-volta/
https://public.wmo.int/en/events/workshops/inception-workshop-and-executive-partners-meeting-planned-under-framework-of-volta
https://www.fratmat.info/article/91460/62/gestion-des-inondations-et-de-la-secheresse-l-autorite-du-bassin-de-la-volta-lance-un-projet
https://www.gwp.org/fr/GWP-Afrique-Ouest/GWP-in-Action/News--Activities/un-nouveau-projet-pour-soutenir-la-resilience-au-changement-climatique-dans-le-bassin-de-la-volta/
Denmark
| Project contacts: |  | Djibouti
WMO Project Manager/Coordinator |  |  | Dominica
| Name: | Mr Ramesh Tripathi, World Meteorological Organization Secretariat | Dominican Republic
| Email: | rtripathi@wmo.int | Ecuador
| Date: | 2020-09-14 | Egypt
Government DA Benin
| Name: | Mr. Euloge Lima, Ministère en charge de l’Environnement | Equatoral Guinea
| Email: | limeloge@gmail.com/limeloge@yahoo.fr | Eritrea
| Date: | 2020-06-22 | Estonia
Government DA Burkina Faso
| Name: | Mr. Ambroise Kafando, Ministère de l’Economie, des Finances et du Développement
| Email: | ambkafando@gmail.com
| Date: | 2020-06-22
Government DA Côte d’Ivoire
| Name: | Mr. Oreste Santoni Akossi, Ministry of Environment and Sustainable Development
| Email: | akossisantoni@gmail.com
| Date: | 2020-06-22
Government DA Ghana
| Name: | Mr. Fredua Agyeman, Ministry of Environment, Science, Technology and Innovation
| Email: | Fredua_a@yahoo.com / Fredua_agyeman@hotmail.com
| Date: | 2020-06-22
Government DA Mali
| Name: | Mr. Seydou Keita, Ministère de l’Environnement, de l’Assainissement et du Développement Durable
| Email: | keitasey37@yahoo.fr
| Date: | 2020-06-22
Government DA Togo
| Name: | Mr. Essobiyou Thiyu Kohoga, Directeur de l’Environnement
| Email: | denv_togo@yahoo.fr,essobiyou@hotmail.com
| Date: | 2020-06-22
Implemeting Agency-WMO
| Name: | Giacomo Teruggi, VFDM Project Executive/Scientific Officer, WMO
| Email: | gteruggi@wmo.int | Finland
| Date: | 2020-09-14 | France
| Name: | Jean-Paul Gaudechoux, Senior Programme Manager, WMO | Gambia
| Email: | jpgaudechoux@wmo.int | Georgia
| Date: | 2020-09-14 | Germany
| Executing Agency-WMO |  | Ghana
| Name: | Mr Ramesh Tripathi, Project Officer
| Email: | rtripathi@wmo.int
| Date: | 2020-09-14
| Executing Agency-VBA |  | Greece
| Name: | Mr Robert Dessouassi , Executive Directorate | Grenada
| Email: | rdessouassi@abv.int | Guatemala
| Date: | 2020-06-22 | Guinea
| Name: | Mr Boukary NIAMPA, Project Technical Manager
| Email: | b.niampa@abv.int
| Date: | 2020-06-22
| Executing Agency-GWP-WA |  | Guinea Bissau
| Name: | Mr Armand Houanye, Executive Secretary | Guyana
| Email: | armand.houanye@gwpao.org | Haiti
| Date: | 2020-06-22 | Honduras
| Name: | Mr Maxime TEBLEKOU, Project Technical Assistant
| Email: | maxime.teblekou@gwpao.org
| Date: | 2020-06-22
Hungary
Iceland
India
Indonesia
Iran (Islamic Republic of)
Iraq
Ireland
Israel
Italy
Jamaica
Japan
Jordan
Kazakhstan
Kenya
Kiribati
Kuwait
Kyrgyzstan
Lao People’s Democratic Republic
Latvia
Lebanon
Lesotho
Liberia
Libyan Arab Jamahiriya
Liechtenstein
Lithuania
Luxembourg
Madagascar
Malawi
Malaysia
Maldives
Mali
Malta
Marshall Islands
Mauritania
Mauritius
Mexico
Micronesia, Federated States of
Monaco
Mongolia
Montenegro
Morocco
Mozambique
Myanmar
Namibia
Nauru
Nepal
Netherlands
New Zealand
Nicaragua
Niger
Nigeria
Norway
Oman
Pakistan
Palau
Panama
Papua New Guinea
Paraguay
Peru
Philippines
Poland
Portugal
Qatar
Republic of Korea
Republic of Moldova
Romania
Russian Federation
Rwanda
Saint Kitts and Nevis
Saint Lucia
Saint Vincent and the Grenadines
Samoa
San Marino
Sao Tome and Principe
Saudi Arabia
Senegal
Serbia
Seychelles
Sierra Leone
Singapore
Slovakia
Slovenia
Solomon Islands
Somalia
South Africa
Spain
Sri Lanka
Sudan
Suriname
Swaziland
Sweden
Switzerland
Syrian Arab Republic
Tajikistan
Thailand
The former Yugoslav Republic of Macedonia
Timor-Leste
Togo
Tonga
Trinidad and Tobago
Tunisia
Turkey
Turkmenistan
Tuvalu
Uganda
Ukraine
United Arab Emirates
United Kingdom of Great Britain and Northern Ireland
United Republic of Tanzania
United States of America
Uruguay
Uzbekistan
Vanuatu
Venezuela, Bolivarian Republic of
Viet Nam
Yemen
Zambia
Zimbabwe

## Financial Data
Financial information PPR 1: cumulative from project start to [insert date]
DISBURSEMENT OF AF GRANT FUNDS
How much of the total AF grant as noted in Project Document plus any project preparation grant has been spent to date?
Estimated cumulative total disbursement (USD) as of 25/06/2020 |  | 2095000
Add any comments on AF Grant Funds. (word limit=200) |  | Grant funds were well received and disbursements made to the Executing Entities, with VBA and GWP-WA receiving funds for the project staffs in September 2019. The IE hired the Project Manager based at the WMO Secretariat using the IE Fee.The IE Trust Fund and the implementation contracts with the Executing Partners and External Implementing Partners are contracted in the same currency (USD) as provided by the Adaptation Fund.This will avoid losses due to currency fluctuation. The IE and EEs are utilising the project execution costs as indicated in the project document. The Project Inception workshop was organized and conducted on 25 and 26 June 2019 and Inception workshop report was submitted to the AF Secretariat on July 24 2019. Out of the total 2,09,5000 amount received from the Adaptation Fund: 20,000 USD was received as PFG1, 80,000 USD as PFG2 and 1,995,000 USD as first year project disbursement
INVESTMENT INCOME |  | 0
Amount of annual investment income generated from the Adaptation Fund’s grant
EXPENDITURE DATA
List ouput and corresponding amount spent for the current reporting period |  | ITEM / ACTIVITY / ACTION (PFG1: Project Formulation Grant 1, PFG2: Project Formulation Grant 2, A: Project activity) | AMOUNT SPENT (USD) (Assuming 1 CHF approximately equal to 1 USD for some of the expenses) | AMOUNT PENDING WITH OBLIGATION (USD) | COMMENTS OR REMARKS
|  | First installment amount received from the Adaptation Fund | 1995000
Output | 1.1.1-Inventory of information on VCERs for floods and drought in the Volta Basin is conducted | A: 1.1.1.1-Conduct a desk study and field visits to identify VCERs, gaps and additional needs | 77000 | 0 | Mostly completed. National Consultation reports are available here: https://wmoomm.sharepoint.com/:f:/s/Services/EnvmhBfd9RVCtrufTGCqFnABC-xCWUernat8Ja0T4FWeXw?e=Ry86KG
|  | A: 1.1.1.2-Develop an action plan to complement gathered information on the VCERs and fulfil technical gaps (maps, satellite data requirements) | 0 | 21000 | It was planned to be done during the National workshops (initially planned during February and March 2020) under 1.1.1.3 but due to Covid-19 Pandemic situation, National workshops are currently planned from 21 September -13 October 2020.
|  | A:1.1.1.3-Organize workshops/meetings with the relevant stakeholders working on risk management to select priority areas for community consultations | 136000 | 32000 | It was planned for February -March 2020, but due to Covid-19 situation.National workshops are currently planned from 21september -13 October 2020.
|  | A.1.1.1.4 Conduct pilot field studies with 60 communities to identify multi-drivers of vulnerabilities and risks | 59000 | 37000 | on-going
|  | A 1.1.1.5 Draft the field studies reports and the Volta-atlas | 0 | 5000 | on-going
| 1.1.2-Database of VCERs, floods and drought related risk maps are developed | A 1.1.2.1 Assess the available IT equipment (computers, servers, databases, etc.) and IT/GIS expertise | 8000 | 5000 | preparartion on-going. Require visit to the project countries.
|  | A 1.1.2.2 Create the Volta Basin information exchange IT network | 0 | 10000 | On-going
|  | A 1.1.2.4 Develop web-based flood and drought risk maps | 0 | 30000 | Integration of existing information available globally, nationally and through completed and on-going projects
| 1.2.3 | Impact on environmental and ecosystem services indicators is evaluated for current and future scenarios | 62878 | 51622 | Some activities are conducted virtually due to covid-19 and others will be implemented looking at the covid-19 situation
| 2.1.2 The operational centre for the VoltAlarm Early Warning System is established in synergies with the NMHSs and the Volta Basin Authority | A 2.1.2.1-Define the needs related to facilities, equipment, technical capacities, human resources | 18000 | 3000
|  | A 2.1.2.2-Buy, install and test the equipment needed to create and use the VoltAlarm EWS | 55000 | 0 | On-going and will continue for the next three years of the project duration. Development of the VOLTALRAM and integration of existing information is on-going.Check below VOLTALRM EWS website: https://volta.mydewetra.world/ Username: WMO-Volta, password WMO-Volta
|  | A 2.1.2.5-Run and maintain the VoltAlarm system | 10000 | 0
| 2.3.2 | 2.3.2.1-Finalization of the Training Manual for Mainstreaming Gender in the E2E-EWS-FF & IFM | 0 | 14500
|  | Total Project Implementation and Execution cost (June 2019-June 2020) | 287000
|  | TOTAL | 712878 | 209122
|  | Total Expenditure (PFG1+PFG2+First implementation installment) including obligations | 922000
|  | Total Funds unspent from the first year funds (which will be used in the second year) | 1073000 |  | Due to COVID-19 pandemic situtaion, it was not possible to implement some of the planned activities due to travel restrictions, baseline information cannot be collected as National Agencies were not allowed to work from office, vendors or suppliers are not available for procurement etc. so the funds are unspent but they will be utilized in the second year of the project along with the second year activities
|  | Total amount disbursed to the other executing Partner-WMO | 623005
|  | Total amount disbursed to the other executing Partner-VBA | 110351
|  | Total amount disbursed to the other executing Partner-GWP-WA | 188644
PLANNED EXPENDITURE SCHEDULE
List outputs planned and corresponding projected cost for the upcoming reporting period |  | ITEM / ACTIVITY / ACTION | PROJECTED COST (USD) | Est. Completion Date | Comment/Remarks
|  | A1.1.2.3 Develop the database and create the links with the existing databases for the collected information on VCER including the main driving hydro-meteorological parameters for floods and drought events (e.g. precipitation, water levels, temperature, soil moisture, soil type, etc.) | 293300 | 2021-03-30 | Moved to second-year.Could not be implemented due to Global Covid-19 situation
|  | A1.1.2.4 Develop web-based flood and drought risk maps using the VCER database and existing maps developed in Ghana through the past projects funded by the World Bank and the Global Environment Facility (see part G for more information) | 139200 | 2021-03-01 | Moved to second-year.Could not be implemented due to Global Covid-19 situation
|  | A1.1.2.5 Assign roles and responsibilities to the agencies and organisations to regularly complement and improve the database and risk maps | 5000 | 2021-03-01 | Moved to second-year.Could not be implemented due to Global Covid-19 situation
|  | Output 1.1.3 Capacity of stakeholders to use Floods and Drought risk maps is enhanced | 274000 | 2021-06-01
|  | Output 1.1.4 Reports and communication documents on vulnerabilities, capacities,exposure and risks (VCERs) and Floods and Drought risk maps of the VoltaBasin | 10000 | 2021-06-01
|  | Output 1.2.1 Scenarios for socio-economic and environment development along with the climate change projections are collected | 30000 | 2021-03-01 | Moved to second-year.Could not be implemented due to Global Covid-19 situation
|  | Output 1.2.2 Projected impacts on water resources, urban development, environment and agricultural areas are analysed on the basis of future scenarios | 31000 | 2021-03-01 | Moved to second-year.Could not be implemented due to Global Covid-19 situation
|  | Output 1.3.1 Guidance documents for stakeholders are developed to raise awareness about the future scenarios | 12000 | 2021-03-01
|  | Output 1.3.2 Capacity of stakeholders to use future scenarios and to develop action plans is enhanced | 170000 | 2021-07-01
|  | A 2.1.2.2-Buy, install and test the equipment needed to create and use the VoltAlarm EWS | 91000 | 2021-07-31 | Ongoing activity up to end of project.Development of the VOLTALRAM and integration of existing information is on-going.Check below website: https://volta.mydewetra.world/ Username: WMO-Volta, password WMO-Volta
|  | A 2.1.2.5-Run and maintain the VoltAlarm system | 120000 | 2021-07-01
|  | Output 2.1.1 Needs and existing resources of national and regional agencies staffs for web-based EWS are defined | 80000 | 2021-07-31 | Preparationand baseline information collection will be carried out is on-going. Planned completion by Dec-21
|  | A 2.1.2.1 Define the needs related to facilities (rooms for developers, operational shifts, crisis communication, air conditioning, etc.), equipment (hard and software, including real-time connections), technical capacities, human resources (for daily activities and with additional resources during crisis) | 21000 | 2021-06-01
|  | A2.1.2.3 Develop capacity of the operational team in charge of VoltAlarm at the national services and at VBA (hydro-meteorological forecasters, IT specialists, communication officers, on-call teams, etc.) in continuous monitoring of the Web-based EWS | 61000 | 2021-07-31
|  | A2.1.2.4 Write the operational manual including procedures and responsibilities | 17000 | 2021-07-01
|  | Output 2.1.6 The web-based Early Warning dissemination interface forVoltAlarm is designed and developed | 20000 | 2021-07-01 | Ongoing activity up to end of project.
|  | Output 2.2.3 Development and implementation of community-based flood and drought management | 234000 | 2021-07-30 | Planning and preparation will start before June-21 (contract for the activities will be signed and local stakeholders will implement the activities). Planned completion by June-22
|  | Output 2.3.1 Knowledge and capacity development FFG or using the IUCN -Nature-based solution and ecosystem-based approaches and standards (starting with activity 2.3.1.1.) | 122000 | 2020-07-31 | Ongoing activity up to July-20. Entinre output will be completed by Dec 22
|  | A 2.3.2.2 Organize and conduct workshops (at least one per country) on the Training Manual for mainstreaming gender in the E2EEWS-F and flood management with potential participants from NMHSs, local policy-makers, civil authorities, women and community based organizations etc. | 282000 | 2021-07-31 | Planning and preparation will start before June-21 and atleast one National workshop will be conducted before July-21 and others will be planned and carried out between July 21-Dec 21.
|  | Ouput 3.1.1 The transboundary governance plans, policies and guidelines about long term flood and drought management are evaluated | 64000 | 2021-06-01 | Ongoing activity up to end of project.
|  | A3.1.3.1 Draft a report with evidence-based experiences at local level | 22500 | 2021-06-01 | Ongoing activity up to end of project.
|  | Project Implementation and Execution costs (July 2020-June 2021) | 355000
|  | TOTAL Amount to be spent between July 2020-July 2021 | 1732500
|  | Total Funds unspent from the first year funds (which will be used in the second year) | 1073000
ACTUAL CO-FINANCING (If the MTR or TE have not been undertaken this reporting period, DO NOT report on actual co-financing.)
|  | How much of the total co-financing as committed in the Project Document has actually been realized? |  | 0
|  | Estimated cumulative actual co-financing as verified during Mid-term Review (MTR) or Terminal Evaluation (TE). |  | 0 | N/A. Information will be added after the Mid-term Review(MTR) or Terminal Evaluation(TE)
|  | Add any comments on actual co-financing in particular any issues related to the realization of in-kind, grant, credits, loans, equity, non-grant instruments and other types of co-financing. (word limit=200) |  | None
Note on F31: Ramesh TRIPATHI: WMO PM-167500 VBA+GWP-WA-95500 WMO Staff and partners travel-15000 Communication-7000 M&E-2000
Note on F37: Ramesh TRIPATHI: Implementing Arrangement-54250 LoA-56101
Note on F38: Ramesh TRIPATHI: Implementing Arrangement-41250 LoA-146394

## Risk Assesment
RISK ASSESMENT
IDENTIFIED RISKS
List all Risks identified in project preparation phase and what steps are being taken to mitigate them
Identified Risk | Current Status | Steps Taken to Mitigate Risk
Acceptance of the project activities Even though detailed needs assessments have been conducted since 2013, the support of the stakeholders to the proposed activities can differ in the six countries. This results in differential levels of acceptance and slows down of the inception phase of the project. | Low | During the preparation phase of the project, all relevant stakeholders (government, agencies, departments and communities) were/are clearly identified, so that they fully share the vision and goal of the project and are aware of their contribution to the project, hence fostering ownership over the process. - MoU will be signed with the participating stakeholders. - Roles and responsibilities of the implementing agencies and executing agencies will be defined in the initial stages of the project so that all the activities are completed in a coordinated way.
Technical/quality risks Component 1 and 2 of the project is too technical and not adapted to specific area or countries. This results in low commitment and interest from stakeholders | Low | The project activities will be first reviewed with the support of National Focal Points, local decision-makers and participants from community to understand the expectations and suggestions from the participants. The feedbacks and suggestions from the participants will be integrated.
The timeframe for the implementation of activities in each of the six project countries may delay overall project implementation and affect regional activities. | Low | Project focal points have been identified at regional (PMT) and national level to ensure the project moves at required pace and any key issues are raised and addressed as quickly as possible to enable implementation to proceed.
Physical risks Administrative barriers hinder sharing of hydro-meteo, social and topographic data. This will result in difficulties to implement activities and delivery of timely outcome | Low | The executing and implementing entities will ensure from the National Focal Points and National Implementation Structures that the required data and information are shared. Furthermore, VBA is mandated for regional exchange of information and can request the enforcement of the agreements.
Restructuring in the government work structure may cause possible shifts of responsible persons at local and national levels to a different location or agency. This can result in delays and loss of support. | Low | Alternative persons from the departments will be involved in most of the activities so that implementation of project activities will not be hampered at any time.
Human resources/capacity risks ▪ Lack of skills or human resources availability ▪ Adequacy between existing and required experience and skills This results in slowing down the project activities | Low | The project benefits from the deployment of professionals/staffs by the implementing and executing agencies (WMO/GWP WA/VBA) who are selected by a panel of experts. Their ToRs are developed based on the project needs and in collaboration with the hosting institutions. - National support is obtained at the level of the governmental agencies to ensure sufficient human resources
Gender neutral approach Techniques and technology developed are not accepted by all groups of the communities. This decreases the gender equality compliances | Low | The project includes gender sensitive approach in all the activities. Wherever required non-technological or traditional methods will be adopted to reach and get participation from every group of the communities.
Political risks Interference from the local/national political parties This will result in delaying the project activities | Medium | The project will adhere to the goals, laws, and policies of the respective project countries. Whenever and wherever required, permission of national consensus of the countries will be shown.
Uneven speed of implementation and expenditure rate among the three main partners may hamper overall project performance | Medium | Project structures have been formed at regional (Project Management Team (PMT)) and at national level (Project Techncial Advisory Commitee (PTAC)) to ensure the project activites are implemented at required pace and any key issues are raised and addressed as quickly as possible to enable implementation to proceed. Partners are meeting regularly to jointly plan and implement activities.
Irregularities with regards to processess and relationships between executing and implementing bodies | Low | Standard WMO procedures have been used for partner agreements, including the use of Implementing Agreements and Letters of Agreement, WMO reporting requirements are being used for all partners to ensure project status information is regularly updated.
Sub-national governments prioritize alternative implementation frameworks or other initiatives/projects. | Low | Project Team have conducted consultation missions to, and engaged local authorities in, all three countries at both national and sub-national level. All relevant stakeholders are aware of the project and are taking the project as a key initiative to build resilience and adaptive capacity in the project target locations.
Limited coordination with other ongoing adaptation and DRR projects and initiatives in the target countries. | Low | A review of ongoing or completed projects/ initiatives has already been conducted. Consultation and engagement with stakeholders to ensure alignment and additionality to other programmes. In Burkina Faso and Ghana for example, good synergies have been found with ongoing government and development partner projects and programmes such as the CREWS component of Burkina Faso, West AFrica components and at the regional, discussion with project partners of FDMT, REWARD are regularly carried out to ensure synergies and complementarities. During National or regional workshops, the other project partners will be invited for awareness and a common approach to programming will be encouraged with the National Stakeholders
Delay in the disbursement of Funds to implementation partners | Low | The use of standard WMO IAs, LoAs and SSA will be used to engage partners and ensure quick disbursement of funds.
Critical Risks Affecting Progress (Not identified at project design)
Identify Risks with a 50% or > likelihood of affecting progress of project
Identified Risk | Current Status | Steps Taken to Mitigate Risk
The outbreak of covid-19 pandemic (at national, regional and Global) or political crisis which can cause travel restrictions for the project partners and stakeholders | Major | As there was no travel possible to the Countries, the meetings are held virtually through BlueJeans or telephone and discussion documents are shared via emails.
Volta Basin's vulnerability to natural hazards, capacity and resource limitations could constrain sustainability of the project achievements. Even if the Project succeeds in developing resilience and capacities at National level through EWS and Risk maps, it may not be enough for preparedness to the climate change events. | Low | The Project Team is regularly informing the benefits of the project and how National investments could help in building resources and capacities at local, national and regional level.
Risk Measures: Were there any risk mitigation measures employed during the current reporting period? If so, were risks reduced? If not, why were these risks not reduced?
Add any comments relevant to risk mitigation (word limit = 500)
The Implementing Partner will be conducting regular risk monitoring and evaluation of the project activities, and the results will be tracked and reported in WMO’s internal monitoring system. In addition to this, a dedicated Monitoring and Evaluation (M&E) team will be formed, to ensure essential budget and resources are allocated to execute the M&E framework. Risk mitigation measures as indicated above were executed as and when needed, ensuring that the likelihood of occurrence of any risks remained the same or lower than at the time of project submission and did not affect project implementation. The implementation of first-year activity is severely impacted by the Covid-19 Pandemic situation and delays are caused to complete the agreed current activities as well as future upcoming activities (many activities are linked with each other). Contingency plan or approach was or will be defined and developed so as to ensure continuation in the implementation of the activities (vuirtual consultations with the Countries, Capacity development of local staffs or partners to execute the activities and remote assistance by Implementing Partner and External consultants) . The management of risks has been facilitated through close and open lines of communications with project stakeholders as well as regular interaction among project partners at the regional and national level.

## ESP Compliance
ENVIRONMENTAL AND SOCIAL POLICY COMPLIANCE
SECTION 1: IDENTIFIED ESP RISKS MANAGEMENT
Was the ESP risks identification complete at the time of funding approval? [1]
ESP principle [2] | Are environmental or social risks present as per table II.K (II.L for REG) of the proposal? [3] | During project/programme formulation, an impact assessment was carried out for the risks identified. Have impacts been identified that require management actions to prevent unacceptable impacts? (as per II.K/II.L) [4] | List the identified impacts for which safeguard measures are required (as per II.K/II.L) | List here the safeguard measures (i.e. avoidance, management or mitigation) identified for each impact that are supposed to be (or had to be) implemented during the reporting period. Please break down the safeguard measures by activity. [5] | List the monitoring indicator(s) for each impact identified. [6] | State the baseline condition for each monitoring indicator | Describe each safeguard measure that has been implemented during the reporting period [7] | Describe the residual impact for each impact identified - if any - using the monitoring indicator(s) [7] | Describe remedial action for residual impacts that will be taken. [7]
1 - Compliance with the law |  |  | Lack of compliance with local and national laws in project activities. | Measure to avoid: 1) The project design and implementation will be compliant with all relevant regional and national laws following extensive consultation with national and regional stakeholders. 2) Management: In case of a lack of compliance, the ESP risk management plan procedure will be executed. 3) No USPs or any project activities will be conducted if they do not comply with local, national and international laws. | - Minutes of the meetings/ reports of consultations with regional, national and local authorities will be monitored for compliance during designing and implementation phase - The adaptation action plans and investments will be reviewed to ensure adequate compliance with the laws | The project design was made to be compliant with all relevant regional and national laws following extensive consultation or requirements formulation with national and regional stakeholders. | During the project design and implementation phase, activities are screen for the ESP principles and will be made compliant with all relevant regional and national laws following extensive awareness and consultation with national and regional stakeholders. In case of any adherence to local and national laws for any USPs, measures will be designed through an expert and implemented during the course of the project. If required international laws on data sharing protocol among different countries will be consulted. During the design of the project activities both regional and national stakeholders will be consulted to update data sharing protocol/laws between the six countries. | None at the moment | None at the moment
2 - Access and equity |  |  | Lack of access to project resources and outputs of the activities implemented | Given that the project will provide support to shared natural resources, the project team will ensure that outputs or developments through activities do not negatively affect community rights to shared natural resources as well as ensuring equitable benefits from concrete adaptation investments and other project activities. Any activities involving shared resources will be conducted in the context of the relevant local or national laws and in joint consultation with the National and local stakeholders. | - Minutes of the meetings/ reports of consultations with regional, national and local authorities will be monitored for access and equity compliance during designing and implementation phase of the activities - The community-based action plans and investments will be reviewed to ensure equal access and quity to the community individuals. | Presently, the activity design is carrying out requirements and need analysis of the communities during which access and equity riks are or will be considered at a maximum level -Disparity are identified between mens and womens on the ownership of assets for building self-help resilience | - A sensitivity design of the project activities at the local and national level will be conducted by the project team ensurring access and equity principles being screened thoroughly. - The project team or experts will do a consultation with both men and women, considering different social and economic status, so as to ensure the project activity delivers resources in both equiy and accessibility - Further safeguard measures will be identified in subsequent years. | None at the moment | None at the moment
3 – Marginalized and vulnerable Groups |  |  | Exclusion of marginalised and vulnerable groups from project activities. | Avoidance, management or mitigation There is a risk that vulnerable and marginalized groups will have insufficient knowledge and access to technological devices such as mobile phones or lack of good cellular connectivity especially required for component 2.1 of the proposed activities. To avoid the exclusion of marginalized and vulnerable communities, local radio channels and traditional practices will be implemented to reach these groups especially women, girls, elderly, physically challenged individuals. Management- Ensure participation of all relevant stakeholders in project activities without social discrimination and with the aim of providing voice in decision making and gaining benefits including for women and elderly as well as marginalized groups. Avoidance: Ensure community consultation from the design and planning phase so the project activities target and support the most marginalized and vulnerable groups to become more resilient to climate change events including women, women-headed households, children and the youth. | Terms of Reference prepared for the consultations with communities and MoM with communities and local authorities | Knowledge and awareness on the gendered impacts of climate hazards and climate change is low. -Lack of tools and guidelines to integrate marginalized and vulnerable groups in the design, implementation and sustainabililty of the project activities | Concept note and ToR is developed after screening the AF ESP and Gender policy ensuring all the criteria are added in the selection of participants and beneficiaries. Experts with experiences of working with social integration and engagement are involved. | None at the moment | None at the moment
4 – Human rights |  |  | No further impact assessment is required. The proposed activities are or will not be against any of the established international human rights. Moreover, the proposed project will promote the basic human rights of access to water, food and information. The project will provide an opportunity for every individual to give their views, perceptions and needs in developing better climate change adaptation measures. | N/A | N/A | N/A | N/A | N/A | N/A
5 – Gender equality and women’s empowerment |  |  | Lack of gender equality and women’s empowerment in project implementation and outcomes. | Avoidance or Mitigation: The proposed project will improve the gender equity and women empowerment through the WMO developed tool: Training Manual for mainstreaming gender in End to End Early Warning system for Floods and integrated Flood Management through a participatory design approach. This will help in increasing the participation of women, girls and other vulnerable groups in Flood and Drought management activities as well as decision making processes. Avoidance: - sex disaggregated data and gender specific tools will be made available for consultations Management: Aim for 50% participation of women in project activities Management- Provision of forming Women Self Help Group to be part of decision-making processes (under local community-based flood and drought management activities planned part of output 2.2.3) | Percentage or number of women, men, elderly or youths involved in the project activities Concept note and technical report of the activities including capacity development workshops/trainings | - Lack of knowledge and awareness on the gendered impacts of climate hazards and climate change . -lack of tool and guidelines to support the community based planning pocesses and various trainings. - Womens presence in project activities and leadership positions varies from country to country and activity to activity. | - Development and testing of Training Manual for mainstreaming Gender in the end to end early warning system for floods and flood management. - All workshops and training have incorporated both men and women as participants with the need for gender parity and having women in key roles and decision making processes - Seperate discussion with women and men respectively to better understand the needs and capabilities for development resilience and adaptation measures -Sex-disaggregated data collection tool for community consultation -Involvement of the National and International Gender focal points in the designing and implementation of activities | None at the moment | None at the moment
6 – Core labour rights |  |  | No further impact assessment is required. The project will be implemented and managed in compliance with the countries designated labour laws. No individual will be hired without pay and the payment will be according to the countries labour legislation/laws. Children’s labour will be forbidden and it will not be accepted from other project partner agencies. Local communities will be involved in the adaptation measures but will not be exposed to any risk of accidents. Core labour rights will be respected and considered in project design and implementation. | N/A | N/A | N/A | N/A | N/A | N/A
7 – Indigenous peoples |  |  | There is a risk that the traditional use of water resources; irrigation system and land use pattern will be challenged. Therefore, a detailed analysis will be carried out by local and national agencies to understand the traditional use of natural resources especially regarding water access and land use. | Avoidance, management or mitigation The indigenous population in the region will be consulted and involved during the design and implementation of the project activities. The traditional knowledge of indigenous people on Flood and Drought will be useful when preparing the risk maps, the early warnings and information dissemination. | Minutes of meetings with the indigenous people -Voices from the field | - Lack of knowledge and awareness on the impacts of climate hazards and climate change on the indigenous people. -Involvement of indigenous communities in the project activities (may be due to the accessibility to the indigenous communities) | -Selection of indigenous communities to develop their resilience to climate change impact -Use of traditional practices and skills in the management of flood and drought events | N/A | N/A
8 – Involuntary resettlement |  | The involuntary resettlement principle was screened during the ESIA but no direct impact was identified due to activities but indirectly it could result in resettlementt of people from the flood and drought risk zones. | There are no activities proposed in the project which will create direct involuntary resettlement of communities. However, the risks of displacement of the population after the mapping of floods and drought risk areas could be possible as some areas could be classified as high risk for the loss of life. | Management: The National stakeholders will be informed of risk zones and impacted sectors (human-life, economy, environment, bio-diversity etc.) and joint consultation and discussion will be planned for managing risks and impacts. | National consultation reports, National action plan and guidelines for management of risks and impacts. | - Lack of knowledge and awareness on the risk zones and impacts of future climate hazards and climate change variability at all locations of the Volta Basin region. | On the basis of evidence-based and scientific information, the National agencies will be requested to move the people from high risk zones to safer zones ensuring proper human rights and laws are followed during resettlements. Also National agencies will be informed to propose a new prevention plan to prohibit future settlement in the high risk areas. | None at the moment | None at the moment
9 – Protection of natural habitats |  |  | There are no potential direct risks to the protection of ecosystems and its natural habitats and biological diversity through the project activities. There is a possibility of indirect risks through the revised policies and plans at national and transboundary scale decreasing the protection level of critical habitats. | Avoidance, management or mitigation: Capacity development activities with the National stakeholders will be carried out for example: Natural and nature-based solutions will be promoted using the IUCN standards for Nature-based solutions or Flood Green Guide by WWF( but they will not be implemented in the course of the Volta project as they would need detailed ecological assessment) | Technical reports, Consultation meeting notes, voices from the field | - Limited knowledge and awareness on the impacts to the habitat due to climate hazards and climate change | - Capacity development of stakeholders at every stage of the activities (designing, data collection, finding and analysis, reporting, decision making ). -Development of joint effective measures to mitigate or manage the risks (providing support of international and national experts to the National Agencies) The existing and new policies, plans and activities to protect natural habitats will be screened with the stakeholders to ensure that the critical habitats are legally protected through the convention on wetlands such as RAMSAR, Iran, 1971. and consultation with authoritative sources like IUCN, UNESCO as well as indigenous communities. Furthermore the activities under output 1.2.3 will consider native species characteristics and critical values for defining environmental thresholds. | None at the moment | None at the moment
10 – Conservation of biological diversity |  | The conversation of biological diversity principle was screened during ESIA but no direct risks or impact was identified due to project activities | There will be no direct risks associated with the conservation of biological diversity as the project activities will not involve any physical action on natural resources and introduce any known invasive species. The project activities (activities under output 1.1.1, 1.2.1, 1.2.2, 1.2.3, 2.1.3, 2.1.4) will provide opportunities to improve the understanding of natural processes in relationship with the water cycle. Nevertheless, the project activities could trigger changes in agricultural and irrigation practices and the use of pesticides. Also, the outcomes (flood and drought risks maps, EWS information) of the project might lead to encroachment on the protected areas, buffer zones and natural habitats. | Avoidance, management or mitigation: The project activities will ensure that the principles of the Convention on Biological Diversity (CBD) which has been signed by the six countries between 2011 and 2017 will be followed and supported. Furthermore, the National Biodiversity Strategy and Action Plan of the countries will provide valuable information and methodologies, opportunities to disseminate information as well as coordination at the national level and for the transboundary level. The project will promote planning for activities of biodiversity conservation, such as reforestation, nature-based solutions through an assessment at pilot sites with the concerned national agencies. The project will promote capacity building and peer learning to strengthen the efficient management of natural resources, including aquatic species, animals and forests. -Wherever required, the project will carry out consultation and capacity development activities with the local, national and regional stakeholders so that the protected areas, buffer zones and natural habitats are preserved from encroachment | Consultation meeting reports, voices from the fields | - Lack of knowledge and awareness on the impacts to the biological diversity due to climate hazards and climate change | - Capacity development of stakeholders at every stage of the activities (designing, data collection, finding and analysis, reporting and decision making). -Development of joint effective measures to mitigate or manage the risks (providing support of international and national experts to the National Agencies) | None at the moment | None at the moment
11 – Climate change |  | The climate change principle was screened during ESIA but no impact was identified | The proposed project activities will not result in any greenhouse gas emission to the atmosphere and deforestation, so there will not be any impact to climate change. Furthermore, the project does not only increase the flood and drought adaptation capacities and resilience of the local population but also contributes to develop better governance structure, policies and plans at both national and regional level for climate change adaptation. | N/A | N/A | N/A | N/A | N/A | N/A
12 – Pollution prevention and resource efficiency |  | The pollution prevention and resource efficiency principle was screened during the ESIA but no impact was identified | None of the project activities implementation are expected to result in any form of water, air and soil pollution. | N/A | N/A | N/A | N/A | N/A | N/A
13 – Public health |  | The public health principle was screened during the ESIA but no impact was identified | The project activities should not have negative effect on public health. On the contrary, it will contribute to prevent the population from natural disasters, to improve income for getting access to health facilities, etc. Nevertheless in case of disaster, the displacements of the populations can be sources of epidemics due to the lack of hygiene (not due to project activities) The project will identify the communities at risks (that are prone to inundation) and provide awareness of best practices for health related safety during various capacity building activities.The project will regularly promote, inform and sensitize the populations on diseases related to the presence of flood water (malaria, typhoid fever, Amoebiasis, Cholera etc.); | N/A | N/A | N/A | N/A | N/A | N/A
14 – Physical and cultural heritage |  | The physical and cultural heritage principle was screened during the ESIA but no impact was identified | The project does not have any activity related to affecting physical and cultural heritage. The purpose of the project is to develop better management of water resources and have traditional and cultural integration among the individuals. Participatory design and mapping approach under output 2.2.3–will involve local communities and authorities to identify areas of physical and cultural significance and ensure that community-based flood and drought management activities will not negatively impact them. | N/A | N/A | N/A | N/A | N/A | N/A
15 – Lands and soil conservation |  | The Lands and soil conversation principle was screened during the ESIA but no impact was identified | The project will promote the conservation of soil and land resources, especially through the selection of natural and nature-based solution with environmental-friendly solutions. Also, the project activities will contribute to improve agricultural practices and help to build the capacity of farmers and technicians. | N/A | N/A | N/A | N/A | N/A | N/A
SECTION 2: MONITORING FOR UNANTICIPATED IMPACTS / CORRECTIVE ACTIONS REQUIRED
Has monitoring for unanticipated ESP risks been carried out? |  | During project formulation, a detailed ESIA study was carried out. For any unanticipated ESP risks, the project is continously monitoring for any risks in the implementation so that it will be mitigated at the initial stage
Have unanticipated ESP risks been identified during the reporting period? |  | None till present date In the second and subsequent year, many activities are planned at both community and national level which might lead to any unanticipated ESP risks
If unanticipated ESP risks have been identified, describe the safeguard measures that have been taken in response and how an ESMP has been prepared/updated |  | N/A
SECTION 3: CATEGORISATION
Is the categorisation according to ESP standards still relevant?
If No, please describe the changes made at activity, output or outcome level, approved by the Board, that resulted in this change of categorization. |  | N/A
SECTION 4: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to implement the required ESP safeguard measures? |  | N/A - All the ESP risks will be discussed during the executing partners meeting, Project Techncial Advisory committee as well as consultations with National and local agencies. In case of any activities where a ESP risk is foreseen, a dedicated team will be formed to ensure adequate measures are developed to avoid or to manage it and later implemented with proper reporting.
Have the implementation arrangements been effective during the reporting period? |  | N/A- PPR-II will include if any risk is encountered
What arrangements have been put in place by each Executing Entity during the reporting period to implement the required ESP safeguard measures? |  | N/A- PPR-II will include if any risk is encountered
Have the implementation arrangements at the EEs been effective during the reporting period? |  | N/A- PPR-II will include if any risk is encountered
SECTION 5: PROJECTS/PROGRAMMES WITH UNIDENTIFIED SUB-PROJECTS (USPs). This section needs to be completed only if the project/proramme includes USPs. |  |  |  | N/A as the VFDM does not have any USPs
Have the arrangements for the process described in the ESMP for ESP compliance for USPs been put in place? [8]
Is the required capacity for ESMP implementation present and effective with the IE and the EE(s)? Have all roles and responsibilities adequately been assigned and positions filled? Please provide details. |  | N/A
Has the overall ESMP been updated with the findings of the USPs that have been identified in this reporting period? [9] |  | N/A
N/A for the first PPR report
List each USP that has been identified in the reporting period to the level where effective ESP compliance is possible. Add lines as necessary, one line for every USP identified. | Has the ESMP been applied to the USP that has been identified? | List all the ESP risks that have been identified for the USP | Has an impact assessment been carried out for each ESP risk that has been identified for the USP? | Has adequate consultation been held during risks and impacts identification for the USP? [10] | Have the data used to identify risks and impacts been disaggregated by gender as required? | List the environmental and social safeguard measures (avoidance, mitigation, management) that have been identified for the USP | List the monitoring indicator(s) for each impact identified
USP 1: [name the USP]
USP 2: [name the USP]
USP 3: [name the USP]
USP 4: [name the USP]
USP 5: [name the USP]
SECTION 6: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to environmental and social risks and impacts? |  | Grievance mechanism can be submitted through: https://www.floodmanagement.info/floodmanagement/volta-basin/contacts/
List all grievances received during the reporting period regarding environmental and social impacts; gender related matters; or any other matter of project/programme activities [11] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
None |  | N/A
No, the project/programme includes Unidentified Sub-Projects (USPs) (also complete Section 5)
Yes, all project/programme activities had been formulated to the level where effective risks identification is possible
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
Yes
No
No
Yes
No
Partially
Yes
No
Yes
No
Partially
Yes
No
Partially
Yes
No

## GP Compliance
GENDER POLICY COMPLIANCE
SECTION 1: QUALITY AT ENTRY [to be completed only at PPR1]
Was an initial gender assessment conducted during the preparation of the project/programme's first submission as a full proposal? |  | During the preparation phase, gender considerations were taken into account mainly highlighting the following aspects for ensuring integration of gender-sensitive and inclusive approach during project implementation and outcomes: 1) Baseline with sex-disaggregated data and gender-specific questions at National, sub-National, and local levels. 2) Use of participatory tools for gender-sensitive community consultation and M&E of the activities implemented. 3) Use of Training Manual developed by WMO for mainstreaming gender in End-to-End EWS for Flood forecasting and Integrated Flood Management and tool for Nature-based solutions 4) Aim for 50% participation of women in project activities and 50% of project direct beneficiaries to be women, while also targeting specific project activities building resilience of women or women groups to climate change events. 5) Foster equal participation of men and women in institutions and decision-making processes related to the project. 6)Ensure women are involved in maintaining long-term sustainability of the project outcomes.
Does the results framework include gender-responsive indictors broken down at the different levels (objective, outcome, output)? |  | Yes. The results framework includes baseline as well as targeted indicators at the objective, outcome, and output level which either refer to targets for women's participation or engagement as well as to identify gender-disaggregated data for capacity development and usage of tools and products delivered through project activities.
List the gender-responsive elements that were incorporated in the project/programme results framework
Gender-responsive element [1] | Level [2] | Indicator | Baseline | Target | Rated result for the reporting period (poor, satisfactory, good)
Capacity of stakeholders to use Floods and Drought risk maps is enhanced | Output | % of women participated | 0 | 50% | To be measured during year 2
Risk Management strategies in short, medium and long term to be integrated into development plans (economic, social, environmental aspects) | Outcome | % of women participated | 0 | 50% | To be measured at the end of year 2
Improved flood and drought forecasting instruments and Early Warning Systems (EWS) and coordination at the transboundary level to reduce disaster risks in vulnerable communities | Outcome | Number of women participated | 9 | 5000 | To be measured at the end of year 3
Pilot testing for a number of areas over the basin during the monsoon and dry seasons is performed | Output | % of women participated in coordination meeting and decision-making | 0 | 50% | To be measured at the end of project
Development and implementation of community-based flood and drought management | Output | % of women participated and benefitting from the local system and capacity development | 0 | 1000 | To be measured at the end of year 3
Knowledge and capacity development using the Flood Green Guide (FGG) or IUCN Nature-based standards | Output | % of women participated | 0 | 50% | To be measured at the end of year 3
Capacity development based on the Training Manual for mainstreaming gender in the E2E-EWS-F and flood management . | Output | % of women participated with dialog and advocacy Percentage of women with physical, social, political and economic empowerment | 0 | 50% | To be measured at the end of year 3
Awareness of policy-makers from the six countries on the key long-term strategies for floods and drought management and environmental impact is strengthened | Output | % of women participated | 0 | 50% | To be measured at the end of year 4
Experiences of local communities on key long term strategies for floods and drought management are collected | Output | number of women, elderly and youths consulted | 0 | 50% | To be measured at the end of year 4
A collaborative process is developed to ensure those instruments and strategies are accepted by the local organization and communities and adapted to the local context | Outcome | number of women, elderly and youths consulted | 0 | 50% | To be measured at the end of year 4
SECTION 2: QUALITY DURING IMPLEMENTATION AND AT EXIT [to be completed at final PPR]
List gender equality and women's empowerment issues encountered during implementation of the project/programme. For each gender equality and women's empowerment issue describe the progress that was made as well as the results. [3]
Gender equality and women's empowerment issues [4] |  | Rated result for the reporting period (poor, satisfactory, good)
N/A - to be completed and shared with final PPR |  | N/A - to be completed for final PPR as per guidance notes.
N/A - to be completed and shared with final PPR |  | N/A - to be completed for final PPR as per guidance notes.
SECTION 3: IMPLEMENTATION ARRANGEMENTS
What arrangements have been put in place by the Implementing Entity during the reporting period to comply with the GP |  | The Implementing Entity and Executing Entities, have all made efforts to comply with the principle of the AF Gender Policy, including gender equity, gender mainstreaming, gender responsiveness, gender sensitivity, gender-inclusive, and women's empowerment. In particular the following aspects have been put in place to ensure compliance with the AF gender policy: 1 - Ensuring that the local or household baseline incorporated sex disaggregated data and gender-specific questions. 2 - Encouraging project partners/ executing entities/consultants/national stakeholders to hold gender-sensitive consultations and assessments, for example conducting separate focus group discussions for men and women, therefore allowing women's views to be better captured without being overshadowed by men. 3 - Ensuring Local, National, Regional Workshops and Training (including VFDM Inception workshop) has the participation of both men and women. 4 - Ensuring that gender issues were discussed at Inception and during consultation and work planning meetings - for example, the question of how activities are designed so as to encourage full participation and engagement of women
Have the implementation arrangements at the IE been effective during the reporting period? |  | The implementation arrangements at the IE for Gender Policy compliance has been effective. The Gender Focal of the IE was/is involved in designing activities including also Monitoring and Evaluation. Discussions regarding gender issues or participation are held during project activities implementation and work planning meetings, ensuring: 1) all partners consider the needs (language, cultural, ensure equal participation of women and men) and constraints (given floor to women participants to present their views etc.) of women participation in project activities; 2) ensure Gender participation (checking availabilities from their schedule) in all activities; 3) aim for assigning activity leadership to women and 4) capture sex-disaggregated data for the baseline and other assessments and activities. This has laid the foundation for effective Gender Policy implementation in the project. -During the hiring of consultants or experts, a higher selection weightage is given to female applicants.
What arrangements have been put in place by each Executing Entity during the reporting period to comply with the GP? [5] |  | WMO: During Consultation and implementation of activities (workshops, development of products, and tools), a review is carried out through a Gender expert or with a Gender Lens while designing activities or requirement gatherings. The experts involved in the implementation of the activities are made aware of Gender policy consideration and ensure the involvement of women, youths as much as possible in their activities.
VBA: The VBA at the regional level ensures National gender focal points, where available are involved, in project planning meetings and on review of reports, concept notes, and documents to ensure the incorporation of gender aspects. - While organizing workshops and training both men and women are invited as participants. In Inception workshop, more than 40% percent of participants were female -During the hiring of consultants, a higher selection weightage is given to female applicants.
GWP-WA: - While organizing workshops and training as well as during implementation both men and women are invited as participants and engaged in tasks. -During the hiring of consultants, a higher selection weightage is given to female applicants.
Have the implementation arrangements at the EE(s) been effective during the reporting period? [5] |  | The implementation arrangements for Gender Policy compliance has been effective to some extent but not in all. Women's participation in project activities, as well as their engagement in leadership and training roles have been below expectations due to cultural barriers or lack of women at management or decision-makers level at the National services of the six countries. The effectiveness of the EEs efforts has also varied from country-to-country (For example: at Ghana, there are more consultations with women working in the field of Hydro-meteorological services as compared to Women) and activity to activity. The EEs will continue to emphasize or implement Gender-specific, sensitive or inclusive approach among stakeholders.
Have any capacity gaps affecting GP compliance been identified during the reporting period and if so, what remediation was implemented? |  | During the reporting period, no major capacity gaps affecting Gender Policy compliance have been identified at both IE or the EEs. In the project countries, it is always challenging to have expected participation of women in the project activities (identified in other completed projects due to social and cultural barriers). IE and EEs will continue to implement or comply with the GP of the Adaptation Fund during the implementation phase.
SECTION 4: GRIEVANCES
Was a grievance mechanism established capable and known to stakeholders to accept grievances and complaints related to gender equality and women's empowerment? [to be completed at PPR1] |  | Grievance mechanism can be submitted through: https://www.floodmanagement.info/floodmanagement/volta-basin/contacts/
List all grievances received through the grievance mechanism during the reporting period regarding gender-related matters of project/programme activities [6] |  | For each grievance, provide information on the grievance redress process used and the status/outcome
N/A-No Grievances related to Genders matters were received during the reporting period but suggestions related to gender participation and involvement are highlighted during meetings |  | N/A
Yes
No
Partially

## ESP and GP Guidance notes
ESP and GP Guidance Notes
ENVIRONMENTAL AND SOCIAL POLICY
Reference | Guidance
1 | The ESP requires that environmental and social risks are identified for all project/programme activities prior to funding approval. When not all the project/programme activities have been sufficiently formulated at that time so that adequate risks identification is possible, then the ESP risks identification is not complete.
2 | Complete this section for all the ESP risks that have been identified, not taking into account any USPs
3 | The project proposal includes an overview table of identified environmental and social risks (Section II.K of the proposal, Section II.L for regional projects). For each of the 15 principles of the ESP, please copy here the findings on the presence or absence of risks by ticking the corresponding box.
4 | Only complete for those ESP principles for which risks were identified
5 | The safeguard measures that must be implemented during a project/programme are normally described in detail in the ESMP of the project/programme
6 | See the monitoring plan in the ESMP
7 | For the first PPR report of the project/programme, this column needs to be completed with full information. For subsequent PPR reports, an update of the information previously provided is sufficient.
8 | The case being, please include details on the planned timing to have all the USP implementation arrangements in place.
9 | Please submit the updated ESMP together with the PPR
10 | Clarify also if the grievance mechanism has been made widely known to identified and potentially affected parties
11 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Conficential information may be redacted by the IE in the report.
GENDER POLICY
Reference | Guidance
1 | Add lines as appropriate, one line for each gender-responsive element
2 | Objective, outcome, output
3 | Risks related to gender equality and women's empowerment should be reported in the ESP compliance tab
4 | Add lines as appropriate, one line for each issue
5 | Add lines as appropriate, one line for each executing entity
6 | If any grievances were received that must not be made public, please inform the AF Secretariat of such grievances, detailing the reasons for them to remain confidential. Confidential information may be redacted by the IE in the report. This section will not be published on the AF webiste.

## Rating
RATING ON IMPLEMENTATION PROGRESS
For rating definitions and text of AF outcomes please see bottom of page.
Click above the columns captions in every table for guidance on reporting.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Implementing and Executing Entity: WMO | Outcome 1.1: Improved knowledge of risks, climate change impacts and risk management capacities through knowledge sharing and participatory mechanisms |  | Outcome 1 | The project team has identified premilinary existing information in relation to floods and drought risk maps in each of the six countries and integration of existing information through different projects on risk maps and national data and information collection is on-going |  | 1. The baseline information has been completed for all six countries and draft reports are available. 2. The missing information or new needed data survey sheet is shared with the countries 3. identification of Globally available datasets and integration in the web-based EWS is on-going | Satisfactory
| Outcome 1.2: Bridging the gap in adaptation measures to integrate future scenarios (economic, urban, climate, environment etc.) into current practices and knowledge |  | Outcome 6 | Building awareness of future risks and impacts on economic, urban, climate, environment etc. due to climate change and variability |  | 1. Global information related to climate projections are being collected 2. Discussion with the National stakeholders are on-going to share National data and information 3. Discussion with other completed, on-going project's are on-going | Will be reported in PPR 2
| Outcome 1.3: Risk management strategies in short, medium and longterm to be integrated into development plans (economic, social, environmental aspects) |  | Outcome 7 | Capacity development of relevant stakeholders for integrating risk management strategies into development plans with assigned roles and responsibilities |  | 1. Secondary literature review and discussion with the National stakeholders are carried out to identify existing information (plans, policies or guidelines) for managing risks related to floods and drought events. | Will be reported in PPR 2
| Outcome 2.1: Improved flood and drought forecasting instruments and Early Warning Systems (EWS) and coordination at the transboundary level to reduce disaster risks in vulnerable communities |  | Outcome 2 | At least 70 % of the population in Volta Basin region has Forecasting and EWS and it is been utilized. |  | 1. Development of the web-EWS is on-going 2.Integration of the existing information from other National and Regional projects | Will be reported in PPR 3
| Outcome 2.2 Demonstration of the added value of the E2E EWS VoltAlarm through a series of pilot testing during monsoon and dry seasons |  | Outcome 2 | Atleast one pilot locations of each Volta Basin countries have been tested with developed tool and models |  | Identification of the pilot sites in each of the project countries in joint consultation with the National agencies | Will be reported in PPR 3
| Outcome 2.3: Strengthened awareness of vulnerable people on hydro-meteorological risks, prevention, preparedness, and response strategies through education programs using participative solutions |  | Outcome 3 | More than 300 participants are trained on hydro-meteorological risks, prevention, preparedness, and response strategies. These participants disseminate knowledge and tools to other stakeholders. |  | Identification of the National Agencies staffs and local representatives for capacity building trainings and skills development activities | Will be reported in PPR 3
| Outcome 3.1: Decision support and policy development for strengthening resilience at the local, national and transboundary levels of the Volta Basin |  | Outcome 3 | Strengthened plans, policies and guidelines documents with necessary amendments. |  | Plans, policies and guidelines documents are reviewed | Will be reported in PPR 4
| Outcome 3.2: Strengthened capacities of actors and decision makers at national and transboundary level on long term risk management policies, plans and strategies |  | Outcome 7 | Locals/national/regional stakeholders integrate risk management policies, plans into national and transboundary development plans. |  | Identification of the National Agencies staffs and local representatives for capacity development and awareness activities | Will be reported in PPR 4
| Outcome 3.3: A collaborative process is developed to ensure those instruments and strategies are accepted by the local organization and communities and adapted to the local context |  | Outcome 7 | Risk management instruments and strategies is adapted and applied at the local level |  | Identification and consultation with the local communities representatives for capacity development and awareness activities | Will be reported in PPR 4
[6 empty] | Overall Rating | Marginally Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
| Name: | Ramesh Tripathi, VFDM Project Manager
| Email: | rtripathi@wmo.int
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
The project implementation is proceeding well. Due to the covid-19 outbreak situation, some of the activities from the first year have been postponed to the second year as the project team and external partners were not allowed to travel to the project countries as well as some of the National Agencies staff were working from home. It is expected that by the end of Year 2 major activities will be on schedule in line with milestones in the logframe, particularly for the development of the risk maps and climate scenarios under Component 1 and development of EWS (integration of Global datasets, project-specific information, etc.) along with capacity development planned under Component 2. The project management team (PMT) at the regional level is meeting regularly and virtual meetings with the countries were organized to present the on-going activities along with the planned activities. Coordination between the implementing entity and executing entities has been good with regular meetings and communication being held to ensure integration between project activities as well as with the different partners and levels (regional to local level). The inception workshop and joint partner consultation missions enhanced understanding of the role of national partners, including the national meteorological and hydrological services (NMHSs), civil protection, and the ministries responsible for water resources management in the respective countries. National stakeholders have welcomed and committed their support to what is considered an innovative and tailored project for the Volta Basin region. Completion of baseline data collection and National consultation reports (which will provide benchmarks to measure project impacts), community identification (60 from the entire Volta Basin region) for local risk mapping, Nationalized/Centralized Database development are on-going and have laid the foundation for implementation of the project. The project team sometimes goes through s challenging situation in terms of organizing activities in the six countries for example organization of National consultation meetings with the Project Team and External implementing partners taking into consideration availability of project team and national stakeholders, budget limitation, and other logistical issues. The formation of Project Technical Advisory Committee(PTAC) is completed and the PTAC Members will review yearly project progress, risks encountered and mitigation measures, provide suggestions and technical assistance on the implementation of activities in the subsequent years. Main next steps include: 1) Finalising consultation reports, local risk mapping, identification of ecosystem and environment indicators under Component 1; 2) development of risk maps and climate scenarios under component 1; and 3) development of the EWS incorporating information from the completed, on-going projects and National datasets. Major recommendations for future activities: 1)The project team will involve national focal points in the organizing and implementation of sub-activities or tasks where National agencies' staff support will be needed. 2) Ensure timely preparation of the concept note or ToR which will be shared in advance to the National Stakeholders 3) Regular consultation through face-to-face or virtual meetings with different National stakeholders for setting-up of the National Integrated databases.
| Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity-VBA | Outcome 1.1: Improved knowledge of risks, climate change impacts and risk management capacities through knowledge sharing and participatory mechanisms |  | Outcome 1 | VBA provided communication with national Focal Points, facilitated the negotiation of work agendas and provided technical support in collecting data on flood and drought risks in different countries |  | 1. At least, 20 official letters have been written and sent to the 6 VBA Line Ministries in support the mobilization of actors for the various meetings; 2. Provisional reports have been sent to the various Focal Points for amendment and additional missing information; 3. A country-by-country agenda was negotiated and obtained for the various meetings and activities. | Satisfactory
|  |  |  | Database of VCERs, floods and drought related risk maps are developed |  | 1. Support the concept note finalization for the conduct of the diffrent activities; 2. Identification and creation of IT/ and Database Expert list in support of the completion of the 1122 activity; 3. Support the concept note finalization for a virtual meeting on the implementation of the activity in the 6 countries | Satisfactory
| Outcome 1.2: Bridging the gap in adaptation measures to integrate future scenarios (economic, urban, climate, environment etc.) into current practices and knowledge |  | Outcome 6 | Impact on environmental indicators is evaluated for current and future scenarios |  | 1.Support the concept finalization of activities 1113, 1114, 1122, 1231-1237 in the 6 countries; 2. Support concept notes finalization for the holding of the various virtual meetings for the implementation of activities 1113, 1114, 1231-1237 in the 6 countries; 3. Organizing and holding a meeting to harmonize the understanding of the terms of reference for carrying out the activity 1231-1237; 4. Support for the development of the final version of the Concept Note for the Conduct of Activities 1231-1237 5. Preparing and sending a message to the National Focal Points to share the finalized conceptual notes of the activities and the virtual meeting with the 6 countries | Satisfactory
| Outcome 1.3: Risk management strategies in short, medium and longterm to be integrated into development plans (economic, social, environmental aspects) |  | Outcome 7 | Capacity development of relevant stakeholders for integrating risk management strategies into development plans with assigned roles and responsibilities |  | 1. Secondary literature review and discussion with the National stakeholders are carried out to identify existing information (plans, policies or guidelines) for managing risks related to floods and drought events. | Will be reported in PPR 2
| Outcome 2.1: Improved flood and drought forecasting instruments and Early Warning Systems (EWS) and coordination at the transboundary level to reduce disaster risks in vulnerable communities |  | Outcome 2 | At least 70 % of the population in Volta Basin region has Forecasting and EWS and it is been utilized. |  | 1. Development of the web-EWS is on-going 2.Integration of the existing information from other National and Regional projects | Will be reported in PPR 3
| Outcome 2.2 Demonstration of the added value of the E2E EWS VoltAlarm through a series of pilot testing during monsoon and dry seasons |  | Outcome 2 | Atleast one pilot locations of each Volta Basin countries have been tested with developed tool and models |  | Identification of the pilot sites in each of the project countries in joint consultation with the National agencies | Will be reported in PPR 3
| Outcome 2.3: Strengthened awareness of vulnerable people on hydro-meteorological risks, prevention, preparedness, and response strategies through education programs using participative solutions |  | Outcome 3 | More than 300 participants are trained on hydro-meteorological risks, prevention, preparedness, and response strategies. These participants disseminate knowledge and tools to other stakeholders. |  | Identification of the National Agencies staffs and local representatives for capacity building trainings and skills development activities | Will be reported in PPR 3
| Outcome 3.1: Decision support and policy development for strengthening resilience at the local, national and transboundary levels of the Volta Basin |  | Outcome 3 | Strengthened plans, policies and guidelines documents with necessary amendments. |  | Plans, policies and guidelines documents are reviewed | Will be reported in PPR 4
| Outcome 3.2: Strengthened capacities of actors and decision makers at national and transboundary level on long term risk management policies, plans and strategies |  | Outcome 7 | Locals/national/regional stakeholders integrate risk management policies, plans into national and transboundary development plans. |  | Identification of the National Agencies staffs and local representatives for capacity development and awareness activities | Will be reported in PPR 4
| Outcome 3.3: A collaborative process is developed to ensure those instruments and strategies are accepted by the local organization and communities and adapted to the local context |  | Outcome 7 | Risk management instruments and strategies is adapted and applied at the local level |  | Identification and consultation with the local communities representatives for capacity development and awareness activities | Will be reported in PPR 4
[6 empty] | Overall Rating | Marginally Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
|  | Name: | NIAMPA Boukari, Project Technical Officer at VBA
|  | Email: | niampaboukary@yahoo.fr; bniampa@abv.int
As a project implementation partner, the Volta Basin Authority (VBA) provided support in several areas as follows: - At the technical level, it contributed to technical and coordination meetings both in and outside of Burkina Faso. It took part in the meetings to amend and finalize the working papers (Work Plan, Budget and Terms of Reference). It participated in the preparation and holding of the Launch Workshop for the Project's activities in June 2019 in Abidjan and the second meeting of project implementation partners on harmonization, ownership, finalization of technical documents and the work plan and budget for the year 2019-2020 in February 2020 in Geneva. It has been actively involved in EWSs mission preparation meetings in 3 out of 6 countries (Burkina Faso, Côte d’Ivoire, and Mali) and produced mission reports. In addition, VBA has coordinated the preparation of the terms of reference for the elaboration of the project's operational documents (Communication, Monitoring and Evaluation and Knowledge Management); - in terms of mobilizing the partnership and the stakeholders for the implementation of the project, VBA facilitated the transmission of information, consultations and the mobilization of non-financial co-financing and synergy commitments in favor of the implementation of the VFDM project. It has constantly informed the 6 VBA Line Ministries on the implementation of the project's activities in each country and reported to the Council of Ministers of the Volta Basin. In addition, it has regularly linked the National Focal Points VBA, WMO, and GWP/WA in favor of synergistic support of the project's activities; - administratively, VBA provided institutional communication through over 20 official letters and at least 60 e-mail messages sent to the countries, including in relation to (i) the organization and conduct of EWS missions; (ii) interim study reports, (iii) the selection of national consultants and 60 sites for mapping vulnerability and capacity at the community level, (v) the organization of virtual meetings for the presentation of study reports, concept notes and questionnaires relating to the completion of activities 1113; 1 1.1.4; 1.1.2.2; 1.1.2.3; 1.2.3.1 to 1.2.3.7; This support facilitated the political and technical anchoring of the project which greatly supported it's visibility. To better achieve efficiency and effectiveness in the implementation of the project, it is necessary to: - have a Work Plan and Budget on time, with clear responsibilities indicated; - provide the Ntaional Actors necessary support to facilitate the carrying out of the activities; - hold regular meetings for updating and orientation between the three partners; - operationalize the Technical Advisory Committee as well as the operational documents; - send regularly and on-time the budgets for salaries, operations and activities.
Please justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Executive Entity -GWP-WA | Project components/outcomes |  | Alignment with AF outcome(s) | Expected Progress |  | Progress to Date | Rating
Executing Entity: GWP-WA | Outcome 1.1: Improved knowledge of risks, climate change impacts and risk management capacities through knowledge sharing and participatory mechanisms |  | Outcome 1 | The project team has identified premilinary existing information in relation to floods and drought risk maps in each of the six countries and integration of existing information through different projects on risk maps and national data and information collection is on-going |  | 1- Local, national and regional partners were identified and mobilized for the regional and the national missions 2- The Project Technical Assistant attended the missions to collect data with the consultants at the regional level, in Togo, in Burkina Faso and in Benin 3. The Project Technical Assistant prepared and provided reports on the missions at the regional level and in the three countries to the consultants 4. Comment and improvements were provided to the draft baseline information 5. Dissemination of the six baseline information reports in all six countries 6. Dissemination of the missing information or new needed data survey sheet with the countries 7. Comment and improvements provided to the draft concept note including the methodological approach and the data collection tools for the community vulnerabilities and capacities mapping in the volta basin 8. Designing and conducting the process leading to recruit six national local experts for the community vulnerabilities and capacities mapping in the volta basin | Satisfactory
| Outcome 1.2: Bridging the gap in adaptation measures to integrate future scenarios (economic, urban, climate, environment etc.) into current practices and knowledge |  | Outcome 6 | Building awareness of future risks and impacts on economic, urban, climate, environment etc. due to climate change and variability |  | 1. Dissemination of tools for collecting global information related to climate projections in the six countries of the Volta Basin 2. Planning and attendance to virtual meetings to share the draft reports on the available data and information and gathering comments and inputs from stakeholders of the six countries 3. Following up with each of the six volta basin riparian countries for the nomination of two junior assistant to support the collection of remaining data and information 4. Collecting and providing information on implemented and on going projects and programmes in the Volta Basin countries related to climate risk management 5. Comment and improvements provided to the draft concept note and the methodological approach for assessing impact on environmental and ecosystem services indicators in the Volta Basin | Will be reported in PPR 2
| Outcome 1.3: Risk management strategies in short, medium and longterm to be integrated into development plans (economic, social, environmental aspects) |  | Outcome 7 | Capacity development of relevant stakeholders for integrating risk management strategies into development plans with assigned roles and responsibilities |  | Faciliting the discussion with national stakeholders to identify existing information (plans, policies or guidelines) for managing risks related to floods and drought events | Will be reported in PPR 2
| Outcome 2.1: Improved flood and drought forecasting instruments and Early Warning Systems (EWS) and coordination at the transboundary level to reduce disaster risks in vulnerable communities |  | Outcome 2 | At least 70 % of the population in Volta Basin region has Forecasting and EWS and it is been utilized. |  | Facilitating the planning and attending the six national virtual meeting to present the Web-EWS to the national stakeholders and to obtain their acceptance for its development | Will be reported in PPR 3
| Outcome 2.2 Demonstration of the added value of the E2E EWS VoltAlarm through a series of pilot testing during monsoon and dry seasons |  | Outcome 2 | Atleast one pilot locations of each Volta Basin countries have been tested with developed tool and models |  | Contributing to the elaboration of the guidance note provided to the national agencies to identify pilot sites in each of the six countries of the Volta Basin | Will be reported in PPR 3
| Outcome 2.3: Strengthened awareness of vulnerable people on hydro-meteorological risks, prevention, preparedness, and response strategies through education programs using participative solutions |  | Outcome 3 | More than 300 participants are trained on hydro-meteorological risks, prevention, preparedness, and response strategies. These participants disseminate knowledge and tools to other stakeholders. |  | Facilating the identification of the national agencies staffs and local representatives for capacity building trainings and skills development activities | Will be reported in PPR 3
| Outcome 3.1: Decision support and policy development for strengthening resilience at the local, national and transboundary levels of the Volta Basin |  | Outcome 3 | Strengthened plans, policies and guidelines documents with necessary amendments. |  | Faciliting the discussion with national stakeholders to identify existing plans, policies or guidelines for managing risks related to floods and drought events in the volta bassin | Will be reported in PPR 4
| Outcome 3.2: Strengthened capacities of actors and decision makers at national and transboundary level on long term risk management policies, plans and strategies |  | Outcome 7 | Locals/national/regional stakeholders integrate risk management policies, plans into national and transboundary development plans. |  | Facilating the identification of the national agencies to identify staffs and local representatives for capacity development and awareness activities | Will be reported in PPR 4
| Outcome 3.3: A collaborative process is developed to ensure those instruments and strategies are accepted by the local organization and communities and adapted to the local context |  | Outcome 7 | Risk management instruments and strategies is adapted and applied at the local level |  | Facilitating the identification and consultation with the local communities representatives for capacity development and awareness activities | Will be reported in PPR 4
[6 empty] | Overall Ratings | Marginally Satisfactory
Please Provide the Name and Contact information of person(s) reponsible for completeling the Rating section
|  | Name: | Maxime TEBLEKOU
|  | Email: | maxime.teblekou@gwpao.org
lease justify your rating. Outline the positive and negative progress made by the project since it started. Provide specific recommendations for next steps. (word limit=500)
Basically, the project implementation is going well. At the start, different workshops and consultations were held to allow the three executing partners to agree on the roles and responsibilities in the implementation of activities. Virtual meetings were organized periodically to ensure the progress of activities at the level of each partner. These meetings also made it possible to find solutions to problems encountered by the partners in the implementation of activities. The concept notes of the activities are finalized by considering comments and improvements provided by different partners. The same applies to the methodological approaches and data collection tools proposed by the consultants for conducting activities. These various documents (concept notes and methodological guide) are shared with the focal points (WMO, VBA and GWP-WA) of the Volta Basin countries to enable them to take ownership of the activities as well as to provide their contributions. During this first year of implementation, GWP-WA contributed to the collection of baseline data and the preparation of national consultation reports on the assessment of national capacities and needs for flood and drought forecasting and warning systems (which will provide benchmarks for measuring project impacts), the recruitment of local experts, the identification of sixty site in the entire Volta Basin for local community risk mapping. Nationalized/Centralized Database development are on-going and have laid the foundation for implementation of the project. GWP-WA also contributed in the on-going development of the project monitoring-evaluation manual, the on-going development of the project communication plan, the communication around project activities, the formation of the Project Technical Advisory Committee (PTAC) and PTAC members will annually review project progress, risks encountered and mitigation measures, provide suggestions and technical assistance on the implementation of activities in subsequent years. Due to covid-19 outbreak situation, some of the activities from the first year have been postponed to the second year as the project team and external partners were not allowed to travel to the project countries as well as some of the National Agencies staff were working from home. It is expected that by the end of Year 2 major activities will be on schedule in line with milestones in the LogFrame, particularly for development of the risk maps and climate scenarios under Component 1 and development of EWS (integration of Global datasets, project specific information etc.) along with capacity development planned under Component 2 . In addition to the situation of Covid 19, there is also a delay in the implementation of some activities due to the availability of the external partners of the Project. The main next steps are: 1) finalization of consultation reports including holding the six national validation workshop, local risk mapping, identification of ecosystem and environmental indicators under Component 1; 2) development of risk maps and climate scenarios under Component 1; and 3) development of the EWS integrating information from completed and ongoing projects and national data sets. To do this end, the three executing partners will exchange with external partners to agree on how to mitigate the impact of the covid 19 on the project activities implementation going forward.
Please justify your rating and address the following points: 1. Indicate trends, both positive and negative, in achievement of outcomes as per the project indicators. 2. Detail critical risks that have affected progress. 3. Outline response to MTR undertaken this reporting period. 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words |  |  | 1. Indicate trends, both positive and negative, in the achievement of outcomes as per the project indicators. After the inception workshop (June 25, 2019), the project has moved into full implementation and the project is progressing as expected (except some activities which are delayed or postponed due to the global covid-19 situation) and the overall implementation experience has been positive. The project executing entities are working well under overall guidance or oversight of the Implementing Entity (WMO). Also, the project team is continuously involving the National stakeholders from the six countries including the ministries responsible for Meteorological, Hydrological, Agriculture, who committed to provide their support and staff engagement in the implementation of the activities and ensuring the deliverables are effective, tailored, open-source and sustainable. this Project continues with high visibility and relevance in the national context. The institutional arrangements for the Project Management Team (PMT) are in place and operational including the Project Technical Advisory Committee (PTAC). As part of the PMT, a Project Coordinator/Manager was hired on May 18, 2019, based at WMO Secretariat and later the other two support staff respectively with the other Executing Entities (VBA and GWP-WA) were hired. At the National, each country is requested to provide focal points that will provide necessary support or assistance in fulfilling the tasks or activities of the project. Once the National Focal Points (NFP) and National Implementation Partners (NIP) are identified, the implementation of activities will intensify at both the National and Regional levels. In the first phase, the project team spent considerable time and effort to meet and consult the relevant stakeholders identifying current needs, capabilities for developing an early warning system for floods and drought and to discuss synergies with other projects and avoid duplication of efforts. Several Terms of References (TORs) or Concept Note were prepared for the activities planned in the first year and shared with the National stakeholders for their review, feedback, and support in the implementation. Progress related to the development of risk maps and climate scenarios under Component 1 has been made and will help the National stakeholders build preparedness measures for climate change events as well as for economic development. Later with the development of the National/Centralized database in each of the project countries, the development of risk maps and climate scenarios could be scaled from the Basin level to the National level. The database (data from different agencies or from different on-going or completed projects) will be connected to the Early Warning System for floods and drought (planned for the second and third year of the project). Implementation is expected to be intensified in the coming years and looks promising in delivering on its planned targets. Local authorities have played an active role in the identification of the communities for capacity and adaptation activities and this will surely support engagement and sustainability of the actions in the target communities. The adaptation fund grant for the second year implementation will be a key through which these outcomes will be delivered. 2. Detail critical risks that have affected progress. A major pandemic (COVID-19) situation has severely affected project progress to date. As informed to the Adaptation Fund in early March 2020, National workshops and other planned activities were not conducted due to travel restrictions imposed on the project team and other partners. Several consultations were made with the countries to inform about the delay and even virtual meetings were held to progress in the implementation of activities. Informing the National stakeholders at an early stage was well appreciated by the project partners, and continued open communication on any challenges or issues were welcomed. 3. Outline response to MTR undertaken this reporting period. N/A 4. Outline action plan to address projects with a rating of HU, U or MU. Please keep your input to 1200 words N/A
| AF Outcomes |  |  |  | Rating Definitions
Outcome 1 | Reduced exposure to climate-related hazards and threats |  |  | Highly Satisfactory (HS) | Project actions/activities planned for current reporting period are progressing on track or exceeding expectations to acheive all major outcomes/outputs for given reporting period, without major shortcomings. The project can be presented as “good practice”.
Outcome 2 | Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses |  |  | Satisfactory (S) | Project actions/activities planned for current reporting period are progressing on track to achieve most of its major outcomes/outputs with only minor shortcomings.
Outcome 3 | Strengthened awareness and ownership of adaptation and climate risk reduction processes at local level |  |  | Marginally Satisfactory (MS) | Project actions/activities planned for current reporting period are progressing on track to achieve most major relevant outcomes/outputs, but with either significant shortcomings or modest overall relevance.
Outcome 4 | Increased adaptive capacity within relevant development sector services and infrastructure assets |  |  | Marginally Unsatisfactory (MU) | Project actions/activities planned for current reporting period are not progressing on track to achieve major outcomes/outputs with major shortcomings or is expected to achieve only some of its major outcomes/outputs.
Outcome 5 | Increased ecosystem resilience in response to climate change and variability-induced stress |  |  | Unsatisfactory (U) | Project actions/activities planned for current reporting period are not progressing on track to achieve most of its major outcomes/outputs.
Outcome 6 | Diversified and strengthened livelihods and sources of income for vulnerable people in targeted areas |  |  | Highly Unsatisfactory (U) | Project actions/activities planned for current reporting period are not on track and shows that it is failing to achieve, and is not expected to achieve, any of its outcomes/outputs.
Outcome 7 | Improved policies and regulations that promote and enforce resilience measures
Outcome 8 | Support the development and diffusion of innovative adaptation practices, tools and technologies

## Project Indicators
PROJECT Indicators
Please provide all indicators being tracked for the project as outlined in the project document
Type of Indicator (indicators towards Objectives, Outcomes, etc…)
Type of Indicator | Indicator | Baseline | Progress since inception | Target for Project End
Overall objectives The VFDM project will strengthen community resilience through integrated approach for flood and drought management and support to decision-making. | • Degree of improvement in populations’ resilience to floods and drought events • Quantitative details of the reduced number of the deaths and damage to assets and environment •Change in quality of climate related advisory to target population by the National services. | • Lack of investment for concrete measures developing resilience to climate change • Insufficient understanding of risks, shortage of hydro-meteo infrastructures and resources | • Assessment of current capabilities and needs related to the development of risk maps and EWS • Identification and discussion with other national and regional projects (completed and on-going ) for developing synergies and complementarities To be measured at the mid-term and end of project | • Development of the risks map and end-to-end web-based early warning systems for floods and drought events. • 70% of floods and drought events are foreseen and adequate preparedness measures are taken by the beneficiaries
| Percentage of targeted population with sustained climate-resilient alternative livelihoods. | 10% of the direct target population implementing traditional adaptation practices | To be measured at the mid-term and end of project | 60% of direct target population with climate resilience livelihoods Alternative, improved and sustainable livelihoods among 50% of target population.
| Percentage change in income (number, types and levels) among target population affected by climate change events | Approximately around 100$ across the project locations from secondary literature | To be measured at the endline | A 40% increase in number, types, and/or levels among 80% of direct beneficiaries.
Outcome 1.1 Improved knowledge of risks, climate change impacts and risk management capacities through knowledge sharing and participatory mechanisms | Development of Flood and Drought risks maps for the Volta Basin region | The existing products, reports and documents don’t have information on Floods and Drought risks mapping for the Volta Basin region and its consequences on human and natural resources. | • Assessment of current capabilities and needs related to the development of risk maps • Identification and discussion with other national and regional projects (completed and on-going ) for developing synergies and complementarities To be measured at the mid-term and end of project | Availability of Flood and Drought risks maps for risk-informed decision making
Output 1.1.1 Inventory of information on vulnerabilities, capacities, exposure and risks (VCERs) for floods and drought in the Volta Basin is conducted | Percentage of baseline information on vulnerabilities, capacities, exposure and risks will be made available for the | There is a lack of updated and integrated information on Floods and Drought related VCERs for the Volta Basin region | • Assessment of current capabilities and needs related to the development of risk maps • Identification and discussion with other national and regional projects (completed and on-going ) for developing synergies and complementarities To be measured at the mid-term and end of project | The VCERs database and flood and drought risk maps (risk zones) for the Volta Basin will be developed with the available data; Metadata of VCERs will be available
Output 1.1.2 Database of VCERs, floods and drought related risk maps are developed | Progress in terms of developing the database and risk maps (zones) on VCERs of Volta Basin (Percentage of basin surface area). The data from different countries will be made compatible with products and services highlighting the missing data and information of respective countries | No database and risk maps are available for Floods and Drought events at the Volta Basin region. The Volta Basin lacks updated classifications of the regions according to Flood and Drought risks. | • Assessment of current capabilities and needs related to the development of risk maps • Identification and discussion with other national and regional projects (completed and on-going ) for developing synergies and complementarities To be measured at the mid-term and end of project | The VCERs database and flood and drought risk maps (risk zones) for the Volta Basin will be developed with the available data; Metadata of VCERs will be available
Output 1.1.3 Capacity of stakeholders to use Floods and Drought risk maps is enhanced | No. of staff trained to develop skills for developing risk maps and mitigate the impact of climate –related events (by gender-number of women trained). Number of workshops are organized for the dissemination of knowledge on VCERs and Flood and Drought risk maps | The risks related to Floods and Drought are not well identified and are not taken into account by the different actors of Volta Basin Limited knowledge and skills with the National services to develop risk maps for floods and drought events | • Assessment of current capabilities, skills and needs related to the development of risk maps • Identification and discussion with other national and regional projects (completed and on-going ) for developing synergies and complementarities To be measured at the mid-term and end of project | Atleast one workshop per country will be organised to disseminate knowledge on VCERs database and Flood and Drought risk maps 1 transboundary level consultation workshop with National Focal Point (NFP)
Output 1.1.4 Reports and communication documents on VCERs and risk maps | Progress in the development of the VCER and Flood and Drought risk maps report, guidance documents for both national services and communities | Report on the VCER and Flood and Drought risk maps are not available for various actors managing climate change adaptation and disaster risk reduction activities | List of actors and stakeholders to whom the document will be shared To be measured at the mid-term and end of project | Report, guidelines and infographics materials on VCERs and Flood and Drought risk maps are developed
Outcome 1.2 Bridging the gap in Adaptation measures to integrate future scenarios (economic, urban, climate, environment etc.) into current practices and knowledge | Development of future scenario for the climate change variability and Floods and Drought events with VCERs database, Hydro-meteo information, climate projections etc. | There is no prediction about the role of future scenarios on socio-economic, urban, climate and environmental conditions | To be measured at mid-term | Future scenarios are developed for the climate change variability and Floods and Drought events
Output 1.2.1 Scenarios for socio-economic and environment development along with the climate change projections are collected | Progress in acquiring data and information on socio-economic, climate change projections for developing future scenarios | There is no availability of future scenarios for socio-economic and environmental development related to the climate change projections | To be measured at mid-term | Data and information on climate change projection and environment development is made available to the National stakeholders
Output 1.2.2 Projected impacts on water resources, urban development and bio-diversity and agricultural areas are analysed on the basis of future scenarios | Progress in terms of modeling, analysis of qualitative or modeled data output | Lack of methodology to understand the impact of Flood and Drought events on risks; | To be measured at mid-term | The future scenarios are developed and impact on various sectors are visualized and presented to the stakeholders
Output 1.2.3 Impact on environmental indicators is evaluated for current and future scenarios | Progress in terms of impact assessment, designing measures and identification of actors Progress in the development of guidelines for integrated basin-wide wetland guidelines to promote ecosystem services sustainability (aquatic/terrestrial transition zone (ATTZ)) Development of bankable project proposal and identification of financial institution or donors | Lack of strategy and action plans for managing environmental risks in the Volta Basin | To be measured at mid-term | A tool-kit is designed and developed for assessing environmental risks for current and future scenarios One bankable National project proposal is submitted to the financial institute
Outcome 1.3 Risk Management strategies in short, medium and long term to be integrated into development plans (economic, social, environmental aspects) | Participation and training of the relevant stakeholders (Number of women involved) on risk management strategies and action plan | A knowledge tool to integrated risk management strategies into development plans are unavailable for the policy-makers of the Volta Basin countries | To be measured at mid-term | Capacity development of relevant stakeholders and assigning roles and responsibilities
Output 1.3.1: Guidance documents for stakeholders are developed to raise awareness about the future scenarios | Guidance document on future scenarios for the Volta Basin region is been developed for the National portion of the Volta Basin or transboundary level | There are no reports or guidance documents available for future scenarios of climate change projections on socio-economic and environment in the Volta Basin region. | To be measured at mid-term or end of the project | Availability of Guidance document for risk-informed decision making on future scenarios due to the climate change projections.
Output 1.3.2: Capacity of stakeholders to use future scenarios and to develop action plans is enhanced | Number of workshops are organized for the dissemination of risk management strategies and action plan for their integration into development plans | National stakeholders lack knowledge and tools to mitigate or manage risks due to Floods and Drought events. | To be measured at mid-term or end of the project | Atleast one workshop per country will be organised 1 transboundary level consultation workshop with National Focal Point(NFP) An action plan is available with roles and responsibilities of the relevant actors
Outcome 2.1 Improved flood and drought forecasting instruments and Early Warning Systems (EWS) and coordination at the transboundary level to reduce disaster risks in vulnerable communities | Progress in the establishment of Forecasting and EWS for Floods and Drought Number of beneficiaries (male and female – data disaggregated by gender) and regions are identified for forecasting and EWS | Presently, there is a lack of integrated forecasting and early warning systems for both Floods and Drought Agencies and populations are unaware of the relevance and utility of the Forecasting and EWS and how to use it | To be measured at mid-term or end of the project | The Flood and Drought forecasting and EWS is operational At least 70 % of the Volta Basin region covered by Forecasting and EWS and there are used. More than 60% of the women have direct access to the EWS information
Output 2.1.1 Needs and existing resources of national and regional agencies staffs for web-based EWS are defined | Number of meetings and consultation workshops organised and conducted to understand capacities and needs of the NHS and other stakeholders | There is a lack of skills and knowledge on the forecasting and early warning systems among the local and national staffs | To be measured at mid-term or end of the project | Meeting and consultation workshop are organised at the national and transboundary level with identification of needs and capabilities
Output 2.1.2 The operational centre for the VoltAlarm Early Warning System is established | Progress in the identification of need and procurement of the resources (equipment’s, staffs etc.) List of sofware and hardware required with technical specifications Tentative list of vendors or suppliers | Presently, there is no real-time Early Warning System for Floods and Drought covering the entire Volta basin region | To be measured at mid-term or end of the project | The operational centre is established in consultation with NMHSs and Volta Basin Authority
Output 2.1.3 The historical and real-time hydrological data from the gauging stations are collected and the procedure to link with the meteorological data is defined | Percentage of data collection, storage and management at National and local level | Hydro-meteo data are not available timely and as well not managed | To be measured at mid-term or end of the project | Compatible data or meta-data are available from the respective countries for flood and drought forecasting and EWS
Output 2.1.4 Thresholds for Floods and Drought risk levels are selected for the various parts of the Volta Basin and linked with environment thresholds | Progress in the development of thresholds levels for Floods and Drought risks linked with the environmental thresholds | Thresholds levels for the Floods and Drought risks linked with the environmental thresholds are not available for the Volta Basin region | To be measured at mid-term or end of the project | Availability of the thresholds for Floods and Drought risks linked with the environmental thresholds in the Volta Basin region
Output 2.1.5 The procedure for producing impact based forecasts for the sub-basins and vulnerable areas on a daily basis is defined | Percentage of operationalization of Floods and Drought forecasting at the local and regional centers. | Adequate Floods and Drought Modelling and Forecasts are not available at the local and national levels in the Volta Basin region | To be measured at mid-term or end of the project | Modeling and Impact based forecasting of Floods and Drought are available at the local and national centres of the Volta Basin region.
Output 2.1.6 The web-based Early Warning dissemination interface for VoltAlarm is designed | Progress in the design and development of the early warning dissemination tool Percentage of the population (men, women, elderly, and youths) understanding the added-value of the early warning system | Currently there are no forecasting and early warning techniques available for the communities and agencies of the Volta Basin region, which can be interpreted easily | Development of the web-based platform with existing data and information (from Global level and other projects) are incorporated and visualized To be measured at the end of the project | The web-based Early Warning dissemination interface is co-designed and developed so that the early warning information will reach more than 70 % of the communities in the Volta Basin prone to floods and drought events
Output 2.1.7 Knowledge and awareness about VoltAlarm within the user groups are increased | Number of workshops/meetings are organised and conducted to develop capacities of the participants (by Gender) Percentage of the population understands the added-value of the early warning system | Lack of knowledge on forecasting and EWS for Floods and Drought | To be measured at the end of the project | Atleast 1 or 2 workshops/meetings per each country are conducted and participants (communities and agencies) have increased knowledge, awareness and skills.
Outcome 2.2 Demonstration of the added value of the E2E EWS VoltAlarm through a series of pilot testing during monsoon and dry seasons | Pilot-tests are organised to assess the impact of tools and models developed | Lack of medium and long-term adaptation measures with early warning system. | To be measured at the end of the project | Atleast one pilot locations of each countries have been tested with developed tool and models
Output 2.2.1 Pilot testing for a number of areas over the basin during the monsoon and dry seasons is performed | Progress in the pilot testing (identification and selection of pilot tests, monitoring during the floods and dry season etc.) of forecasting and EWS Participation of various actors and stakeholders working for Floods and Drought management | Agencies and Communities have limited knowledge about the forecasting and EWS for both Floods and Drought events | To be measured at end of the project | Pilot testing in atleast one location of each riparian countries More than 80% of the participants benefits from the pilot-testing to understand their roles and responsibilities beneficiaries
Output 2.2.2 Feedback from the series of pilot testing is collected | Workshops are organised and conducted to take feedback and develop capacities of the participants for future events Development of the communication material | Lack of coordination and collaboration between the actors and stakeholders. | To be measured at the end of the project | Atleast 1 workshop per each country is conducted with local and National stakeholders Success stories, best practices, lessons learned are shared through various social media channels so as to reach a broader audience.
Output 2.2.3 Development and implementation of community-based flood and drought management | Progress in the identification and implementation of the local systems Number of people contributing and benefiting from the local systems | Need for local flood and drought systems empowering the communities for enhanced hazard management | To be measured at the end of the project | Atleast one local community in each country has measures and is using the products, tools and methodologies for management of floods and drought events
Outcome 2.3 Strengthened awareness of vulnerable people on hydrometeorological risks, prevention, preparedness, and response strategies through education programs using participatory solutions | One workshop is organised with national focal points of countries involved in natural and nature based solutions and mainstreaming gender Number of women participate and involved in decision making | Lack of tools and awareness on mainstreaming gender and natural and nature-based solutions for flood management | To be measured at the end of the project | Workshops are organised and conducted to develop capacities of the participants for mainstreaming gender and nature-based solutions for the management of floods and/or drought
Output 2.3.1 Knowledge and capacity development using the Flood Green Guide (FGG) | Number of workshops organised and conducted to develop capacities of the participants Number and type of local and national staffs selected for the training Number of women trained | Lack of knowledge on natural and nature-based solutions for Floods | To be measured at the end of the project | Atleast 1 workshop per each country is organised and Nature based solutions are identifed for regions in the country affected by floods and drought
Output 2.3.2 Capacity development based on the Training Manual for mainstreaming gender in the E2E-EWS-F and flood management | Workshops are organised and conducted to develop capacities of the participants Percentage of women participating in the workshops with dialogue and advocacy Percentage of women with physical, social, political and economic empowerment | Lack of knowledge on mainstreaming gender in forecasting and early warning system for Floods | To be measured at end of the project | Atleast 1 workshop per each country is organised and mainstreaming Gender is practiced in management of floods events
Outcome 3.1 Decision support and policy development for strengthening resilience at the local, national and transboundary levels of the Volta Basin | Workshops and meetings are organised with list of participants from different agencies (by Gender) | Unavailability of decision support system and policies for developing resilience to Floods and Drought | To be measured at the end of the project | A decision support system framework and governance policies are established with the stakeholders
Output 3.1.1 The transboundary governance plans, policies and guidelines about long term flood and drought management are evaluated | Desk study and meetings are organised and available baseline data and information is shared as supporting details Number of policies, plans and guidelines to be revised | Lack of strategic framework and information at the transboundary level for the management of water resources , floods and drought event | To be measured at the end of the project | The transboundary level information for water resources management, floods and drought management is available The strategic framework at the transboundary level is available in consultation with the stakeholders
Output 3.1.2 Awareness of policy-makers from the six countries on the key long-term strategies for floods and drought management and environmental impact is strengthened | Number of workshops organised and conducted to develop capacities of the participants (decision-makers, policy-makers) Number of women participating in the workshops | Lack of knowledge and tools for the key stakeholders to manage flood and drought events at the transboundary level | To be measured at the end of the project | One workshop at the transboundary level is conducted. The present information gap and key long-term strategies are identified and disseminated
Output 3.1.3 Experiences of local communities on key long term strategies for floods and drought management are collected | Progress in the organising meetings or consultation workshops at local level Number of women, elderly, and youths consulted | Lack of involvement of key-stakeholders in the development of key long term strategies for floods and drought management | To be measured at the end of the project | More than 20 meetings or consultation takes place at various locations of the Volta Basin region. The discussion outcomes are drafted to improve the existing policies, plans etc.
Outcome 3.2 Strengthened capacities of actors and decision makers at national and transboundary level on long term risk management policies, plans and strategies | Workshops are organised and conducted to develop capacities of the participants Number of documents reviewed and discussed | Limited knowledge of transboundary policies, plans and guidelines for the key actors to manage risks | To be measured at the end of the project | The available policies, plans and guidelines are used and key long-term strategies are implemented
Output 3.2.1 Strengthened implementation of the revised, or new, climate adaptation plans (NAPA, NAP, NDC), policies and guidelines (on data and information exchanges) on issues related to risk reduction and Early Warning System (EWS) | Number of transboundary consultative workshop organised with the policy-makers and advisors Number of documents reviewed and discussed Number of women participants | Limited knowledge and implementation of action plans, policies and guidelines for the risk management | To be measured at the end of the project | One transboundary consultative workshop is conducted with participants from each country of Volta Basin Climate adaptation plans (NAPA, NAP, NDC), policies and guidelines (on data and information exchanges) on issues related to flood and drought risk reduction and the Early Warning System are revised or developed and shared with the stakeholders for their approval
Output 3.2.2 Improved integration of national policies on long term risk reduction and climate adaptation into the transboundary Strategic Action Programme (SAP) | Consultative meetings are organised so that new or existing plans, polices and guidelines on climate change adaptation and disaster risks management are integrated into the transboundary SAP. | There is lack of integration of national policies on long term risk reduction and climate adaptation into the transboundary Strategic Action Programme | To be measured at end of the project | Improved integration of national policies on risk reduction and climate adaptation into the Transboundary Strategic Action Programme (SAP) resulting in better management of water resources and flood and drought events at the national and transboundary level
Outcome 3.3 A collaborative process is developed to ensure those instruments and strategies are accepted by the local organization and communities and adapted to the local context | Collaboration meeting is organised with the stakeholders (including community representatives, associations and civil authorities) Number of men, women, elderly, and youths consulted | Lack of consultation and collaboration with the direct and in-direct beneficiaries on the instrument and strategies for climate change risk management | To be measured at the end of the project | Atleast 2-3 meetings in each of the Volta Basin countries are conducted and measures and plans are adapted to the local context
Outcome 3.3.1 Collaboration with local communities and organizations in defining the procedures and measures to manage risks and to adapt to climate change | Number of meetings organised with the communities and organizations (NGO's, associations etc.) Number of men, women, elderly, and youths consulted | Communities knowledge and experience are not involved in the development of the policies and action plans for managing risks and climate change adaptation | To be measured at the end of the project | Workshops/meetings are conducted and participants are provided with opportunities to share their views and perceptions on the policies and action plans Communities and organizations involvement in the designing and implementation of action plans is drafted
Output 3.3.2 Collaboration with local communities and organizations in finalising the policies, plans and further adopting to manage risks | Number of meetings organised with the communities and organizations Number of men, women, elderly, and youths consulted | Communities are not consulted and involved in the refining of the policies and action plans for managing risks and climate change adaptation | To be measured at the end of the project | Meeting for reviewing and finalizing is conducted and approval or necessary changes suggested by the participants are considered

## Lessons Learned
QUALITATIVE MEASURES and LESSONS LEARNED
Please complete the following section every reporting period
Implementation and Adaptive Management | Response
What implementation issues/lessons, either positive or negative, affected progress? | - Being a regional Adaptation Fund project, the modalities for inception at the regional and national level with several stakeholders required adequate planning and coordination. With six targeted countries, every country was interested to host the inception workshop, however, considering the cost available, accessibility with e-visa, or on-arrival visa, one of the countries was selected. This made other countries neglected but the implementing and executing partners assured other countries that upcoming regional workshops will be hosted in other 5 countries. - The project is executed by three partners namely WMO, VBA, and GWP-WA. Each of the entities has their respective National focal points and when sharing project information., it was challenging initially to reach out to all the respective focal points. However, coordination at both regional and national levels among project partners and stakeholders will be fully established soon (a committee of 3-4 individuals who will provide technical and coordination support). and it will be crucial for project success. - The project is mainly Nationally focussed and driven and involves consultation, engagement, and agreement with various national and sub-national stakeholders. These engagements sometimes take time and can result in delays, however, they are necessary to ensure sustainability, ownership, and ultimate success of the project. - One of the six countries is English speaking and others are francophone. So all the concept notes, ToR, and other reporting documents are developed in both English and the French language in order to ensure National stakeholders are provided documents in their respective language and their continuous support and participation are received. This sometimes causes a delay in the implementation of the activities. - The involvement of stakeholders from different National agencies requires proper coordination and support in terms of defining proper roles and responsibilities to each of them.
Were there any delays in implementation? If so, include any causes of delays. What measures have been taken to reduce delays? | There was a delay in project inception largely due to the following three factors: 1) Appointment of the project staffs at WMO, VBA, and GWP-WAs as the MoU and Implementing Arrangement between the three partners were not signed, there was a delay in transferring funds to hire project staffs 2) Development of detailed work plan and agreement with External implementing partners was done in the next three months of the inception workshop, which caused a delay in starting the implementation of the first project activities (already informed in the Inception workshop report) Due to the COVID-19 outbreak globally, many of the planned has to be postponed or moved to the second year of the project as there were travel restrictions to the project countries. Measures are taken to reduce delays: 1) ToR of staff and external partners were developed by Implementing Partners and shared with the executing partners and roaster of potential applicants or candidates were established. Once the funds were allocated, candidates were selected from the roaster. 2) A detailed work plan was simultaneously developed with the Inception workshop report in order to save time for contracting the external technical partners. 3) The Project Team continued working virtually at both regional levels as well as with National stakeholders. Virtual meetings were organized with the National stakeholders to present the National consultation reports and collect missing information from their side. The project team is currently following up with the National stakeholders.
Describe any changes undertaken to improve results on the ground or any changes made to project outputs (i.e. changes to project design)* | No changes have been made to project Outputs or activities at the moment. The development of flood and drought risks initially scheduled for Year 1, has been moved to Year two after informing and discussing with EEs and stakeholders, who agreed that the implementation would best be conducted in Year 2 once the capacity assessments, existing information, and methodologies are identified.
Have the environmental and social safeguard measures that were taken been effective in avoiding unwanted negative impacts? | For the activities undertaken to date, the environmental and social safeguards have been adequate and as yet no negative impacts have emerged. The major delays were caused by external factors (due to the Covid-19 situation) beyond the control of the project partners.
How have gender considerations been taken into consideration during the reporting period? What have been the lessons learned as a consequence of inclusion of such considerations on project performance or impacts? List lessons learned specific to gender, detailing measures and project/programme-specific indicators highlighting the role of women as key actors in climate change adaptation. | The project partners have undertaken the following measures in relation to gender considerations in the VFDM project: - Baseline assessment survey tools were reviewed by WMO gender experts and had the inclusion of sex-disaggregated data, questions on impacts of climate change, and climate hazards on different stakeholders (including Women, elderly, etc.), decision-making opportunities, etc. were considered. - Aiming for 50% participation of men and women in all the consultation meetings, training, and project activities at ground level (including as participants and trainers). - Aim for 40-50% participation and engagement of women in project activities and 50% of project direct beneficiaries to be women - Foster equal participation of men and women in institutions and decision-making processes related to the project. However, it is not always possible to ensure equal participation of men and women due to social and cultural barriers existing in the countries, however, efforts for such are being made. Some lessons emerging from the project relating to gender include the following: - Based on the initial consultation, women are participating in decision-making processes and in the development of resilience in some of the regions on the six countries affected greatly by climate change. - The knowledge of climate change variability and impacts was found to be lower among National services professionals (very few countries have female staffs in their Hydrological and Meteorological services) providing products and services for managing extreme events. This will be improved after conducting National workshops on mainstreaming gender in E2E-EWS-Floods. To keep track of issues and lessons learned over the course of the project, the M&E survey for the project will include questions disaggregated by gender as well as gender-specific questions on the impacts of project activities. - The number of staff trained to issue impact-based warnings, respond to and mitigate the impact of, climate-related events (by gender). -Percentage of women receiving timely early warnings for floods and drought events and the associated impacts - Percentage of local volunteers (male and female) who are integrating disaster risk reduction and adaptation strategies at the community level
*Inform promptly the secretariat of any changes in the budget or project results framework in accordance with the Project Implementation Policy https://www.adaptation-fund.org/wp-content/uploads/2017/11/OPG-ANNEX-7-Project-Programme-Implementation-Approved-Oct-2017.pdf
Please complete the following section at mid-term and project completion
Lessons for Adaptation | Response
Climate Resilience Measures
What have been the lessons learned, both positive and negative, in implementing climate adaptation measures that would be relevant to the design and implementation of future projects/programmes for enhanced resilience to climate change? | N/A - to be filled at mid-term and project completion.
What is the potential for the climate resilience measures undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A - to be filled at mid-term and project completion.
Readiness Interventions (Applicable only to NIEs that received one or more readiness grants)
What have been the lessons learned, both positive and negative, in accessing and implementing climate finance readiness support that would be relevant to the preparation, design and implementation of future concrete adaptation projects/programmes? | N/A - to be filled at mid-term and project completion.
How have the outputs (such as manuals, guidelines, procedures or the experience from providing peer support, etc) from employing readiness grants been used to inform institutional capacity needs, gender issues, and environmental and social aspects in developing and implementing concrete projects/programmes for enhanced resilience to climate change? | N/A - to be filled at mid-term and project completion.
Concrete Adaptation Interventions
What have been the lessons learned, both positive and negative, in implementing concrete adaptation interventions that would be relevant to the design and implementation of future projects/programmes implementing concrete adaptation interventions? | N/A - to be filled at mid-term and project completion.
What is the potential for the concrete adaptation interventions undertaken by the project/programme to be replicated and scaled up both within and outside the project area? | N/A - to be filled at mid-term and project completion.
Community/National Impact
What would you consider to be the most successful aspects for the target communities? | N/A - to be filled at mid-term and project completion.
What measures are/have been put in place to ensure sustainability of the project/program results? | N/A - to be filled at mid-term and project completion.
What measures are being/could have been put in place to improve project/program results? | N/A - to be filled at mid-term and project completion.
Knowledge Management
How has existing information/data/knowledge been used to inform project development and implementation? What kinds of information/data/knowledge were used? | N/A - to be filled at mid-term and project completion.
Has the existing information/data/knowledge been made available to relevant stakeholder? If so, what chanels of dissemination have been used? | N/A - to be filled at mid-term and project completion.
Please list any knowledge products generated and include hyperlinks whenever posssible (e.g. project videos, project stories, studies and technical reports, case studies, tranining manuals, handbooks, strategies and plans developed, etc.) | N/A - to be filled at mid-term and project completion.
If learning objectives have been established, have they been met? Please describe. | N/A - to be filled at mid-term and project completion.
Describe any difficulties there have been in accessing or retrieving existing information (data or knowledge) that is relevant to the project. Please provide suggestions for improving access to the relevant data. | N/A - to be filled at mid-term and project completion.
Has the identification of learning objectives contributed to the outcomes of the project? In what ways have they contributed? | N/A - to be filled at mid-term and project completion.
Innovation
Describe any innovative practices or technologies that figured prominently in this project. | N/A - to be filled at mid-term and project completion.
Complementarity/ Coherence with other climate finance sources
Has the project been scaled-up from any other climate finance? Or has the project build upon any other climate finance initiative?
If you answered yes above, kindly specify the name of the Fund/Organization. | N/A - to be filled at mid-term and project completion.
Yes
No
N/A - to be filled at mid-term and project completion.

## Results Tracker
Results Tracker for Adaptation Fund (AF) Projects
Goal: Assist developing-country Parties to the Kyoto Protocol and the Paris Agreement that are particularly vulnerable to the adverse effects of climate change in meeting the costs of concrete adaptation projects and programmes in order to implement climate-resilient measures. Impact: Increased resiliency at the community, national, and regional levels to climate variability and change.
Important: Please read the following guidance document (also posted on the Adaptation Fund website) before entering your data
https://www.adaptation-fund.org/wp-content/uploads/2019/10/Results-Tracker-Guidance-Document-Updated_July-2019.docx
Adaptation Fund Strategic Results Framework
Project ID
Implementing Entity | World Meteorological Organization(WMO)
Type of implementing entity | MIE
Country | Benin, Burkina Faso, Cote d'Ivoire, Ghana, Mali and Togo
Region | Africa
Sector | Disaster risk reduction
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Impact: Increased resiliency at the community, national, and regional levels to climate variability and change | Core Indicator: No. of beneficiaries |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project |  | Total (direct + indirect beneficiaries) | Direct beneficiaries supported by the project | Indirect beneficiaries supported by the project
|  | Total | 0 | 0 | 0 | Total | 100000 | 30000 | 70000 | Total |  |  |  | Total
|  | % of female beneficiaries | 0% | 0% | 0% | % of female beneficiaries | 50% | 50% | 50% | % of female beneficiaries |  |  |  | % of female beneficiaries
|  | % of Youth beneficiaries | 0% | 0% | 0% | % of Youth beneficiaries | 10% | 10% | 10% | % of Youth beneficiaries |  |  |  | % of Youth beneficiaries
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 1: Reduced exposure to climate-related hazards and threats | Indicator 1: Relevant threat and hazard information generated and disseminated to stakeholders on a timely basis | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness | Number of targeted stakeholders |  | Hazards information generated and disseminated | Overall effectiveness
|  | Total | 100000 | Inland flooding | 5: Very effective | Total | 100000 | Inland flooding | 5: Very effective | Total |  |  |  | Total
|  | % of female targeted | 50% |  |  | % of female targeted | 50% |  |  | % of female targeted |  |  |  | % of female targeted
Output 1.1 Risk and vulnerability assessments conducted and updated | Indicator 1.1: No. of projects/programmes that conduct and update risk and vulnerability assessments | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | 10 | Disaster risk reduction | Regional | 2: Undertaking or updating of assessments in progress | 10 | Disaster risk reduction | Regional | 3: Risk and vulnterability assessments completed or updated
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
|  | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status | No. of projects/programmes that conduct and update risk and vulnerability assessments | Sector | Scale | Status
Output 1.2 Targeted population groups covered by adequate risk reduction systems | Core Indicator 1.2: No. of Early Warning Systems | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 1: Risk knowledge | Geographical coverage | Regional | 1 | 1: Risk knowledge | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 1000 |  |  | Number of municipalities | 1000 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard | Inland flooding | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 2: Monitoring and warning service | Geographical coverage | Regional | 1 | 2: Monitoring and warning service | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 1000 |  |  | Number of municipalities | 1000 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 1: Risk knowledge | Geographical coverage | Regional | 1 | 1: Risk knowledge | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 1000 |  |  | Number of municipalities | 1000 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard | Drought | No. of adopted Early Warning Systems | Category targeted | Hazard |  | No. of adopted Early Warning Systems | Category targeted | Hazard
|  | 1 | 2: Monitoring and warning service | Geographical coverage | Regional | 1 | 2: Monitoring and warning service | Geographical coverage | Regional |  |  | Geographical coverage |  |  |  | Geographical coverage
|  |  |  | Number of municipalities | 1000 |  |  | Number of municipalities | 1000 |  |  | Number of municipalities |  |  |  | Number of municipalities
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 2: Strengthened institutional capacity to reduce risks associated with climate-induced socioeconomic and environmental losses | Indicator 2: Capacity of staff to respond to, and mitigate impacts of, climate-related events from targeted institutions increased | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level | Number of staff targeted |  | Sector | Capacity level
|  | Total | 100 | Disaster risk reduction | 3: Medium capacity | Total | 100 | Disaster risk reduction | 3: Medium capacity | Total |  |  |  | Total
|  | % of female targeted | 40% |  |  | % of female targeted | 0.4% |  |  | % of female targeted |  |  |  | % of female targeted
Output 2.1 Strengthened capacity of national and sub-national centres and networks to respond rapidly to extreme weather events | Indicator 2.1.1: No. of staff trained to respond to, and mitigate impacts of, climate-related events | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type |  | Total staff trained | % of female staff trained | Type
|  | 100 | 50% | Public |  | 100 | 40% | Public
| Indicator 2.1.2: No. of targeted institutions with increased capacity to minimize exposure to climate variability risks | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level | Type | Scale | Sector | Capacity level
|  | Public | National | Disaster risk reduction | 3: Medium capacity | Public | National | Disaster risk reduction | 3: Medium capacity
Output 2.2. Increased readiness and capacity of national and sub-national entities to directly access and program adaptation finance | Indicator 2.2.1: No. of targeted institutions benefitting from the direct access and enhanced direct access modality | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level | Number of beneficiaries | Scale | Sector | Capacity level
|  | 30 | National | DRR | 3: Medium capacity | 100 | National | DRR | 3: Medium capacity
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 3: Strengthened awareness and owernship of adaptation and climate risk reduction processes | Indicator 3.1: Increase in application of appropriate adaptation responses | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector |  | Percentage of targeted population applying adaptation measures |  | Sector
|  | 40% |  | Disaster risk reduction |  | 40 |  | Disaster risk reduction
Output 3: Targeted population groups participating in adaptation and risk reduction awareness activities | Indicator 3.1.1: Percentage of targeted population awareness of predicted adverse impacts of climate change, and of appropriate responses | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness |  | No. of targeted beneficiaries | % of female participants targeted | Level of awareness
|  | 50000 | 50% | 4: Mostly aware |  | 50000 | 50% | 4: Mostly aware
Output 3.2: Stengthened capacity of national and subnational stakeholders and entities to capture and disseminate knowledge and learning | Indicator 3.2.1: No. of technical committees/associations formed to ensure transfer of knowledge | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness |  | No. of technical committees/associations | % of women represented in committes/associations | Level of awareness
|  | 20 | 40% to 60% | 4: Mostly aware |  | 20 | 40% to 60% | 4: Mostly aware
| Indicator 3.2.2: No. of tools and guidelines developed (thematic, sectoral, institutional) and shared with relevant stakeholders | No. of tools and guidelines | Type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale |  | No. of tools and guidelines | type | Scale
|  | 20 | technical guidelines | National |  | 20 | Technical guidelines | National
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 4: Increased adaptive capacity within relevant development sector services and infrastructure assets | Indicator 4.1: Increased responsiveness of development sector services to evolving needs from changing and variable climate | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level |  | Project/programme sector | Geographical scale | Response level
|  | Disaster risk reduction | National | 4: Mostly responsive (Most defined elements) |  | Disaster risk reduction | National | 4: Mostly responsive (Most defined elements)
| Core Indicator 4.2: Assets produced, developed, improved or strengthened | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative) |  | Sector | Targeted asset | Changes in asset (quantitative or qualitative)
|  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved |  | Disaster risk reduction | 2: Physical asset (produced/improved/strenghtened) | 4: Mostly Improved
|  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved |  | Agriculture | 1: Health and Social Infrastructure (developed/improved) | 4: Mostly Improved
|  | Urban development | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved |  | Urban development | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved
|  | Water management | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved |  | Water management | 1: Health and Social Infrastructure (developed/improved) | 3: Moderately improved
|  | Food security | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved |  | Food security | 2: Physical asset (produced/improved/strenghtened) | 3: Moderately improved
Output 4: Vulnerable development sector services and infrastructure assets strengthened in response to climate change impacts, including variability | Indicator 4.1.1: No. and type of development sector services to respond to new conditions resulting from climate variability and change | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector | Number of services | Type |  | Sector
|  | 20 | National |  | Disaster risk reduction | 20 | National |  | Disaster risk reduction
|  | 10 | Departmental |  | Disaster risk reduction | 10 | Departmental |  | Disaster risk reduction
|  | 10 | Community |  | Disaster risk reduction | 10 | Community |  | Disaster risk reduction
|  | 10 | Community |  | Agriculture | 10 | Community |  | Agriculture
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Target performance at completion
Outcome 5: Increased ecosystem resilience in response to climate change and variability-induced stress | Indicator 5: Ecosystem services and natural resource assets maintained or improved under climate change and variability-induced stress | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type | Natural resource improvement level |  | Sector | Type
|  | 3: Moderately effective |  | Disaster risk reduction | biological assets | 3: Moderately effective |  | Disaster risk reduction | biological assets
Output 5: Vulnerable ecosystem services and natural resource assets strengthned in response to climate change impacts, including variability | Core Indicator 5.1: Natural Assets protected or rehabilitated | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Mangroves | 10 | km protected | 4: Effective | Mangroves | 10 | km protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Protected areas/National parks | 10 | km protected | 3: Moderately effective | Protected areas/National parks | 10 | km protected | 3: Moderately effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Forests | 10 | km protected | 4: Effective | Forests | 10 | km protected | 4: Effective
|  | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation | Natural asset or Ecosystem (type) | Total number of natural assets or ecosystems protected/rehabilitated | Unit | Effectiveness of protection/rehabilitation
|  | Cultivated land/Agricultural land | 10 | km protected | 2: Partially effective | Cultivated land/Agricultural land | 10 | km protected | 2: Partially effective
|  | Baseline information |  |  |  | Targeted performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 6: Diversified and strengthened livelihoods and sources of income for vulnerable people in targeted areas | Indicator 6.1: Increase in households and communities having more secure access to livelihood assets | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level |  | No. of targeted households | % of female headed households | Improvement level
|  | 10000 | 30% | 4: High improvement |  | 10000 | 30% | 4: High improvement
| Indicator 6.2: Increase in targeted population's sustained climate-resilient alternative livelihoods | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 10000 | 30% | From 10% to 20% | Agricultural-related | 10000 | 30% | From 40% to 50% | Agricultural-related
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 5000 | 40% | From 10% to 20% | Construction/repairing business | 5000 | 40% | From 40% to 50% | Construction/repairing business
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 10000 | 40% | From 10% to 20% | Services | 10000 | 40% | From 40% to 50% | Services
|  | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source | No. of targeted households | % of female headed households | % increase in income level vis-à-vis baseline | Alternate Source
|  | 10000 | 40% | From 10% to 20% | Cultivation | 10000 | 40% | From 40% to 50% | Cultivation
Output 6 Targeted individual and community livelihood strategies strengthened in relation to climate change impacts, including variability | Indicator 6.1.1: No. and type of adaptation assets created or strengthened in support of individual or community livelihood strategies | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy | Number of Assets | Type of Assets | Sector | Adaptation strategy
|  | 0 | Adaptation strategies | Disaster risk reduction | Supporting livelihoods | 0 | Adaptation strategies | Disaster risk reduction | Supporting livelihoods
| Core Indicator 6.1.2: Increased income, or avoided decrease in income | Number of households (total number in the project area) | Income source |  | Income level (USD) p.a | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 50000 | Agribusiness |  | 1000 | 50000 | Agribusiness |  | 1000
|  | Number of households (total number in the project area) | Income source |  | Income level (USD)p.a | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 20000 | Services |  | 1000 | 20000 | Services |  | 1000
|  | Number of households (total number in the project area) | Income source |  | Income level (USD)p.a | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 20000 | Fishing |  | 1000 | 20000 | Fishing |  | 1000
|  | Number of households (total number in the project area) | Income source |  | Income level (USD)p.a | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source |  | Income level (USD) | Number of households (total number in the project area) | Income source | Income source
|  | 20000 | Agriculture |  | 1000 | 20000 | Agriculture |  | 1000
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 7: Improved policies and regulations that promote and enforce resilience measures | Indicator 7: Climate change priorities are integrated into national development strategy | Integration level |  |  |  | Integration level |  |  |  | Integration level |  |  |  | Integration level
|  | 4: Most |  |  |  | 4: Most
Output 7:Improved integration of climate-resilience strategies into country development plans | Indicator 7.1: No. of policies introduced or adjusted to address climate change risks | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type | No. of Policies introduced or adjusted | Sector | Scale | Type
|  | 13 | Disaster risk reduction | National | Communication & Information policy | 13 | Disaster risk reduction | National | Communication & Information policy
| Indicator 7.2: No. of targeted development strategies with incorporated climate change priorities enforced | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness | No. of Development strategies | Regulation |  | Effectiveness
|  | 20 | 4: Enforced (Most elements implemented) |  | 4: Effective | 20 | 4: Enforced (Most elements implemented) |  | 4: Effective
Glacier lake outburst flood
|  | Inland flooding | fr | biological assets |  | Company policy | 5: Fully enforced (All elements implemented)
|  | Salinization | Decrease | land |  | Communication & Information policy | 4: Enforced (Most elements implemented)
|  | Drought | Same | water areas |  | Defense policy | 3: Partially enforced (Some elements implemented)
|  | Wind |  | subsoil assets | increased adpative capacity | Domestic policy | 2: Partially not enforced (Most elements not implemented) |  | Agribusiness
|  | Coastal flooding |  | air | achieved | Economic policy | 1: Not enforced (No elements implemented) |  | Agricultural-related | Financial capital
|  | Storm surge | Please choose |  | enhanced level of protection | Education policy |  |  | Agriculture | Human capital
|  | Hurricane | Selected | [5 empty] | Aquaculture | Physical capital
|  |  | Not relevant |  |  | 5: All (Fully integrated) |  |  | Construction/repairing business | Social capital
[6 empty] | 4: Most |  |  | Cultivation | Natural capital
[6 empty] | 3: Some |  |  | Fishing | Personal capital
Select | 5: All | Select |  |  | Community | 2: Most not integrated |  | Other | Forestry | Adaptation strategies
1 | 4: Almost all | Private | Type | Yes | Multi-community | 1: None |  | Agriculture | Handicrafts
2 | 3: Half | Public | Scale | No | Departmental |  |  | Coastal management | Livestock production
3 | 2: Some | NGO | Sector |  | National |  |  | Disaster risk reduction | Manufacturing
4 | 1: None |  |  |  |  | 5: Very high improvement | Established | Food security | other
|  | National |  |  |  | 4: High improvement | Maintained | Health | Services
|  | Regional |  |  |  | 3: Moderate improvement | Improved | Urban development | Tourism-related
|  | Local |  |  |  | 2: Limited improvement |  | Water management | Trading
[6 empty] | 1: No improvement |  | Multi-sector
|  | 1 -generated information is irrelevant, and neither the stakeholders reached nor the timeframe managed were achieved | 1: No info transferred on time | 4: High capacity | 5: Fully aware | 5: Highly responsive (All defined elements ) | 5: Fully improved | Roads | 5: Very effective
Asia-Pacific | NIE | 2 -the existence of some challenge in any of the three aspects of the indicator (generation of dissemination, stakeholders reached or timeframe managed) | 2: Somewhat info transferred | 3: Medium capacity | 4: Mostly aware | 4: Mostly responsive (Most defined elements) | 4: Mostly Improved | Gov Buildings | 4: Effective
Latin America and Caribbean | RIE | 3 -relevant information is generated and disseminated to all identified stakeholders on timely basis | 3: Info transferred on time | 2: Low capacity | 3: Partially aware | 3: Moderately responsive (Some defined elements) | 3: Moderately improved | Causeways | 3: Moderately effective
Africa | MIE |  |  | 1: No capacity | 2: Partially not aware | 2: Partially responsive (Lacks most elements) | 2: Somewhat improved | Airports | 2: Partially effective
Eastern Europe |  |  |  |  | 1: Aware of neither | 1: Non responsive (Lacks all elements ) | 1: Not improved | Schools | 1: Ineffective
| ha protected | [6 empty] | Training Centres
| ha rehabilitated | [5 empty] | Monitoring/Forecasting capacity | Hospitals
Afghanistan, Islamic Rep. of | km protected | [5 empty] | Policy/regulatory reform | Drinking water systems
Angola | km rehabilitated | 1: Risk knowledge | 1: No plans conducted or updated |  |  |  | Capacity development | Other
Albania |  | 2: Monitoring and warning service | 2: Undertaking or updating of assessments in progress |  |  | Communication & Information policy | Sustainable forest management
Argentina |  | 3: Dissemination and communication | 3: Risk and vulnterability assessments completed or updated |  |  | Domestic policy | Strengthening infrastructure | 1: Health and Social Infrastructure (developed/improved)
Armenia | Forests | 4: Response capability |  |  |  | Economic policy | Supporting livelihoods | 2: Physical asset (produced/improved/strenghtened)
Antigua and Barbuda | Mangroves |  |  |  |  | Education policy | Mangrove reforestation
Azerbaijan | Coasts |  | From 0 to 0.5% |  |  | Energy policy | Coastal drainage and infrastructure
Burundi | Rangelands |  | From 0.5 to 1% |  |  | Environmental policy | Irrigation system
Benin | Cultivated land/Agricultural land |  | From 1% to 5% |  |  | Foreign policy | Community-based adaptation
Burkina Faso | Catchment area/Watershed/Aquifer |  | From 5% to 10% |  |  | Health policy | Erosion control
Bangladesh | Protected areas/National parks |  | From 10% to 20% |  |  | Housing policy | Soil water conservation
Bulgaria | Other |  | From 20% to 30% |  |  | Human resource policies | Microfinance
Bahrain |  |  | From 30% to 40% |  |  | Information policy | Special Program for women
Bahamas, The |  |  | From 40% to 50% |  |  | Macroeconomic policy | Livelihoods
Bosnia and Herzegovina |  |  | Above 50% |  |  | Monetary policy | Water storage
Belarus | [5 empty] | Population policy | ICT and information dissemination
Belize | [5 empty] | Private policy
Bolivia | [5 empty] | Public policy
Brazil | [5 empty] | Science policy
Barbados | [5 empty] | Social policy
Bhutan |  | 3- relevant information is generated and disseminated to all identified stakeholders on timely basis |  |  |  | Transportation policy
Botswana |  | describe |  |  |  | Urban policy
Central African Republic |  | 2- the existence of some challenge in any of the three aspects of the indicator |  |  |  | Water policy
Chile |  | describe |  |  |  | Other policy
China, People's Republic of |  | 1- generated information is irrelevant and neither the stakeholders reached nor the timeframe managed were achieved
Cote d'Ivoire |  | describe
Cameroon
Congo, Dem. Rep. of
Congo, Republic of
Cook Islands
Colombia
Comoros
Cape Verde
Costa Rica
Cuba
Czech Republic
Djibouti
Dominica
Dominican Republic
Algeria
Ecuador
Egypt
Eritrea
Estonia
Ethiopia
Fiji
Micronesia, Fed. States of
Gabon
Georgia
Ghana
Guinea
Gambia, The
Guinea-Bissau
Equatorial Guinea
Grenada
Guatemala
Guyana
Honduras
Croatia
Haiti
Hungary
Indonesia
India
Iran, Islamic Republic of
Jamaica
Jordan
Kazakhstan
Kenya
Kyrgyz Republic
Cambodia
Kiribati
Saint Kitts and Nevis
Korea, Republic of
Lao People's Democratic Republic
Lebanon
Liberia
Libya
Saint Lucia
Sri Lanka
Lesotho
Lithuania
Latvia
Morocco
Moldova
Madagascar
Maldives
Mexico
Marshall Islands
Macedonia, former Yugoslav Republic of
Mali
Malta
Myanmar
Montenegro
Mongolia
Mozambique
Mauritania
Mauritius
Malawi
Malaysia
Namibia
Niger
Nigeria
Nicaragua
Niue
Nepal
Nauru
Oman
Pakistan
Panama
Peru
Philippines
Palau
Papua New Guinea
Poland
Korea, Dem. People's Rep. of
Paraguay
Romania
Russian Federation
Rwanda
Saudi Arabia
Sudan
Senegal
Solomon Islands
Sierra Leone
El Salvador
San Marino
Serbia
Sao Tome and Principe
Suriname
Slovak Republic
Slovenia
Swaziland
Seychelles
Syrian Arab Republic
Chad
Togo
Thailand
Tajikistan
Turkmenistan
Tonga
Trinidad and Tobago
Tunisia
Turkey
Tuvalu
Tanzania
Uganda
Ukraine
Uruguay
Uzbekistan
Saint Vincent and the Grenadines
Venezuela
Vietnam
Vanuatu
Samoa
Yemen, Republic of
South Africa
Zambia
Zimbabwe
Timor-Leste
|  | Baseline information |  |  |  | Target performance at completion |  |  |  | Performance at mid-term |  |  |  | Performance at completion
Outcome 8: Support the development and diffusion of innovative adaptation practices, tools and technologies | Indicator 8: Innovative adaptation practices are rolled out, scaled up, encouraged and/or accelerated at regional, national and/or subnational level | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovative practice | Geographic Scale | Type |  | Sector of innovatice practice | Geographic scale | Type
|  | Disaster risk reduction | National | Innovation accelerated |  | Disaster risk reduction | National | Innovation accelerated
Output 8: Viable innovations are rolled out, saled up, encourages and/or accelerated | Indicator 8.1: No. of innovative adaptation practices, tools and technologies accelerated, scaled-up and/or replicated | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness | No. of innovative practices/tools technologies | Sector | Status | Effectiveness
|  | 13 | Disaster risk reduction | Undertaking innovative practices | 4: Effective | 13 | Disaster risk reduction | Undertaking innovative practices | 4: Effective
| Indicator 8.2: No. of key findings on effective, efficient adaptation practices, products and technologies generated | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | Type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness | No. of key findings generated | type |  | Effectiveness
|  | 20 | Innovative product |  | 4: Effective | 20 | Innovative product |  | 4: Effective
Note on K21: Ramesh TRIPATHI: Some activiites like risk maps and EWS development can benefit several million population in directly
Note on E55: Ramesh TRIPATHI: No of female working Agencies is not equal to number of male
Note on E71: Ramesh TRIPATHI: training manual, tools, guidelines, policy and action plan documents will be prepared
Note on F71: Ramesh TRIPATHI:for all levels-regional, national and local