ANNEXURES TO THE FULL PROPOSAL TITLED:

“An integrated landscape approach to enhancing the climate resilience of small-scale farmers and pastoralists in Tajikistan”

## Table of contents

LIST OF ANNEXURES	3

Annex 1. Consolidated mission and stakeholder consultation report	4

Annex 2. List of endorsements and endorsement letters	20

Annex 3. Justification for selection of the Kofirnighan River Basin	22

Annex 4. Environmental and Social Management Framework (ESMF)	37

Annex 5. Grievance mechanism	63

Annex 6. Hydromet list of needs for the repair and rehabilitation of weather stations	64

Annex 7. UNDP Social and Environmental Screening Procedure (SESP)	67

Annex 8. Letter of Agreement between UNDP and Government for the provision of Support Services…..81

Annex 9: UNDP Fees for Support to Adaptation Fund Project…………………………………………………87

# LIST OF ANNEXURES TO THE FULL PROPOSAL

Annex 1. Consolidated mission and stakeholder consultation report

Annex 2. List of endorsements and endorsement letters

Annex 3. Justification for selection of the Kofirnighan River Basin

Annex 4. Environmental and Social Management Framework (ESMF)

Annex 5. Grievance mechanism

Annex 6. Hydromet list of needs for the repair and rehabilitation of weather stations

Annex 7. UNDP Social and Environmental Screening Procedure (SESP)

Annex 8. Letter of Agreement between UNDP and Government for the provision of Support Services

Annex 9: UNDP Fees for Support to Adaptation Fund Project

# ANNEXURES TO THE FULL PROPOSAL

## Annex 1. Consolidated stakeholder consultation and mission report

Courtney Hill & René Schieritz

June 2018

Stakeholder Consultation and Mission Report

Development of a Full Proposal to be submitted to Adaptation Fund by UNDP

‘An integrated landscape approach to enhancing the climate resilience of small-scale farmers and pastoralists in Tajikistan’

- Table of contents

List of acronyms and abbreviations	6

1.	Brief introduction to proposal	6

1.1.	Proposal description	6

2.	Information collection and project design	6

2.1.	Scoping mission	6

2.2.	Validation mission	7

2.2.1.	Site visits	8

2.2.2.	Validation Workshop	9

List of annexures	10

- List of acronyms and abbreviations

| ACTED | Agency for Technical Cooperation and Development |
| --- | --- |
| ADB | Asian Development Bank |
| AF | Adaptation Fund |
| AKDN | Aga Khan Development Foundation |
| CEP | Committee for Environmental Protection |
| CoES | Committee of Emergency Services and Civil Defence |
| CP | Concept Proposal |
| DoG | Department of Geology |
| DRMP | UNDP Disaster Risk Management Programme |
| EbA | Ecosystem-based Adaptation |
| EU | European Union |
| FAO | Food and Agriculture Organisation of the United Nations |
| FP | Full Proposal |
| GIZ | Deutsche Gesellschaft für Internationale Zusammenarbeit |
| Hydromet | National Agency on Hydrometeorology |
| MEDT | Ministry of Economic Development and Trade |
| MEWR | Ministry of Energy and Water Resources |
| PUU | Pasture User Union |
| RTA | Regional Techniacl Advisor |
| SDC | Swiss Agency for Development and Cooperation |
| UCA | University of Central Asia |
| UNDP | United Nations Development Programme |
| UNICEF | United Nations Children’s Fund |
| USAID | United States Agency for International Development |

Brief introduction to proposal

Proposal description

A project proposal was requested by the United Nations Development Programme (UNDP) with the objective to achieve rural community resilience in the most vulnerable regions of Tajikistan. Community vulnerability is increasing in the country in response to the shifting climate and an increasing number of extreme climate events. The original concept brief has been included as Annex 1.

Information collection and project design

Scoping mission

A Scoping Mission was undertaken from 1–7 March 2018 to support UNDP in developing a proposal for submission to the Adaptation Fund (AF). Following the mission, a Concept Proposal (CP) was developed and submitted for comment to the UNDP Country Office and the UNDP Regional Technical Advisor (RTA). The design of the project outlined in the CP focused on climate change adaptation through implementing Ecosystem-based Adaptation (EbA) in an integrated approach in specific catchments where vulnerable Tajik communities reside, titled ‘An integrated landscape approach to enhancing the climate resilience of small-scale farmers and pastoralists in Tajikistan’.

The primary objectives of the mission were to: i) identify baseline projects and existing gaps; ii) identify an overarching project objective based on the original concept; iii) gather suitable information to develop a CP. These objectives were addressed through conducting meetings with inter alia priority stakeholders in government, international agencies and academia. A list of the stakeholders consulted during the Inception Mission are detailed in Table 1.

Table 1. List of all stakeholders consulted during the Inception Mission to Dushanbe, Tajikistan.

| - Stakeholder | - Stakeholder type |
| --- | --- |
| - Aga Khan Development Foundation (AKDN) | - Regional development agency |
| - Agency of Statistics | - Government agency |
| - Asian Development Bank (ADB) | - International development agency |
| - ClimAdapt | - International organisation |
| - Committee of Environmental Protection (CEP) | - Government agency |
| - Deutsche Gesellschaft für Internationale Zusammenarbeit (GIZ) | - International development agency |
| - European Union (EU) | - International organisation |
| - Food and Agriculture Organisation of the United Nations (FAO) | - International development agency |
| - Forestry Agency | - Government agency |
| - KFW | - International development bank |
| - Ministry of Economic Development and Trade (MEDT) | - Government agency |
| - Ministry of Energy and Water Resources (MEWR) | - Government agency |
| - Ministry of Transport | - Government agency |
| - National Agency on Hydrometeorology (Hydromet) | - Government agency |
| - Swiss Agency for Development and Cooperation (SDC) | - International development agency |
| - UNDP Disaster Risk Management Programme (DRMP) | - UNDP programme |
| - United Nations Children’s Fund (UNICEF) | - International development agency |
| - United States Agency for International Development (USAID) | - International development agency |
| - University of Central Asia (UCA) | - Regional academic institution |
| - World Bank | - International development bank |

Validation mission

A Validation Mission was undertaken from 11–22 June 2018 to support UNDP in further developing a Full Proposal (FP) for submission to the AF. The mission followed feedback received on the CP and information gathered during the Inception Mission. Keti Chachibaia, the UNDP RTA, joined the first week of the mission from 11–14 June 2018 to partake in stakeholder engagement meetings.

The objectives of the mission were to: i) identify the river basin – and relevant catchment(s) for the project to be focused on; ii) identify districts and sites for activity implementation; iii) confirm baseline projects and co-financing; iv) collect information by visiting demonstration plots of integrated catchment management approaches; v) update the outcomes, outputs and activities designed from the CP stage; and vi) develop indicative financing/budget for proposed project activities – including AF grant funding, co-financing amounts from baseline projects and any additional local funding that may be available. Additional objectives of the mission were to:

- detail and refine proposed project activities (ensuring that they are not replicating activities implemented by other projects but rather complementing them);

- meet with a variety of stakeholders in government, civil society organisations (CSOs), academia and other institutions to check relevancy of proposed project activities and ensure that they are beneficial;

- align proposed activities with the ongoing goals of government as well as other projects and programmes;

- ensure that regional administration support is – and will be made – available to endorse the proposed activities;

- identify potential risks and barriers to the proposed project and ways to overcome them;

- identify stakeholders to partake in project activities;

- identify areas for project interventions; and

- collect relevant on-the-ground information for the design of the project.

A list of all stakeholders consulted during the Validation Mission are included in Table 2.

Table 2. List of stakeholders consulted during the Validation Mission to Dushanbe, during site visits to demonstration plots as well as during field trips to potential sites in the Kofirnighan River Basin.

| - Stakeholder | - Stakeholder type |
| --- | --- |
| - Agency for Technical Cooperation and Development (ACTED) | - International development agency |
| - AKDN | - Regional development agency |
| - Agency of Forestry | - Government agency |
| - CARITAS, Muminibad | - International development agency |
| - Committee of Emergency Services and Civil Defence (CoES) | - Government |
| - CEP | - Government agency |
| - Faizabad Region Chairman | - Government |
| - Kabodyon Region Chairman | - Government |
| - MEWR | - Government agency |
| - Nosiri Khisrav Region Chairman | - Government |
| - Open Centre, Department of Geology (DoG) | - Government |
| - Pasture User Union (PUU) Representative, Faizabad | - Community organisation |
| - UCA | - Academic institution |
| - Vahdat Region Chairman | - Government |
| - World Bank | - International development bank |

Site visits

Field trips were undertaken to showcase the results of demonstration plots that have successfully implemented integrated catchment management interventions. In addition, field visits were conducted to potential sites within:

- Faizabad area in the north of the Kofirnighan River Basin;

- Vahdat area in the north of the Kofirnighan River Basin;

- Kabodyon area in the south of the Kofirnighan River Basin;

- Shaartuz area in the south of the Kofirnighan River Basin; and

- Nosiri Khisrav area in the south of the Kofirnighan River Basin.

The sites visited had evidence of drought, flood and erosion damage as a result of a mixture of climate change-induced events and unsustainable catchment management practices. Consultations were held with district-level authorities both in the north and south of the Kofirnighan River Basin to discuss potential sites and adaptation measures that could be implemented through the proposed project. A list of the site visits conducted is included in Table 3.

Table 3. List of site visits conducted during the Validation Mission.

| - Date | - District | - Details of site(s) |
| --- | --- | --- |
| - Sunday 17 June 2018 | - Muminibad | - Not located within Kofirnighan River Basin. - SDC-implemented project in Muminibad to the east of Dushanbe, with CARITAS. - Project is currently in its third phase, having been implemented for eight years. - Sites included intercropping, establishment of bee hives, exclusion zones, rehabilitation of slopes, constructing gabions along rivers and the diversion of river pathways. - ‘Espacett’ (‘alpha alpha’) grown extremely well as fodder crops and is attractive to bees for apiary. |
| - Monday 18 June 2018 | - Faizabad | - North (upstream) within Kofirnighan River Basin. - To the north-east of Dushanbe to visit a WB, SDC and AKDN-implemented project. - Met with chairman who took us to sites along the river that require dams because of flood damage. |
| - Tuesday 19 June 2018 | - Kabodyon | - South (downstream) within Kofirnighan River Basin. - South of Dushanbe, between ~10–25 km north of the Afghanistan border, within the Kofirnighan River Basin. - Potential sites along the Kofirnighan River that were highlighted all require river bank reinforcement. - Demonstration site of the concrete tetrahedrons used to reinforce the river bank to enable trees be planted for stabilisation. - Met with chairman of the district, as well as representatives from Water Department – Representative from the water department took us to sites. |
| - Tuesday 19 June 2018 | - Shaartuz | - South (downstream) within Kofirnighan River Basin. - Saxaul trees/shrubs have been grown there for 11 years for dust capture. - Located close to the borders of Afghanistan and Uzbekistan – mountain ranges in both countries are visible from this plateau. Wind travels from across the borders across this plateau. - Considered the hottest area in Tajikistan. |
| - Wednesday 20 June 2018 | - Nosiri Khisrav | - South (downstream) within Kofirnighan River Basin. - ~1,000 cultivated land that cannot be used because of saline groundwater. - Pumps constructed in 1972 (Soviet era) to pump groundwater into the river. Five pumps constructed, only one is operational. If that one stops working, the entire pumphouse floods. - Tried planting rice in the region but there is not enough water for it, but there is too much water for other crops |
| - Thursday 21 June 2018 | - Vahdat | - North (upstream) within Kofirnighan River Basin. - Met with chairman and four other department representatives. - Visited a site where the bank is eroding into the river from a distance up the mountain and silting up the canal to the communities. |

Validation Workshop

On Friday 22 June 2018, a Validation Workshop was held in the Lotus Conference Room, UNDP DRMP Project Office, Dushanbe. The workshop was attended by 50 people, including representatives from international agencies, government ministries and local stakeholders, namely: i) CEP; ii) CoES; iii) HydroMet; iv) World Bank; and v) GIZ.  A full list of workshop attendees is attached as Annex 2. The purpose of the Validation Workshop was to:

- provide information to priority stakeholders on the proposed project, the current proposal development process and the work carried out on mission;

- obtain stakeholder contributions/inputs; and

- facilitate integration of stakeholder inputs into the final stage of development process.

During the workshop, group work was conducted whereby the participants were asked to identify areas within the Kofirnighan River Basin where climate resilience should be improved through the proposed project. Participants were expected to use their local knowledge of the region as well as their on-the-ground experience to list what activities would be beneficial in which regions. Full minutes of the workshop, group work and Q&A have been included as Annex 3.

The Validation Workshop was a successful event with positive feedback from all participants. Feedback on the concept and design was constructive with all participants willing to be a part of the process and activities going forward.

- List of appendices to the Consolidated Mission Report

The following annexures are attached as separate documents to this report:

Appendix 1. Original conceptual brief for project;

Appendix 2. List of Validation Workshop attendees; and

Appendix 3. Minutes of Validation Workshop.

- Appendix 1. Original conceptual brief for project

CONCEPT NOTE

Increasing Climate Resilience of Rural Communities in Tajikistan

Background

Tajikistan is a small landlocked country in the heart of Central Asia, bordered by Afghanistan, China, the Kyrgyz Republic, and Uzbekistan. Roughly one-tenth of its 7 million total population lives in Dushanbe, the capital city. The country has abundant water resources, contributing to its specialization in cotton production and a considerable hydropower generation potential. Only 7 percent of its total land area of 143,000 square kilometers is arable. High mountain ranges across its territory make communication between different parts of the country difficult, especially in winter. Tajikistan is highly susceptible to natural disasters, and is regularly affected by floods, landslides, and droughts. Up to 40 percent of the country’s national workforce is employed abroad (mostly in Russia) and sends home remittances equal to more than one-third of its gross domestic product. However, with global financial crisis and economic downfall in Russia associated with sanctions the remittance incomes are already adversely affected. Preliminary forecasts from IMF and the World Bank suggest that remittance income will fall by more than the 31% fall in remittance income. Lastly, low agricultural productivity and rudimentary safety nets still leave those below the poverty line vulnerable to shocks and stresses, including women who have experienced lowered rates of poverty reduction than men. The above factors combine to make Tajikistan one of the poorest and most vulnerable economies in the world.

The agricultural sector in Tajikistan accounts for 64% of employment, and is generally characterized by low productivity. Environmental degradation and unsustainable use of natural resources are important constraints, and the country’s predominantly mountainous terrain makes it particularly vulnerable to natural disasters. Mono-cropping and improper land use practices, such as wasteful irrigation methods and inadequate drainage, continue to contribute to soil degradation and stagnating yields, especially in lowland areas. Pasture degradation, due in part to overgrazing and poor stocking practices, is an important threat. In upland areas, the conversion of steep slopes to cereal production has contributed to land degradation. Chronic energy shortages have also resulted in increased burning of organic matter and vegetation that would otherwise be available as fertilizer or ground/tree cover.

Climate variability and change are likely to pose additional and significant risks, and only reinforce the need to follow sound land resource management principles. In the Europe and Central Asia region, Tajikistan is ranked the most vulnerable to the adverse impacts of climate change due to: a) dependence on natural resources, e.g., agriculture and hydropower; b) inadequacies of climate resilience of key economic sectors; and c) low adaptive capacity to respond to on-going and projected changes. Even under the most conservative scenarios, climate change is projected to lead to higher temperatures, more rapid glacier melt, increased incidence of flooding, and also more severe and prolonged droughts. These climate change-related shocks to agricultural systems can result in dramatic development challenges and poverty impacts. While the population is vulnerable as a whole, those pursuing subsistence agriculture and pastoralism will be particularly affected as they depend more directly on vulnerable land and water resources. Sustainable adaptation solution will require significant investments in land and water management at watershed / landscape level that is climate risk informed and addresses

Project Objective and Components

The overall project objective is to achieve rural community resilience in particularly vulnerable mountainous regions through the climate risk-informed landscape management.

Proposed activities include:

Outcome 1. Climate resilient food systems: field and horticultural crop productivity and diversification, livestock production efficiency, agro-processing and market access.

The work under this outcome will support to vulnerable farmers to promote climate resilient food systems. This will include climate resilient practices for land preparation and management; water management to secure water inputs to farms, research and multiplication systems of climate resistant crop and livestock breed varieties; integrated and diversified systems of farming to achieve greater resilience to intensified climate variability; post-harvest storage and bulking management strategies to minimize the post-harvest losses; and strengthening community groups and associations for local adaptation services (water management groups, community systems for management and maintenance of community infrastructure, marketing and processing strategies for local produce, and local funding mechanisms to support value chain for climate resilient food production).

Outcome 2. Catchment management practices to increase landscape stability and resilience: The work under this outcome will include, land and water management at catchment level, including pasture management, water retention and drainage control with pond systems created through landscaping methods at natural land depressions. Sustainable sloping lands cultivation (including orchards, woodlots, shelter-belts), including bio-engineering schemes, community forest management, and on-farm and off-farm agroforestry. Landscape level work will be informed and supported by hydrological models and impact scenarios across all key receptors (population, land assets, local infrastructure etc) to prioritize the areas of intervention and land treatment. Landscape planning methods will be introduced to underpin the suite of preferred nature-based solutions. Catchment / sub-catchment areas will be used as units of local land use planning and management.

Estimated project budget: US$ 8 mln.

- Appendix 2. List of Validation Workshop attendees

- Appendix 3. Minutes of Validation Workshop

# Consolidated Mission Report Annex 3: Minutes of Validation Workshop

Welcoming remarks from Nargiza

Introduction of participants

Welcoming remarks from Zarrina Nazarzoda, Deputy Chairman of CoEP

Importance of climate change adaptation measures in the development process of Tajikistan, where all national and international stakeholders should assist the country to address climate vulnerabilities and increase communities’ resilience.

Overview of the Presentations

Questions from Participants

Marhabo, GIZ

You have been talking about climate risk information to be used and which data will be used in the projects, climatic projections?

Criteria for the selection of the target communities?

C4: CRI will be used to develop multi-hazard mapping. We will be using available data and also increasing the density of Hydromet in information management in the selected districts.

Selection will be based on the vulnerability, EbA suitability to a selected area.

Nargiza: Firuz please explain the difference between catchment and basin.

Firuz: In TJ we have 5 basins. Kofirnighan basin is divided into 3 watersheds.

Jamshed Kamolov, CoES: Want to know about this project, will you consider climate change impact on flora and fauna? This year we had ES in Panj and during flood some specifies have been moved to inhabited areas, some of them have are currently at the Red book list.

C4: EbA is targeted to help people rather than species. However, some activities envisage that and we can do some conservation of eco and biodiversity. The focus will be on people and how they interact with eco-systems.

Zafar Mahmudov, CoEP: When you are expecting to launch the project of course considering approval procedure.

What about cooperation with other state and IOs or establishing a WG to address issues not related to CoEP. For instance, some issues might raise which other ministries or agencies can address.

C4: Implementation arrangements have not been finalized. Tentative launch of the project is envisaged in 2020. We can identify certain WG to assist in the project implementation and Working Steering Committee, which will regularly meet and discuss the progress, targets and guide national priorities alignment with our project.

Kairat, Climadapt Project: On-ground activities on EbA interventions?

Rene: Later during the group work we will provide a comprehensive explanation on types on interventions. Our main activities will be focused on reducing erosion and protection activities.

GIZ: How selected communities will handle the process and project management at the grassroots, it’s very essential to deliver a proper understanding of EbA.

C4: capacity building component will assist communities. We will be also utilizing best practices and knowledge management and sharing with national and international stakeholders.

CoES: In component one natural hazards are mainly considered, will be consider any protection measures for avalanches or other hazards?

C4: we will develop a multi-hazard approach, but some risks require hard interventions, whereas, the project will be working in EbA component and some reduction measures.

Nargiza: This project aims to address ICM and EbA, while other projects funded by the GoJ will be focused on hard interventions.

Wish from district representatives: Include demographic component and enlightment of people on these matters in the framework of the project.

Group Presentations

Group 1: all general questions apply to all regions, strategy on population density is not reflected and should be applied in the project implementation. How to implement these measures? What type of irrigation will be used?

Group 2: first we identified ecological and irrigation problems. It was proposed to apply IWRM, create WUAs, measures for pasture crop rotation. To improve WRM we should support existing WUAs and some infrastructure projects. Gender aspect also should be considered, introduce innovative technologies (drip irrigation).

Question: representatives of your group was from upstream and downstream?

Answer: Representative of Water Management Department noted that water from hills and floods should be managed. Storage of water can be introduced in Kabodien (upstream districts).

Firuz Saidov: now at all basins there are RBO financed by raion vodhozes. We need to differentiate activities of the project and these institutions in order to avoid repetition.

Region representative: create reservoirs for irrigation in south parts.

Khurshed Kholov, UNDP: indicate waste management component in the project

Group 3: assessed downstream of the basin and did a comprehensive analysis on soil, water usage and irrigation. Measures to be taken: reduce land degradation, change legislation in land ownership, air pollution, clean of drainage systems, create medium stations, improve pasture management, create field schools on agriculture knowledge, give local subsidies to farmers.

Firuz Saidov: downstream zones are prone to floods and erosion.

Group 4: Kofirnighan is divided into 4 watersheds. Water intensity in the lower part of Kofarnogan decline in summer time and risk of natural hazards increase every year.

Group 5: highlighted the most important activities for local communities of the basin, which are gabions, drip irrigation, pasture rotation, restore degraded land, sustainable crop management. In downstream all activities can be implemented except gabions, energy saving stoves.

Firuz Saidov: While applying a certain activity downstream we should consider its impact on upstream and vice versa. Panj river neighboring villages are affected by floods a lot.

Oxfam: also use negative experience of other organizations (for instance energy saving stoves). In south this approach was not useful from CCA approach.

Forestry specialist: more than 680 ha of forest are cut or land degraded due to improper pasture management. Therefore, we should focus on tree planting and agroforestry. We can share these methods with other districts.

Region representative: each region has own ecological system which needs restoration and different approach taking into account geographical peculiarities of each region.

Group 5: closely cooperate with local authorities, apply experience of other country and show economic/social impact and numbers. Local and transit pastures, in long term perspective we should apply it on local communities not district level. We should rely on the local interest in drafting a project. Upstream and downstream inhabitants should inherit a certain mindset on resource management in both catchments and its impact.

Closing remarks:

- Existing projects

- Field sites

- We will integrate today’s suggestions in the project

- Fully covered CC situation in the region

- Narrow down geographical interventions

Nargiza thanks participants for time, contribution as well as local consultants for the productive work!

- End of Consolidated Mission Report

## Annex 2. Endorsement letter

## Annex 3. Justification for selection of the Kofirnighan River Basin

SUPPLEMENTARY INFORMATION

TO PROJECT PROPOSAL:

JUSTIFICATION FOR PROJECT TARGET AREA SELECTION

“An integrated landscape approach to enhancing the climate resilience

of small-scale farmers and pastoralists in Tajikistan”

# River Basins in Tajikistan

## Overview

The terrain of Tajikistan has been eroded to form a diverse range of mountains and steep valleys. Tajikistan’s mountain ranges create several hydrographic areas, which in turn form numerous river basins. The country’s Water Sector Reform Programme for 2016–2025 (Water Reform Programme) delineates four river basins according to hydrological boundaries. These four basins are listed below with brief summaries for each.

- A section of the Syr Darya River that is located in Tajikistan. The Tajik part of Syr-Darya River Basin consists of the Syr-Darya River and its tributaries within Tajik borders. As a management unit, Syr-Darya includes the Zarafshan sub-river basin. Both are of inter-state importance, and the management of their water resources is part of the Interstate Commission for Water Coordination in Central Asia (ICWC).

- A section of the Pyanj River that is located in Tajikistan. The Tajik part of the Panj River Basin includes the area of the Panj River and its tributaries within Tajik borders. The boundaries of the basin to the North and West are the boundaries of the Vakhsh River basin, while the boundary to the South is the channel of the Panj River, which also forms the border with Afghanistan.

- Vakhsh River Basin. The Vakhsh River Basin includes the whole basin of the Vakhsh River and its tributaries, except for the extreme upstream part, which is located in Kyrgyzstan.

- Kofirnighan River Basin. The Kofirnighan River Basin (KRB) consists of the Kofirnighan River and its tributaries, namely Elok, Sarvo, Varzob. Further details on the KRB are provided below.

## Kofirnighan River Basin

Situated in the south-western and western parts of the country, the KRB occupies a total area of ~11,600 km2, with the mountain catchment making up 8,070 km2 of this – equating to ~70% of the total basin area. The basin is divided into two regions, namely the north and the central/south regions. The Gissar Valley encompasses the north region, which includes the city of Dushanbe, while the Kofirnighan and Beshkent valley depressions make up the south region. The Gissar Ridge forms the highland areas, extending for 250 km to elevations of ~4,500 masl and is home to 343 glaciers, covering a total area of 115 km2. The river of Kofirnighan, at ~387 km long, is one of the major contributing inflows of Tajikistan’s largest river, the Amu Darya River. It flows through different mountain ranges and zones within the basin including high mountains, intermediate foothills and low and flat zones. The basin’s groundwater reserves are economically important and are used to irrigate crops (~98,000 ha) and pastures (~56,000 ha). Most of the irrigated land is in the arid southern sub-basin, while cultivated land in the northern sub-basin is largely rain-fed.

### Surface- and ground-water in the Kofirnighan River Basin

The average annual flow of surface water in Kofirnighan is approximately 5.2 km3. Given that more than 90% of the river runoff floods each year, the prevalence of mudflows in the KRB is high. The greatest mudflow activity occurs at the headwaters of Kofirnighan, where destructive mudstone and water-stone flows are formed. Such activity is particularly problematic because the population living in this basin has already been facing extreme events associated with natural and anthropogenic climate change.

Operational reserves of groundwater in the KRB constitute 0.53 km3/year and are also subject to negative anthropogenic influences. Potential reserves of hydropower resources of the KRB are estimated to make 2.883 million kW, only 1.07% of which is currently being realised. In addition to energy generation, groundwater reserves are also being used for irrigation, whereby there are also approximately 56,000 ha of watered pastures. For example, the large Hissar channel irrigates approximately 38 thousand hectares of land. Further development of irrigation in the downstream of the basin will depend on the construction of the Lower (Nijny) Kofirnighan water reservoir.

### Population and its effects on water resources

In terms of political divisions, the KRB is made up of 10 administrative districts, 4 cities including Dushanbe, 10 villages and 77 jamoats (rural self-governance bodies) (Table 1). As of January 2017, the total KRB population was 2.8 million people, with ~62% living in rural areas and ~38% in towns. Over the past 13 years, the KRB population has increased by 712,000 people (representing a ~34% total increase and an annual growth rate of 2.5%). The KRB, unlike other basins in the country, is characterized by high population density (205 people per km2) and developed economic activities. Indeed, 32% of the Tajikistan’s total population resides in the KRB, which makes up only 11% of the country’s territory. Both this high population density and degree of economic activity has affected water resources in the basin. Due to rapid population growth and economic development, the volume of water withdrawal in the KRB is high, constituting 3.6 km3/year, 410 million m3 of which comes from groundwater. Water supply is also seasonal, whereby the inflows to Kofirnighan – from Varzob, Khanaka, and Ilyak – only run during flood seasons, resulting in downstream areas suffering from seasonal water shortages.

Table 1. Population data for cities and districts of Kofirnighan River Basin.

| # | Cities and districts | Population data as of 1.01.2017 in thousands |  |  | Population density for 1 km2 | Number of cities | Number of urban-type villages | Number of jamoats |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Total | % |  |  |  |  |  |
|  |  |  | Urban | Rural |  |  |  |  |
| 1 | Dushanbe city | 816,2 | 100 | 0 | 8162 | 1 | - | - |
| 2 | Varzob | 76,9 | 3,3 | 96,7 | 45,2 | - | 1 | 6 |
| 3 | Vahdat | 324 | 16,8 | 83,2 | 87,6 | 1 | 1 | 10 |
| 4 | Hissar | 287,4 | 14,4 | 85,6 | 287,4 | 1 | 1 | 11 |
| 5 | Fayzabad | 96,9 | 10,0 | 90,0 | 107,7 | - | 1 | 7 |
| 6 | Tursunzade | 280 | 18,9 | 81,1 | 233,3 | 1 | - | 9 |
| 7 | Shahrinav | 114,4 | 6,4 | 93,6 | 114,4 | - | 1 | 6 |
| 8 | Rudaki | 476,5 | 10,9 | 89,1 | 264,7 | - | 3 | 13 |
| 9 | Nosiri Khisrav | 35,9 | 0 | 35,9 | 44,9 | - | - | 3 |
| 10 | Qabodiyon | 173,8 | 6,6 | 93,4 | 96,6 | - | 1 | 7 |
| 11 | Shahrituz | 120,5 | 13,5 | 86,5 | 80,3 | - | 1 | 5 |
| Total |  | 2802,5 | 37,9 | 62,1 | 180,8 | 4 | 10 | 77 |

To improve water supply to areas in the basin, it is necessary to reconstruct several reservoirs in the KRB, particularly the Zidin, Lower (Nijny) Kofirnighan and Shirkent reservoirs. It will also be necessary to work on marking the boundaries of the KRB as a management unit.

# Selection criteria for project target areas

The selection of target areas is based on three main criteria:

- relevance of a chosen site to Integrated Water Resources Management (IWRM), River Basin Management (RBM) and the Water Sector Reform Programme under implementation by the Government of the Republic of Tajikistan;

- degree of climate-related vulnerabilities, including a population’s climate resilience and adaptive capacity at a chosen site; and

- distribution of donor development support at a chosen site.

Based on the criteria above, as well as discussions with national authorities and donor development partners, it is suggested that the target area for project interventions is the KRB. Indeed, preliminary analyses of relevant interventions in various regions of Tajikistan indicate that project objectives will be most effective in the KRB. A detailed justification for the site selection is provided in the sections that follow.

# Analysis

While vulnerabilities are significant in each river basin of Tajikistan, the KRB is particularly vulnerable, based primarily on the area’s: i) population number and density; ii) having received limited support for the implementation of IWRM; iii) markedly high exposure to mudflows. In addition, the KRB fulfils all the selection criteria for project target areas, as described below.

## Criterion 1: Integrated Water Resources Management (IWRM)

### Water Reform Programme and the river basin management approach

In 2016, the Government of Tajikistan endorsed the Water Sector Reform Programme, focussing primarily on transitioning to Integrated Water Resources Management (IWRM) and River Basin Management (RBM). The proposed water reforms are based on common regulatory principles of IWRM and focus on considering social, economic and environmental interests through the sustainable and balanced management water resources. Given the importance of water to the agriculture sector – that employs approximately two thirds of Tajikistan’s population – the water reform is inextricably linked to the agricultural reform that was approved in 2012.

Despite the many different definitions for IWRM, almost all of them employ the same principles. In the context of Tajikistan, the definition of IWRM is proposed as:

“Integrated Water Resources Management is based on the interaction of various sub-sectors with the objective of good accessibility to high quality water and sanitation services for the population, ensuring water availability for Irrigation, hydropower, environment and other users within river basins defined by hydrographic boundaries. IWRM promotes protection of water resources from over-exploitation and pollution, provides protection of vulnerable mountain environments and of river banks and floodplains from flooding and erosion, and facilitates public participation in decision-making, planning, financing and development of water resources in the interests of economic growth, sustainable development of the society and preservation of the environment.”

Proper water resource planning is only possible within the natural flow area of the water resources, because all actions upstream have an immediate effect on the downstream water availability and quality. Therefore, the river basin is the best management area for water resource management. A basin can be defined as an area that is drained by one river outlet and bordered by the water source upstream and the outflow body (sea or lake) downstream. In this regard, the introduction of the basin management approach to water resources management, which is an integral part of IWRM, is considered an important principle of the water sector reform.

In addition to promoting IWRM and river basin management, the water sector reform foresees the establishment of National Water Council (NWC), which will be the highest authority in the development of policy in the water sector. In line with the principles and objectives of the reform, the NWC will have the following tasks and objectives:

- adoption and development of public policy and legislation in the field of IWRM and effective use and protection of water resources;

- request to develop policy on management of water resources and protection of the environment;

- development of policy for control of the rational use of water resources;

- recommendation of limitation of water use;

- elaboration of an investment policy for the development, use and protection of water resources;

- drafting and management of international agreements in the use and protection of water resources; and

- development of policies to cope with the impacts from climate change in the use and protection of water resources.

### IWRM and climate change

Climate variability and change have significant impacts on the water resources of Tajikistan. According to the available data, during the last decades average temperature in Tajikistan increased by 0.7–1.9oC and ~1,000 small glaciers have melted. Over the short term, glacial melt has resulted in hydroclimatic disasters such as floods, droughts, landslides and mudslides (Figure 1). Considering that the main source of water of the Tajikistan’s rivers are glaciers, glacial melt over the medium and long terms reduce water flow in the country’s rivers.

To address the above climate change threats, the IWRM has made provisions for assisting communities to cope with climate variability. This role is characterised by three focal points, namely: i) water resources management at adequate level; ii) the organization of participatory management practices; and iii) policy development. Each of the above-described focal points carefully considers the country’s various vulnerable groups. Hence, IWRM aims to address climate change within Tajikistan’s water governance in the context of reducing vulnerability of poor people, specifically by maintaining livelihoods and supporting sustainable development.

Critical management functions of IWRM that may assist communities adapt to changing climate in the context of Tajikistan consider the following water allocation, pollution control, monitoring, financial management, flood and drought management, information management, river basin planning and stakeholder participation. Such functions of IWRM are instrumental in coping with climate variability in the following ways:

- monitoring water quantity and quality allows management to proactively take action towards adaptation;

- management of floods and droughts allows for direct intervention in cases of extreme events; and

- river basin planning, risk assessment and adaptation measures can ensure rapid response and build climate resilience.

Figure 1. Schematic presentation of the linkages of IWRM to water related disasters.

Of the four river basins identified by Tajikistan’s Water Reform Programme, the Kofirnighan River Basin (KRB) is one that currently does not have focused efforts being made towards IWRM. Compared to the other three basins, KRB has received the fewest interventions from government and donors to date. The KRB is topographically and climatically very variable and is highly vulnerable to extreme climate events such as GLOFs, floods, mudflows and landslides,. It is also the smallest of the country’s four basins and is fully encompassed within Tajikistan – i.e. is not transboundary. A Kofirnighan River Basin Management Plan (KRBMP) has been developed for the basin. Although this plan includes water management, it does not integrate land and natural resources into that management.

It is the view of all national ministries and agencies (MoEWR, CEP, ALRI) involved in water resources management that the KRB is the most suitable basin for the project. The MoEWR, CEP and ALDI have also agreed that the project is relevant to Tajikistan’s water sector reform and would contribute to implementing of IWRM in the country, as well as linking it to building climate resilience.

## Criterion 2: Climate vulnerability

The KRB has been identified as a region within Tajikistan that is particularly vulnerable to the impacts of extreme climate events, with almost 200 communities living in the basin experiencing severe negative impacts,. All four of Tajikistan’s agro-ecological zones are represented within the KRB as a result of the considerable altitudinal variation from south to north. This altitudinal variation also results in the KRB being vulnerable to a wide range of climatic hazards, including both sudden-onset and slow-onset climate events, such as GLOFs and droughts, respectively (Table 2). Communities in the KRB are frequently exposed to such extreme climate events. Flooding and landslides pose the greatest threats to these communities, with flooding seasons differing between upper, middle and lower reaches of the KRB. Upstream reaches experience floods from April to June, the middle reaches from March to May, and the downstream reaches from February to May. Because of the longer season in the downstream areas, the risk of flooding and landslides is much greater for these communities.

Six districts within the KRB have been identified as the most vulnerable to the impacts of climate change. These are the: i) Vakhdat, Faizobod and Varzob districts in the north; and ii) Nosiri Khusrav, Kabodiyon and Shaartuz districts in the south. Many of the households in these districts are located in hazardous areas and experience a number of climate-related threats and disaster events including: i) floods; ii) mudflows; iii) landslides; iv) rockfalls; and v) avalanches.

In addition to increased exposure to climate-related threats, these are all rural communities with limited adaptive capacity because of their dependence on agriculture for livelihoods, and limited opportunities for alternative income. About one-third of the agricultural losses in Tajikistan are currently attributable to climate change and variability, meaning that communities in the KRB who rely on agriculture for income are extremely vulnerable to the current and future impacts of climate change.

The impacts of climate change are likely to be different in the northern sub-basin of the KRB to those in the southern sub-basin. Rural communities in the Vakhdat, Faizobod and Varzob districts are expected to become increasingly exposed to hydrometeorological hazards such as increased flooding, mudflows, landslides and GLOFs. In particular, the steep terrain in these areas increase the likelihood of sudden onset multi-hazard risks, such as landslides occurring directly after a GLOF or similar flooding event. Concomitantly, watersheds in the northern sub-basin are frequently degraded as a result of unsustainable land-use practices that increase the likelihood and impact of the above-mentioned risks. Such unsustainable practices also increase the rate of erosion and soil loss, which compromises agricultural productivity in these regions and increases flood risk in downstream areas.

Communities in the Nosiri Khusrav, Kabodiyon and Shaartuz districts, conversely, are increasingly exposed to slow onset hazards such as drought and river bank erosion. In these areas, water availability is the greatest threat to livelihoods. Water availability is limited by poorly functioning irrigation supply infrastructure. This infrastructure is being damaged by: i) high levels of sedimentation from water-borne and wind-borne sediment; and ii) floods in the Kofirnighan River that damage irrigation dams and canals. Floods in the Kofirnighan River also cause riverbank erosion that results in the loss of arable land.

Table 2. Environmental disaster events for the period 1997–2010.

| # | Districts of KRB | Frosts and cold spells | Wind storms | Hails | Thunderstorms | Rains | Rainfall | Drought | Land-slides | Crumbling | Rock-falls | Soil sedimentation | Avalanches | Mudflows | Floods | Waterlogging | Water run-off | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Варзоб | 0 | 1 | 4 | 0 | 17 | 1 | 1 | 8 | 0 | 0 | 0 | 3 | 8 | 4 | 0 | 0 | 47 |
| 2 | Вахдат | 0 | 7 | 9 | 0 | 19 | 2 | 0 | 1 | 1 | 0 | 0 | 0 | 11 | 15 | 0 | 0 | 65 |
| 3 | Гиссар | 0 | 2 | 6 | 1 | 13 | 3 | 2 | 3 | 2 | 1 | 0 | 0 | 10 | 7 | 0 | 0 | 50 |
| 4 | Кабодиён | 0 | 4 | 3 | 0 | 13 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 8 | 12 | 0 | 0 | 42 |
| 5 | Н.Хисрав | 1 | 19 | 0 | 0 | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 31 |
| 6 | Рудаки | 0 | 8 | 6 | 0 | 34 | 6 | 0 | 5 | 0 | 0 | 1 | 0 | 36 | 8 | 0 | 0 | 104 |
| 7 | Турсунзаде | 0 | 0 | 2 | 0 | 7 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 7 | 3 | 0 | 1 | 22 |
| 8 | Файзабад | 0 | 9 | 8 | 0 | 11 | 3 | 0 | 2 | 0 | 0 | 0 | 0 | 7 | 8 | 0 | 0 | 48 |
| 9 | Шахринав | 0 | 1 | 4 | 0 | 14 | 2 | 0 | 1 | 0 | 0 | 0 | 1 | 10 | 3 | 0 | 0 | 36 |
| 10 | Шахритус | 0 | 3 | 1 | 0 | 13 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 1 | 0 | 33 |
| 11 | Всего | 1 | 54 | 43 | 1 | 147 | 19 | 6 | 22 | 3 | 1 | 1 | 4 | 106 | 68 | 1 | 1 | 478 |

A population’s ability to conduct meteorological and hydrological monitoring plays an important role in the early detection of flooding and mudflow events. The most optimal average number of stations for monitoring must comprise 1 station per 1000km/sq (Table 3). In the KRB, there is an average of 11 meteorological stations and 13 hydrological stations (equating to 1.55 units per 1000km2). This indicates that there is sufficient means for monitoring in the basin. Nevertheless, specialized agencies and units require significant improvements in functional reliability with regards to analysis, prognosis, zoning and monitoring of water related hazards.

Table 3. List of meteorological stations (hydroposts) in the Kofirnighan River Basin.

| # | Stations | Index | Latitude |  | Longitude |  | Height, meters ​​above sea level | Work period |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Degrees | Minutes | Degrees | Minutes |  |  |
| 1 | Ayvadj | 38930 | 36 | 58 | 68 | 2 | 318 | 2014-2018 |
| 2 | Anzob | 38719 | 39 | 5 | 68 | 52 | 3373 | 1939-2018 |
| 3 | Bustonobod | 38842 | 38 | 40 | 69 | 38 | 1964 | 1948-2018 |
| 4 | Hissar | 38837 | 38 | 30 | 68 | 39 | 768 | 1968-2018 |
| 5 | Dushanbe | 38836 | 38 | 35 | 68 | 44 | 800 | 1946-2018 |
| 6 | Isambay | 38838 | 38 | 3 | 68 | 21 | 563 | 1949-2018 |
| 7 | Fayzabad | 38845 | 38 | 32 | 69 | 19 | 1215 | 1943-2018 |
| 8 | Hushyori | 38833 | 38 | 53 | 68 | 50 | 1361 | 1945-2018 |
| 9 | Chormagzak | 38841 | 38 | 28 | 69 | 12 | 1730 | 1963-2018 |
| 10 | Shahrituz | 38937 | 37 | 19 | 68 | 9 | 378 | 1929-2014 |
| 11 | Maykhura | 38717 | 39 | 1 | 68 | 47 | 1922 | 1963-2018 |

## Criterion 3: Distribution of development support

Following the endorsement of the Water Sector Reform Programme by the Government of Tajikistan, the lead agency (MoEWR) has agreed with key donor development partners on a plan to equitably distribute technical assistance and development projects in each river basin. This equitable distribution was decided in the context of upcoming multi-million projects being channelled in support of water sector reforms by the World Bank, Asian Development Bank, Swiss Development Agency and Cooperation, Japan International Cooperation Agency, and the European Union (Table 4). In more recent months, other organizations and international NGOs have joined existing projects through consultations with the MoEWR and the Donor Development Council (DDC).

In each river basin that has secured support, donor organisations are required to provide technical assistance to the MoEWR with regards to the following activities:

- establishment of the River Basin Organisations and Sub-river Basin Organisations;

- establishment of River Basin Councils;

- development of long-term basin plans for the use, protection and development of water resources, as well as annual and seasonal plans for the distribution and management of water resources; and

- development of capacity-building workshops for River Basin Organisations and Sub-river Basin Organisations.

Table 4. River basins, key donor agencies and the status of interventions per river basin in Tajikistan.

| # | River basins | Key donor agencies | Status |
| --- | --- | --- | --- |
| 1 | Syr-Darya river basin | World Bank, Swiss Agency for Development and Cooperation, HELVETAS Swiss Inter-cooperation | Ongoing since 2016 |
| 2 | Zeravshan sub-river basin | World Bank, European Union, German Cooperation Agency | Ongoing since 2016 |
| 3 | Vakhs River Basin | World Bank | Ongoing since 2016 |
| 4 | Pyanj River basin | World Bank, Asian Development Bank, Japan International Cooperation Agency | Ongoing since 2016 |
| 5 | Kofirnighan River Basin | World Bank | Preparation phase since 2018 |

The KRB was the last of Tajikistan’s river basins to receive donor support – i.e. from the World Bank in 2018. Yet, having secured this support, the KRB fulfils the third criteria of site selection, which makes it eligible as a target site in the proposed project.

# Preliminary target districts in the Kofirnighan River Basin

Based on the preliminary analysis above, as well as an analysis of climate-related vulnerability information from District Development Plans of the KRB, it is suggested that the following six districts within the KRB are target sites for the project (Table 5). The target districts Vahdat, Fayzabad and Varzob are located upstream of the KRB, while Nosiri Khistrav, Kabodiyon and Shaartuz are located downstream of the KRB. The specific number of jamoats, raions and villages are also selected based on a preliminary assessment of vulnerability data (including inter alia climate change observations and projections, climate related disaster events, upstream-downstream linkages) as well as the adaptive capacities of local authorities and target populations.

Table 5. Target districts, total number of jamoats and villages and the target number of jamoats and villages for respective funding options in the KRB.

| # | Target Districts | Total number of units |  | Target number of jamoats and villages for respective funding option |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | US$6 million |  | US$8 million |  | US$10 million |  |
|  |  | Jamoats | Villages | Jamoats | Villages | Jamoats | Villages | Jamoats | Villages |
| 1 | Fayzabad | 8 | 71 | 2 | 16 | 3 | 22 | 4 | 30 |
| 2 | Varzob | 6 | 70 | 2 | 24 | 3 | 30 | 4 | 35 |
| 3 | Vahdat | 10 | 178 | 4 | 45 | 5 | 55 | 6 | 65 |
| 4 | N. Khisrav | 2 | 15 | 1 | 2 | 1 | 4 | 2 | 6 |
| 5 | Shaartuz | 5 | 35 | 2 | 7 | 3 | 9 | 4 | 12 |
| 6 | Kabodiyon | 7 | 43 | 3 | 7 | 4 | 11 | 5 | 15 |
| Total |  | 38 | 412 | 14 | 101 | 19 | 131 | 25 | 163 |

A more specific breakdown of selection indicators for each district is outlined in Table 6 below.

Table 6. District, indicators and sources regarding selection indicators for each district in the KRB.

| # | District | Indicators | Sources |
| --- | --- | --- | --- |
| 1 | Fayzabad | (a) number of population and households living in hazardous zones (b) types of disaster events typical in target Jamoats and villages: mud-flows, floods, landslides. | Programme for socio-economic development of Fayzabad district for the period 2016-2020, p.60 (also referred to as DDP) |
| 2 | Varzob | (a) number of villages located in hazardous zones; (b) types of disaster events: landslides, mudflows, rockfalls. | Programme for socio-economic development of Varzob district for the period 2016-2020, p.80 (also referred to as DDP) |
| 3 | Vahdat | (a) number of villages located in hazardous zones; (b) types of disaster events: landslides, mudflows, rockfalls. | Programme for socio-economic development of Vahdat district for the period 2016-2020, p.53 (also referred to as DDP) |
| 4 | Nosiri Khisrav | (a) number of population and households living in hazardous zones; (b) types of disaster events: strong winds, droughts, mudflows. | Programme for socio-economic development of Nosiri Khisrav district for the period 2016-2020, p.60 (also referred to as DDP) |
| 5 | Shaartuz | (a) number of villages located in hazardous zones; (b) types of disaster events: flooding, mudflows, sand storms. | Programme for socio-economic development of Shaartuz district for the period 2016-2020, p.66 (also referred to as DDP) |
| 6 | Kabodiyon | (a) number of villages, households and population in hazardous climatic zones; (b) types of disaster events: flooding, mudflows. | Programme for socio-economic development of Kabodiyon district for the period 2016-2020, p.67 (also referred to as DDP) |

Figure 2, 3 and 4 illustrate the average annual temperature and precipitation in the KRB.

Figure 2. Average atmospheric temperature (January) in the KRB.

Figure 3. Average atmospheric temperature (July) in the KRB.

Figure 4. Average annual precipitation in the KRB.

End of justification for KRB

## Annex 4. Environmental and Social Management Framework (ESMF)

UNITED NATIONS DEVELOPMENT PROGRAMME (UNDP)

ENVIRONMENTAL AND SOCIAL MANAGEMENT FRAMEWORK (ESMF)

for the project titled:

“An integrated landscape approach to enhancing the climate resilience of small-scale farmers and pastoralists in Tajikistan”

# Introduction

This Environmental and Social Management Framework (ESMF) has been developed by the United Nations Development Programme (UNDP) together with the Government of Tajikistan (GoT) for the project “An integrated landscape approach to enhancing the climate resilience of small-scale farmers and pastoralists in Tajikistan”. The aim of the ESMF is to provide clear and systematic guidelines to identify environmental and social risks linked to project interventions as well as to outline the institutional and administrative pathways to address these risks. To minimise the negative environmental and social impacts of the proposed project, it has been ensured that the ESMF is in line with UNDP’s Social and Environmental Safeguards policy (SESP), which will guide all aspects of project implementation. In addition, the project will meet the criteria of the Adaptation Fund’s Environmental and Social Safeguards (E&S) Checklist.

From the screening and preliminary analysis based on the SESP and the E&S, it is unlikely that the project activities will result in significant social and environmental impacts. Indeed, these social and environmental impacts – which are most likely to occur during the construction phase of EbA interventions – are expected to be minor and without long-term adverse effects.

## Overview of the proposed project

The overall objective of the proposed project is to enhance the climate resilience of small-scale farmers and pastoralists in Tajikistan. To address the country’s vulnerability to climate change, project activities will introduce an integrated approach to landscape management with the objective to develop the climate resilience of rural communities in Tajikistan. The proposed project’s activities will focus on one of the country’s most climate-vulnerable river basins, namely the Kofirnighan River Basin (KRB). An integrated catchment management strategy will be developed for this basin which will be operationalised at raion (district), jamoat (subdistrict) and village levels6. The strategy will provide detailed guidelines for suitable landscape management interventions to reduce the vulnerability to climate change. These interventions include using Ecosystem-based Adaptation (EbA) solutions that will build the resilience of rural communities while also promoting the sustainable management of natural resources through an integrated landscape approach. To achieve the above-described objective, several components, outcomes, outputs and activities have been identified for the project. These components, outcomes, outputs and activities are outlined in Table 1 and are further detailed in the Full Proposal.

Table 1. Project components, expected outcomes, outputs and indicative activities.

| Expected Outcomes | Expected concrete Outputs | Indicative activities |
| --- | --- | --- |
| Component 1. Integrated catchment management to build climate resilience. |  |  |
| 1. Catchment management strategy to manage climate risks operationalised at Raion (district) and Jamoat (sub-district) levels in Kofirnighan River Basin (KRB). | 1.1. Multi-hazard climate risk models developed for target watersheds in the KRB. | 1.1.1. Conduct a gap analysis on existing risk information in the KRB. |
|  |  | 1.1.2. Develop Multi-Hazard Climate Risk Models for the KRB. |
|  | 1.2. Support provided for establishing automated weather stations in Kofirnighan River Basin watersheds. | 1.2.1. Provide technical support for the rehabilitation of automated weather stations in the most vulnerable districts of the KRB. |
|  |  | 1.2.2. Collect and collate data from improved automated weather stations. |
|  |  | 1.2.3. Use collected data to inform climate risk information and adaptation advisories for agro-ecological extension service providers. |
|  | 1.3. Integrated catchment management strategy developed for the KRB. | 1.3.1. An integrated catchment management strategy developed for the KRB to inform and facilitate cross-sectoral landscape planning. |
|  |  | 1.3.2. Training programme delivered on mainstreaming climate risks for integrated catchment management planning. Sub-activities are detailed below. 1.3.2.1. Training conducted to relevant Committee for Environmental Protection (CEP) representatives to integrate catchment management into implementation and monitoring activities for all projects going forward, both those with a focus on climate change and without. 1.3.2.2. Training provided to the personnel of the supported knowledge management centres – including the DoG Open Centre and to UCA – on assessing available climate risk information and ensuring it is all made available through the relevant portals/hubs. 1.3.2.3. Training provided to raion-and jamoat-level government departments on integrated catchment management and identifying climate risks that require such a management approach. |
|  |  | 1.3.3. Provide training for selected communities on identification of EbA activities and implementation. |
|  | 1.4. Strengthened coordination and training mechanisms for integrated climate-resilient catchment management. | 1.4.1. Strengthen existing training mechanisms at the raion and jamoat levels. |
|  |  | 1.4.2. Training provided on integrating EbA into catchment management. |
|  | 1.5. Payment for Ecosystem Services (PES) models to support the long-term financing of integrated catchment management strategy implementation. | 1.5.1. Suitable PES models developed for the KRB. |
| Component 2. Ecosystem-based Adaptation (EbA), including Climate-smart Agriculture (CSA) and Sustainable Land Management (SLM), implemented in agro-ecological landscapes. |  |  |
| 2. An integrated approach to building climate resilience of agro-ecological landscapes operationalised at a village level in KRB. | 2.1. Agro-ecological extension services supported at the jamoat level to provide technical support for EbA implementation. | 2.1.1. Agro-ecological extension services supported by training existing service providers on EbA, climate-resilient agriculture and multi-hazard climate risk management. |
|  |  | 2.1.2. Establish EbA demonstration plots in each of the target villages. |
|  |  | 2.1.3. Farmer field schools conducted in target villages making use of demonstration plots [Activity 2.1.2]. |
|  | 2.2. Watershed Action Plans (WAPs) developed that promote climate resilience and enhance economic productivity for target communities. | 2.2.1. Participatory mapping conducted at the watershed level. |
|  |  | 2.2.2. Watershed Action Plans developed for vulnerable watersheds in the Kofirnighan River Basin. |
|  | 2.3. EbA interventions implemented in target watersheds by local communities. | 2.3.1. Support local communities to implement priority EbA interventions. |
|  |  | 2.3.2. Support local community members in developing Enterprise Plans (EPs) based on EbA interventions. |
|  |  | 2.3.3. Monitor the impacts of EbA interventions. |
| Component 3. Knowledge management on building climate resilience through integrated catchment management and EbA in the KRB. |  |  |
| 3. Existing knowledge management platforms supported for integrated catchment management and EbA. | 3.1. Existing knowledge management platforms supported for collating information on the planning, implementation and financing of EbA interventions. | 3.1.1. Existing knowledge management platforms responsible for collating, analysing and disseminating information on climate risks and suitable adaptation options will be supported. |
|  |  | 3.1.2. Data and information will be collected from automated weather stations, agro-ecological extension centres and international publications. |
|  | 3.2 An impact evaluation framework to enable effective adaptive management of EbA activities. | 3.2.1. An impact evaluation framework will be established to enable the effective quantification of project benefits and to provide information for future planning and implementation of EbA interventions. |
|  |  | 3.2.2. Data and information obtained through applying the framework will be disseminated via the knowledge platform(s). |

## Potential social and environmental impacts

The Social and Environmental Screening Procedure (SESP; see Annex 7 of the Full Proposal) classified the project as low risk, with minimal negative social and environmental impacts expected. This is because the use of EbA interventions is intended to improve the management of land, water and natural habitats, having an overall positive environmental impact. Furthermore, by improving the agricultural productivity of smallholder farmers, the project will lead to a reduction in poverty and an improvement in the social condition. However, as described in the SESP, there are still several social and environmental risks associated with the proposed project that will need to be considered during implementation (Table 2).

Based on preliminary analyses and screening, project interventions are unlikely to result in significant negative social and environmental impacts. Indeed, these social and environmental impacts – which are most likely to occur during the construction phase of EbA interventions – are expected to be minor and without long-term adverse effects.

Table 2. Potential social and environmental impacts and mitigation measures.

| No. | Activity/risk | Potential social and environmental impact | Potential project benefit | Mitigation measures | Monitoring |
| --- | --- | --- | --- | --- | --- |
| 1. | Changes in pasture and livestock management practices and reforestation measures (grazing control, rotational grazing, livestock exclusion zones and reforestation) may limit the availability of/accessibility to some basic services. | Project activities could restrict the availability of, quality of and access to resources or basic services, particularly for marginalized individuals or groups. | Improved livelihoods, health and well-being of target communities, specifically: - increased pasture productivity and carrying capacity; - increased provision of food and fodder; - increased nutrition for local community; - increased provision of fuel-wood and timber; - protected crops and livestock from extreme climatic conditions; - increased biodiversity conservation; - increased soil moisture; and - slowed water run-off. | To mitigate the potential social and environmental impacts of this risk, the project activities will: - promote alternative business solutions and community enterprise developments that will help communities to generate alternative incomes. - engage widely with relevant stakeholders at regional, sub-regional and community levels to agree on rotational routes for the transit of larger herds, as well as to monitor grazing control measures applied locally by large herd owners from other communities, districts and/or regions. - introduce jamoat-level monitoring and control mechanisms to enforce agreed-upon measures for the mitigation of land degradation and to improve vegetation growth in target pasture lands, as well as to ensure that target communities effectively benefit from project interventions. - introduce energy-efficient stoves into target communities to compensate for the limited access to forest resources for energy. Best practices and lessons learned from similar past projects in Tajikistan will be adapted for and applied to the KRB context. | Mid-term review; project monitoring missions. |
| 2. | Alien and invasive alien seeds and species may be used in reforestation activities. | Through reforestation and rehabilitation efforts, alien and invasive species may be introduced to ecologically-sensitive regions that will damage the ecosystems. | The project’s activities will promote the rehabilitation/restoration of abandoned and overexploited forests and degraded forest ecosystems, as well as the reforestation of areas adversely affected by extreme climate events. The overall benefits will include: - reduced forest degradation; - increased bio-diversity conservation; - increased water infiltration; - increased above-ground biomass (increased plant survival); - protected crops and livestock from extreme climatic conditions; - reduced slope instability and risk of minor mudslides and landslides; - slowed water run-off; - increased soil moisture; and - reduced soil loss. | The use of native and climate-resilient varieties will be promoted, but alien species may be introduced if necessary. Certain alien species may be used for complementary planting (climate-resilient crops seed varieties) in areas being reforested to increase biological biodiversity and enhance climate resilience. Prior to such introduction, relevant experts at the CEP and among development partner agencies will be consulted on successful examples across the regions. National environmental norms, standards and procedures for the introduction of alien species will be followed in each case. The project will also support the setting up of a procedure for tracking and monitoring all restoration actions implemented. During the last year of the project, an ecological and land use assessment will be carried out to evaluate the rate of success of the restoration. | Organise knowledge-sharing hub to document past experiences (successes and failures); screening of alien and invasive seeds and species; risk analysis and management plan for alien and invasive species; mid-term review. |
| 3. | Establishment of pasture use groups | Unregulated pasture use, rotational grazing and pasture transit routes may compromise the project outcomes in the target pasturelands. | The project will promote the sustainable use of pasturelands that will benefit livestock owners and positively impact on their livelihoods. These benefits will be achieved through the introduction of exemplary pasture management practices, governance and joint community participation schemes (i.e. pasture use groups). | To mitigate this risk, the project activities will support livestock owners to take responsibility of sustainable pasture use. This will be achieved first and foremost by the establishment of pasture use groups. In addition, project activities will: - educate pasture use groups on the stock of pasturelands in target areas, as well as their level of degradation; - help pasture use groups to develop pasture improvement plans; - consulting with local authorities to agree on alternative transit routes for livestock owners; and - introducing incentives and payment mechanisms to ensure the sustainability of the interventions. | Mid-term review; capacity building workshops; project monitoring missions. |
| 4. | Over-harvesting of restored forest resources by local communities | Unsustainable community harvesting of restored forests may compromise project outcomes. | The project will support the rehabilitation/restoration of degraded forest ecosystems in areas affected by adverse climatic events. Reforestation activities are designed to also enhance biodiversity and ecosystem services of degraded areas. These reforestation activities will be guided by existing Forest Development Plans and prioritised in consultation with local municipalities. | Following forest restoration, the project will aim to prevent and mitigate unsustainable harvesting practices for the future. Such prevention will be achieved through jamoat- and raion-level awareness campaigns, as well as the introduction of concrete measures to support sustainable harvesting. Specific activities to support sustainable harvesting include inter alia: - actively engaging communities in joint forest management activities, including planting woodlots for fuelwood and timber, implementing agroforestry actions, promoting commercial plantations in salinised and degraded lands, and providing alternative business support (such as bee-keeping and fodder production). - providing training for communities concerning suitable fuelwood plantations, fast growing tree species, and best practices in sustainable use of forest resources; and - providing communities with fruit trees (to support alternative livelihoods) and energy-efficient eco-stoves (to support alternative energy use) to further reduce the use of restored wood material in vulnerable communities. | Mid-term review; capacity building workshops; project monitoring missions. |
| 5. | Project activities (particularly forest restoration) is sensitive to the impacts of climate change. | The adverse impacts of extreme climatic events (particularly flooding and water run-off) have the potential to affect forests and agricultural areas, as well as the livelihoods that depend on them. | The project activities directly support the implementation of ecosystem-based adaptation, including climate-smart agriculture and sustainable land management in agro-ecological landscapes. Such actions include the rehabilitation and restoration of degraded forest ecosystems, vegetation growth support, water retention measures and climate-resilient crop planting. These actions are expected to prevent and mitigate water-related climatic events that threaten local livelihoods. | To minimise the impact of water-related extreme climatic events, the project activities will support the development of a catchment management strategy to manage and operationalize climate risks at jamoat and raion levels in the KRB. Current and predicted climatic variability has been taken into account during project design. Throughout the inception and implementation phase, any projected changes in climate have been – and will continue to be – taken into account, as outlined below: - drought- and flood-resilient species, as well as indigenous species, will be used wherever possible; - techniques to assist plant growth particularly in the seedling/sapling phases and to reduce risk of damage from extreme climate events will be used; and - as part of Early Warning Systems, multi-hazard climate risk models (MHCRM) will be developed for vulnerable watersheds in KRB and provide technical support for the modernization of automated weather stations in the most vulnerable districts of KRB. These will help authorities and communities adequately assess risks, climate related projections and incorporate these risks in the KRBMP. | Use of climate risk management tools and assessments; mid-term reviews; project monitoring missions. |
| 6. | Small-scale construction activities under the proposed project may pose safety risks to community members implementing them. | The EbA measures selected for the project will involve the construction of: i) water-saving irrigation systems; ii) rainwater-harvesting systems; and iii) rehabilitation of irrigation, draining and pumping systems. Other activities may include the construction of gabions, terraces, small damns and riverbank enforcement. These construction activities may pose safety risks to the individuals implementing them. | The project’s ecosystem-based adaptation measures will benefit communities, specifically by protecting their livelihoods and improving agricultural production. | The project activities will follow all relevant Environmental Impact Assessment (EIA) procedures, as well as ensure compliance with national construction standards and norms, sanitary norms and regulations, and other national laws and regulations (relating to forestry, water, environment, and health). In all instances, project activities will be guided by technical best practices regarding the construction of rain-water harvesting systems, drip-irrigation techniques, and micro-reservoirs. | Mid-term review; project monitoring missions. |
| 7. | Pest control measures and agricultural support may involve the use of pesticides. | There may be a risk of application of pesticides that may have a negative effect on the environment or human health. | The Project will support producers to adopt improved farming techniques (e.g. organic agriculture, soil and water conservation) that would reduce the use of fertilizers and harmful pesticides, thus reducing the contamination of soil and water bodies. | The project will promote safe and healthy agro-ecological practices, specifically by avoiding the use of pesticides. Such avoidance will be achieved by: - using agro-ecological extension services to provide communities with support and information on the safe implementation of EbA; - not introducing species that are dependent on high pesticide or fertilizer use; - the project not financing pesticides; and - integrated pest and nutrient management approaches being included within EbA interventions as appropriate. | Mid-term review; project monitoring missions. |
| 8. | National and regional authorities may not have the capacity to meet their obligations to the project. | The capacities of national institutions and district authorities may not be sufficient to provide effective governance solutions to climate problems that are complex and multi-sectoral. | The project design includes a dedicated component (Component 3) with an extensive set of capacity building actions and knowledge building and sharing at national, regional, local and community levels. These actions are based on analyses of institutional frameworks and capacities which were carried out during project preparation. | At the national level, focal institutions will be strengthened through the participatory development of integrated catchment management strategies and Watershed Action Plans (WAPs) for the KRB. Coordination and training mechanisms will be strengthened within target jamoats, which include capacity-building for the mainstreaming of integrated catchment management into planning and budgetary processes. Training will also target relevant government institutions involved in catchment and watershed management, including the Committee for Environmental Protection (CEP) and Ministry of Energy and Water Resources (MEWR). The project’s activities will contribute to river basin development and planning processes through integrating catchment management strategies and watershed action plans with EbA-related interventions. This will occur within the frameworks of the KRB Management Plan under the leadership of the MEWR, as well as the GoT Water Reform Programme. The use of these existing frameworks will contribute to building capacities of relevant national and district authorities. | Capacity building workshops; exchange visits to related sites where partner projects have been implemented; mid-term review; project monitoring missions; |
| 9. | Marginalised groups could potentially be excluded from fully participating in decisions that may affect them. | Local stakeholders, specifically poor and vulnerable groups, may be limited in their abilities to participate effectively in decision making. | The project activities target the most vulnerable groups in the KRB. In doing so, these activities will directly benefit these groups. The full extent of these benefits is outlined in the Full Proposal. | Marginalised groups in the KRB include those living in places with increased impacts of climate change, food insecure households, households with limited or no productive assets (limited resilience), livestock and/or agricultural land plots. Such vulnerable groups currently have limited awareness and ability to participate during critical stages of project design and implementation. During the project’s inception phase, a vulnerability assessment of target communities will be carried out in a participatory manner. Where feasible, vulnerable and marginalised groups will be prioritised for adaptation interventions. The Stakeholder Engagement Plan (see Section 4) will guide such consultations during preparation phases, ensuring the broad representation of existing relevant community-based organisations and groups. These organisations and groups involve inter alia farming associations and cooperatives, women’s committees, intervention-related initiative groups, pasture development associations, water user associations (WUAs), forestry cooperatives and communal health promoters. The project will monitor and assess the extent of involvement of vulnerable and marginalised within such groups and associations. The targeted actions that will be prioritised and deemed suitable for vulnerable groups may include on-farm adaptation interventions, household plots, improved productivity measures and the selection of demonstration plots with support from farmer field schools. Certain enterprise developments and income-generating activities (such as bee keeping, fodder production, livestock productivity support) may also be suitable for the given groups to ensure that benefits are distributed inclusively and in an equitable manner. | Inception assessments; mid-term review; consultation workshops; project monitoring missions. |
| 10. | Gender-based discrimination may be present, especially regarding women’s participation in project design and implementation. As a result, women may have limited access to resources, opportunities and/or benefits. | Women may not be adequately represented with regard to decision-making or participation in the design and implementation of the project. | Project activities will be designed and implemented so that all genders: i) are able to participate fully and equitably; ii) receive comparable social and economic benefits; iii) do not suffer disproportionate adverse effects as per UNDP’s Gender Mainstreaming Strategy. | A gender analysis will be undertaken in the initial phase of the project to assess divisions of labour and the role of women and their access to resources in the target areas. The analysis will also develop recommendations as to how the project’s activities will promote women’s equality and empowerment, including participation in project decision-making. Appropriate measures will be put in place to ensure that women receive an equitable share of project benefits and that their interests are not compromised. Participatory processes will include methodologies that enhance the participation of women and promote the inclusion of their views into the activities of the project. The monitoring of project outputs will include disaggregated and measurable data related to gender equality and the empowerment of women. Furthermore, measures and techniques that contribute to closing the inequality gap between men and women will be promoted, where possible. | Gender assessment; use of disaggregated and measurable indicators related to gender equality and women’s empowerment; capacity building workshops; mid-term review; project monitoring missions. |

# National policy framework for environmental and social matters

## 2.1. National policies, plans, strategies and development goals

Table 3 has been taken from Part II: D of the Full Proposal where it outlines the national and sub-national policies, plans, strategies and development goals that are relevant to project activities.

Table 3. National policies, plans, strategies and development goals.

| Strategy | Year enforced | Alignment |
| --- | --- | --- |
| National strategies |  |  |
| National Development Strategy 2016–2030 (NDS) | 2016 | The primary focus of the NDS is on the long-term development of Tajikistan to improve living standards for the population. Specific NDS objectives to achieving this include: i) poverty eradication; ii) sustainable economic growth; iii) promotion of sustainable consumption and production patterns; and iv) sustainable use of natural resources. The vulnerability of the Tajik population to climate change is acknowledged throughout the NDS, with the importance of agriculture and water management to alleviating this highlighted. Outcome 1 and 2 of the project therefore align with achieving the ultimate goal of the NDS in the country. |
| National Strategy and Action Plan on the Conservation and Sustainable Use of Biodiversity (CBD Strategy) | 2003 | Several interconnected components contribute to the primary objective of the CBD Strategy. A priority element of the ‘geo system level approach’ outlined in the CBD Strategy is the restoration and reforestation of degraded landscapes to reduce soil erosion, particularly in landslide and already eroded areas. Outcome 2 is aligned with this strategic component through implementing EbA activities that contribute to restoration and reforestation in degraded landscapes. |
| National Strategy on Disaster Risk Management for 2010–2015 (NDRMS) | 2010 | The NDRMS identifies the significance of climate change related disasters in the country such as droughts and high-water events. It is also acknowledged in the strategy that mitigation for these types of events needs to be incorporated into the design phase of new development projects. The project is therefore aligned with the NDRMS under Outcome 1, relating to integrated catchment management which includes the improvement of water monitoring systems. |
| The National Climate Change Adaptation Strategy (NCCAS) | 2016 | Within the NCCAS there are guidelines provided for priority adaptation actions to be undertaken in Tajikistan. The proposed project is well-aligned with the NCCAS because they both recognise that climate change effects on the agricultural sector result in significant negative impacts for the population. The NCCAS also recognises the potential of EbA as an effective adaptation approach. The NCCAS is currently in draft format and has not yet been accepted by the government. Notwithstanding this information, the proposed project is aligned with the NCCAS through both Outcome 1 and 2. |
| Living Standards Improvement Strategy for the Republic of Tajikistan for 2013–2015 (LSIS) | 2013 | LSIS recognises the cross-cutting nature of climate change adaptation in relation to environmental sustainability, economic growth and reducing poverty. The importance of water, soil quality and improving the capacity to collate and disseminate climate change information are also identified as important fields for poverty reduction. In this regard, all three outcomes of the project align with LSIS objectives. |
| National programs and plans |  |  |
| National Program of Actions to Combat Desertification (NPACD) | 2001 | Outcome 2 of the project aligns with the NPACD focus on ‘rational land tenure’ and ‘measure on rational nature using’. These focal points refer to the sustainable use of natural resources, with clear guidelines on reforestation and mitigating the effects of water erosion. Outcome 3 aligns with two further objectives of the NPACD, namely: i) the development of better platforms to disseminate climate change information; and ii) increasing the role of the local population in collecting and collating data. |
| Strategic Program for Climate Resilience (SPCR) | 2011 | The SPCR was developed in response to the specific vulnerability of Tajikistan to climate change and the associated economic, environmental and social impacts. It is the strategic overview of the Pilot Programme for Climate Resilience (PPCR), which consists of six core components. One of these core components is ‘Agriculture and sustainable land management’, which focusses on incorporating climate resilience into all sectors of land management. Outcome 2 of the proposed project has a strong alignment with this component. |
| National Action Plan for Climate Change Mitigation (NAPCC) | 2003 | The NAPCC is the only strategic framework in the country that specifically addresses the implications of climate change. All outcomes of the project are strongly aligned with the NAPCC. |
| National Environmental Action Plan (NEAP) | 2006 | The NEAP focusses on a broad spectrum of current environmental concerns, many of which are likely to be exacerbated by climate change. Amongst the most prevalent concerns included in the NEAP include: i) soil erosion; ii) deforestation and land degradation; iii) high water events; and iv) water scarcity. Outcome 1 and 2 of the project align with these concerns. The NEAP also recognises the need to improve environmental knowledge in Tajikistan at both institutional and local levels, which is complemented in Outcome 3 of the project. |
| Water Sector Reforms Programme of the Republic of Tajikistan for 2016–2025 (Water Reform Programme) | 2015 | Under the Water Reform Programme, the GoT is initiating a shift towards managing water resources according to hydrographic rather than administrative boundaries. Further to this, the programme aims to promote the implementation of Integrated Water Resources Management (IWRM) at the basin level. IWRM was specifically defined for Tajikistan as being: “based on the interaction of various sub-sectors with the objective good accessibility to high quality water and sanitation services for the population, ensuring water availability for irrigation, hydropower, environment and other users in river basins defined by hydrographic boundaries. IWRM promotes the protection of water resources from over-exploitation and pollution; provides protection of vulnerable mountain environments including river banks and floodplains from flooding and erosion, and facilitates public participation in decision- making, planning, financing and development of water resources in the interests of economic growth, sustainable development of the society and preservation of the environment.” River Basin Organisations (RBOs) and River Basin Councils (RBCs) will be established in each of the six identified basins, as well as in sub-basins as required. RBOs will mainly be responsible for: i) planning the use and protection of water resources annually and in the long-term; and ii) monitoring the distribution of water as well as the state of rivers. RBCs will mainly be responsible for reviewing the plans developed by the RBOs and managing interactions with stakeholders such as water users and Water User Associations (WUAs). RBOs are expected to become operational in 2019, with the GoT being expected to allocate ~US$160,000 annually towards the operation of RBOs and RBCs. Outcome 1 aligns with the Water Reform Programme in involving RBOs and RBCs in developing an integrated catchment management strategy for the KRB. |
| Agricultural Reform Programme of the Republic of Tajikistan for 2012–2020 | 2012 | The Agricultural Reform Programme includes a direct focus on mitigating the negative impacts of climate change for agricultural production. This includes the primary activity of ‘systematic reduction of soil erosion, land degradation and deforestation by improving natural resources management’. The programme includes a focus on EbA strategies with emphasis on soil erosion activities. Both Outcome 1 and 2 of the project align with these focal points of the Agricultural Reform Programme. Another important component of the programme is the ‘development and establishment of information management systems that would enable communities, local and national authorities to effectively collect, record and analyse reliable information on the impact of natural disasters and climate change’. Outcome 3 of the project is strongly aligned with this component. |
| Strategies with a focus on climate change |  |  |
| Greenhouse Gas Abatement Strategy (GHG Strategy) included in the NAPCC | 2003 | In order to meet the UNFCCC commitments for Tajikistan, the GHG Strategy was developed with the focus to address the problem of source-based anthropogenic emissions. Outcome 2 of the proposed project aligns with the objective of promoting sustainable forms of agriculture in light of climate change considerations. Additionally, Outcome 2 aligns the priority of enhancing natural sinks of carbon including forests and soils. |
| Strategy of Adaptation to Climate Change, Prevention and Minimization of its Adverse Effects (Adaptation Strategy) included in the NAPCC | 2003 | In order to meet the UNFCCC commitments for Tajikistan, the Adaptation Strategy was included within the NAPCC to ensure that climate change adaptation remained a focal point for development in the country. Outcome 2 and 3 of the project align with the following components of the strategy: - improvement of systematic observation and monitoring network for ensuring timely adjustment of adaptation measures; and - improvement of the data collection system and analysis, interpretation and dissemination of the results among the end users. Outcome 1 of the project is aligned with two of the priorities relating to water resources: - development of measures in the field of water resources protection, water and energy saving in the conditions of climate change; and - development of new, and improvement of existing technical and economical tools on water use at national and regional levels. In addition, Outcome 2 of the project aligns with four of the five ‘measures of adaptation and minimisation of adverse impacts of climate change’ relating to land use. These are listed below. - Zoning of territory depending on the extent and type of influence of climatic factors on the condition of lands taking into account its vulnerability to the different forms of erosion. - Setting a selection of soil protection measures for specific landscapes according to the influence of climatic and anthropogenic factors. - Conducting land-reclamation measures, which include crop rotation, soil protection and limiting the ploughing of steep lands that will help to conserve the humus in the soils under the expected conditions of climate change. - Forest rehabilitation measures in the regions prone to drought and wind erosion. |
| Laws |  |  |
| Land Code of The Republic of Tajikistan (Land Code) | 1996 | The Land Code regulates all land relations and is directed at the rational use and protection of land. This focus is targeted to improve the fertility of soil, and to maintain and improve the natural environment. In this way, opportunities for equal development of all forms of economic activity will be promoted in Tajikistan. |
| Water Code of The Republic of Tajikistan (Water Code) | 2000 | The Water Code is aimed at regulating water relations to ensure rational use. This is so that there is adequate supply for the needs of the population and the natural environment. |
| Law of the Republic of Tajikistan on Land Reform (Land Reform Law) | 1994 | The Land Reform Law includes tasks listed by the GoT specifically for further developing land management. These tasks are all designed with the purpose to increase the agricultural production of the country and include the: i) creation of optimal conditions for equal rights; ii) development of various forms of land management; iii) formation of a multi-structural economy; iv) rational use; and v) the protection of land. |
| Law of the Republic of Tajikistan on Land Management (Land Management Law) | 2001 | The objective of the Land Management Law in Tajikistan is to create conditions for equal development for all sectors in the country. |
| Law on Environmental Protection | 2011 | This law provides the legal base for developing the state policy on environmental protection. Further to this, it aims to conserve the natural resources of the country and ensure the environmental sustainability for socio-economic development. Therefore, the law ensures that the human right to a healthy environment is guaranteed. This Law determines the legal basis of state policy in the field of environmental protection and is aimed at providing sustainable social and economic development, guarantee of human rights for the healthy and favorable environment, strengthening of law and order, prevention of negative impact of economic and other activity on the environment, the organization of rational use of natural resources and providing ecological safety. This Law determines the legal basis of state policy in the field of environmental protection and is aimed at providing sustainable social and economic development, guarantee of human rights for the healthy and favorable environment, strengthening of law and order, prevention of negative impact of economic and other activity on the environment, the organization of rational use of natural resources and providing ecological safety. |
| Law on Ecological Expertise | 2012 | The law defines principles and norms for environmental experts to adhere to and provides for the prevention of negative impacts on planned economic interventions on environment. |
| Law on the Republic of Tajikistan on Dehkan Farms (Dehkan Law) | 2016 | This law defines the legal base for establishing and maintain the efficient functioning of dehkan enterprises. In addition, the law aims to create an enabling environment for the development of farming in the country. |

## 2.2. Consistency with national technical standards

The project is aligned with the requirements of the March 2016 Revision of the Environmental and Social (E&S) Policy of the Adaptation Fund (see Part II: Section K of the Full Proposal). During project development, the Full Proposal was screened according to the UNDP Social and Environmental Safeguards Procedure (SESP). This was to ensure that all necessary safeguards have been addressed and incorporated into the project design.

In addition to complementing the efforts of the CEP and the GoT to improve catchment management in the KRB, project activities will increase rural Tajik resilience to climate change in throughout the country. The Adaptation Fund-accredited Implementing Agency, UNDP, together with CEP and relevant national partners, will ensure that the project follows procedures outlined in the ESP. This includes the requirement that project activities funded by the Adaptation Fund reflect local circumstances and needs and draw upon national actors and capabilities.

The project will also adhere to all relevant national technical standards. At the Full Proposal development stage, the following legislation has been identified with relevance to the proposed activities:

- 1996 Land Code of The Republic of Tajikistan;

- 2000 Water Code of The Republic of Tajikistan;

- 2001 Law of the Republic of Tajikistan on Land Management;

- 2001 Law About Environmental Protection; and

- 2012 Law on Ecological Expertise.

Given the small scale of the project’s EbA interventions in the target sites and communities, as well as their focus on environmental protection, Environmental Impact Assessments (EIAs) are not expected to be necessary for any of the planned interventions. In addition, the proposed projects activities are in line with national social norms, including gender equality and equal access.

## 2.3. UNDP Social and Environmental Standards

UNDP’s Social and Environmental Standards (SESs) have been applied during development of the project. The SES objectives are to: i) strengthen the social and environmental outcomes of programmes and projects; ii) avoid adverse impacts to people and the environment; iii) minimise, mitigate and manage adverse impacts where avoidance is not possible; iv) strengthen UNDP and partner capacities for managing social and environmental risks; and v) ensure full and effective stakeholder engagement, including through a mechanism to respond to complaints from project-affected people. These SESs have been reviewed by the Adaptation Fund and found to address the requirements of the Adaptation Fund’s Environmental and Social Policy.

UNDP will not support activities that do not comply with national law and obligations under international law – whichever standard is higher (hereafter referred to as ‘applicable law’). It seeks to support governments in adhering to their human rights obligations, as well as to empower individuals and groups, particularly the most marginalised, to realise their rights. Marginalised groups will be encouraged to fully participate throughout the project cycle.

The proposed project was screened with UNDP’s SESP, which resulted in a “Low” overall project social and environmental risk categorisation. It was determined that the following UNDP SESs were particularly relevant to the project:

- Principle 1: Human Rights;

- Principle 2: Gender Equality and Women’s Empowerment;

- Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management;

- Standard 2: Climate Change Mitigation and Adaptation;

- Standard 3: Community Health, Safety and Working Conditions; and

- Standard 7: Pollution Prevention and Resource Efficiency.

The project is aligned with the requirements of the March 2016 Revision of the E&S Policy of the Adaptation Fund. UNDP, together with CEP and relevant national partners, will ensure that the project follows procedures outlined in the E&S Policy. This includes the requirement that project activities funded by the Adaptation Fund reflect local circumstances and needs, as well as draw upon national actors and capabilities.

# ESMF requirements and procedures for screening, assessment and management

## 3.1. Objectives and requirement of the ESMF

An ESMF is a management tool used to assist in addressing potentially adverse social and environmental impacts associated with project activities. It identifies steps for screening potential social and environmental risks, as well as impacts of project activities as their specific locations are further defined. It also helps in the preparation and approval of appropriate action plans for avoiding or, when avoidance is not possible, mitigating and managing adverse impacts. To ensure the social and environmental objectives of the project are met, and adverse impacts are avoided and/or mitigated, the present ESMF will be used by the project implementers.

In the context of the proposed project, the objective of the ESMF is to identify environmental and social impacts and risks associated with the interventions selected for each target community of the Kofirnighan River Basin (KRB). This will allow the project implementation teams (National Project Team, as well as national and local authorities) to identify and implement appropriate risk mitigation measures. In addition, the ESMF aims to:

- increase climate resilience and adaptive capacity of KRB municipalities and target communities;

- implement on-the-ground, EbA measures for forest, land and water resources management in targeted areas;

- strengthen knowledge building, information management and monitoring systems associated with assessing climate change vulnerability;

- promote sustainable livelihoods, health and wellbeing of target communities, as well as sustainable management practices regarding the utilisation of natural resources;

- detail all monitoring procedures required to identify environmental and social impacts;

- adopt best available practices to avoid or mitigate environmental and social impacts; and

- ensure compliance with all applicable laws, regulations and standards for the protection of the environment and of local communities’ wellbeing.

## 3.2. Screening procedures of the ESMF

Prior to project implementation, activities will be screened against an agreed ‘negative list’. Project activities could be deemed ineligible for implementation in the KRB if they:

- involve significant conversion or degradation of natural habitats (e.g. forest ecosystems or pasturelands);

- may cause measurable adverse impacts to critical natural habitats;

- risk the introduction of alien and potentially invasive alien species;

- may negatively affect endangered species;

- involve the physical displacement of people;

- do not comply with construction norms and standards;

- involve the purchase, application or storage of harmful pesticides or hazardous materials;

- involve forced labour/harmful child labour; and

- involve the trade in wood or other forestry products from unmanaged forests.

The final activities to be funded will be selected based on the following performance criteria:

- the degree to which the activities address the adaptation needs identified in the KRB;

- cost-effectiveness;

- ease of implementation; and

- innovativeness.

## 3.3. Environmental and social assessment procedures of the ESMF

Under the ESMF, an Environmental and Social Impact Assessment (ESIA) is carried out to identify and predict impacts of proposed project activities. The process includes impact: i) screening and scoping; ii) mitigation; and iii) management, monitoring and evaluation.

The ESIA also defines the degree to which the future benefits of project activities will be distributed in an equitable manner across the targeted population and examines opportunities to: i) enhance social inclusion and accountability; ii) strengthen social cohesion; iii) increase social capital; and iv) build ownership as per AF principles. All interventions will be evaluated and screened against the 15 Environmental and Social (E&S) Principles of the AF, presented in Table 4.

Table 4. Adaptation Fund Environmental and Social Principles.

| Checklist No. | Environmental and Social Principle |
| --- | --- |
|  | Compliance with the Law |
|  | Access and Equity |
|  | Marginalised and Vulnerable Groups |
|  | Human Rights |
|  | Gender Equity and Women’s Empowerment |
|  | Core Labour Rights |
|  | Indigenous Peoples |
|  | Involuntary Resettlement |
|  | Protection of Natural Habitats |
|  | Conservation of Biological Diversity |
|  | Climate Change |
|  | Pollution Prevention and Resource Efficiency |
|  | Public Health |
|  | Physical and Cultural Heritage |
|  | Lands and Soil Conservation |

The purpose of the screening process is to: i) determine whether project activities are likely to have potential negative environmental and social impacts; ii) determine appropriate mitigation measures for activities with adverse impacts; iii) incorporate mitigation measures into project design; iv) review and approve project proposals; and v) monitor environmental parameters during project implementation.

Proposed project activities were evaluated against the above E&S Principles as well as the UNDP SESP. Results of the preliminary assessment of the project according to the UNDP SESP are listed below.

- Risk Assessment: Tentative Low.

- Categorisation: Tentative C (no expected adverse environmental and social impacts).

- Result: Requires a thorough environmental and social screening process to take place during the project formulation phase.

Activities under the project are not expected to cause any significant environmental or social impacts. However, project activities could have some adverse impacts regarding the E&S Principles of the AF in the context of the KRB. An overview of these impacts, as well as mitigation measures is provided in Table 5.

In addition, the following targeted assessments and mitigation/management measures are required for project activities:

- a gender assessment in the initial phase of the project to develop recommendations on how the project will promote women’s equality and empowerment;

- a marginalised and vulnerable groups assessment in the project inception phase to prioritise communities and groups for adaptation interventions;

- an ecological and land use assessment to evaluate the rate of success of forest restoration activities; and

- a pasture use assessment providing an indication of the degrees of degradation and over-grazing, as well as lessons learned from past successful pasture restoration projects across the country.

Table 5. Checklist of Environmental and Social Principles for the proposed project.

| Checklist of Environmental and Social Principles | Potential impacts and risks | Mitigation measures |
| --- | --- | --- |
| Compliance with the Law | N/A | Project activities will be undertaken in full compliance with the domestic laws of Tajikistan, as well as with all relevant international laws. |
| Access and Equity | Project activities could restrict availability and/or quality of, and access to, resources or basic services. Particularly for marginalised individuals or groups. | To address the potential limitations regarding gaining access to pasture lands and forests, activities under the project will promote alternative business solutions and community enterprise developments that will help communities to generate alternative incomes. The project will also address the need to reduce extensive livestock grazing through: i) enhanced fodder production techniques (within exclusion zones, rotational grazing, on-site production and demonstration plots); ii) productive on-site animal husbandry; and iii) the establishment of watering sites at mid-stream levels of watershed areas (saving livestock energy in search of water sources in the upstream). There will be widespread engagement with relevant stakeholders at regional, sub-regional and community levels to agree on rotational routes for the transit of larger herds. Such engagement will also facilitate monitoring of grazing control measures applied locally by large herd owners from other communities, districts and/or regions. Jamoat-level monitoring and control mechanisms will be introduced to enforce agreed-upon measures for the mitigation of land degradation and to improve vegetation growth in target pasture lands, as well as to ensure that target communities effectively benefit from project interventions. Energy-efficient stoves will also be introduced into target communities to compensate for the limited access to forest resources for energy. Best practices and lessons learned from similar past projects in Tajikistan will be adapted and applied to the Kofirnighan River Basin (KRB) context. The project will also support the implementation of long-term financing of an integrated catchment management strategy through Payment for Ecosystem Services (PES) models that will be developed for each target district. These models will further enable communities to access the finance required to undertake initiatives that strengthen and increase access to ecosystem services, as well as build climate resilience within each target district. The PES models will be designed based on a combination of regional, international and local best practices. PES model design will also be informed by the results of existing PES models used in Tajikistan. |
| Marginalised and Vulnerable Groups | Marginalised groups could potentially be excluded from fully participating in decisions that may affect them. | Marginalised groups in the KRB include those: i) living in areas exposed to increasing impacts of climate change; ii) food-insecure households; and iii) households with limited or no productive assets, livestock and/or agricultural land plots. Single female-headed households, and those with small children and/or elderly members may also be considered vulnerable. Such vulnerable groups have a limited ability to participate during critical stages of project design and implementation. During project inception phase, a vulnerability assessment of target communities will be carried out in a participatory manner, through focused consultations. Where feasible, vulnerable and marginalised groups will be prioritised for adaptation interventions. The Stakeholder Engagement Plan will guide consultations during preparation phases, ensuring the broad representation of relevant community-based organisations and groups. These organisations and groups include farming associations and cooperatives, women’s committees, intervention-related initiative groups, pasture development associations, water user associations (WUAs), forestry cooperatives and communal health promoters. Throughout the project, the extent of involvement of vulnerable and marginalised people within such groups and associations will be monitored and assessed. Targeted actions that may be prioritised for vulnerable groups may include on-farm adaptation interventions, household plots, improved productivity measures and the selection of demonstration plots with support from farmer field schools (FFSs). Certain enterprise developments and income-generating activities (such as beekeeping, fodder production and livestock productivity support) may also be suitable for the given groups to ensure that benefits are distributed inclusively and in an equitable manner. |
| Human Rights | N/A | Project activities will adhere to and, where applicable, promote international human rights. The project will directly benefit an estimated 50,000 individuals who are especially vulnerable to the impacts of climate change, through the design and implementation of on-the-ground EbA interventions for more efficient natural resources management. These measures will also provide social and economic benefits to the target population in terms of livelihoods, health and wellbeing. In particular, the project’s interventions will: i) increase profit margins and income from farming activities; ii) reduce crop losses as a result of slope instability, drought and dry spells, ineffective agricultural practices and overgrazing of livestock; iii) reduce agricultural inputs and water consumption; iv) reduce the risk of economic failure by diversifying on- and off-farm production; v) reduce the susceptibility of crops to pests; vi) increase food security; vii) increase availability of fuelwood and timber; and viii) increase pasture productivity and fodder production. In addition, project interventions will increase non-material benefits such as ecosystem services, tourism, recreation and the conservation value of the natural Tajikistan landscape. Throughout the implementation period, the project will seek to ensure that benefits are shared broadly, and in a non-discriminatory and equitable manner. The project will ensure that all relevant stakeholders participate in decision-making processes and consultations, and that such participatory processes are transparent. Necessary strategies, action plans, site selection criteria and lessons learned will be documented and shared regularly through community-driven consultation platforms facilitated by those implementing the project. |
| Gender Equity and Women’s Empowerment | Women may not be adequately represented with regard to decision-making or participation in the design and implementation of the project activities. As a result, women may have limited access to resources, opportunities and benefits. | Tajikistan has a relatively large Gender Inequality Index rating of 0.36, with women’s labour force participation representing ~59% of the female population, as opposed to men participation representing ~77% of the male population in the country. In rural Tajikistan, the relatively larger rates of labour migration among men typically leave women with large workloads, including formal employment to earn income, household and care responsibilities, and growing of food for household consumption. Project interventions will therefore ensure that women are actively included in stakeholder participation and take part in all decision-making processes. This will ensure that benefits are distributed equitably and fairly among men and women in target zones. In particular, project activities will be designed and implemented so that all genders are: i) able to participate fully and equitably; ii) receive comparable social and economic benefits; and iii) do not suffer disproportionate adverse effects as per the UNDP Gender Mainstreaming Strategy. A gender analysis will be undertaken in the initial phase of the project to develop recommendations on how project activities will promote women’s equality and empowerment, including participation in decision-making processes, as outlined in the ESMF. It is anticipated that at least 50% of project beneficiaries will be women. Appropriate measures will ensure that women receive an equitable share of benefits and that their status and interests are not marginalised. Participatory processes will include methodologies that enhance the participation of women and promote the inclusion of their views into the activities of the project. Monitoring of project outputs will include disaggregated and measurable data related to gender equality and empowerment of women. Furthermore, measures and techniques that contribute to closing the inequality gap between men and women will be promoted, where possible. |
| Core Labour Rights | N/A | Project activities will adhere to the core labour standards of Tajikistan, as well as those identified by the International Labour Organisation. |
| Indigenous Peoples | N/A | Project activities will be designed in accordance with the rights and responsibilities set forth in the UN Declaration on the Rights of Indigenous Peoples, as well as with all other applicable national and international instruments relating to indigenous people. |
| Involuntary Resettlement | N/A | Project activities will not lead to any involuntary resettlement of local communities. |
| Protection of Natural Habitats | N/A | Project activities will not involve any conversion or degradation of critical natural habitats, including those that are: i) legally protected; ii) officially proposed for protection; iii) recognised by authoritative sources to be of high conservation value; and iv) recognised as protected by traditional or indigenous local communities. |
| Conservation of Biological Diversity | There is a risk that alien and/or invasive alien species are used in reforestation activities. | The project’s activities will promote the rehabilitation/restoration of abandoned and overexploited forests and degraded forest ecosystems, as well as reforestation of areas adversely affected by extreme climate events. The use of native and climate-resilient varieties will be promoted, but alien species may be introduced if necessary. Certain alien species may be used for complementary planting (climate-resilient crops seed varieties) in areas being reforested to increase biological biodiversity and enhance climate resilience. Prior to such introduction, relevant experts at the Committee for Environmental Protection (CEP) and among development partner agencies will be consulted on successful examples across the regions. National environmental norms, standards and procedures for the introduction of alien species will be followed in each case. |
| Climate Change | N/A | Project activities will not result in a significant increase in GHG emissions or any other drivers of climate change. In contrast, project interventions directly support the implementation of climate change adaptation and mitigation measures, including climate-smart agriculture and sustainable land management in agro-ecological landscapes. Such interventions include: i) the rehabilitation and restoration of degraded forest ecosystems; ii) vegetation growth support; iii) water retention measures; and iv) climate-resilient crop seed planting. All of these interventions prevent and mitigate water-related extreme climate events that have typically threatened the livelihoods and health of target communities. |
| Pollution Prevention and Resource Efficiency | The application of pesticides may have a negative effect on the environment or on human health. | Local communities will be supported to adopt improved farming techniques, including organic agriculture, and soil and water conservation. These techniques would reduce the use of fertilisers and harmful pesticides. Although biological pest control is preferred, pesticides may be needed for specific use. In this case, they will be properly managed and stored, following national and international standards, regulations and procedures. Project activities will be designed and implemented in a way that meets applicable international standards for maximising energy efficiency while minimising material resource use, waste production and the release of pollutants. Interventions included in project design are not expected to produce any significant amounts of waste or other pollutants. Any potential opportunities identified for improved resource efficiency and pollution reduction during the project development phase will be captured in the project design. |
| Public Health | Small-scale construction activities under the proposed project may pose safety risks to community members implementing them. | All construction activities will follow the relevant environmental impact assessment procedures and will ensure compliance with: i) national construction standards and norms; ii) sanitary norms and regulations; and iii) all relevant national laws and regulations related to forestry, water, environment, and health. Activities will also follow technical guidance and best practices regarding rainwater-harvesting systems, drip-irrigation techniques, and micro-reservoirs. Other project activities may include the construction of gabions, terracing, bank enforcement and small dams. Best practices and lessons learned from other previous and ongoing projects in Tajikistan will be used to address community safety risks from such construction. |
| Physical and Cultural Heritage | During project implementation, there is a risk that physical or cultural heritage sites are disturbed. | Project activities will be designed and implemented in a way that avoids the alteration, damage or removal of any physical cultural resources and sites, as well as any sites recognised as having unique value at the community, national or international level. Regional experts will be consulted to ensure compliance with national heritage legislation and that project design adheres to best-practice guidelines. |
| Lands and Soil Conservation | N/A | Activities under the project will promote soil conservation, while avoiding the degradation and conversion of productive land or land that provides valuable ecosystem services. Specifically, through the implementation of EbA measures under Component 2, soil stability will be increased, runoff of nutrients from topsoil will be reduced and soil horizons at project sites with sheet and/or gulley erosion will be restored. |

## 3.4. Management measures

The Project Management Committee (PMC), along with primary stakeholders, will develop monitoring and evaluation systems and plans that will be used at all sites. Appropriate environmental and social indicators will be developed within the framework of the ESMP. Regular monitoring and evaluation will take place for each of the community-based adaptation interventions implemented in the KRB under Component 2. This will be undertaken by extension officers and local government officials at each of the project intervention sites. In addition, members of the National Project Team will undertake a mid-term review and a terminal evaluation of the proposed project’s activities. The results of the environmental and social risk mitigation will be evaluated by the PCU, comparing baseline data collected in the planning phases with targets and post-project outcomes.

In the event of any occurrences which may result in serious health, safety and environmental damage, emergency response or contingency actions will be implemented as soon as possible to limit the extent of the damage. Administration of project deliverables will need to incorporate emergency responses into the project which comply with the requirements under the Occupational, Health and Safety Policy of relevant national legislation.

The following performance criteria are set for project construction activities:

- no failure of water-retaining structures;

- no major chemical hazards;

- provision of an immediate and effective response to incidents that represent a risk to public health, safety or the environment; and

- minimisation of environmental harm due to unforeseen incidents.

Responsible authorities and UNDP staff must be notified immediately in the event of any emergency, including any health-related matter, and any incident that has resulted in serious damage to the environment.

# Stakeholder engagement plan

## Project stakeholders

A wide range of stakeholders were consulted with during the scoping and validation phase of proposed project development. Importantly, the project’s Executing Entity, the CEP, was consulted through the iterative process of refining the project design. As the national organisation responsible for implementing adaptation projects in the country, the CEP is comprised of numerous technical experts. Therefore, the CEP is well-positioned to ensure that the project design is tailored to local requirements, that it benefits vulnerable groups and includes necessary gender considerations.

A Validation Workshop was held in Dushanbe on 22 June 2018 that included representatives from relevant KRB districts, international organisations, academia and partner projects. The primary stakeholders that will be involved in the implementation of the project are detailed in Part II: H of the Full Proposal, while a complete list of all participants present at the workshop is included in Annex 1 of the Full Proposal.

## Stakeholder Engagement Programme

The Stakeholder Engagement Program (SEP) will establish the procedures for ensuring consultation and engagement with stakeholders during the development of action plans. It will also ensure that environmental and social impacts associated with specific project activities are monitored, and that all information disclosure requirements are met. The National Project Coordinator is responsible for facilitating stakeholder engagement activities, with support from the PMU and with additional technical assistance provided through the project if needed.

A team comprised of representatives from the UNDP, CEP and the MoEWR will develop and release project-related information to communities, organisations and municipalities where the project is implementing its activities. In order to do so, the project will make use of: i) newspapers; ii) local radio podcasts; iii) local television; iv) brochures and leaflets; v) non-technical summary documents; and vi) technical reports.

The UNDP SESP will be made available to project stakeholders during the project inception phase, and the final SESP will be made available upon approval. If site-specific, targeted environmental and social assessments are required, the draft assessment and findings, including specific management measures, will be made available to project stakeholders for public comment. Final assessments and plans will be disclosed upon completion. Stakeholders will be notified of the availability of draft and final documents.

The SEP will promote participatory processes, joint decision-making, and partnerships among local communities, NGOs, and local governments. The participation of marginalised groups such as women, youth and the elderly will be specifically promoted to enhance the inclusion of their views. Exchange visits, inter-agency collaboration, and training and capacity-building initiatives will also be supported. Stakeholder engagement activities will take place throughout the project’s lifespan and in a wide range of locations within the KRB. The two main stakeholder engagement workshops will be during the inception and the final phases of project implementation, where all relevant stakeholders will have the opportunity to participate and to be informed about the project outcomes.

## Annex 5. Grievance mechanism

When necessary, UNDP will ensure that an effective project-level grievance mechanism is available. The mandate and functions of a project-level grievance mechanism will be executed either by the Project Management Committee (PMC) or through an Implementing Partner’s existing grievance mechanisms and procedures for addressing stakeholder concerns. Where needed, UNDP and Implementing Partners will strengthen the Implementing Partners’ capacities to address Project-related grievances.

Project-level grievance mechanisms and UNDP’s Stakeholder Response Mechanism will address concerns promptly through dialogue and engagement, using an understandable and transparent process that is culturally appropriate, rights compatible, and readily accessible to all stakeholders at no cost and without retribution. They will be gender- and age-inclusive and responsive and address potential access barriers to women, the elderly, the disabled, youth and other potentially marginalized groups as appropriate to the Project. These grievance mechanisms and Stakeholder Response Mechanism will not impede access to judicial or administrative remedies as may be relevant or applicable.

Ongoing reporting to affected communities and individuals

For projects with potentially significant risks and impacts, UNDP will ensure that periodic reports are provided to the affected communities that describe progress with implementation of project management and action plans and on issues that the consultation process or grievance mechanism has identified as a concern. Any material changes or additions to the mitigation measures or actions plans will be communicated to affected communities. Reports will be provided at a frequency proportionate to the concerns of affected communities but not less than annually.

## Annex 6. Hydromet list of needs for the repair and rehabilitation of weather stations

Hydrological stations presented for restoration:

- Kofirnighan River – Tartki;

- Kofirnighan River – Chinar; and

- Sardai-miyona River – Romit.

Hydrometric crossing

Hydrometric crossing (SEBA) is designed for the implementation of hydrometric operations on rivers up to 250 meters wide and flow velocity up to 5.0 m/s. The hydrometric crossing should provide a measurement of the flow velocity, depth and width of the flow and the sampling of water turbidity with remote control from the shore.

The minimum requirements for the hydrometric crossing are as follows:

- strain of the supporting and towing cables with the help of tightening screw couplings; and

- a maximum load of 150 kg.

The minimum requirements for hydrometric crossing are as follows:

- cable system;

- carriages for roller;

- roller block;

- observation booths;

- electric double-drum winch; and

- ancillary equipment.

Cable system

The rope system should include at minimum the following:

- supporting cable with a diameter of 20-24 mm;

- towing cable for horizontal movement of carriage rollers with a diameter of 6 mm (at least);

- suspension cable with a conductive wire for vertical displacement of a gauging load with a diameter of at least 3.25 mm; and

- a set of coastal support.

Roller carriage

The roller carriage is designed to move the gauging weight along the Carrier Cable #3. It is a solid construction with rubberised rollers and ball bearings.

Roller block

The roller block is designed for operation of a tow rope with a cable voltage of 21/2 – to prevent the cable from slipping.

Observer cabin

The observer's cabin must meet the following minimum requirements.

- Material: steel 4–5 mm.

- Dimensions: width – not less than 180 cm; length – not less than 300 cm; height – not less than 230 mm.

- Double-leaf metal door with lock.

- Holes for wiring of the tow rope and the hanging rope.

The Electric double-drum winch and the Control Panel should be located in the Observer's Cabin.

Electric double-drum winch

The electric double-drum winch is designed for horizontal and vertical movement of the gauging weight and must meet the following requirements.

- Electric motor: 3-step motor (1.5 kW, 380 V, 3 different speeds – 13.26 and 53 cm/s) or adjustable motor (1.5 kW, 220 V AC, adjustable speed from 0 to about 50 cm/sec; it is possible to work with a generator.

- Ability to work with a safe handle in the absence of electricity.

- Equipment electric clutch switch for switching the direction of work from horizontal to vertical (lifting and lowering).

- Block of horizontal and vertical displacement counters, which includes a combined (automatic/mechanical) meter for measuring distance (river width) with 5 digits and a counter for measuring the depth with 4 digits.

- Indicator of the drift angle of the suspended turntable.

- Work side: right.

- Maximum loading: 100 kg.

Remote Control

On the Control Panel, all controls, alarms, an electric pulse counter and a stopwatch must be placed.

The control panel should, at a minimum, include the following.

- 1 (one) measuring unit must meet the following requirements:

  - range of measured revolutions: 1–3000;

  - measurement interval: 60–300 s;

  - range of calculation of the water flow rate: 0.01–5 m/s;

  - degree of protection IP40; and

  - electrical supply.

- 1 (one) surface and bottom contact adapter must meet the following minimum requirements:

  - indication of the operation of the Flowmeter (p.);

  - indication of the operation of the bottom contact of the Flowmeter;

  - indication of the operation of the surface contact of the Flowmeter;

  - toggle switch for surface contact of the Flowmeter;

  - terminals for connection of the Measuring unit;

  - terminals for connecting the signal conductors of a rope with a conductive wire;

  - stopwatch;

  - electrical supply.

- 1 (one) table for recording observations in size: width and length – not less than 50 cm; height – not more than 75 cm.

Specific technical characteristics of the Control Panel should be offered by the Contractor depending on its technical solution.

Auxiliary equipment

The auxiliary equipment kit should include:

hydrometric load (SEBA) 50/75 100 kg; and

flow velocity meter (SEBA).

## Annex 7. UNDP Social and Environmental Screening Procedure (SESP)

The completed template, which constitutes the Social and Environmental Screening Report, must be included as an annex to the Project Document. Please refer to the Social and Environmental Screening Procedure and Toolkit for guidance on how to answer the 6 questions.

Project Information

| Project Information |  |
| --- | --- |
| - Project Title | An integrated landscape approach to enhancing the climate resilience of small-scale farmers and pastoralists in Tajikistan |
| - Project Number | 00111538 |
| - Location (Global/Region/Country) | Tajikistan |

Part A. Integrating Overarching Principles to Strengthen Social and Environmental Sustainability

QUESTION 1: How Does the Project Integrate the Overarching Principles in order to Strengthen Social and Environmental Sustainability?

Briefly describe in the space below how the Project mainstreams the human-rights based approach

Tajikistan is the most vulnerable country to climate change in Central Asia. The negative effects of climate change on the Tajik population include glacial and permafrost melt, increased rainfall intensity as well as longer and more frequent dry spells. Together, these effects have increased the rate of topsoil erosion, which has threatened the livelihoods, health and wellbeing of the local population. The costs of the losses caused by extreme climate events currently amount to ~20% of the country’s GDP. Together, the impacts of climate change are predicted to increase the costs of such losses, where costs are expected to rise from ~US$50 million in 2014 to ~US$132 million by 2030. Approximately 33% of all agricultural losses in the country are currently attributable to climate change and variability. Furthermore, it has been projected that crop yields in Tajikistan will decrease by an additional 5–30% by 2050, with the potential for severe impacts on the country’s economy. Moreover, by 2050, ~77% of the country’s population will be living in areas most exposed to the impacts of climate change. Tajikistan’s vulnerabilities are attributed to the country’s weak social structures, low adaptive capacity, underdeveloped infrastructure, low income insecurity, poor service provision, strong dependence on agriculture and institutional constraints. To address the above-described challenges, the project activities will support Tajikistan’s authorities to enhance the climate resilience of small-scale farmers and pastoralists of the Kofirnighan River Basin (KRB). Improving the climate resilience of these communities will involve developing an integrated catchment management strategy to inform the climate-resilient planning and development of rural areas. Interventions will also promote the sustainable management of natural resources through an integrated landscape approach to catchment management. The project will directly benefit an estimated 50,000 individuals who are especially vulnerable to the impacts of climate change, through the design and implementation of on-the-ground EbA interventions for more efficient natural resources management. These measures will also provide social and economic benefits to improve the population’s livelihoods, health and wellbeing. In particular, the project’s interventions will have the following social and economic benefits for the population of the KRB: i) increased profit margins and farm income; ii) reduced losses of crops and land caused by slope instability, drought or dry spells; iii) reduced agricultural inputs, water consumption and thus production costs; iv) reduced risk of economic failure in response to diversifying both on- and off-farm production; iv) reduced crop susceptibility to pests; v) increased nutrition and food security for local communities; vi) increased provision of fuelwood and timber and to reduce the losses of trees following droughts and dry spells; and vii) increased pasture productivity, fodder production and carrying capacity. In addition, project interventions will increase non-material benefits to the population such as ecosystem services (including tourism and recreation) derived from the improved conservation value of landscapes. Throughout the implementation period, the project will seek to ensure that benefits are shared equitably, in a non-discriminatory manner. The project will ensure that all relevant stakeholders participate in decision-making processes and consultations, and that such participatory processes are transparent. All of the necessary strategies, action plans, site selection criteria and lessons learned will be documented and shared regularly through community-driven consultation platforms that the project will seek to facilitate. A wide range of stakeholders were consulted with during the scoping and validation phase of project development. Importantly, the project’s Executing Entity, the Committee for Environmental Protection (CEP), was consulted through the iterative process of refining the project design. As the national organisation responsible for implementing adaptation projects in the country, CEP is comprised of numerous technical experts. Therefore, CEP is well-positioned to ensure that the project design is tailored to local requirements, that it benefits vulnerable groups and includes necessary gender considerations. A Validation Workshop was held in Dushanbe on 22 June 2018 that included representatives from relevant KRB districts, international organisations, academia and partner projects. For a complete list of validation workshop participants and stakeholders consulted with during the development of the Concept and Full Proposal, please see the annexures of the Full Proposal.

Briefly describe in the space below how the Project is likely to improve gender equality and women’s empowerment

Tajikistan has a relatively large Gender Inequality Index rating of 0.36, with women’s labour force participation representing ~59% of the female population, as opposed to men participation representing ~77% of the male population in the country. In addition, higher rates of urban labour migration in men results in the rural women left behind having to take responsibility for: i) employment for income; ii) household and care; and iii) growing food for consumption. The project will ensure that women take part in the decision-making processes to enable benefits to be distributed equitably and fairly among men and women in the target zones. Project activities will be designed and implemented so that all genders: i) are able to participate fully and equitably; ii) will receive comparable social and economic benefits; and iii) do not suffer disproportionate adverse effects as per UNDP Gender Mainstreaming Strategy. The project anticipates that at least 50% of beneficiaries will be women. All necessary provisions will be made to ensure that women are able to represent their interests effectively. In addition, all social impact indicators and corresponding targets of the project will be gender-sensitive, ultimately ensuring that women receive an equitable share of benefits and that their statuses and interests are not marginalised.

Briefly describe in the space below how the Project mainstreams environmental sustainability

Project components have been designed to ensure the sustainability and replicability of project benefits in the long term. Specifically, project sustainability will be supported through: i) emphasising the active participation of relevant regional, national and district level stakeholders in decision-making and implementation of project activities; ii) strengthening institutional and technical capacity at the raion and jamoat levels to ensure that stakeholders have adequate knowledge and skills to maintain the benefits of project EbA interventions; and iii) raising awareness of the benefits of integrated catchment management practices, including EbA, CSA and SLM activities, at the village level. Particular aspects of the project’s sustainability are outlined below. - Developing the capacities for catchment management which will be informed by climate risks. Multi-hazard climate risks models (MHCRMs) will be developed for the target river basin (namely, Kofirnighan River Basin) that will inform future planning to develop climate resilience. Such models will be replicable for other catchments across the country. Payment for ecosystems services (PES) models will also be developed to strengthen the sustainability of project interventions ensuring sustainable financing for climate-resilient management and EbA. - Training agro-ecological extension staff and developing extension services to local communities. Generally, EbA interventions require less maintenance than non-EbA alternatives and such maintenance can usually be conducted by unskilled labourers. As a result, the proposed interventions will be more likely to be maintained than non-EbA alternatives. - Providing extensive support to knowledge management centres to ensure that climate information, as well as lessons learned, are accessible for decision makers and local communities. The impact evaluation framework (under Output 3.2) will enable adaptive management on project interventions and will enable the accurate attribution of EbA benefits. This will help to demonstrate the cost-effectiveness of EbA, thereby promoting its utility in developing climate resilience in communities across Tajikistan.

Part B. Identifying and Managing Social and Environmental Risks.

| QUESTION 2: What are the Potential Social and Environmental Risks? Note: Describe briefly potential social and environmental risks identified in Attachment 1 – Risk Screening Checklist (based on any “Yes” responses). If no risks have been identified in Attachment 1 then note “No Risks Identified” and skip to Question 4 and Select “Low Risk”. Questions 5 and 6 not required for Low Risk Projects. | QUESTION 3: What is the level of significance of the potential social and environmental risks? Note: Respond to Questions 4 and 5 below before proceeding to Question 6 |  |  | QUESTION 6: What social and environmental assessment and management measures have been conducted and/or are required to address potential risks (for Risks with Moderate and High Significance)? |  |
| --- | --- | --- | --- | --- | --- |
| Risk description | Impact and Probability (1-5) | Significance (Low, Moderate, High) | Comments on risk of activity | Description of assessment and management measures as reflected in the Project design (if ESIA or SESA is required note that the assessment should consider all potential impacts and risks) |  |
| Risk 1: Principle 1 (Q3). Project activities could potentially restrict availability of, quality of and access to resources or basic services, particularly for marginalized individuals or groups. | I: 3 P: 3 | Moderate | Changes in pasture and livestock management practices and reforestation measures (grazing control, rotational grazing, livestock exclusion zones and reforestation) may limit the availability of/accessibility to some basic services. | To address the short-term limitations of gaining access to pasture lands and forests, the project will promote alternative business solutions and community enterprise developments that will help communities to generate alternative incomes. The project will also address the need to reduce extensive livestock grazing through enhanced fodder production techniques (within exclusion zones, rotational grazing, on-site production, demonstration plots, etc), productive on-site animal husbandry, and establishment of watering sites at mid-stream levels of catchment/watershed areas (saving livestock energy in search of water sources in the upstream). The project will engage widely with relevant stakeholders at regional, sub-regional and community levels to agree on rotational routes for the transit of larger herds, as well as to monitor grazing control measures applied locally by large herd owners from other communities, districts and/or regions. Jamoat-level monitoring and control mechanisms will be introduced to enforce agreed-upon measures for the mitigation of land degradation and to improve vegetation growth in target pasture lands, as well as to ensure that target communities effectively benefit from project interventions. Energy-efficient stoves will also be introduced into target communities to compensate for the limited access to forest resources for energy. Best practices and lessons learned from similar past projects in Tajikistan will be adapted for and applied to the Kofirnighan River Basin (KRB) context. The project will also support the implementation of the long-term financing of an integrated catchment management strategy through PES models that will be developed for each target district. These models will further enable the financing to undertake initiatives that strengthen ecosystem services and build climate resilience with each target district and community. The PES models will be designed based on a combination of regional, international and local best practices. The design will also be informed by the results of existing PES models made use of in Tajikistan. Such models will be accessed through the knowledge hubs that proposed project is supporting (under Outcome 3). |  |
| Risk 2: Principle 1 (Q4). Marginalised groups could potentially be excluded from fully participating in decisions that may affect them. | ## I: 3 P: 2 | Moderate | Local stakeholders, in particular poor and vulnerable groups, may be limited in their abilities to participate effectively in decision making. | Marginalised groups in the KRB include those living in places with increased impacts of climate change, food insecure households, households with limited or no productive assets (limited resilience), livestock and/or agricultural land plots. Such vulnerable groups have the limited ability to participate during key stages of project design and implementation. During the project’s inception phase, a vulnerability assessment of target communities will be carried out in a participatory manner. Where feasible, vulnerable and marginalised groups will be prioritised for adaptation interventions. The Stakeholder Engagement Plan will guide such consultations during preparation phases, ensuring the broad representation of existing relevant community-based organisations and groups. These organisations and groups involve inter alia farming associations and cooperatives, women’s committees, intervention-related initiative groups, pasture development associations, water user associations (WUAs), forestry cooperatives and communal health promoters. The project will monitor and assess the extent of involvement of vulnerable and marginalized within such groups and associations. The targeted actions that will be prioritised and deemed suitable for vulnerable groups may include on-farm adaptation interventions, household plots, improved productivity measures and the selection of demonstration plots with support from farmer field schools. Certain enterprise developments and income-generating activities (such as bee keeping, fodder production, livestock productivity support) may also be suitable for the given groups to ensure that benefits are distributed inclusively and in an equitable manner. |  |
| Risk 3: Principle 1 (Q5). National and regional authorities may not have the capacity to meet their obligations to the project. | I: 3 P: 5 | Moderate | The capacities of national institutions and district authorities may not be sufficient to provide effective governance solutions to climate problems that are complex and multi-sectoral. | The project design includes dedicated components for capacity-building actions (Component 1), knowledge building and sharing at national, regional, local and community levels (Component 1 and 3). These actions are based on analyses of institutional frameworks and capacities which were carried out during project preparation. At the national level, focal institutions will be strengthened through participatory development of integrated catchment management strategies and Watershed Action Plans (WAPs) for the KRB. Coordination and training mechanisms will be strengthened within target jamoats (sub-district government level), which include capacity-building for the mainstreaming of integrated catchment management into planning and budgetary processes. Training will also target relevant government institutions involved in catchment and watershed management, including the Committee for Environmental Protection (CEP) and Ministry of Energy and Water Resources (MEWR). The project’s activities will contribute to river basin development and planning processes through integrating catchment management strategies and watershed action plans with EbA-related interventions. This will occur within the frameworks of the KRB Management Plan under the leadership of the MEWR, as well as the GoT Water Reform Programme. The use of these existing frameworks will contribute to building capacities of relevant national and district authorities. |  |
| Risk 4: Principle 2 (Q2). Gender-based discrimination may be replicated, especially regarding women’s participation in project design and implementation, as well as access to opportunities and benefits. | ## I: 3 P: 4 | Moderate | Women may not be adequately represented with regards to decision-making or participation in the design/implementation of the project's activities. As a result, they may have limited access to resources, opportunities and benefits. | Project activities will be designed and implemented so that all genders: i) are able to participate fully and equitably; ii) receive comparable social and economic benefits; and iii) do not suffer disproportionate adverse effects as per the UNDP Gender Mainstreaming Strategy. A gender analysis will be undertaken in the initial phase of project inception to assess divisions of labour and the role of women and their access to resources. The analysis will also develop recommendations as to how the project’s activities will promote women’s equality and empowerment, including participation in project decision-making, as outlined in the ESMF. Appropriate measures will ensure that women receive an equitable share of benefits and that their status and interests are not marginalised. Participatory processes will include methodologies that enhance the participation of women and promote the inclusion of their views into the activities of the project. Monitoring of project outputs will include disaggregated and measurable data related to gender equality and empowerment of women. Furthermore, measures and techniques that contribute to closing the inequality gap between men and women will be promoted, where possible. |  |
| Risk 5: Standard 1 (Q1.5). Regarding reforestation activities, alien and invasive alien species may be used. | ## I: 2 P: 1 | Low | Through reforestation and rehabilitation efforts, alien and invasive species will be introduced to ecologically sensitive regions that will damage the ecosystems. | The project’s activities will promote the rehabilitation/restoration of abandoned and overexploited forests and degraded forest ecosystems, as well as reforestation of areas adversely affected by extreme climate events. The use of native and climate-resilient varieties will be promoted, but alien species may be introduced if necessary. Certain alien species may be used for complementary planting (climate-resilient crops seed varieties) in areas being reforested to increase biological biodiversity and enhance climate resilience. Prior to such introduction, relevant experts at the CEP and among development partner agencies will be consulted on successful examples across the regions. National environmental norms, standards and procedures for the introduction of alien species will be followed in each case. |  |
| Risk 6: Standard 1 (Q1.6). Involving reforestation activities in degraded forest areas may promote communities to exploit newly-established forest resources through over-harvesting. | I: 3 P: 2 | Low | Project activities are targeted in areas that will include community-managed forest areas. This means that harvesting of forest resources for fuelwood and timber is currently taking place. This may cause the interventions under the project to be threatened. | Although harvesting of forest resources for fuelwood has generally declined across Tajikistan because of increased access to electricity supply, the financial implications of using electricity may lead to relatively poor households continuing to harvest forest materials. The project activities will target such communities where harvesting practices continue. Implementation of project activities will prevent and mitigate extensive harvesting practices through an awareness campaign aimed at communities at jamoat and district levels, as well as introduce measures to contain harvesting practices within healthy forest ecosystems (‘sustainable’ harvesting). Communities will be actively engaged in joint forest management activities, including: i) planting woodlots for fuelwood and timber; ii) implementing agroforestry techniques such as bee keeping and fodder production; and iii) establishing commercial plantations in salinised and degraded lands. Training will be provided for communities on suitable fuelwood plantations, fast-growing tree species and sustainable use of forest resources. Communities will also be supported in establishing commercial fruit tree plantations and will be provided with energy-efficient eco-stoves to further reduce the use of wood for fuel. The abovementioned measures and techniques will be incorporated into the forestry and integrated catchment management strategies to be developed under the project. |  |
| Risk 7: Standard 2 (Q2.2). Some expected outcomes of the project, particularly under the forest restoration component, are sensitive to potential impacts of climate change. | I: 3 P: 2 | Moderate | The project’s activities are directly addressing climate change vulnerabilities and adaptation capacities of communities living in the KRB. While it directly promotes adaptation measures, adverse impacts of extreme climate events (particularly flooding and water run-off) can affect forest and agricultural areas, as well as related livelihoods. | The project’s activities directly support the implementation of EbA, including climate-smart agriculture and sustainable land management in agro-ecological landscapes. Such measures include: i) the rehabilitation and restoration of degraded forest ecosystems; ii) vegetation growth support; iii) water retention measures; and iv) climate-resilient crop planting. These measures will prevent and mitigate the adverse effects of water-related extreme climate events that have typically threatened the livelihoods and health of target communities. The project also aims to build climate resilience through the development of a catchment management strategy to manage climate risks at district and jamoat levels in the KRB. As part of an Early Warning System, multi-hazard climate risk models (MHCRM) will be developed for vulnerable watersheds in the KRB and technical support for the modernisation of automated weather stations will be provided in the most vulnerable districts of the KRB. These will help authorities and communities to adequately assess risks and climate projections, incorporating them into the Kofirnighan River Basin Management Plan and assisting in making informed decisions surrounding EbA activities. |  |
| Risk 8: Standard 3 (Q3.1). Small-scale construction activities under the proposed project may pose safety risks to community members implementing them. | I: 3 P: 1 | Low | The EbA measures selected for the project may involve the construction of: i) water-saving irrigation systems; ii) rainwater-harvesting systems; and iii) rehabilitation of irrigation, draining and pumping systems. These construction activities may pose safety risks to the individuals implementing them. | All construction activities will follow the relevant environmental impact assessment procedures and will ensure compliance with: i) national construction standards and norms; ii) sanitary norms and regulations; and iii) all relevant national laws and regulations related to forestry, water, environment, and health. Activities will also follow technical guidance and best practices regarding rainwater-harvesting systems, drip-irrigation techniques, and micro-reservoirs. Other project activities may include the construction of gabions, terracing, bank enforcement and small dams. Best practices and lessons learned from other projects will be used to address community safety risks from such construction. |  |
| Risk 9: Standard 7 (Q7.4). The application of pesticides may have a negative effect on the environment or on human health. | I: 3 P: 1 | Low | Pest control measures and agricultural support may involve the use of pesticides which could be harmful to human health or the health of the environment. | As noted in the ESMF, project activities will facilitate the adoption of improved farming techniques among communities, including organic agriculture, and soil and water conservation. These techniques would reduce the use of fertilisers and harmful pesticides, thus reducing the potential for the contamination of soil and water bodies. Communities will be trained on these techniques with the technical support of agro-ecological extension services at the jamoat level. If potentially harmful pesticides are needed and will be used, they will be properly managed and stored, following national and international standards, regulations and procedures. |  |
|  | QUESTION 4: What is the overall Project risk categorization? |  |  |  |  |
|  | Select one (see SESP for guidance) |  |  | Comments |  |
|  | Low Risk |  |  | X | Project activities are designed to support the incorporation of EbA measures into the Kofirnighan River Basin Management Plan and catchment/watershed management strategies to enhance climate resilience of the most vulnerable communities in the KRB. Although the project will not contribute to any adverse environmental impacts, the occurrence of extreme climatic events (e.g. flooding, landslides, mudflows) may compromise certain activities supported by the project. A risk management plan and a monitoring and evaluation plan are provided by the project to mitigate potential negative environmental impacts. It is therefore expected that the project will result in overall positive environmental and social impacts. |
|  | Moderate Risk |  |  | ☐ | N/A |
|  | High Risk |  |  | ☐ | N/A |
|  | QUESTION 5: Based on the identified risks and risk categorization, what requirements of the SES are relevant? |  |  |  |  |
|  | Check all that apply |  |  | Comments |  |
|  | Principle 1: Human Rights |  |  | X | The project design includes a component (Component 3) with an extensive set of capacity-building actions, as well as knowledge-building and sharing activities at national, regional, local and community levels. Coordination and training mechanisms will be strengthened within target jamoats (sub-district government level), which include capacity-building for mainstreaming integrated catchment management into planning and budgetary processes. |
|  | Principle 2: Gender Equality and Women’s Empowerment |  |  | X | Project activities will be designed and implemented so that all genders: i) are able to participate fully and equitably; ii) receive comparable social and economic benefits; and (iii) do not suffer disproportionate adverse effects as per the UNDP Gender Mainstreaming Strategy. A gender analysis will be carried out during the project development phase to ensure this. The design of project activities will ensure that women receive an equitable share of benefits and that their status and interests are not marginalised. Participatory processes will ensure the participation of women and include their views in the activities of the project. |
|  | 1. Biodiversity Conservation and Natural Resource Management |  |  | X | The project will promote activities in environmentally sensitive areas, but will reduce negative impacts in these areas, resulting in a net positive impact. |
|  | 2. Climate Change Mitigation and Adaptation |  |  | X | Although the project directly supports adaptation actions, adverse impacts of extreme climate events (particularly flooding, water run-off, landslides, mudflows, and drought) may affect forest ecosystems, agricultural areas and related livelihoods. |
|  | 3. Community Health, Safety and Working Conditions |  |  | ☐ | N/A |
|  | 4. Cultural Heritage |  |  | ☐ | N/A |
|  | 5. Displacement and Resettlement |  |  | ☐ | N/A |
|  | 6. Indigenous Peoples |  |  | ☐ | N/A |
|  | 7. Pollution Prevention and Resource Efficiency |  |  | X | Project activities have been designed and will be implemented in a way that aligns with international standards for maximising energy efficiency and minimising material resource use. They will also minimise the production of waste materials and the release of pollutants. Project interventions are not expected to produce any significant amounts of waste or other pollutants. Any potential opportunities identified for improved resource efficiency and pollution reduction during the project development phase will be captured in the project design. Project interventions will provide support to communities for adopting improved farming techniques (e.g. organic agriculture, more resilient crop varieties) that would reduce the use of fertilisers and pesticides. Although biological pest control is preferred, potentially harmful pesticides may be needed for specific use. In this case, they will be properly managed, stored and used, following national and international standards, regulations and procedures. |

### SESP Attachment 1. Social and Environmental Risk Screening Checklist

| Checklist Potential Social and Environmental Risks |  |
| --- | --- |
| Principles 1: Human Rights | Answer (Yes/No) |
| 1. Could the Project lead to adverse impacts on enjoyment of the human rights (civil, political, economic, social or cultural) of the affected population and particularly of marginalized groups? | No |
| 2. Is there a likelihood that the Project would have inequitable or discriminatory adverse impacts on affected populations, particularly people living in poverty or marginalized or excluded individuals or groups? | No |
| 3. Could the Project potentially restrict availability, quality of and access to resources or basic services, in particular to marginalized individuals or groups? | Yes |
| 4. Is there a likelihood that the Project would exclude any potentially affected stakeholders, in particular marginalized groups, from fully participating in decisions that may affect them? | Yes |
| 5. Is there a risk that duty-bearers do not have the capacity to meet their obligations in the Project? | Yes |
| 6. Is there a risk that rights-holders do not have the capacity to claim their rights? | No |
| 7. Have local communities or individuals, given the opportunity, raised human rights concerns regarding the Project during the stakeholder engagement process? | No |
| 8. Is there a risk that the Project would exacerbate conflicts among and/or the risk of violence to project-affected communities and individuals? | No |
| Principle 2: Gender Equality and Women’s Empowerment |  |
| 1. Is there a likelihood that the proposed Project would have adverse impacts on gender equality and/or the situation of women and girls? | No |
| 2. Would the Project potentially reproduce discriminations against women based on gender, especially regarding participation in design and implementation or access to opportunities and benefits? | Yes |
| 3. Have women’s groups/leaders raised gender equality concerns regarding the Project during the stakeholder engagement process and has this been included in the overall Project proposal and in the risk assessment? | No |
| 4. Would the Project potentially limit women’s ability to use, develop and protect natural resources, taking into account different roles and positions of women and men in accessing environmental goods and services? For example, activities that could lead to natural resources degradation or depletion in communities who depend on these resources for their livelihoods and well being | No |
| Principle 3: Environmental Sustainability: Screening questions regarding environmental risks are encompassed by the specific Standard-related questions below |  |
| Standard 1: Biodiversity Conservation and Sustainable Natural Resource Management |  |
| 1.1 Would the Project potentially cause adverse impacts to habitats (e.g. modified, natural, and critical habitats) and/or ecosystems and ecosystem services? For example, through habitat loss, conversion or degradation, fragmentation, hydrological changes | No |
| 1.2 Are any Project activities proposed within or adjacent to critical habitats and/or environmentally sensitive areas, including legally protected areas (e.g. nature reserve, national park), areas proposed for protection, or recognized as such by authoritative sources and/or indigenous peoples or local communities? | No |
| 1.3 Does the Project involve changes to the use of lands and resources that may have adverse impacts on habitats, ecosystems, and/or livelihoods? (Note: if restrictions and/or limitations of access to lands would apply, refer to Standard 5) | No |
| 1.4 Would Project activities pose risks to endangered species? | No |
| 1.5 Would the Project pose a risk of introducing invasive alien species? | Yes |
| 1.6 Does the Project involve harvesting of natural forests, plantation development, or reforestation? | Yes |
| 1.7 Does the Project involve the production and/or harvesting of fish populations or other aquatic species? | No |
| 1.8 Does the Project involve significant extraction, diversion or containment of surface or ground water? For example, construction of dams, reservoirs, river basin developments, groundwater extraction | No |
| 1.9 Does the Project involve utilization of genetic resources? (e.g. collection and/or harvesting, commercial development) | No |
| 1.10 Would the Project generate potential adverse transboundary or global environmental concerns? | No |
| 1.11 Would the Project result in secondary or consequential development activities which could lead to adverse social and environmental effects, or would it generate cumulative impacts with other known existing or planned activities in the area? For example, a new road through forested lands will generate direct environmental and social impacts (e.g. felling of trees, earthworks, potential relocation of inhabitants). The new road may also facilitate encroachment on lands by illegal settlers or generate unplanned commercial development along the route, potentially in sensitive areas. These are indirect, secondary, or induced impacts that need to be considered. Also, if similar developments in the same forested area are planned, then cumulative impacts of multiple activities (even if not part of the same Project) need to be considered. | No |
| Standard 2: Climate Change Mitigation and Adaptation |  |
| 2.1 Will the proposed Project result in significant greenhouse gas emissions or may exacerbate climate change? | No |
| 2.2 Would the potential outcomes of the Project be sensitive or vulnerable to potential impacts of climate change? | Yes |
| 2.3 Is the proposed Project likely to directly or indirectly increase social and environmental vulnerability to climate change now or in the future (also known as maladaptive practices)? For example, changes to land use planning may encourage further development of floodplains, potentially increasing the population’s vulnerability to climate change, specifically flooding | No |
| Standard 3: Community Health, Safety and Working Conditions |  |
| 3.1 Would elements of Project construction, operation, or decommissioning pose potential safety risks to local communities? | Yes |
| 3.2 Would the Project pose potential risks to community health and safety due to the transport, storage, and use and/or disposal of hazardous or dangerous materials (e.g. explosives, fuel and other chemicals during construction and operation)? | No |
| 3.3 Does the Project involve large-scale infrastructure development (e.g. dams, roads, buildings)? | No |
| 3.4 Would failure of structural elements of the Project pose risks to communities? (e.g. collapse of buildings or infrastructure) | No |
| 3.5 Would the proposed Project be susceptible to or lead to increased vulnerability to earthquakes, subsidence, landslides, erosion, flooding or extreme climatic conditions? | No |
| 3.6 Would the Project result in potential increased health risks (e.g. from water-borne or other vector-borne diseases or communicable infections such as HIV/AIDS)? | No |
| 3.7 Does the Project pose potential risks and vulnerabilities related to occupational health and safety due to physical, chemical, biological, and radiological hazards during Project construction, operation, or decommissioning? | No |
| 3.8 Does the Project involve support for employment or livelihoods that may fail to comply with national and international labour standards (i.e. principles and standards of ILO fundamental conventions)? | No |
| 3.9 Does the Project engage security personnel that may pose a potential risk to health and safety of communities and/or individuals (e.g. due to a lack of adequate training or accountability)? | No |
| Standard 4: Cultural Heritage |  |
| 4.1 Will the proposed Project result in interventions that would potentially adversely impact sites, structures, or objects with historical, cultural, artistic, traditional or religious values or intangible forms of culture (e.g. knowledge, innovations, practices)? (Note: Projects intended to protect and conserve Cultural Heritage may also have inadvertent adverse impacts) | No |
| 4.2 Does the Project propose utilizing tangible and/or intangible forms of cultural heritage for commercial or other purposes? | No |
| Standard 5: Displacement and Resettlement |  |
| 5.1 Would the Project potentially involve temporary or permanent and full or partial physical displacement? | No |
| 5.2 Would the Project possibly result in economic displacement (e.g. loss of assets or access to resources due to land acquisition or access restrictions – even in the absence of physical relocation)? | No |
| 5.3 Is there a risk that the Project would lead to forced evictions? | No |
| 5.4 Would the proposed Project possibly affect land tenure arrangements and/or community-based property rights/customary rights to land, territories and/or resources? | No |
| Standard 6: Indigenous Peoples |  |
| 6.1 Are indigenous peoples present in the Project area (including Project area of influence)? | No |
| 6.2 Is it likely that the Project or portions of the Project will be located on lands and territories claimed by indigenous peoples? | No |
| 6.3 Would the proposed Project potentially affect the human rights, lands, natural resources, territories, and traditional livelihoods of indigenous peoples (regardless of whether indigenous peoples possess the legal titles to such areas, whether the Project is located within or outside of the lands and territories inhabited by the affected peoples, or whether the indigenous peoples are recognized as indigenous peoples by the country in question)? If the answer to the screening question 6.3 is “yes” the potential risk impacts are considered potentially severe and/or critical and the Project would be categorized as either Moderate or High Risk. | No |
| 6.4 Has there been an absence of culturally appropriate consultations carried out with the objective of achieving FPIC on matters that may affect the rights and interests, lands, resources, territories and traditional livelihoods of the indigenous peoples concerned? | No |
| 6.5 Does the proposed Project involve the utilization and/or commercial development of natural resources on lands and territories claimed by indigenous peoples? | No |
| 6.6 Is there a potential for forced eviction or the whole or partial physical or economic displacement of indigenous peoples, including through access restrictions to lands, territories, and resources? | No |
| 6.7 Would the Project adversely affect the development priorities of indigenous peoples as defined by them? | No |
| 6.8 Would the Project potentially affect the physical and cultural survival of indigenous peoples? | No |
| 6.9 Would the Project potentially affect the Cultural Heritage of indigenous peoples, including through the commercialization or use of their traditional knowledge and practices? | No |
| Standard 7: Pollution Prevention and Resource Efficiency |  |
| 7.1 Would the Project potentially result in the release of pollutants to the environment due to routine or non-routine circumstances with the potential for adverse local, regional, and/or transboundary impacts? | No |
| 7.2 Would the proposed Project potentially result in the generation of waste (both hazardous and non-hazardous)? | No |
| 7.3 Will the proposed Project potentially involve the manufacture, trade, release, and/or use of hazardous chemicals and/or materials? Does the Project propose use of chemicals or materials subject to international bans or phase-outs? For example, DDT, PCBs and other chemicals listed in international conventions such as the Stockholm Conventions on Persistent Organic Pollutants or the Montreal Protocol | No |
| 7.4 Will the proposed Project involve the application of pesticides that may have a negative effect on the environment or human health? | Yes |
| 7.5 Does the Project include activities that require significant consumption of raw materials, energy, and/or water? | No |

ANNEX 8. STANDARD LETTER OF AGREEMENT BETWEEN UNDP AND THE GOVERNMENT FOR THE PROVISION OF SUPPORT SERVICES

Dear Mr. Khairullo Ibodzoda,

1.	Reference is made to consultations between officials of the Government of Tajikistan (hereinafter referred to as “the Government”) and officials of UNDP with respect to the provision of support services by the UNDP country office for nationally managed programmes and projects.  UNDP and the Government hereby agree that the UNDP country office may provide such support services at the request of the Government through its institution designated in the relevant programme support document or project document, as described below.

2.	The UNDP country office may provide support services for assistance with direct payments.  In providing such support services, the UNDP country office shall ensure that the capacity of the Government-designated institution is strengthened to enable it to carry out such activities directly.  The costs incurred by the UNDP country office in providing such support services shall be recovered from the administrative budget of the office.

3.	The UNDP country office may provide, at the request of the designated institution, the following support services for the activities of the programme/project:

(a)	Identification and/or recruitment of project and programme personnel;

(b)	Identification and facilitation of training activities;

(c)	Procurement of goods and services;

4.	The procurement of goods and services and the recruitment of project and programme personnel by the UNDP country office shall be in accordance with the UNDP regulations, rules, policies and procedures.  Support services described in paragraph 3 above shall be detailed in an annex to the project document, in the form provided in the Attachment hereto.  If the requirements for support services by the country office change during the life of a programme or project, the annex to the programme support document or project document is revised with the mutual agreement of the UNDP resident representative and the designated institution. Maximum possible amount of support services shall not exceed the amount indicated in the Project Document ($132,000).

5.	The relevant provisions of the Standard Basic Assistance Agreement between the Government of the Republic of Tajikistan and UNDP signed on 03 December 1993, (the “SBAA”), including the provisions on liability and privileges and immunities, shall apply to the provision of such support services. The Government shall retain overall responsibility for the nationally managed programme or project through its designated institution.  The responsibility of the UNDP country office for the provision of the support services described herein shall be limited to the provision of such support services detailed in the annex to the programme support document or project document.

6.	Any claim or dispute arising under or in connection with the provision of support services by the UNDP country office in accordance with this letter shall be handled pursuant to the relevant provisions of the SBAA.

7.	The manner and method of cost-recovery by the UNDP country office in providing the support services described in paragraph 3 above shall be specified in the annex to the programme support document or project document.

8.	The UNDP country office shall submit progress reports on the support services provided and shall report on the costs reimbursed in providing such services, as may be required.

9.	Any modification of the present arrangements shall be effected by mutual written agreement of the parties hereto.

10.	If you are in agreement with the provisions set forth above, please sign and return to this office two signed copies of this letter.  Upon your signature, this letter shall constitute an agreement between your Government and UNDP on the terms and conditions for the provision of support services by the UNDP country office for nationally managed programmes and projects.

Yours sincerely,

________________________

Signed on behalf of UNDP

Pratibha Mehta

UNDP Resident Representative

_____________________

For the Government

Mr. Khairullo Ibodzoda

Chairman of the Committee for Environmental Protection under the Government of the Republic of Tajikistan

[Date]

Attachment

# DESCRIPTION OF UNDP COUNTRY OFFICE SUPPORT SERVICES

1.	Reference is made to consultations between Committee for Environmental Protection (CEP), the institution designated by the Government of Tajikistan and officials of UNDP with respect to the provision of support services by the UNDP country office for the nationally managed project “An integrated landscape approach to enhancing the climate resilience of small-scale farmers and pastoralists in Tajikistan”, (Project #: 00111538) “the Project”.

2.	In accordance with the provisions of the letter of agreement signed on [insert date of agreement] and the project document, the UNDP country office shall provide support services for the Project as described below.

3.	Support services to be provided:

| Support services (insert description) | Schedule for the provision of the support services |  | Cost to UNDP of providing such support services (where appropriate) | Amount and method of reimbursement of UNDP (where appropriate) |
| --- | --- | --- | --- | --- |
| 1. Human Resources |  |  |  |  |  |
| a) TOR review and post classification + creation |  | Jun-19 | 34.35 | 240.45 |  |
| b) Advertisement |  | Jun-19 | 119.96 | 839.72 |  |
| c) Short-listing (including long-listing) |  | Jun-19 | 239.92 | 1,679.44 |  |
| d) Test Evaluation |  | Jun-19 | 88.83 | 621.81 |  |
| e) Interviewing |  | Jun-19 | 239.92 | 1,679.44 |  |
| f) Reference check |  | Jun-19 | 40.06 | 280.42 |  |
| g) Review recruitment case |  | Jun-19 | 25.85 | 180.95 |  |
| h) Contract issuance |  | Jun-19 | 82.38 | 576.66 |  |
| i) Recurrent personnel management services: staff payroll & banking administration & management (for whole contract period): |  | Annual fee per employee per year) |  | 0.00 |  |
| Payroll validation, disbursement |  |  | 157.04 | 5,653.44 |  |
| Extension, promotion, entitlements |  |  | 134.6 | 3,499.60 |  |
| Performance evaluation |  |  | 134.6 | 4,845.60 |  |
| Leave monitoring |  |  | 22.43 | 807.48 |  |
| Leave monitoring - Absence data management in Atlas only |  |  | 5.7 | 205.20 |  |
| l) Staff HR & Benefits Administration & Management (one time fee, per staff. Services incl. contract issuance, benefits enrollment, payroll setup - this price applies to the separation process as well) |  | Yearly | 205.66 | 1,233.96 |  |
| Total, HR: |  |  |  | 22,344.17 |  |
| 2. Finance |  |  |  |  |  |
| a) Payment to vendor and staff |  | Daily/Monthly | 38.49 | 27,712.80 |  |
| - Urgent payments to vendor and staff (within 1 day) |  | Ad hoc | 76.98 | 923.76 |  |
| - Urgent payments to vendor and staff (within 3 day) |  | Ad hoc | 57.74 | 1,385.76 |  |
| b) Issue check only (Atlas Agencies only) |  | Ad hoc | 16.7 | 501.00 |  |
| - Issue check only (Atlas Agencies only - within 1 day) |  | Ad hoc | 33.4 | 400.80 |  |
| - Issue check only (Atlas Agencies only - within 3 days) |  | Ad hoc | 25.05 | 601.20 |  |
| c) Vendor profile only (Atlas Agencies only) |  | As per the working plan | 20.66 | 3,099.00 |  |
| AR Management Process (create/apply receivable pending item- Atlas Agencies Only) |  | As per the working plan | 35.6 | 356.00 |  |
| d) Journal Voucher or General Ledger Journal Entry (GLJE) |  | Quarterly, yearly | 35.67 | 713.40 |  |
| e) PCA reports review and certification |  | As per the working plan | 25.8 | 258.00 |  |
| f) F10 Settlement |  | As per the working plan | 23.12 | 2,774.40 |  |
| g) Issue/Apply Deposits Only |  | As per the working plan | 21.74 | 217.40 |  |
| Total, Finance: |  |  |  | 38,943.52 |  |
| 3. Procurement |  |  |  |  |  |
| a) Procurement not involving CAP - below US$ 50,000 |  |  |  |  |  |
| -Identification and selection |  | As per the working plan | 282.29 | 27,664.42 |  |
| - Issue Purchase Order |  | As per the working plan | 41.95 | 3,775.50 |  |
| b) Procurement process involving CAP (and/or ITB, RFP, requirements) - above US$ 50,000) |  | As per the working plan |  | 0.00 |  |
| - Identification & selection |  | As per the working plan | 489.45 | 12,236.25 |  |
| - Contracting/Issue Purchase Order |  | As per the working plan | 104.07 | 2,601.75 |  |
| c) Consultant recruitment |  | As per the working plan |  | 0.00 |  |
| - Advertising |  | As per the working plan | 36.11 | 1,805.50 |  |
| - shortlisting and selection |  | As per the working plan | 157.13 | 7,856.50 |  |
| - Contract issuance |  | As per the working plan | 72.22 | 3,611.00 |  |
| d) Procurement involving RACP (goods, services & consultant > US$150,000) |  | As per the working plan |  | 0.00 |  |
| - Identification & selection |  | As per the working plan | 582.33 | 1,164.66 |  |
| - Contracting |  | As per the working plan | 60.67 | 121.34 |  |
| - Issue PO |  | As per the working plan | 48.01 | 96.02 |  |
| - Follow up |  | As per the working plan | 60.67 | 121.34 |  |
| e) Asset disposal involving CAP |  | By the closure of the project | 275.14 | 2,751.40 |  |
| Total, Procurement: |  |  |  | 63,805.68 |  |
| 4. Admin Support |  |  |  |  |  |
| Ticket request (booking, purchase) |  | As per the working plan | 71.79 | 4,307.40 |  |
| Travel cost estimates- Simple |  | As per the working plan | 26.42 | 2,599.23 |  |
| Total, Admin Support: |  |  |  | 6,906.63 |  |
| Total DPC |  |  |  | 132,000.00 |  |

4.         Description of functions and responsibilities of the parties involved:

As the national implementing partner, the Committee for Environmental Protection under the Government of the Republic of Tajikistan (CEP) will oversee all aspects of project implementation.  CEP is responsible for the protection of ecosystems, protection of surface and underground water resources and monitoring the environment and natural resources, and climate monitoring. In addition, it carries out environmental assessments of various projects. The CEP structure includes local CEP representation at the district and provincial (Oblast) level. Among other tasks, district and provincial units of the CEP supervise the wastewater monitoring and control water use permit. They carry out systematic review and assessment of the environment in Tajikistan and develop standards for pollution control.  The CEP will appoint National Project Coordinator (NPC) to oversee the project implementation.

Overall governance of the project will be carried out by the Project Steering Committee, which will include CEP, other national agencies including the Ministry of Energy and Water Resources, Ministry Agriculture and Agency for Land Reclamation and Irrigation, local Khukumat representatives and UNDP.  The PSC may invite other agencies to join as members, with the roster to be definitively set and approved no later than the project’s inception period. The National Project Coordinator will serve as Chair of the Project Steering Committee, with assistance from UNDP in organizing and running all meetings and other exchanges of information.  Meetings of the Project Steering Committee will take place at least once annually in time for approval of the following year’s Annual Work Plan.  Additional meetings may be called as needed by the NPC.

UNDP will join CEP in managing the project and providing quality assurance, in accordance with plans approved by the Project Steering Committee.  Most of UNDP’s work for the project will be based in its Country Office (CO) in Dushanbe, under the supervision of the Team Leader for Disaster Risk Reduction, Environment and Energy and other senior programme staff, including the UNDP Resident Representative and UNDP Country Director as warranted.  UNDP will also engage contractors to carry out Midterm and Final Evaluations of the project.  The UNDP Regional Technical Advisor, based in the UNDP Regional Service Centre in Istanbul, will provide technical support, assistance with coordination, and overall project monitoring to ensure consistency with expectations from UNDP and Adaptation Fund.

The day-to-day operations of the project will be carried out by six full-time project staff, headed by the Project Manager.  The Project Manager will be responsible for carrying out the activities of the project as set forth in this Project Document and any revisions approved by the Project Steering Committee.  At least one month in advance of the start of each project year, the Project Manager will prepare Annual Work Plans.  These plans will be reviewed and approved by the Project Steering Committee and thereafter will be used by project staff as tools for planning, implementing, and tracking work flows. In addition, for each meeting of the Project Steering Committee, the Project Manager will prepare a full status report on project activity, including recent accomplishments, risks, and proposed mitigation measures. The Project Manager will also be responsible for preparing all required annual reports for UNDP and Adaptation Fund.

UNDP country office staff will assist the Project Manager in all the administrative work of the project, including logistics and clerical work.  In addition, the country office will provide administrative support to the Government with regard to various specific administrative functions, whose costs will be billed as Direct Project Costs according to this Letter of Agreement.

Responsibilities of other entities of the Government are set forth in the table below.

Maximum DPC amount to be charged to AF fund is USD 132,000.

| Annex 9: UNDP Fees for Support to Adaptation Fund Project |  |  |
| --- | --- | --- |
| “An integrated landscape approach to enhancing the climate resilience of small-scale farmers and pastoralists in Tajikistan” |  |  |
| Category | Services Provided by UNDP | UNDP Fee (8.5%) |
| Identification, Sourcing and Screening of Ideas | Provide information on substantive issues in adaptation associated with the purpose of the Adaptation Fund (AF). | $ 39,157 |
|  | Engage in upstream policy dialogue related to a potential application to the AF. |  |
|  | Verify soundness & potential eligibility of identified idea for AF. |  |
| Feasibility Assessment / Due Diligence Review | Provide up-front guidance on converting general idea into a feasible project/programme. | $ 117,470 |
|  | Source technical expertise in line with the scope of the project/programme. |  |
|  | Verify technical reports and project conceptualization. |  |
|  | Provide detailed screening against technical, financial, social and risk criteria and provide statement of likely eligibility against AF requirements. |  |
|  | Determination of execution modality and local capacity assessment of the national executing entity. |  |
|  | Assist in identifying technical partners. Validate partner technical abilities. Obtain clearances from AF. |  |
| Development & Preparation | Provide technical support, backstopping and troubleshooting to convert the idea into a technically feasible and operationally viable project/programme. | $ 156,626.20 |
|  | Source technical expertise in line with the scope of the project/programme needs. |  |
|  | Verify technical reports and project conceptualization. |  |
|  | Verify technical soundness, quality of preparation, and match with AF expectations. |  |
|  | Negotiate and obtain clearances by AF. Respond to information requests, arrange revisions etc. |  |
| Implementation | Technical support in preparing TORs and verifying expertise for technical positions. | $ 352,409 |
|  | Provide technical and operational guidance project teams. |  |
|  | Verification of technical validity / match with AF expectations of inception report. |  |
|  | Provide technical information as needed to facilitate implementation of the project activities. |  |
|  | Provide advisory services as required. |  |
|  | Provide technical support, participation as necessary during project activities. |  |
|  | Provide troubleshooting support if needed. Provide support and oversight missions as necessary. |  |
|  | Provide technical monitoring, progress monitoring, validation and quality assurance throughout. |  |
|  | Allocate and monitor Annual Spending Limits based on agreed work plans. |  |
|  | Receipt, allocation and reporting to the AFB of financial resources. |  |
|  | Oversight and monitoring of AF funds. Return unspent funds to AF. |  |
| Evaluation and Reporting | Provide technical support in preparing TOR and verify expertise for technical positions involving evaluation and reporting. | $ 117,470 |
|  | Participate in briefing / debriefing. |  |
|  | Verify technical validity / match with AF expectations of all evaluation and other reports |  |
|  | Undertake technical analysis, validate results, and compile lessons. |  |
|  | Disseminate technical findings |  |
| Total |  | $ 783,131 |

Water Sector Reforms Programme of the Republic of Tajikistan for 2016–2025 (Water Reform Programme). 2015. Resolution of the Government of the Republic of Tajikistan. Unofficial translation.

Water Reform Programme 2015.

Tahirov IG & Kupayi GD. 1994. Water resources of Tajikistan of the Republic of Tajikistan. Dushanbe 1:181.

Fergana Valley WRM 2018 KRBMP Unpublished.

Ibid.

Tahirov & Kupayi 1994 Water resources of Tajikistan.

Tahirov I & Kupai G. 1998. Water resources of Tajikistan. Dushanbe.

Agency for Statistics under the President of the Republic of Tajikistan. 2017. Districts of the Republic of Tajikistan.

Agency for Statistics under the President of the Republic of Tajikistan. 2017. Regions of the Republic of Tajikistan.

International Network for Capacity Building on IWRM (CAPNET). 2009. IWRM as a Tool for Adaptation to Climate Change. UNDP.

CAPNET 2009 IWRM as a Tool.

Fergana Valley WRM 2018 KRBMP Unpublished.

State Agency for Hydrometeorology (Hydromet). 2018. Assessment of Kofirnighan River Basin (KRB), natural disasters and needs. Unofficial document.

see sub-section on KRB below

Hydromet 2018 Assessment of KRB, Unofficial document.

Further information concerning the KRB’s vulnerability to extreme climate events is presented under ‘Climate change context’.

Tajikistan’s agro-ecological zone are classified according to elevation, with the lower zones (1 and 2) primarily being used to grow irrigated crops such as cotton and sub-tropical fruit. Zones of higher elevation (3 and 4) are primarily rain-fed agriculture and used primarily for pasture land and for growing wheat, barley and lucerne.

Hydromet 2018 Assessment of Kofirnighan River Basin.

Fergana Valley WRM 2018 KRBMP Unpublished.

Further information concerning district-specific vulnerability to extreme climate events is presented under district descriptions.

NHDR 2012 Tajikistan: Poverty in the Context of Climate Change.

Source: Committee for Emergency Situations and Civil Defence.

National Agency for Hydrometeorology.

Detailed in Part II: K and Annex 7 of the Full Proposal.

This table has been adapted from Part B of the SESP included as Annex 7 to the Full Proposal. For more information on risk impact, probability and significance, please see the full SESP detailed in Annex 7.

Water Reform Programme 2015.

Land Code of the Republic of Tajikistan (Land Code). No. 498 of 1997. Republic of Tajikistan.

Water Code: Law of the Republic of Tajikistan (Water Code). 2001. Government of Tajikistan, Dushanbe.

Republic of Tajikistan Law on Land Reform (Land Reform Law). 1994. Republic of Tajikistan.

Law of the Republic of Tajikistan “on Land Management” (Land Management Law). 2001. Republic of Tajikistan.

Republic of Tajikistan Law “on Dehkan Farms” (Dehkan Law). 2002. Republic of Tajikistan.

Refer to Part II: K on the environmental social impacts and risks of the project.

UNDP Social and Environmental Safeguards Procedure. Refer to Annex 7 of the Full Proposal.

Land Code 1997.

Water Code 2001.

Land Management Law 2001.

Prohibited grounds of discrimination include race, ethnicity, gender, age, language, disability, sexual orientation, religion, political or other opinion, national or social or geographical origin, property, birth or other status including as an indigenous person or as a member of a minority. References to “women and men” or similar is understood to include women and men, boys and girls, and other groups discriminated against based on their gender identities, such as transgender people and transsexuals.

In regards to CO2, ‘significant emissions’ corresponds generally to more than 25,000 tons per year (from both direct and indirect sources). [The Guidance Note on Climate Change Mitigation and Adaptation provides additional information on GHG emissions.]

Forced evictions include acts and/or omissions involving the coerced or involuntary displacement of individuals, groups, or communities from homes and/or lands and common property resources that were occupied or depended upon, thus eliminating the ability of an individual, group, or community to reside or work in a particular dwelling, residence, or location without the provision of, and access to, appropriate forms of legal or other protections.