Application for a Grant to facilitate learning and knowledge sharing

Submission Date: 07 January 2019

Adaptation Fund Grant ID:       Country/ies: Senegal

National Implementing Entity: Centre de Suivi Ecologique

# Timeframe of Activity

| Expected start date | March 2019 |
| --- | --- |
| Completion date | June 2020 |

# Proposed learning activities

Describe the activities to be undertaken to share knowledge with other NIEs or the wider climate adaptation community or to develop knowledge/guidelines through partnerships

| Proposed Learning Activities | Description of activities | Expected Output of the Activities | Country/Institution to share/transfer knowledge with/to or to develop guidelines for, including NIE(s) | Requested budget (USD) | Tentative timeline (Completion date) |
| --- | --- | --- | --- | --- | --- |
| 1. Development of a knowledge management system on direct access | 1.1. Need analysis 1.2. Development of the knowledge management system charter 1.3 Development of an online platform for sharing knowledge 1.4 Acquisition of e-learning material and equipment 1.5 Preparing a note on best practices on direct access | 1.1. Needs in terms of material, tools and services are identified Deliverable : Needs analysis report 1.2 Charter elaborated Deliverable : Charter 1.3 Online platform for collecting and sharing knowledge Deliverables : Report of the launch workshop of the platform ; User guide of the platform 1.4. Equipment and material 1.5 Lesson-learning document elaborated Deliverables : Lesson-learning document | Adaptation Fund NIEs | 6,000 6,000 36,000 12,000 9,000 | March 2020 |
| 2. Setting up the governance system of the Community of Practice | 2.1. Finalizing and validating the governance document for the Community of Practices | 2.1 Document on Governance elaborated and validated Deliverable : Document on Governance ; Validation workshop report | Adaptation Fund NIEs | 54,000 | April 2019 |
| 3. Experience sharing with two NIEs in Africa | 3.1 Exchange visits with SANBI and DRFN | 3.1 Mission Report | DRFN and SANBI | 14,000 | February 2020 |
| Audits Costs | 6,000 | June 2020 |
| Management Costs | 6,290` |  |
| Total Grant Requested (USD) 149,290 |

# Implementing Entity

This request has been prepared in accordance with the Adaptation Fund Board’s procedures

# Record of endorsement on behalf of government

Provide the name and position of the government official, Designated Authority (DA) of the Adaptation Fund, and indicate date of endorsement. The DA endorsement letter must be attached as an annex to the request.

Endorsement letter by Designated Authority